## Sheet1
CLARIFICATION LOG
Tender: | Park Gerry - Skate park
Tender Reference:
Published Date: | 2023-04-11
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | Within the tender documents of Vol 1 ITT, the client states they have undertaken a number of surveys. If possible, please provide reports from the surveys undertaken to aide the tender submission. | Following documents have been added for information purposes: South West Water Ltd Drainage & Water Search (Commercial Premium); FLOOD_RISK_ASSESSMENT-7134911; HERITAGE_STATEMENT-7126774; PA22_11292-PRELIMINARY_ECOLOGICAL_APPRAISAL-7126696; TRANSPORT_STATEMENT-7126734; Phase I Preliminary Risk Assessment (PRA) - Park Gerry 21441 | 2023-03-16
2 | Please can you also review the pricing section that has been uploaded to Contracts Finder as it appears to be missing some information. If there are provisional sums to be included within the contract sum, these are currently not shown. | The Price Schedule has been updated - please respond on version 2 as per Contracts Finder. No provisional sums have been included | 2023-04-11
3 | Are the advised trial pits to be carried out contract award and if so, are tenderers to assume good ground conditions to assure controlled conditions for tender pricing? | For the purposes of pricing assume good conditions, but if there are additional costs at feasibility stage, then this can be assesed and added as an addition to the specified budget. | 2023-04-11
4 | Page 13 of the ITT mentions Phase 1: Design and feasibility work (including funding) being marked. Is Funding assistance to be evaluated? | No, this would not form part of the evaluation.There is no current plan to be seeking further funding for the project. The current budget is 100% secured. | 2023-04-11
5 | We note extensive consultation has taken place. Has any consultation taken place with a skatepark specialist to date? If so, are the results available? | We have had informal conversations with some of the respected members of the skateboarding community who have made recommendations, but there is no formal consultation to report. | 2023-04-11
6 | We intend to visit the site during the Tender stage. Is a project representative available / preferred to be present at the visit? | The site is open park and anyone is welcome to visit. If it is preferred that a member of our project team is available, then we will happily book that in and show you around and talk through the proposals. | 2023-04-11
7 | Is it preferred / feasible to meet with any user groups during the Tender stage or is this to be post-contract award? | This will be an essential part of the next stages of the design work, but not something that we would consider appropriate during the tender stage. | 2023-04-11
8 | Can you confirm that a design is required at Tender stage? If so, can you confirm the panel make-up for scoring the design? | As this is a design and build contract, evidence of the ability to carry out the work is essential. This will be done through previous projects and processes that have secured exceptional results. Early design concepts and any indicative layouts would be well received, but it is understood that there is a lot of input required before a design can be submitted. Camborne Town Council do not want a progressed plan without further community engagement, so do not expect to see detailed one's in the tender return. | 2023-04-11
9 | Taking into account Bank Holidays in the tender period is it possible to extend the return date? | Yes, the Council is prepared to extend the return date to noon on 5 May 2023 - documents have been updated (Volume 1 and Volume 2 - see version 2) | 2023-04-11
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: