## Guidance Notes
Risk Identification, Evaluation & Control Tool Guidance Notes
This tool is to aid Project Managers to identify, evaluate and control risks associated with their Projects
The most important thing to remember in using this tool is that YOU as the Project Manager:
Identify the potential Risks associated with your project
Evaluate the probability of the Risks occurrin and their potential impact
Control and help manage the Risks by identifying mitigations
To calculate a Score & RAG (Red, Amber, Green) rating for each of the Risks click on the 'REIC tool' tab and provide detail any identified risks, you will then be required to indicate the following:
A. How probable it is that the Risk will occur by giving it a rating of 2, 4, 6, 8 or 10 where 2 means that the chance of the risk occurring is very low and 10 means that you consider the chances of the risk occurring are very high
B. Estimate the impact (eg on safety, time, financial) should the Risk occur and give it a rating of 2, 4, 6, 8 or 10 (where 2 is a low impact and 10 would be a very high impact)
The tool will then calculate the Risk score by multiplying the probability score by the financial impact score e.g. 2x4=8.
The resulting score will then be given a RAG rating in accordance with the matrix below e.g. a score of 40 would be given a 'Amber' rating. Project Managers should focus their attention on controlling 'Red' risks as a priority.
The Project will then be given an overall Risk Score and RAG rating which is the average of all of the individual Risk scores.
Scored Risk Matrix
Calculated Risk Score & RAG Rating (=PxI)
Probability of occurrence (P) | Very High 10 | 20 | 40 | 60 | 80 | 100
| High 8 | 16 | 32 | 48 | 64 | 80
| Medium 6 | 12 | 24 | 36 | 48 | 60
| Low 4 | 8 | 16 | 24 | 32 | 40
| Very Low 2 | 4 | 8 | 12 | 16 | 20
|  | Very Low 2 | Low 4 | Medium 6 | High 8 | Very High 10
Impact (I)

## RIEC Tool
Risk Identification, Evaluation & Control
Project Title | A46 NB SB Sixhills Geotech - Water Erosion
Project Manager | Sean Foster
Date updated | 2019-10-09
Version Control | 1
Overall Risk Score and RAG Rating | 21.1429
Identification |  |  | Evaluation |  |  | Control
Area of Risk | Risk | Comment/Impact | Probability of occurrence | Impact | Risk Score and RAG Rating | Mitigations | Notes
Pre-construction | TM suitability | Working window is dependant on traffic flow and TM needs to be put out one hour before works are due to commence and taken off the network when traffic flow increases over a scertain threshold. This can increase the duration of the proposed works and the expected cost of TM | 6 | 6 | 36 | TM will be put out during periods of anticepated low traffic volume, at night, where it is not anticepated that TM will need to be removed primaturley due to an influx in traffic flow. | TM provider will add further clarification regarding appropriate working windows to avoid disruption to the works and the road users.
Pre-construction | Programme coordination | In order for the on site activities to run smoothley and efficiently, coordination between the teams needs to be priority. If a good level of communication is not upheld then this may enhibiting access to parts of the site due to works restricting access to parts of the site. Conversley, periods could exist where no teams are on site at all, wasting the cost and time for TM. | 4 | 6 | 24 | A schedule of works will be abided by and the principal contractor (TM provider) will maintain communication and coordination between the teams. | Works should be carried out in the following order: - Vegetation clerence then ground investigation, topo survey, drainage survey. GI, topo and drainage teams should coordinate to ensure they don’t restrict on site activities for one another.
Pre-construction | Contractor availability | Contractors need to be available within the TM window in order to ensure the programme runs continually and efficiently. Any disruptions to contractor availability will cause disruption to the programme and increased costs. | 4 | 4 | 16 | Contractor availability will be confirmed prior to any activities being carried out on site to ensure the on site activities can run seemlesley. | All contractors involved should liase with the principal contractor (TM provider) prior to site mobilisation
Pre-construction | Unforseen ground conditions | This could result in deeper boreholes being required, prolonging the ground investigation contractos time on site. This may influence the requirement for laboratory testing and increase GI costs. | 2 | 2 | 4 | All relivent information pertaining to the scheme has been reviewed and reported. It is not expected that unforeen ground conditions will be encountered but this can not be ruled out. | The GI is will be in direct contact with a geotechnical engineer to provide guidance if unforseen ground conditions are encountered to minimise distruption to the project.
Pre-construction | Weather | Weather may cause delays to the on site activities as adverse conditions could reduce visability meaning TM can't be put out, prolonging the duration and cost of the on site activities. | 6 | 6 | 36 | Weather forecasts will be reviewed prior to site mobilisation each night to confirm that adverse weather conditions will not disrupt works. | TM will not be put out should extreame weather conditions be expected.
Pre-construction | Theft of Kit | Theft of any kit left on site during the day will increase the time required on site whilst replacement kit is found and subsequently increase costs. | 2 | 4 | 8 | Any kit left on site between shifts will be secured and/or locked
Pre-construction | Encounter Aspestos | Should asbestos be encountered on site, more samples will need to be collected for sampling and depending on the severity, works may stop whilst the issue of asbestos on site is addressed, increasing the time and cost of the scheme. | 4 | 6 | 24 | Sampling of any materials suspected to contain asbestos will be carried out and the correct measures will be adobted should measures be required to address asbestos.
Please refer to the "Designers Hazard Checklist and Risk Reduction Schedule" and "Safety Risk Management Decision Matrix" documents which form part of the TST package for further risk reference.
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select
Please Select |  |  | Please select | Please select