## Sheet1
CLARIFICATION LOG
Tender: | Public Toilet Replacement and Refurbishment Tender - Teignmouth Town Council
Tender Reference: | 01-(10.24)
Published Date: | 24.11.2024
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | All the pricing documents in excel so we can complete and return, they are currently part of the PDF pack of each site only so cannot be completed | These have now been added to the Contracts Finder documents for the individual sites. Also included is a Total Collection Sheet for updating and including as part of any tender submission | 2024-11-17
2 | Form of tender – documents say this is in the ITT but I cannot see it can you please provide a copy | The form of Tender and accompanying declarations are to be found in Part A document of the supplier response. | 2024-11-17
3 | Funding requirements – documents say this is in the ITT but I cannot see it can you please provide a copy | The funding is solely from Teignmouth Town Council | 2024-11-17
4 | The pricing schedule sections states there are various foundation options on the architect drawings and specification but this pack has not been provided. Are we to provide the options on complete additional breakdowns or as extra over costs ? | Response pending | 2024-11-17
5 | The Den: Pre construction information says to follow, can you advise when? | This has now been uploaded onto Contracts Finder | 2024-11-18
6 | The Den: Architect information says further information to follows, can you advise what and when ? | These have now been uploaded onto Contracts Finder | 2024-11-18
7 | The Den: M&E says included in architect information but the architect section is to follow | Please refer to drawings and updated specification | 2024-11-18
8 | The Den: Employers documents says included in architect information but the architect section is to follow | Please refer to drawings and updated specification | 2024-11-17
9 | The Den: Planning information say to follow, can you advise when ? | Response pending | 2024-11-17
10 | Having read all the info and further we think you may have the employee requirements completely wrong ( attached). This refers to 3 unisex 1 disabled toilet whereas the planning drawing shows 19 unisex 1 disabled?? I asked the question when on site with them and they told me as per planning however there was a small planning revision. Also, the programme shows 14 weeks build time which is pretty much the same as the others but 5 times bigger | Response pending | 2024-11-17
11 | With regards the replacement toilets can we offer a Modular option rather than a new build construction? | The Council would be prepared to accept a modular (offsite) construction that meets the design parameters whch have been set out as a compliant tender. If this is to be provided the Council would be seeking assurances of a design life minimum of 25 years. | 2024-11-17
12 | Can you also please clarify the allowed mobilisation period ? the tender programme provided says 16/12 through to 06/01, but as this falls over the Christmas shut down period for the industry this is actually only 5 working days. More time will be required to mobilise for the project, can you please confirm that: We will not be penalised on the tender return marking for extending the mobilisation period to 15 working days (the period allotted if it did not fall over Christmas). The end date can move in line with the adjusted start date? | Yes, the timetable is indicative and the Council recognises that the dates and alignment with the Christmas shutdown. We would be prepared to accept suitable alternative programmes as long as not substantitively different from what is indicatively set out. | 2024-11-17
13 | The tender programme says about the blocks being carried out one after another, is there no option to overlap any sites during the works ? | The Council's rationale for the programme is to complete a small block first to iron out any issues. We then can have an overlap in the Den and Lower Brook Street and finally finance dictates the completion of the final two blocks into the next budgetary year. | 2024-11-17
14 | In the PDF file with the information for ‘The Den’ there isn’t any detailed drawing(s) of the new, proposed, toilet block. The only drawing that we have is a drawing of the old aquarium building showing / talking about the retaining wall page 101. If you could you send the new toilet drawings through that would be ideal. | These drawings have now been issued on 18/11/2024 | 2024-11-18
15 | Have Teignmouth Town Council made contact with both or either National Grid or South West Water regarding the water and electrical connections that will be going into these toilets. | Response pending | 2024-11-18
16 | Regarding the water connections, will we need or be able to close down roads or at least lanes, at East Cliff, The Point and Quay Road Carparks, to be able to run new connections to the proposed toilets. Has there been any consideration of these issues with dialogue with the highway department? | Response pending | 2024-11-18
17 | Knowing the clarification responses are scheduled for 22/11/24, but I was wondering if it would be possible to send out The Den drawings a bit earlier to give us additional time to price them accordingly. | These drawings have now been issued on 18/11/2024 | 2024-11-18
18 | With the clarification answers due to be published on the 22nd of November and no drawings for The Den having been issued yet, we kindly request an extension of time to ensure we can provide a comprehensive and accurate submission. | Teignmouth TC have amended the return date to noon on Monday 9 December 2024 - the Invitation to Tender document Volume 1 and Part A and B have been updated with the revised dates. | 2024-11-18
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: