# Annex A

| Title of project: | Review of approaches for the assessment of marine Natural Capital in the context of UK marine environmental policy and management |
| --- | --- |
| Date and time for return of tenders: | Friday 2 July @ 16:00 hours |
| Contract Reference No: | C21-0484-1570 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO LAUREN MOLLOY, VICKY MORGAN OR DORA IANTOSCA VIA THEIR EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR BID Submissions must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact the individuals below, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Email: lauren.molloy@jncc.gov.uk Tel: 01733 866905 OR Joint Nature Conservation Committee Email: Vicky.morgan@jncc.gov.uk Tel: 01733 866830 / 07964 110283 |
| Contact for any queries regarding the procurement procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | 12 July 2021 |
| Proposed end-date: | 5 November 2021 |

Title of Project (contents page is optional)

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	4

4.	Project Objectives	4

5.	Project Objectives: Detailed tasks	5

6.	Outputs	7

7.	Dissemination (delete if non-applicable)	8

8.	Timescale	8

9.	Health and safety	8

10.	Product specification	8

11.	Project management	9

12.	Instructions for tender submission	9

13.	Evaluation Criteria	10

14.	Payment	11

15.	Additional Contractor requirements	11

16.	References	12

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features, and sustaining natural systems.

Our role is to provide evidence, information, and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: https://jncc.gov.uk/about-jncc/

## Project Aims

Defra aims to identify an agreed uniform approach to applying natural capital rationale to managing the marine environment and so, working with its arms-length bodies, is commissioning an independent critical analysis of approaches, methods and tools to support development and application of a natural capital approach for the marine environment.  The ultimate purpose of the project will be to evaluate existing developments in the field in a coordinated and meaningful way, to inform the development of a national framework, methods and guidance for marine natural capital assessment to support the objectives of the 25 Year Environment Plan.

The aim of the project is to perform an evaluation of existing marine natural capital tools, methods, and projects and to develop recommendations for a common approach that could be applied in the context of marine policy and management. This process will include the identification of important gaps in evidence or weaknesses in methods and how these might be addressed. Recommendations on the best current approaches will be given and priority areas for further development identified.

The project will mainly consider approaches that have been developed directly in the context of informing marine resource management and/or marine policy in the UK, although the most relevant international examples of best practice should also be considered. There will be a greater focus on the assessment of ecosystem services and tools such as asset and risk registers than on methods for economic valuation.

## Project Background

The policy and regulations governing marine environmental assessment, monitoring and management are founded in the application of the Ecosystem Approach1, e.g. UK Marine Policy Statement, UK Marine Strategy (2019), OSPAR, marine plans.  An Ecosystem Approach requires equitable consideration of environmental, social and economic issues.  The 25 Year Environment Plan (25YEP) (2021) recognises that the full value of the benefits offered by the environment and cultural heritage needs to be assessed in order to make appropriate choices on sustainable use of natural resources. The Dasgupta Review (2021) stresses the importance of the assessment of Natural Capital in the management of biodiversity and the sustainable use of natural resources. Taking a natural capital approach (as part of the Ecosystem Approach) allows the environment its due regard as a natural asset and contributor to the overall economy and societal wellbeing. Whilst application of the natural capital approach on land is developing at pace, challenges remain to applying it to the marine environment. A number of organisations have picked up the challenge and developed, independently, solutions in the form of case studies, pilots, interpretation of existing evidence, conceptual frameworks, methods and tools.  At this stage it is considered beneficial to evaluate the piecemeal marine natural capital assessment approaches that have been developed to date, to identify the most promising and make recommendations for a common approach, which could be used if appropriate; and further to inform the development of future work.

## Project Objectives

To meet the overall aim of this project (Section 2), the objectives are to:

- Collate information about existing marine natural capital tools, methods and projects (hereafter referred to as the products), and perform an in-depth SWOT (Strengths, Weaknesses, Opportunities, Threats) analysis on each, including consideration of their relevance to marine policy and management.

- Based on the results of the SWOT analysis for each product undertaken in 1 above, consider the suite of products collectively in order to:

  - identify the most effective elements across the existing products

  - identify, and prioritise, the principal methodological weaknesses or evidence gaps.

- Recommend a common approach making the most of the strengths of existing products and enabling critical gaps to be addressed.

- Prepare a clearly formulated question for a Quick Scoping Review (QSR) relevant to addressing a key gap (as identified in 2b above).

- Undertake a Quick Scoping Review using the question identified in 4 above.

## Project Objectives: Detailed tasks

This project will focus on mechanisms for the selection, collation and presentation of evidence on the extent and condition of marine natural capital assets (including both habitats and species), and the delivery and status of ecosystem services, goods and benefits. Marine in this context includes both intertidal and subtidal areas, estuaries, the coast and offshore. Tools and approaches such as asset and risk registers, natural capital asset indices, logic chains, asset-service matrices, and physical accounts are therefore all within scope. Methods for monetary valuation and economic accounting are not within the scope of work, although should be considered where such work includes wider elements of the natural capital system (e.g. logic chains). This reflects the ongoing work to develop natural capital accounting standards both nationally and internationally. The relevance of outputs from valuation and accounting in terms of their application in policy and management contexts (including as a communication tool) is within the scope of the project.

The contractor will be expected to engage regularly with the project steering group, through meetings at start up, at the end the SWOT analysis (including to agree the QSR question) and at the conclusion of the project. Fortnightly catch ups with the JNCC project officer will also be required. All meetings are expected to take place remotely. Draft outputs will also be submitted to the steering group for review.

Part 1: SWOT Analysis

The SWOT analysis is expected to be completed within 2.5 months and should include the products in the following list.  Please note that this is not exhaustive and although Defra and its arms-length bodies will identify and supply copies of or links to relevant material, the contractor will be expected to do a small amount of independent searching and checking to identify other products and evidence to feed in to the analysis (particularly examples of international best practice). Additional products developed during early phases of Defra’s Natural Capital Ecosystem Assessment programme may be identified for inclusion in the SWOT.

Marine pioneer and related projects

- Ashley, M., Rees, S., Mullier, T., Reed, B., Cartwright, A., Holmes, L., Sheehan, E. (2020). Isles of Scilly Natural Capital Asset and Risk Register to Inform Management of Isles of Scilly Fisheries Resources. A report by research staff of the Marine Institute at the University of Plymouth

- Ashley, M., Rees, S.E., and Cameron, A. (2018). North Devon Marine Pioneer Part 1: State of the art report of the links between ecosystem and ecosystem services in the North Devon Marine Pioneer. A report to WWF-UK by research staff the Marine Institute at Plymouth University

- Hooper, T., and Austen, M. 2020. Application of the natural capital approach to Sustainability Appraisal. Final Report. October 2020. Report prepared as part of the South West Partnership for the Environment and Economic Prosperity (SWEEP) and the Marine Pioneer programme.

- Rees, S.E., Ashley, M., Cameron, A. (2019). North Devon Marine Pioneer Report 2: A Natural Capital Asset and Risk Register A SWEEP/WWF-UK report by research staff the Marine Institute at Plymouth University

Defra and arms-length bodies

- Defra. (2020). Enabling a Natural Capital Approach: Guidance. January 2020. https://www.gov.uk/guidance/enabling-a-natural-capital-approach-enca#enca-guidance

- Hooper, T., Ashley, M., Börger, T., Langmead, O., Marcone, O., Rees, S., Rendon, O., Beaumont, N., Attrill, M. and Austen, M. 2019. Application of the natural capital approach to the marine environment to aid decision-making. Phase 1 Final Report. Report prepared for the Department for Environment Food and Rural Affairs (project code ME5115)

- Lusardi, J., Rice, P., Waters, R.D., & Craven, J. (2018). Natural capital indicators: for defining and measuring change in natural capital. Natural England Research Report

- Thornton, A., Luisetti, T., Grilli, G., Donovan, D., Phillips, R. and Hawker, J., 2019. Initial natural capital accounts for the UK marine and coastal environment. Final Report. Report prepared for the Department for Environment Food and Rural Affairs.

- Wigley, S., Paling, N., Rice, P., Lord, A., and Lusardi, J. (2020) National Natural Capital Atlas, Natural England Commissioned Report Number 285.

Other UK examples

- Tillin, H.M., Langmead, O., Hodgson, B., Luff, A, Rees, S., Hooper, T. & Frost, M. 2019. Feasibility study for a Marine Natural Capital Asset Index for Scotland. Scottish Natural Heritage Research Report No. 1071.

- Lovett, A., Turner, K., Sünnenberg, G., Ferrini, S., Stephanou, E., & Greaves, S. (2018). A natural capital asset check and risk register for the Anglian Water combined services area. Report to Anglian Water Services Ltd.

International

- Erhard, M., Teller, A., Maes, J., Meiner, A., Berry, P., Smith, A. et al. (2016). Mapping and assessment of ecosystems and their services. mapping and assessing the condition of Europe’s ecosystems: Progress and challenges. Luxembourg: Publications office of the European Union.

- Maes, J., Teller, A., Erhard, M., Grizzetti, B., Barredo, J. I., Paracchini, M. L. et al. (2018). Mapping and assessment of ecosystems and their services: An analytical framework for ecosystem condition. Luxembourg: Publications office of the European Union.

- Maes, J., Teller, A., Erhard, M., Liquete, C., Braat, L., Berry, P. et al. (2013). Mapping and assessment of ecosystems and their services. An analytical framework for ecosystem assessments under action 5 of the EU biodiversity strategy to 2020. Luxembourg: Publications office of the European Union.

- ETC/ICM Report 2/2019: EU Policy-Based Assessment of the Capacity of Marine Ecosystems to Supply Ecosystem Services Report:https://www.eionet.europa.eu/etcs/etc-icm/products/etc-icm-report-2-2019-eu-policy-based-assessment-of-the-capacity-of-marine-ecosystems-to-supply-ecosystem-services Annexes: https://www.eionet.europa.eu/etcs/etc-icm/products/annexes-to-etc-icm-report-2-2019-eu-policy-based-assessment-of-the-capacity-of-marine-ecosystems-to-supply-ecosystem-services

- Integrated Valuation of Ecosystem Services and Tradeoffs (INVEST) https://naturalcapitalproject.stanford.edu/software/invest

The SWOT analysis itself should summarise and explain, for each product assessed, its key Strengths, Weaknesses, Opportunities and Threats in the context of its application in marine policy and management, across the whole marine environment from Mean High Water Spring to offshore. Contractors are invited to give more details of the information they would compile in preparation for the SWOT analysis, but it is expected to include review of:

- conceptual frameworks, logic chains, or similar mechanisms used to connect assets, services, goods and benefits;

- the use of existing or bespoke asset/service classifications;

- the assets, services, goods and benefits considered;

- the elements of these assessed (e.g. extent, condition, spatial configuration);

- the method applied;

- data, metrics, indicators and models (which are used, and for what purposes);

- how/if thresholds, tipping points, sustainability or regulatory limits (or proxies for these) are included;

- stakeholder engagement in the process.

Details of these aspects of each product should be summarised in a supporting document. Additional summary information on each of the products should also be compiled, and is expected to include, as a minimum (where available/applicable for each product):

- Title and lead organisations

- Timescale

- Cost

- Customer

- Funding source

- Contractors

- Technical focus and application, e.g. research project, local management, Marine Spatial Planning, UK Marine Strategy.

- Spatial focus

- Description of outputs

- Weblink to final (or interim) outputs

The results of the SWOT analysis for each product should be considered collectively to identify best practice (in terms of the most robust, realistic and rigorous approaches to the different aspects of natural capital assessment) and the most significant weaknesses and gaps. These weaknesses/gaps should be prioritised in terms of the urgency with which they should be addressed to create the most credible, relevant and legitimate methods for marine natural capital assessment for marine management and policy, taking into account its potential application in applied decision making below Mean High Water Spring out to the offshore marine environment.

Contractors are invited to give more details of the process they would use to determine best practice and to prioritise weaknesses/gaps.  For example, would they assess convergence or divergence within the set of products assessed, take account of stakeholder input or peer review, and how much would they rely on expert judgement?

Recommendations should be presented (together with appropriate discussion and justification) for a common approach to marine natural capital assessment that makes the most of the strengths of existing products and enables critical gaps to be addressed.

Part 2: Quick Scoping Review (QSR)

The QSR is expected to take 1-2 months. Defining its scope will be an iterative process, depending on the outcome of the SWOT and Defra’s needs. The first stage will involve defining a primary and supporting secondary questions to address the top priority gap identified in part 1, which will be agreed with the project steering group, before carrying out the QSR itself. Contractors are invited to give details of the search and evaluation methods they would apply for the QSR.

## Outputs

The project has four deliverables.

- SWOT analysis and supporting information

- Summary report including key tabulated outputs from the SWOT, recommendations for a common approach, and discussion (including possible solutions) of key gaps

- Question for the QSR, to be approved by the Steering Group before proceeding

- Report containing the results of the completed QSR, with a method statement for the project with sufficient detail so it may be used by Defra for any future updates

## Dissemination

The report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to JNCC, the UK Conservation Agencies (name them), Defra, (list other parties)

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | Week beginning 12 July 2021 |
| Part 1 – SWOT analysis | July 2021 to mid Sept 2021 |
| Part 2 – Quick Scoping Review | Sept 2021 to 5 Nov 2021 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2021/22 is subject to availability of funds.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house  style guidance http://cms/JNCCIntranet63/pdf/NewDesign_JNCC_DesignIDv1.4LowRes.pdf  unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

(Note for author. If research project/contract See EQA Policy Appendix 4 (Communicating Evidence Quality).  Ensure that data management and storage requirements are stipulated, taking into account relevant policy for data access; see https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/).

Copies of documentation associated with the case studies should be provided in electronic format, with an associated reference catalogue.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Lauren Molloy

Email: lauren.molloy@jncc.gov.uk

Tel: +44 (0)1733 866905

Vicky Morgan

Email:  Vicky.morgan@jncc.gov.uk

Tel: +44 (0)1733 866830

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (these need to be compatible with JNCC’s Evidence Quality Assurance (EQA) Policy).

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough w/c 12th July 2021

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC, Defra and steering group (TBC) staff. Unless otherwise stated in your tender submission, bids will be forwarded to these agencies for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and understanding of marine policy and natural capital evidence) | 10 |  |
|  | Soundness and logicality of methods | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (20% of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 6 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Totals | 30 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

25 Year Environment Plan, 2018. A Green Future: Our 25 Year Plan to Improve the Environment. Defra. https://www.gov.uk/government/publications/25-year-environment-plan

Dasgupta Review, 2021. Final Report – The Economics of Biodiversity: The Dasgupta Review. HM Treasury. https://www.gov.uk/government/publications/25-year-environment-plan

UK Marine Strategy Part One: UK updated assessment and Good Environmental Status, 2019. Defra. https://www.gov.uk/government/publications/marine-strategy-part-one-uk-updated-assessment-and-good-environmental-status

In collaboration with the UK Marine Monitoring and Assessment Strategy (UKMMAS) Productive Seas Evidence Group (PSEG)

OSPAR and HELCOM jointly define the Ecosystem Approach as “the comprehensive integrated management of human activities based on the best available scientific knowledge about the ecosystem and its dynamics, in order to identify and take action on influences which are critical to the health of marine ecosystems, thereby achieving sustainable use of ecosystem goods and services and maintenance of ecosystem integrity”, see also the Convention for Biological Diversity.