## Cover Sheet
OFFICIAL Schedule 5B_Type_B_Take_On_Take_Off_and_Acceptance Issue Date: 05/11/2023

## Process
Annual Maintenance Package Process | Emergent/Proposed Work Approvals Process
Contractor identifies emergent/proposed work task
Yes
“Refurbish”, “repair”, “renew” or “replace” task?
No
Yes
Yes
No
Task within Limit of Liability?
No
Automatic Approval
MOD Authorisation required
Task under 16 hours, £500 material and £500 Specialist Sub-Con cost?
Authority raises WRF for AMP with Limit of Liability
Workboat arrives at Contractor location
Contractor takes formal custody, signs 2010B
Contractor conducts DMT and Condition Survey
Contractor completes Survey and Trials 1A, Proposed Work Scope on 2010B
Contractor sends 2010B to Authority for Proposed Work approval
7 calendar days
Contractor begins Planned Maintenance
Contractor begins automatic approval Proposed Work
Authority approves/rejects Proposed Work tasks
Contractor begins work on approved Proposed Work
Contractor completes Planned, Proposed and Emergent Work
Contractor conducts HATs and SATs
Contractor completes Survey and Trials 2A, Acceptance on 2010B
Contractor submits completed 2010B to Authority
Any rework post-trials is agreed for rectification with Authority
AMP Completed
Workboat delivered back to or collected by User

## Initial Summary
MOD Boats Form 2010B
Boat Upkeep Record - Type B
Boat Name
Date
Formal Custodianship | Formal Custodianship
Formal transfer of boat custodianship to Contractor | The Contractor's Authorised Representative shall sign this part of the form to acknowledge that they are now responsible for the care and custody of the boat, up until the point it is formally returned to the Authority.
On behalf of the Contractor, I accept formal custodianship for the boat identified above (including responsibility for its material state), until its acceptance by the Authority as indicated by the signing of Part E below.
Name
On behalf of (Company Name)
Signed
Date
Summary of Dynamic Machinery Trial | Summary of Dynamic Machinery Trial
Date of DMT: Defects from Survey and Trials form Part 1A: | The Contractor shall summarise the results of the Condition Survey and Dynamic Machinery Trial (DES Ships Boats Survey and Trials Form Part 1A Condition Survey), with particular attention given to areas of deficiency or concern observed. The Contractor shall present and agree with the Authority within one week of receipt of the craft.
Proposed Price of Work | Proposed Price of Work
The Contractor shall provide a quotation for the proposed scope of work identified in this form.
Agreed Limit of Liability for Emergent Work | Agreed Limit of Liability for Emergent Work
The Authority's Authorised Representative shall input the Limit of Liability that has been agreed with the Contractor to allow them to perform emergent work without further approval from the Authority.
Key Dates | Key Dates
Launch | The Contractor shall input the Key Dates as agreed during Take In Hand. Any revisions to dates shall be updated here.
HATs
SATs
Initial Lloyds Register
Follow-up Lloyds Register
Agreed Delivery Date | Agreed Delivery Date
The Contractor shall provide the date by which the work identified in in this form will be completed.
Authorisation to Proceed | Authorisation to Proceed
Name | The Authority's Authorised Representative shall sign this part of the form to authorise the Contractor to proceed with the work package as agreed in this form.
Signed
Date

## Condition Survey
Condition Survey
Survey Report on Material Condition of Vessel
Item | Areas and items to examine | Material Condition |  |  | N/A | Observations and Recommendations
|  | A | B | C
1. | HULL
2. | Hull External. Confirm the external hull is in good condition. Note any damage and repairs.
a. Steel
b. Aluminium
c. GRP/ Composite
d. Wood
3. | Sacrificial Anodes. Confirm all sacrificial anodes on the hull and external equipment are in good condition.
4. | Sea Inlets & Outlets. Confirm in good condition
5. | Draught marks. Confirm condition and accuracy.
6. | Collar - Closed Cell Foam Fender. Confirm in good condition. (i.e., ORC craft)
7. | RIB Collar - Inflatable. Confirm in good condition.
8. | Additional Fixed Hull Fenders. Confirm in good condition.
9. | Weather Deck. Confirm the external weather deck is in good condition.
a. Steel
b. Aluminium
c. GRP/ Composite
d. Wood
10. | Weather Decks. Confirm non-slip surfaces are in good condition.
11. | Weather Deck fittings. Confirm all fittings on the weather deck are in good conditions. (Cleats, bollards, stag horns etc)
12. | Lifting Points & Craft Lifting Hooks (i.e., Henriksen). Confirm are in good condition and where applicable hooks mechanism are in date. Check load test certificates.
13. | Freeing ports. Confirm clear of obstruction.
14. | Anchor and Cable warp. Confirm in good condition.
15. | Air Pipes. Confirm height above deck and means of closure with provision to prevent overpressure.
16. | Watertight Doors. Confirm condition, can be opened both sides and secure space watertight.
17. | Watertight Hatches. Confirm condition and secure space watertight.
18. | Fire Hatches. Confirm are in a good condition.
19. | Fire Flaps. Confirm are in a good condition.
20. | Hull Internal. Confirm the internal hull is in good condition. Note any damage and repairs.
21. | Confirm the Bilge area is in a clean condition.
22. | Deckhead. Confirm deckhead is in good condition.
23. | Bulkheads. Confirm all bulkheads are in good condition.
24. | Internal Fire Doors & Hatches. Confirm are in a good condition.
25. | Sea Inlets & Discharges Valves. Confirm shut off or non-return valves operate freely.
26. | Ventilators. Confirm operate freely.
27. | Buoyancy Tanks. Confirm are in a good condition
28. | Ballast Tanks. Confirm are in good condition.
29. | Fuel Tanks. Confirm are in good condition.
30. | Skylights. Confirm are in good order and can be closed from the outside.
31. | Portholes. Confirm are in good condition.
32. | Authorised hull modifications. Confirm any modifications since the last survey are in good condition.
33. | Unauthorised hull modifications. Confirm no unauthorised modifications have taken place since the last survey.
34. MACHINERY
35. | Craft with in-board Main Engines - Machinery space. Confirm the space is clean, tidy, free of clutter. Signage is clear. Escape routes clearly signed.
36. | Craft with in-board Main Engines. Confirm the engines are in a good condition and securely mounted with guards, exhausts, fuel lines securely installed.
37. | Out-Board Motor Craft. For craft with OBM, confirm securing, fuelling and control systems are in good condition.
38. | Out-Board Motor Craft with assigned OBMS. Confirm the OBM and propeller are in good condition.
39. | Remote stops installed and functional.
40. | Main Fuel. Check the following:
a. Type of fuel
b. Stowage
c. Signage
d. Shutoffs
e. Fuel filtering arrangements
f. Fuel filling arrangements.
g. Fuel tank vents and associated pipework.
41. | Fuel Pipework. Confirm pipework is in a good condition and of the right material and secure.
42. | Valves. Confirm remote means of closing valves on tanks that contain oil fuel, lubricating oil and other flammable oils, and valves operate freely.
43. | Tanks for petrol engine craft. Confirm a suitable approved hydrocarbon gas detector fitted located under or adjacent to tank. Confirm no electrical equipment residing in the vapour area, or are ignition protected.
44. | Exhaust pipework. Confirm pipework is in a good condition of the right material and secure.
45. | Engine cooling system. Confirm filter and seacock isolation in good condition and function correctly.
46. | Fans. Machinery spaces and battery boxes if fitted. Confirm operation.
47. | Compressed air. Confirm system is in a good condition. Check calibration of safety valves.
48. | Bilge Pumps Powered. Confirm are in a good condition, free from obstruction and function correctly (ie Electrical powered pumps)
49. | Bilge Pumps Manual. Confirm all hand operated bilge pumps in a good condition, free from obstruction and function correctly.
50. | Bilge Alarms. Confirm all work correctly.
51. | Pumps Fuel transfer. Confirm in good operating condition.
52. | Pumps Bilge. Confirm in good operating condition. (Electrical and manual pumps.)
53. | Pumps Ballast. Confirm in good operating condition.
54. | Hydraulic system. Confirm in good condition without leaks.
55. PROPULSION AND STEERING
56. | Propulsion shafts. Confirm in good condition and exposed shafts are guarded (Including Cardan shaft)
57. | Steering Gear. Confirm in a good condition.
58. | Propulsion. Confirm in a good condition.
a. Propeller (Open)
b. Propeller (Enclosed.)
c. Water Jet
59. AUXILIARY MACHINERY
60. | Ramps. Confirm in good order and functions correctly. Confirm remote controls.
61. | Anchor windlass. Confirm in good order and functions correctly. Confirm remote control.
62. | Winches. Confirm in good condition. Confirm remote control.
63. ELECTRICAL
64. | Alternators. Confirm are in a good condition, securely mounted, fitted with secure guards
65. | Generators. Confirm are in a good condition, securely mounted, fitted with secure guards, exhausts, fuel lines.
66. | Remote stops installed and functional.
67. | Batteries. Confirm are in a good condition, securely mounted in a container, terminals covered to be electrically safe. Unobstructed ventilation for lead acid batteries.
a. Engine Start Batteries
b. Craft Power Batteries
c. Navs and Comms Batteries
68. | Inverters. Confirm are in a good condition
69. | Distribution Boards. Confirm are in a good condition.,
70. | Electrical cables. Confirm are in a good condition and all cables securely clipped and terminated.
71. | Sockets and Shore Supply connectors. Confirm are in good condition.
72. | Lighting. Confirm are in a good condition, provide adequate lighting for all areas of the craft.
73. FIRE DETECTION/FIRE FIGHTING
74. | Fire Plan. Confirm the craft has a fire plan.
75. | Fire Detectors. Confirm in good condition and comply with the fire-plan.
76. | Fire Alarms. Confirm in good condition and comply with the fire-plan.
77. | Fire extinguishers. Confirm the craft is fitted with the right type, size and numbers of extinguishers for the relevant areas of the craft complying with the fire plan. Confirm in date status of all extinguishers.
a. CO2/CO2 with bayonet
b. Dry Powder
c. Foam AQQ
d. Water
e. Blanket
f. Fire Bucket
78. | Fixed firefighting systems for machinery spaces (Pyrogen etc.). Confirm the system is in good condition and in-date.
79. WHEELHOUSE
80. | Structure. Confirm the outer structure is in good condition.
a. Steel/Armour protection
b. Aluminium
c. GRP/ Composite
d. Wood
81. | Skylights. Confirm are in good order and can be closed from the outside.
82. | Windows. Confirm are in good condition.
83. | Window Wipers and water jets. Confirm in good condition
84. | Wheelhouse Doors. Confirm are in good condition and able to operate from both sides.
85. | Craft Controls. Confirm all craft steering and engine controls are in a good condition. (Steering system, throttle, and gear controls etc)
86. | Craft Machinery Instrumentation Alarms Indication. Confirm the instrumentation in the wheelhouse are in good condition.
a. Engine Instrumentation
b. Auxiliary systems indication. (i.e., generators)
c. Auxiliary systems Alarms
d. Steering Indication (i.e., rudder angle etc)
e. Propulsion and Trim Equipment indication.
f. Fire Alarms
g. Bilge Alarms
h. Engine Alarms
87. OPEN BOAT CONSOLES
88. | Console. Confirm the console structure is in good condition and secure to the craft.
89. | Craft Controls. Confirm all craft steering and engine controls are in a good condition. (Steering system, throttle, and gear controls etc)
90. | Craft Machinery Instrumentation Alarms Indication. Confirm the instrumentation on the console are in good condition.
a. Engine Instrumentation
b. Engine Alarms
c. Steering Indication (ie rudder angle)
d. Propulsion and Trim Equipment indication
e. Bilge Alarms
f. Engine Alarms
91. SEATING
92. | Non shock mitigation seating: Confirm in good condition and secured to craft.
93. | Shock mitigation seating: Confirm in good condition and secured to craft.
94. NAVIGATION AND COMMUNICATION
95. | Navigation equipment. Confirm the correct operation and condition of the following:
a. Compass Gyro
b. Compass Fluxgate
c. Compass GPS
d. Compass Magnetic
e. Secondary back up compass
f. Deviation cards for the magnetic compasses.
g. Pelorus
h. Radar
i. GPS
j. ECDIS (using UKHO charts)
k. Chart plotter (using commercial charts -Navionics, Blue View etc)
l. Automatic Identification System (AIS)
m. Depth sounder
n. Speed and distance indicator
o. Voyage data recorder
p. Wind speed and direction indicator
q. Navtex
r. Navigation Lights.
s. Navigation Shapes
t. Radar reflector
u. Horn
v. Signalling Lamp
96. | Internal communications.
97. | VHF DSC Radio. Confirm in good condition and with correct MMSI loaded and licence.
98. | VHF handheld Radios. Confirm in good condition and charged.
99. | MAST
100. | Mast. Confirm all masts carrying navigation lights, antenna or other equipment are in good condition.
101. | Mast Equipment. Confirm all equipment on the mast (navigation lights, antenna, radar scanner) are in good condition.
102. | Yachts. Mast Sailing. Confirm all mast for sails and associated fittings are in good condition.
103. LIFESAVING
104. | Confirm the following are in good condition, in date and comply with the requirements of the vessel type and passenger carriage.
If these items are not held on board, state what arrangements are made.
a. Lifejackets
b. Life Rafts
c. Life Rafts Hydrostatic releases
d. Lifebuoys
e. Man Overboard recovery
f. Parachute flares
g. Handheld flares
h. Line Throwing apparatus
i. Waterproof torch
j. Medical Kit
k. EPIRB
l. SART
105. ACCOMMODATION
106. | Accommodation area. Confirm the area is in good condition and free of clutter. Ensure the 2 means of escape a clear to use and appropriately signed.
107. | Smoke detectors. Confirm the space has been fitted with Fire Detectors and Alarms.
108. | Galley. Confirm all appliances are in good condition.
109. | Toilet. Confirm the toilet is in good condition and associated seacock operate freely.
Copy from Condition Survey Report

## Proposed Work Scope
MOD Boats Form 2010B
Boat Upkeep Record - Type B
WORKBOAT ASRP - Proposed Work Scope
| Tariff Reference No. | Title | Description Notes | [6 empty] | Authority Agreement | Total cost
| Total | [9 empty] | 0
| Non-Tariffed Reference No. | Title | Description Notes | Hrs | Hrs cost | Material Cost | Sub Con Cost | Material inc handling fee | Sub-Con inc handling fee | Authority Agreement | Total cost
| Total |  |  | 0 | 0 |  |  | 0 | 0 |  | 0
0

## Proposed Work Photos
Proposed Work Photos
Reference No. | Title | Photo(s)

## Emergent Work Scope
MOD Boats Form 2010B
Boat Upkeep Record - Type B
WORKBOAT ASRP - Emergent Work Scope
| Tariff Reference No. | Title | Description Notes | [6 empty] | Total cost
Total
| Non-Tariffed Reference No. | Title | Description Notes | Hrs | Hrs cost | Material Cost | Sub Con Cost | Material inc handling fee | Sub-Con inc handling fee | Total cost
| Total |  |  |  | 0 |  |  | 0 | 0 | 0
0

## Emergent Work Photos
Emergent Work Photos
Reference No. | Title | Photo(s)

## Financial Summary
MOD Boats Form 2010B
Boat Upkeep Record - Type B
Financial Summary
Total Proposed Work Scope
Total Further Emergent Work
Total Final Price

## HATS & SATS
HATs & SATs
Survey and Trials form 2A | Overview Of Trials | [9 empty] | V 1.0
2023-10-16
Boat Type: |  |  |  | Boat Number: |  |  |  |  | Trial Date:
Trials Conducted
Trial 1 Speed Trial | [6 empty] | Yes ☐ / No ☐
Trial 2. Acceleration | [6 empty] | Yes ☐ / No ☐
Trial 3. Emergency Stopping | [6 empty] | Yes ☐ / No ☐
Trial 4. Turning Circles | [6 empty] | Yes ☐ / No ☐
Trial 5. Zig Zag | [6 empty] | Yes ☐ / No ☐
Trial 4. Endurance and Fuel Consumption | [6 empty] | Yes ☐ / No ☐
Trial 5. Sea Keeping | [6 empty] | Yes ☐ / No ☐
Trial 6. Bollard Pull | [6 empty] | Yes ☐ / No ☐
Craft Performance
|  |  | Satisfactory |  | Not Satisfactory |  |  | Notes
Craft Stability |  |  | ☐ |  | ☐
Craft course keeping |  |  | ☐ |  | ☐
Craft manoeuvrability |  |  | ☐ |  | ☐
Craft speed performance |  |  | ☐ |  | ☐
Craft acceleration |  |  | ☐ |  | ☐
Craft ability to stop |  |  | ☐ |  | ☐
Sea Keeping |  |  | ☐ |  | ☐
Defects
Detail any defects noted during the trial:
Declaration
The above boat has completed the trials contained within document and the information contained is a true record of the Boats performance on the date shown. The craft is /is not in a safe and seaworthy condition for acceptance and return to service.
Trial witnessed by Contractor representative
Signature |  | Name |  |  |  | Company |  |  |  | Date
Trial witnessed by Authority representative
Signature |  | Name |  |  |  | Authority Section |  |  |  | Date
Copy from HATs and SATs Report

## Acceptance
MOD Boats Form 2010B
Boat Upkeep Record - Type B
Confirmation that loose items, fuel and oil levels are as pre-refit (Please Tick) | The Contractor shall check the box to confirm that all loose items, fuel and oil levels have been returned to the state they were before the start of the refit.
Acceptance of Boat on behalf of DE&S | The Authority's Authorised Representative shall sign this part of the form to indicate their acceptance of the work completed, as described by the Contractor in this form.
Name
Signed
Date