ROYAL CORNWALL MUSEUM – ENHANCEMENT PROGRAMME	17 January 2024	Version 0.1

PROJECT:  Gallery – Main and Nature

SUMMARY

Proposed route to market – Design and Build:

Phase 1: Design

| CORE REQUIREMENTS | KEY ACTIONS REQUIRED | KEY OBJECTIVES | BUDGET | TIMELINE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |
| - Conservation Architect / Designer - Quantity Survey - Structural Engineer - Mechanical & Electrical Design - Contract administrator - Principal Designer (CDM Regs) | - Finalise budget - Create statements of requirements - Create / issue ITT - Scope out CDM Pre-Construction document | - Appointment of lead contractor on design and build basis - Design phase concluded July 2024 | Funding from Shared Prosperity Fund £1,050,000m (including VAT) Design element being £100k and £200k (including VAT) Build element being £800k and £900k (including VAT) | ITT |  | E.S | Design |  |  |  |  |  | Design – Contract Admin |  |  |  |

Phase 2: Construction

| CORE REQUIREMENTS | KEY ACTIONS REQUIRED | KEY OBJECTIVES | BUDGET | TIMELINE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |
| - Main Contractor - Principal Contractor (CDM Regs) |  | - Construction concluded Jan 2025 |  |  |  |  |  |  |  |  |  | Build phase |  |  |  |  |

| KEY / LEGEND CDM – Construction Design Management Regulations (2015) ITT – Invitation to Tender E – Evaluation E.S – Evaluation and 10 day Standstill (if above threshold) | Funding phase JCT – Joint Contracts Tribunal Below Threshold (Services) less than £213,477 (inc. VAT) Design phase Below Threshold (Works) less than £5,336,937 (inc. VAT) Build phase Above Threshold (Services) greater than £213,477 (inc. VAT) | ITT phase |
| --- | --- | --- |