OPEN TENDER

RSSB INVITATION TO TENDER FOR THE PROVISION OF: T1140 Defining the requirements of a seat comfort selection process

Deadline: Friday 29th December 2017

ITT Reference T1140 Defining the requirements of a seat comfort selection process

# TENDER DOCUMENTS

1.1	Tenders shall be submitted in accordance with the following instructions.  It is important that all the information requested is provided in the format and order specified.  If the Tenderer does not provide all of the information RSSB has requested within the tender pack, RSSB may reject the tender as non-compliant.

1.2	Tenderers must obtain for themselves, at their own responsibility and expense, all information necessary for the preparation of their tender.  Tenderers are solely responsible for any costs and expenses in connection with the preparation and submission of their Tender, and all other stages of the selection and evaluation process.  Under no circumstances will RSSB, or its advisors, be liable for any costs or expenses Tenderers, their sub-contractors, suppliers or advisors incur in this process, including if this tendering process is terminated or amended by RSSB.

1.3	Tenderers are solely responsible for obtaining the information that they consider is necessary in order to prepare the content of their tender and to undertake any investigations they consider necessary in order to verify any information RSSB provides during the procurement process.

1.4	All pages of the tender submission must be sequentially numbered (including any forms to be completed and returned).

1.5	All specifications, plans, drawings, samples and patterns and anything else that RSSB issues in connection with this ITT, remains the property of RSSB and are to be used solely for the purpose of tendering.

1.6	At any time prior to the deadline for receipt of questions, RSSB may modify the tender documents by amendments in writing.

1.7	RSSB (at its sole discretion) may extend the deadline for receipt of Tenders.

RSSB reserves the right to modify or to discontinue the whole of, or any part of, this tendering process at any time and accepts no obligation whatsoever to award a contract.

# GENERAL, LEGAL & COMPLIANCE

2.1	RSSB will check each tender for completeness and compliance with the tender instructions.  RSSB reserves the right to reject any tenders it considers substantially incomplete, or non-compliant (each tender will be assessed on its own merit, according to the level/importance of omitted or non-compliant content).

2.2	The Tenderer will be excluded should any of the grounds for mandatory rejection or discretionary rejection be triggered. Mandatory requirements can be viewed within the Public Contracts Regulations 2015.

2.3	Tenderers are required to confirm in their tender response, they are able to meet all mandatory and discretionary requirements.

2.4	The Tenderer will be excluded should it be assessed that it has a high risk of:

  - Insolvency over the lifetime of the contract; e.g. the Tenderer may be excluded if its current assets to current liabilities ratio is less than 1;

  - Insufficient financial capacity to deliver the services effectively; or

  - Over-dependence on RSSB (e.g. the Tenderer may be excluded if its turnover is less than £ [no more than2x the contract value]

# 3.0	TENDER INSTRUCTIONS

3.1	“RSSB” means the contracting authority, seeking to invite suppliers to participate in the procurement process.

“You” or “Supplier” means the legal entity completing these questions, seeking to be invited to the next step of the procurement process Invitation to Tender (ITT)

3.2	Please ensure all questions are completed in full and in the format requested. Failure to do so may result in your submission being disqualified. If the question does not apply you need to clearly state N/A.

3.3	If it is necessary for you to provide additional information this should be provided as an appendix and clearly referenced as part of your declaration.

3.4	RSSB REPRESENTATIVE

Your main point of contact is: shareditt@rssb.co.uk

RSSB OVERVIEW

If you wish to find out more about RSSB, please visit our website at www.rssb.co.uk

Timetable

The timetable for this procurement follows.  This is intended as a guide and whilst RSSB does not intend to depart from the timetable, it reserves the right to do so at any stage.

The expected milestones are set out below:

|  | Start Date |
| --- | --- |
| Expression of interest meeting | 06/10/2017 |
| RFP issued | 27/11/2017 |
| Supplier clarification questions deadline | 15/12/2017; 12:00 hours |
| Deadline for Submitting Tenders | 29/12/2017; 17:00 hours |
| Post Tender Clarification & Evaluation | W/C 02 Jan 2018 |
| Estimated notification of award decision | W/C 22 Jan 2018 |
| Target contract commencement date | W/C 05 Feb 2018 |

Note: RSSB reserves the right to amend these dates as business requirements demand and will communicate any changes to tenderers.

3.5	QUESTIONS

Should you have any questions relating to the project, please email these before the deadlines detailed in the project timeline above to ensure that these questions can be effectively addressed? To ensure equal and fair treatment to all potential suppliers, RSSB will circulate all questions and responses anonymously.

Questions should be emailed to: shareditt@rssb.co.uk

# 4.0	Evaluation Information

4.1	In the interests of an open, fair and transparent assessment, this document sets out how RSSB intends to evaluate tender responses.  It outlines the evaluation criteria and respective weightings, as well as the evaluation methodology to be applied.

4.2	Verification of Information Provided

Whilst reserving the right to request information at any time throughout the procurement process. RSSB may enable the Supplier to self- certify that there are no mandatory/ discretionary grounds for excluding their organisation. When requesting evidence that the supplier can meet the specified questions relating to Technical and Professional Ability RSSB may only obtain such evidence after the final tender evaluation decision and only from the winning Supplier only.

4.3	Please self-certify whether you already have, or can commit to obtain, prior to the commencement of the contract, the levels of insurance cover indicated below:

- Employer’s (Compulsory) Liability Insurance = £2M

- Public Liability Insurance = £1M

- Professional Indemnity Insurance = £1M

4.4	Sub- contracting Arrangements

Where the Supplier proposes to use one or more sub- contractors to deliver some or all of the contract requirements, a separate Appendix should be used to provide details of the proposed delivery model that includes members of the supply chain and percentage of work being delivered by each sub -contractor and the key deliverables that each sub- contractor will be responsible for.

RSSB recognises that sub- contracting arrangements may be subject to change and not finalised until a later date. However, Suppliers should be aware that where information provided to RSSB indicates that sub- contractors are to play a significant role in delivering the key requirements and any changes to those sub- contracting arrangements significantly affect the ability of the supplier to deliver key requirements the Supplier should notify RSSB immediately of any changes in the proposed supplier sub-contractor arrangements. RSSB reserves the right to deselect the Supplier prior to any award of contract based on an assessment of the updated information.

4.5	Consortia Arrangement

If the Supplier completing this tender submission is doing so as part of a proposed consortium the following information must be provided:

- Names of all consortium members;

- The lead member of the consortium who will be contractually responsible for delivery of the contract (if a separate legal entity is not being created); and

- If the consortium is proposing to form a legal entity, full details of the proposal should be submitted as an Appendix with this Tender.

- RSSB may require the consortium to assume a specific legal form if awarded the contract. If it is deemed that a legal incorporation is necessary for the satisfactory performance of the contract.

- All members of the consortium will be required to provide the information required in all sections of the Tender as part of a single composite response to RSSB i.e. each member of the consortium is required to contribute to completing the response document.

4.6	Confidentiality

RSSB reserves the right to contact the named customer contact and the nominated customer does not owe RSSB any duty of care or have any legal liability, except for any deceitful or maliciously false statements of fact.

RSSB confirms that it will keep confidential and will not disclose to any third parties for any information obtained from the named customer contact, other than to the Crown Commercial Services and or contracting authorities defined by the Public Contract Regulations.

# 5.0	Evaluation Process

5.1	The process that will be used to select an appropriate Tenderer and award the contract for this procurement is available in more detail in the  Evaluation Criteria.

The open procedure is a single stage process.

5.2	Marking for Award Criteria

An evaluation panel consisting of representatives of key stakeholders within RSSB will carry out the evaluation. The procurement team will only act as moderator during the assessment phases of the evaluation.

Each evaluation area is weighted to show the relative importance significance of the criteria specific area’s for assessment.

# 6.0	PROCESS AND PREPARATION OF RESPONSES

6.1	The Supplier shall not enter in any agreement or arrangement with any third party which would in any way cause RSSB or its members to incur any financial obligations to the Supplier or any third party.

6.2	The Supplier shall not approach any Customer employee, the Customer’s Representative or its agents to discuss any aspects of the Tender. All communication should be conducted via the Customers Representative.

6.3	The Supplier shall not canvass support for the award of the contract by approaching any employee of RSSB, its Representative or its agents.

6.4	The documents as enclosed are to be accepted in their entirety.   No alteration 	 Representative before the date stated for the receipt of tenders. If any alteration is made or these instructions to Suppliers are not fully complied with the tender may be invalidated.

6.5	The conditions of contract included in this Invitation to tender apply. The Suppliers standard terms of business or trade will not be accepted.

6.6	Any requested changes to the conditions of contract must be detailed on the Contract Issues Memo document included for consideration. If this is not completed, it is assumed that the Supplier has accepted all terms and conditions detailed and no further changes will be accepted.

6.7	The Supplier shall be deemed to have satisfied itself as to the nature, extent and the content of the goods, services or works to be provided, the extent of staff required and all other matters, which may affect the tender.

6.8	All prices quoted to be GBP (unless otherwise requested in the Invitation to Tender) exclusive Value Added Tax and firm.

It is the Suppliers responsibility to ensure the tender is correct at the time of submission.  No amendment to the tender will be allowed after the due date.

6.9	Any questions must be emailed to the main point of contact no less than five days before the return date. Note: questions/responses will be circulated anonymously to all Suppliers invited to tender.   Tenders received after the closing date and time will not be considered.

6.10	The Customers Representative reserves the right to correct any omissions or inaccuracies in the Invitation to Tender and to clarify and/or amend any of the Customers’ requirements, up to seven days before the return of tenders.

6.11 	All information supplied by RSSB must be treated in confidence and not disclosed to third parties except insofar as this is necessary to obtain sureties or tenders required during the preparation of the Tender.  All information provided by Suppliers will be treated in confidence except in stances where references may be sought.

6.12  	 RSSB reserves the right to cancel this Tender at any point and any cost incurred in the preparation of this Tender is at the Bidder’s expense.

6.13	Tenders must remain open for acceptance for a period of 180 calendar days from the submission date.

6.14	The tenderer should include the following information as part of their tender response:

Legal entity name of Tenderer

Contact person's name, email address, telephone number and postal address for enquiries relating to this procurement

Name:

Postal address:

Telephone number:

Email address:

Tenderer’s registered address

Tenderer’s website address (if available)

Please tick the box for the legal form of the Tenderer

- Sole Trader ☐ - Partnership ☐ - Limited Liability Partnership ☐ - Private Limited Company ☐ - Public Limited Company ☐ - Local Council ☐ - Voluntary/ charitable/ not for profit organisation ☐ - Other (please specify below) ☐

If ‘Other’ has been selected from the question above please provide details.

If your business is a registered company, charity or any other registered organisation (including limited, non-limited or Industrial and Provident Society), please state your registration number.  This must be the registration number of the Tenderer, providing the country and date of incorporation / registration if other than the UK.

Name of ultimate parent company (if this applies)

Companies House Registration number of ultimate parent company (if this applies)

Additional Notes

- Fully answer the question given and consider the weighting for the section

- Explain how you will meet the criteria and provide evidence to support your response.

- Further reading on how to complete the tender is available in section 10

# 7.0 TENDER EVALUATION (SELECTION CRITERIA)

| Heading | Specific question(s) | Evaluation Criteria |
| --- | --- | --- |
| S1 Experience of the supplier in Human Factors Research involving physical ergonomics. | Could you provide a short description (in no more than two pages) of at least two Human Factors Research projects involving physical ergonomics, that you have delivered to clients over the last five years? Please provide a short explanation of why they are relevant to our needs. | Pass/Fail Note: Tenderers who do not achieve a “Pass” mark for this question will be disqualified from the tender evaluation process and said tenderers submission will not be evaluated further. Pass: The tenderer has provided a short description, in no more than two pages, of at least two Human Factors Research projects involving physical ergonomics, that the tenderer has delivered to clients over the last 5 years and the aforementioned projects provided RSSB with a strong degree of confidence in the tenderers experience in delivering Human Factors Research projects involving physical Ergonomics. Additionally, the tenderer provides a short explanation as to why the tenderers examples are relevant to RSSB’s needs. Fail: The tenderer either fails to provide a short description, in no more than two pages, of at least Human Factors Research projects involving physical ergonomics that the tenderer has delivered to clients over the last five years or the tenderer has not provided a short explanation as to why the tenders examples are relevant to RSSB’s needs or fails to provide RSSB with sufficient confidence in its experience of delivering Human Factors Research projects involving physical ergonomics. |
| S2 Experience of the supplier in the measurement of seat dimensions, and seat comfort testing methods. | Could you provide a short description (in no more than two pages) of at least two projects where you have measured seat dimensions, and undertaken seat comfort testing methods over the last five years? Please provide a short explanation of why they are relevant to our needs. | Pass/Fail Note: Tenderers who do not achieve a “Pass” mark for this question will be disqualified from the tender evaluation process and said tenderers submission will not be evaluated further. Pass: The tenderer has provided a short description, in no more than two pages, of at least two projects where the tenderer has measured seat dimensions and undertaken seat comfort testing methods over the last five years and the aforementioned projects provided RSSB with a strong degree of confidence in the tenderers experience in the aforementioned. Additionally, the tenderer provides a short explanation as to why the tenderers examples are relevant to RSSB’s needs. Fail: The tenderer either fails to provide a short description, in no more than two pages, of at least two projects where the tenderer has measured seat dimensions and undertaken seat comfort testing methods over the last five years or has not provided a short explanation as to why the aforementioned projects are relevant to RSSB’s needs or fails to provide RSSB with sufficient confidence in its experience of measuring seat dimensions, and undertaking seat comfort testing methods. |

# 8.0 TENDER EVALUATION (AWARD CRITERIA)

8.1	ITT Assessment

The Contract Award decision is solely based on the basis of Tenderer proposal and price offering.

8.2	RSSB uses the following quality / price ratio to determine the outcome of the evaluation where quality (technical evaluation) and price are weighted and scored individually before being combined.

Quality 70% Price 30%

8.3	Technical criteria are weighted and scored as a percentage of the maximum score available with a minimum quality threshold set.

Technical Evaluation

  - 8.4	Tenders are assessed on how well they satisfy the technical evaluation criteria.

  - The relative importance of each criterion is established by giving it a percentage weighting so that all the weightings equal 100%.  The Evaluation Matrix provides details of the weightings that RSSB will use in assessing Tenderer proposals.

  - The Technical Evaluation will be carried out using Tenderer responses to the tender specification using the scoring scheme (identified in Table below).

8.5	The scored responses are generally assessed out of a maximum of five (5).  The Evaluation Panel will not be allowed to give partial scores (for example 3.5); however, once all scores are aggregated, the technical scores will be rounded to two decimal places prior to consolidating with the price evaluation.

8.6	The following shall constitute a failure to evidence satisfactory delivery of the requirement(s) of the procurement and will automatically disqualify the Tenderer:

- A grade of zero (0) in any of the evaluated technical/quality questions in Section D of Schedule One (a) of Part B of the ITT before the weightings are applied; or

- a grade of one (1) in more than one of the evaluated technical/quality questions in Section D of Schedule One (a) of Part B of the ITT before the weightings are applied

8.7	Those Tender Responses which fail to demonstrate satisfactory delivery of the requirement(s) of the procurement by reason of failing to achieve these minimum thresholds will be set aside and not considered further.

| - Grade | - Definition of grade |
| --- | --- |
| - 5 | - A wholly excellent Tender Response that (where applicable): - Addresses all aspects of the question in an informed and comprehensive manner; - Demonstrates a thorough understanding of what is being asked for; - Provides evidence of how that understanding can be applied in practice; - Offers full confidence that the Tenderer will deliver the service in full; - Addresses the majority of areas of doubt and uncertainty; and - Provides certain, unambiguous commitments or statements of intent that permit reliance through translation into contractual terms |
| - 4 | - A good Tender Response that (where applicable): - Addresses all aspects of the question and is generally of a good standard; - Demonstrates a good understanding of what is being asked for; - Provides a worked-up methodical approach; - Offers confidence that the Tenderer will deliver the service in full with limited areas of doubt or uncertainty; - Addresses key areas of doubt and uncertainty; and - Provides commitments that can be translated well into contractual terms |
| - 3 | - A satisfactory Tender Response that (where applicable): - Addresses the majority of the question and is generally of a good standard but lacks substance or detail in some areas; - Demonstrates an understanding of what is being asked for; - Provides a satisfactory approach; - Offers a general level of confidence that the Tenderer will deliver the service (but with room for doubt in some areas); - Address some areas of doubt and uncertainty; and - Provides some commitments that can be translated well into contractual terms. |
| - 2 | - A Tender Response that (where applicable): - Addresses some of the question but either lacks relevant information and detail or lacks substance in a manner that would suggest the response is a “model answer”; - Demonstrates some understanding but with a lack of clarity in key areas; - Provides an approach which is not wholly appropriate or viable or lacks evidence; - Shows that the level of confidence that the supplier can deliver does not outweigh the doubt; - Does not address many areas of doubt and uncertainty; and - Does not offer sufficient commitment (with doubt as to the extent to which would translate into contractual terms) |
| - 1 | - A generally unsatisfactory Tenderer response that (where applicable): - Does not address the question or has omissions; - Lacks understanding in significant areas: - Provides an approach which has gaps or creates concerns; - Shows that the level of confidence that the supplier can deliver is low; - Creates uncertainty; and - Displays significant lack of commitment (with doubt as to the extent to which would translate into contractual terms) |
| - 0 | - A wholly unsatisfactory Tenderer response that (where applicable): - Provides no response or omissions/oversights that prevent scoring; - Refuses to deliver the requirement; and - Creates concerns so significant that the response would be detrimental to the interests of RSSB |

# 9.0 ITT Evaluation Matrix (Award Criteria)

| Heading | Specific question(s) | Evaluation Criteria | Weight |
| --- | --- | --- | --- |
| A1 Robust methodology and ability to apply it to client’s needs. | In no more than six pages, the tenderer provides a method statement of how it is intended to develop, test and validate the requirements of a seat comfort selection process, and to deliver against all aspects of the objectives of this work. How will the project tasks be split to meet the objectives of the work? What is the proposed methodology for developing, testing and validating the seat comfort selection process? What methods will be used to define: the minimum requirements of seat comfort; testing methodology; and scoring system? Please detail the approach proposed to test seat comfort. How will the seat comfort selection process be validated, and made replicable for use by other industry stakeholders? | The Tenderer’s response: - Explains how they would apply their expertise to meet the specification, including how they would conduct the study. - Demonstrates their understanding of the objectives and provide a coherent and systematic approach to meeting these objectives. - Proposes a sound and credible methodology to define the requirements of a seat comfort selection process, including the methods used to establish the minimum requirements of seat comfort, testing methodology, and scoring system. - Explains how the proposed methodology will validate and test the replicability of the seat comfort selection process. | 30% |
| A2 Independence, Knowledge and expertise in subject area | In no more than four pages, detail the knowledge and expertise of the team who will be undertaking this work, relevant to the development and testing of a seat comfort selection process. What is the tenderer’s knowledge and expertise in the area of seat comfort? How will the tenderer apply their knowledge, expertise and skills to meet the objectives of this work? How will the team ensure fair, independent, and impartial outputs are delivered? | The Tenderer’s response includes: - Evidence of their knowledge and expertise in the subject area. - Evidence of their technical competence in seat comfort research. - Describes how they will apply their knowledge, expertise, and technical competence to deliver the objectives of this research. - Evidence of team independence and impartiality. | 20% |
| A3 Project Delivery and resources | In no more than four pages, please identify the key roles and responsibilities that are essential to deliver the requirements of this work. It is not necessary to produce full bespoke CVs, but it is necessary to clearly identify every team member’s role, their relevant experience and contribution to delivery. How will adequate allocation of appropriate resources be made against each deliverable? How will the key tasks of this work be planned against a schedule? How will effective communication be achieved with key stakeholders, including RSSB, project steering group and the KTR Team? How will the team ensure the quality and the content of the deliverables are fit for purpose? | The tenderer’s response: - Identifies relevant individuals to deliver the work and demonstrates that the mix of skills covered are appropriate to deliver the project. - Identifies a team that has an appropriate mix of experience capable of delivering the objectives. - Identifies and describes which members of the team will be contributing to each deliverable. - Provides a credible plan for delivering successful outcomes to time, quality and cost, including the engagement with relevant project stakeholders. | 10% |
| A4 Risks and opportunities | In no more than two pages, tenderers should detail what risks and opportunities are foreseen in the delivery of the project. The tenderer should detail mitigating actions in relation to these risks, and how opportunities can be maximised. What are the potential risks to this project? How will these risks be managed? What are the potential opportunities that could be maximised in the delivery of this work? | The tenderer’s response: - Identifies appropriate risks and opportunities through the use of a risk register. - Identifies what mitigation actions will be taken with specific regard to each risk or challenge identified. - Identifies approaches to maximising any opportunities through effective management. | 5% |
| A5 Communication | How will you ensure effective communication with both yourself & RSSB? Additionally, how do you propose to communicate with key stakeholders | The tenderer’s response: - The tenderer provides a well thought out and appropriate communication plan for communication between the tenderer and RSSB. - The tenderers communication plan is effective in it's ability to achieve the objectives of the work. - The tenderer provides a robust statement for communicating with key stakeholders. | 5% |
| A6 Cost of project | Provide a fixed cost for the project and the associated cost break down. Describe how and why this represents value for money. | - The tender with the lowest total cost will receive 100% of the available weighted score (30%). Other Tenderer’s tenders will receive a pro-rated relative to the lowest cost according to the following formula: Score of other tender = lowest tender total cost / other tender total cost x 100%. | 30% |

# 10.0	PRICE EVALUATION

10.1	All prices quoted shall be in sterling (unless otherwise requested in the Tender Documents), exclusive of Value Added Tax and shall be firm.

10.2	A full and comprehensive breakdown of all costs and expenses to provide the goods, services or works requested in this invitation to tender must be provided and all assumptions must be clearly stated.

10.3	Failure to provide adequate detail may cause your tender to be judged non-compliant.

10.4	The construction of the price must be clear and easy to understand.  Where appropriate the use of tables to show pricing is preferred.  We require the following information:

    - A breakdown by grade and named individual, indicating the number of days to be worked on each task and the daily rate to be charged.

    - A list of sub-contracts with prices and copies of quotations where available (a similar breakdown by grade, named individuals and rates, as above, is required where the sub-contract is for manpower).

    - Details of any other costs, such as hire charges for equipment.

    - Details of travel and subsistence and all expenses to be incurred. Mileage reclaim will be linked to maximum levels set by HMRC.

    - The above breakdowns should be further broken down into individual work packages.

# 11.0	TENDER EVALUATION CRITERIA AND MINIMUM REQUIREMENTS

11.1	In evaluating tenders, the most economically advantageous tender(s) will be sought.  This will be using the evaluation criteria and weightings detailed in ITT Evaluation Matrix Award Criteria.

11.2	The evaluation criteria detail the minimum requirements. Therefore, any tender which cannot demonstrate that it meets any of the minimum requirements will not be marked and will automatically score zero.

Tenderers are advised to carefully consider the attached specifications, ask clarification questions to ensure these are understood.

# 12.0	CONDITIONS OF CONTRACT

The terms and conditions of the contract are contained with a separate document.

Qualification of the Contract

Where Tenderers have any queries or concerns with any specific condition of the terms and conditions of the contract, these should be submitted in writing to shareditt@rssb.co.uk as soon as possible, and in any case no later than 10 days prior to the deadline for submission of tenders.  Please ensure the specific condition(s) and proposed amendment(s) are provided.  These will be reviewed by RSSB on a case by case basis, and, if accepted, revised terms and conditions will be issued to all Tenderers.  Failure to accept the terms and conditions of the contract or to qualify the tender in any way, may result in the tender being rejected by RSSB.

## 13.0 RSSB Company Information

Insert Work Package TitleIntroduction

RSSB was established in April 2003. The Company’s primary objective is to facilitate the railway industry’s work to achieve continuous improvement in the health and safety performance of the railways in Great Britain, and thus to facilitate the reduction of risk to passengers, employees and the affected public. The railway is a complex system with multiple interfaces delivered by many different organisations. At RSSB we bring these different organisations together to make collective decisions. We help the rail industry carry out research, understand risk, set standards and improve performance. We provide a constant point of reference in a changing environment.

We support rail in the areas of safety standards, knowledge and innovation and a wide range of cross- industry schemes requiring our knowledge and independence. Our work involves close collaboration, but as technical experts we also appoint suppliers in the wider market to provide an informed view.

Key elements of the company’s remit are to:

- Manage Railway Group Standards on behalf of the industry

- Lead the development of long-term safety strategy for the industry, including the publication of annual Railway Strategic Safety Plans

- Propose change through facilitation of the research and development programme, education and awareness

- Measure, report and inform on health and safety performance, safety intelligence, trends, data and risk

- Support cross-industry groups in national programmes which address major areas of safety concern

- Facilitate the effective representation of the UK rail industry in the development of European legislation and standards that impact on the rail system

RSSB is a not-for-profit company owned by major industry stakeholders. The company is limited by guarantee and is governed by its members, a board and an advisory committee. It is independent of any single railway company and of their commercial interests.

# Background

## RSSB Overview

RSSB is a membership organisation in the railway that helps industry by understanding risk, guiding standards and managing research. The rail industry in Britain is made up of many different organisations, but they all form a system and share a common purpose, to move people and freight safely and efficiently by rail. RSSB brings all parts of this system together to make collective decisions, products and services, to help industry drive out unnecessary cost, improve business performance and develop long-term strategies.

RSSB’s activities include:

- Understanding risk – Using safety intelligence from across the rail industry and elsewhere with the latest risk modelling to inform members and support safe decision making.

- Guiding standards – Creating, reviewing and simplifying GB standards to align with European requirements; managing the Rule Book and making it easier for the railway to deliver efficiently and safely.

- Managing research, development and innovation – Undertaking, commissioning and managing research and innovation programmes to address current needs, provide knowledge for decision making now and for the future, and promoting step changes to deliver the Rail Technical Strategy.

- Collaborating to improve – As an independent cross-industry body with a critical mass of technical expertise, supporting activities which require collaboration. These range from supplier assurance schemes (RISQS, RISAS) to confidential reporting (CIRAS), from health and wellbeing strategies to sustainability principles.

Specification

Specification for research project

T1140 Defining the requirements of a seat comfort selection process

# Background

The Rail Technical Strategy (RTS) provides strategic guidance to industry, underpinned by the 4Cs: Cost, Capacity, Carbon, and Customer.  This research presents an opportunity to improve the customer experience, through enhancing passenger satisfaction of seat comfort.  Passenger comfort during rail travel is an important aspect of the customer experience, and forms part of the rolling stock vision for comfortable and attractive train interiors (RTS, 2012).  One key aspect of passenger comfort is the seat, and the comfort of the seating area may contribute up to 5% of the overall impact on customer satisfaction (Transport Focus, 2016).  Recent passenger satisfaction scores revealed that 67% of passengers (n = 24,767) rated the comfort of the seats as satisfied or good (Transport Focus, 2017).  This was below the national average of 83% passengers satisfied with their journey, and the industry wide target of achieving 90% satisfaction by 2035 (Long Term Planning Ahead Framework, 2010).  Improvements in seat comfort may contribute to reaching this target, through offering passengers better value for money and comfort during their journey experience.

Research, guidance and testing methodologies to determine seat comfort have previously been undertaken by the University of Southampton and the Roll2Rail programme.  The Roll2Rail Attractiveness & Comfort Features Report (2017) called for future work to develop a seat comfort methodology to measure a range of design values that can be objectively assessed.  However, as noted in the RSSB Knowledge Search (S240, 2016) on seat comfort, while few measures exist to quantify passenger seat comfort, a standardised specification is yet to be established.  The lack of quantifiable parameters available to sufficiently assess and demonstrate passenger seat comfort may risk underperforming seat comfort, and thereby negating the customer experience.

Quantifying seat comfort is a complex area that may depend on: (a) the human, (b) the product, and (c) the context (de Looze, 2003).  Perceptions of comfort and discomfort occur through the interaction between the passenger and seat within a particular context.  As such, passenger anthropometry and the activities performed while sat in the seat (e.g. reading, sleeping, working on a laptop), can have a bearing on the level of comfort experienced.  The physical constraints of the seat design are also considered to impact passenger comfort.  These include: (a) static factors (e.g. seat pan, backrest and armrest dimensions), (b) dynamic factors (e.g. vibration and pressure, cushion material), and (c) temporal factors (e.g. variation in journey length).  Through assessing these parameters, it is expected that seat comfort can be quantified, and a seat comfort selection process can be developed, tested and validated.  The seat comfort selection process should determine the minimum requirements for seat comfort, a defined testing methodology, and scoring system.

The Rail Industry Vehicle/Vehicle System Interface Committee identified that the RDG Key Train Requirements (KTR) would benefit from more information on specifying passenger seat comfort.  It is expected that this research should develop, test and validate the requirements of a seat comfort selection process, which will directly feed into the KTR.   Subsequently, this research should enable Train Operating Companies (TOCs) and Rolling Stock Operating Companies (ROSCOs) to procure seats above a minimum set of requirements, and from a range of comfort levels.  This may improve passenger satisfaction of seat comfort, and enhance the customer experience during rail travel.

# Work package objectives

The purpose of this research is to develop, test and validate the requirements of a seat comfort selection process, defined across three steps:

- Step 1 – a pre-selection criteria defines the minimum set of requirements for seat comfort according to key dimensions of seat design, and with consideration of seat material (breathability), seat stiffness, and seat styling.

- Step 2 – seats that pass step 1, undergo a defined seat comfort testing methodology, to establish the comfort of the seat with consideration of static, dynamic and temporal factors.

- Step 3 – Steps 1 and 2 feeds into a scoring system that produces an overall rating of seat comfort.  This should allow the comparison of seat comfort across a variety of seat designs.

To achieve the above, the research is structured by the following Work Packages:

- WP T1140-01: RSSB project development costs.

- WP T1140-02: Provisional allowance of a technical expert during project delivery, to support RSSB with the delivery of T1140.

- WP T1140-03: Development of the minimum requirements for seat comfort, testing methodology, and scoring system.

- WP T1140-04: Testing and validation of the minimum requirements for seat comfort, testing methodology, and scoring system.

This invitation to tender is for one supplier to deliver WP T1140-03 (WP03) and WP T1140-04 (WP04).  A Stage Gate Review will take place following completion of WP03, and will be held by the Project Steering Group.  The purpose of the Stage Gate Review is to consider the options on whether to progress this work from WP03 to WP04.  Depending on this review, WP04 may or may not proceed.

It is expected that the costing for WP03 and WP04 will be presented separately, however the evaluation criteria will consider the whole tender value.

It is expected that WP03 will define the minimum requirements for seat comfort, testing methodology, and scoring system, which will undergo testing and validation in WP04.

WP03 will involve a desk based task to collate existing information to define the minimum requirements for seat comfort, testing methodology, and scoring system.  This should include collating and analysing existing literature with the consideration of key seat dimensions, passenger anthropometry, passenger activity, static, dynamic and temporal factors of comfort, seat durability, international best practices and knowledge from other transportation industries.  To facilitate this task, there is an RSSB Knowledge Search (S240, 2016) on seat comfort, as well as a preliminary review undertaken by members of KTR team, and the findings and references of the KTR work can be shared with the supplier once in contract.  T1140 should build on the existing research from the University of Southampton, and must add new knowledge that defines the minimum requirements for seat comfort, testing methodology, and scoring system.  These requirements should be produced in a way that is consistent with the style and format of the KTR, so it can directly feed into issue 6 of the KTR (expected in 2019).

WP04 will involve the testing and validation of the minimum requirements for seat comfort, testing methodology, and scoring system, which was developed in WP03.  This is suggested to include:

- The selection of a representative sample of seats.

- Compare the seat sample to the minimum requirements for seat comfort established in WP03.

- Apply the defined seat comfort testing methodology from WP03, to determine the comfort level of each seat, with consideration of static, dynamic and temporal factors.

- Score the comfort level of each seat using the scoring system defined in WP03.

- Comparison with passenger satisfaction survey methods (e.g. National Rail Passenger Survey, Transport Focus).

- Validity and replicability testing of the minimum requirements for seat comfort, testing methodology, and scoring system.

- Review and update the initial minimum requirements for seat comfort, testing methodology, and scoring system defined in WP03.

The outputs of WP03 and WP04 should be captured in interim reports following completion of each work package.  A final report should also collate and review this work, to define a final version of the minimum requirements for seat comfort, testing methodology, and scoring system, following testing and validation of these items.  The final report should also define the requirements for each seat comfort level scored, to allow stakeholders to select and procure a range of seats with minimal need for further testing.

# Scope

| In scope | Out of scope |
| --- | --- |
| - Desk based review of parameters affecting seat comfort, that also builds on the existing knowledge established by the KTR team. - Key seat dimensions, including seat pan, backrest, armrests, legroom clearances, size and position of lumbar support, headrest (if applicable), body clearances and table positioning, seating arrangement and access clearances. - Static, dynamic, and temporal factors, including testing cushion softness, cushion durability, thermal comfort, vibration control, duration of sitting, seat material (breathability), seat stiffness, seat styling. - A representative sample range of train seats currently in production (including first and standard class, and tip-up seats). - Passenger types (e.g. business, leisure, commuter), activities (e.g. reading, sleeping, working on a laptop), and anthropometry. - Journey type (e.g. inter-city, metro, regional). - Seats comfort knowledge from other passenger transportation industries (e.g. automobile, aviation). - Development, testing and validation of a seat comfort selection process, that defines the minimum requirements for seat comfort, testing methodology, and scoring system. This should be written in a way that is consistent with the style and format of the KTR, to feed directly into the KTR. - Repeatability and validation testing of the minimum requirements for seat comfort, testing methodology, and scoring system. - Comparison with passenger satisfaction survey methods (e.g. National Rail Passenger Survey, Transport Focus). - Ongoing engagement with the project steering group. - Delivery of presentation of findings to cross-industry groups | - Comfort parameters of the whole vehicle (e.g. noise, lighting, temperature). - Review and testing of seat standards (e.g. crashworthiness and fireworthiness). - Seating from non-transportation industries (e.g. office chairs) - Testing rail seats that are not currently in production. - The development of new seats. |

## Methodology

Suppliers will be expected to define the methodology that they are intending to use to successfully meet the project objectives and cover the scope.

# Deliverables

|  | Deliverable Name; Type. Interim Report: Defining the requirements of a seat comfort selection process; Report. The interim report should detail the work undertaken in WP03, which presents the requirements of a seat comfort selection process, defined across three steps: - Step 1 - The minimum requirements for seat comfort - Step 2 - Seat comfort testing methodology - Step 3 - Seat comfort scoring system. These requirements should be written in a way that is consistent with the style and format of the KTR, so they can directly feed into issue 6 of the KTR (expected in 2019). The interim report will be reviewed during a Stage Gate Review Meeting. This will consider options for progressing the work to WP04, for the testing and validation of the minimum requirements for seat comfort, testing methodology, and scoring system. This deliverable is expected to be received by 05 August 2018, and should be accepted by the project steering group and V/V SIC. The report will be produced in the RSSB template and will be made available on SPARK to RSSB members.. Deliverable Name; Type. The testing and validation of a seat comfort selection process; Report. - This report should detail the testing and validation of the seat comfort selection process that was developed in WP03. This should include the following: - Detail on the selection of seats from a representative sample, and how they compare to the minimum requirements for seat comfort. - Results from the testing methodology, which should identify the static, dynamic and temporal comfort of each seat. - Results from the scoring system to determine the comfort rating of each seat. - Results on how each seat compares to passenger satisfaction survey methods (e.g. National Rail Passenger Survey, Transport Focus). - Validation and replicability findings of the minimum requirements for seat comfort, testing methodology, and scoring system. This deliverable is expected to be received by 05 February 2019 and should be reviewed and accepted by the project steering group and V/V SIC. The report will be produced in the RSSB template and will be made available on SPARK to RSSB members.. Deliverable Name; Type. Final Report: Defining the requirements of a seat comfort selection process; Report. It is possible that the testing phase (WP04) will affect the seat comfort selection requirements as defined in WP03. The final report should review and update the minimum requirements for seat comfort, testing methodology, and scoring system. Should an update to requirements defined in WP03 be necessary, this must be consistent with the style and format of the KTR, so they can directly feed into issue 6 of the KTR (expected in 2019). A selection process that minimises user testing and maximises machine testing is preferred, to reduce subjectivity of seat performance. The final report should also specify the seat requirements for each level of comfort within the scoring system, to allow stakeholders to select and procure a range of seats with minimal further testing. The final report should be reviewed and accepted by the project steering group and V/V SIC. It will be made available on the SPARK and RSSB websites. This deliverable is expected to be received by 05 February 2019.. Deliverable Name; Type. Executive Summary Presentation of Key Findings; Presentation. The presentation summarises findings on all components defined as ‘in scope’ for WP03 and WP04, as outlined earlier in this specification document. This presentation is to be created in an easily accessible manner, fit for presenting to cross industry groups of technical experts, to disseminate the key project findings. The presentation will be provided by the supplier, to the project steering group and the V/V SIC. The executive summary presentation will be made available on SPARK to RSSB members. This deliverable is expected to be received by 05 February 2019. If the Stage Gate Review determines that this work should not progress to WP04, then this deliverable will be expected to be received by 05 August 2018.. Deliverable Name; Type. Research in Brief; Report. The research in brief should be created by the supplier, in partnership with RSSB, to summarise the findings of WP03 and WP04, in no more than 4 pages. The research in brief will summarise the aim, findings, impacts and benefits, background, and summary method of this work package. The document should also identify where to find out more information, identify recommendations and next steps for industry and further research and development. The draft research in brief will be produced in a RSSB template, and an example can be provided. The research in brief will be made available on the SPARK and RSSB websites. This deliverable is expected to be received by 05 February 2019. If the Stage Gate Review determines that this work should not progress to WP04, then this deliverable will be expected to be received by 05 August 2018.. |
| --- | --- |

# Stakeholders roles and responsibilities

|  | General role in project | Specific role in acceptance of deliverables |
| --- | --- | --- |
| Delivery manager | The delivery manager is responsible for the detailed project management including project schedules, cost reporting and other relevant project management tasks. The delivery manager leads the project in organising meetings, etc. and ensures timely and effective delivery towards project objectives. | Facilitates technical review and acceptance processes, identifies, and monitors corrective actions where needed, including facilitating decision making |
| Technical expert | Throughout the project, the technical expert ensures that the research accurately reflects technical aspects. Technical aspects can refer to specific issues around Human Factors Research, Seat Comfort, or any other specialist field. | Reviews emerging outputs from technical perspective |
| Industry and RSSB sponsor | The Industry and RSSB sponsors act as a figurehead for the research, championing its importance and its outputs. Their key role is to provide steer to the research as it progresses and exert pressure on the industry to make use of its findings. | Formally accepts deliverables |
| Project supporters | The project supporters represent parts of industry complementary to the champion’s organisation. They offer expertise for effective project delivery and support the implementation of findings led by the champion through networking, advice and other support. | Formally accepts deliverables |
| Project steering group | The project steering group ensures the project delivers to industry needs. As such, it helps formulate specifications, assesses tenders, reviews draft and final outputs and other relevant tasks. | Formally accepts deliverables |

# Budget, timescales and dependencies

The budget for this work is up to £100,000. Any bid above this value will need to provide detailed explanation on why the supplier doesn’t feel that the budget is adequate and in such case we strongly encourage suppliers to provide costed options for RSSB to consider.

The work is expected to start in February 2018 and be completed by February 2019. These are indicative dates and RSSB is prepared to consider bids that cannot meet these expectations if they have a robust and realistic project plan, and an explanation of why the expected start and end date cannot be met.

The seat comfort selection process (minimum requirements for seat comfort, testing methodology, and scoring system), is expected to feed into issue 6 of the KTR, which is estimated to be due Spring 2019.  There is a possibility that following completion of WP03, the development of the seat comfort selection process could be linked to Issue 5 of the KTR via SPARK, following acceptance of this deliverable August 2018.

# Critical success factors and risk management

Industry engagement would be necessary to ensure the seat comfort selection process is a suitable fit within the KTR, and to support the supplier in sourcing seating for the testing and validation work.  The project steering group may support the supplier to source a representative sample of seats, and can support with the engagement of the KTR Team, to ensure the defined requirements are suitable for the KTR.

Supplier expertise on seat comfort is crucial, to develop, test and validate the seat comfort selection process.  The supplier should have the ability to test and validate the minimum requirements for seat comfort, testing methodology, and scoring system.  This will include the measurement of seat geometrics with precision, carry out seat cushion softness and vibration testing, and user testing of passenger seat comfort.  As the seat comfort selection process may also evoke competition among industry members, it is essential that a rigorous, fair and transparent methodology is applied, and guidance is provided for other stakeholders to replicate the methodology.

Appendix X Form of Tender

This section outlines how the offer from the Tenderer is to be constructed. Please return this Tender Declaration along with your Tender and retain a copy for your records.

Having examined the ITT email, the Instructions to Tenderers, the Information Required From Tenderers, the Conditions of Contract, the Specification and this Form of Tender (the “Tender Documents”), we offer to supply all/part of (delete as applicable) the goods, services or works specified in these Tender Documents.

We undertake if selected, to perform the contract in accordance with the Tender Documents, including the Conditions of Contract contained herein.

We agree that this tender shall remain open for acceptance by the Customer for 180 days from the date stipulated for the return of tenders.

We understand that you are not bound to accept the lowest, or any tender you may receive.

We certify that this is a bona fide tender, and that we have not fixed or adjusted the amount of the tender by or under or in accordance with any agreement or arrangement with any other person.  We also certify that we have not done and we undertake that we will not do, at any time before the hour and date specified for the return of this tender, any of the following acts:

Communicate to a person, other than the person calling for the tenders, the amount or approximate amount of the proposed tender.  Except where the disclosure, in confidence, of the approximate amount of the tender was necessary to obtain insurance premium quotations required for the preparation of the tender.

Enter into an agreement or arrangement with any other person that he shall refrain from tendering or as to the amount of any tender to be submitted.

Offer or pay or give or agree to pay or give, any sum of money or valuable consideration directly or indirectly to any person, for doing or having done or causing or having caused to be done, in relation to any other tender or proposed tender for the said goods, services or works, any act or thing of the sort described herein.

We recognise that the Customer reserves the right to clarify details of our offer prior to the award of any contract.

We hereby undertake that the period during which this tender remains open for acceptance not to divulge to any persons, other than the persons to whom the tender is to be submitted, any information relating to the submission of this tender or the details contained therein except where such is necessary for the purpose of submission of this tender.

Appendix X Subcontractors

All suppliers to RSSB are asked to provide details of all sub-contractors that will be used to perform the contract.

| Name & Address of Sub-Contractor |  | Service performed for Contractor | Provide details of staff numbers | Provide latest year’s turnover |
| --- | --- | --- | --- | --- |
| Name: |  |  |  |  |
| Address: |  |  |  |  |
| Name: |  |  |  |  |
| Address: |  |  |  |  |
| Name: |  |  |  |  |
| Address: |  |  |  |  |

Appendix X Conflicts of Interest

Tenderers have a continuing duty to disclose actual or potential conflicts of interest in respect of itself, its named sub-contractors and / or consortia members.

Please describe any (potential) conflicts of interest that the Tenderer has identified and how these will be managed*:

If you DO NOT have any conflicts to declare, please tick this box:

Tenderers are reminded that failure to identify material conflicts of interest may lead to rejection of its tender response.

Guidance to Tenderers:

Tenderers should describe in the detail the perceived conflict (how it could be perceived in the context of this procurement) and the measures it will take to mitigate the conflict through the procurement life-cycle and service delivery

https://www.southampton.ac.uk/hfru/publications/publications.page

http://www.roll2rail.eu/Page.aspx?CAT=DELIVERABLES&IdPage=45291e18-8d8f-4fd6-99f8-5d4b7a519b9c

http://edge.rit.edu/edge/P09454/public/Sitting%20comfort%20%26%20discomfort.pdf

More information about RSSB committees can be found here: https://www.rssb.co.uk/groups-and-committees

The Key Train Requirements is a document that supports the specification of new and refurbished trains.

This may include, the seat pan, backrest, armrests, legroom clearances, body clearances and table positioning, seating arrangement and access clearances.

The project steering group includes a member from the KTR Team, who may offer guidance on structuring the seat comfort specification during project steering group meetings.  To provide guidance on the format of the KTR, Issue 4 can be found here: https://www.rssb.co.uk/Library/improving-industry-performance/2016-08-key-train-requirements.pdf. RSSB research projects T1003 Standardisation of coupling arrangements and T1036 Onboard Injuries Associated with Internal Train Doors may illustrate previous work that has fed into the KTR

Suppliers could use research published by Transport Focus, as indicators of national and TOC level passenger satisfaction of seat comfort (http://d3cez36w5wymxj.cloudfront.net/wp-content/uploads/2017/07/25120605/National-Rail-Passenger-Survey-%E2%80%93-NRPS-%E2%80%93-Spring-2017-%E2%80%93-Main-report.pdf)

This is the average annual numbers of both staff and managerial staff employed over the last trading year