28th April 2017

# Dear Bidders,

Request for Quotation: PRJ 439 Paediatric Critical Care Online Education Programme

I am writing to you on behalf of Lewisham CCG (the CCG). We currently have a requirement for online education for Level 1 and 2 paediatric critical care (for London acute inpatient paediatric services), the details of which are set out in the Annex A to this RFQ letter.

We need our chosen supplier to commence the work in the week commencing 5th June and finish the work on or before June 2022.

Please note the attached (Annex B) NHS Standard Contract Terms and Conditions for the Supply of Services will apply to any contract awarded as a result of this quotation exercise.

If you are interested in quoting for this requirement, please reply with a ‘bid response document’ to the following email box nelcsu.welcpod-procurement@nhs.net by 12 noon on Monday 15th May 2017 with the following information:

- Full name and address of supplier, our reference number and your contact details;

- Details of services to be supplied including details in response to the requirements set out in the Annex A / the evaluation criteria to this letter and a referee (preferably public sector);

- Expected delivery / start / finish date, and a project time table;

- Total price excluding VAT (Annex C);

- Confirmation of acceptance of the terms and conditions of contract (Annex B);

- Annex D – Conflict of Interest Declaration.

The CCG is seeking quotations from a number of suppliers. The following criteria will apply to the selection of the successful supplier:

| Criteria | Ref | Sub-Criteria | Weighting |
| --- | --- | --- | --- |
| 1. Non Price - Quality (80%) | 1.1 | Proven ability to develop effective online learning materials across web platform, and IOS/android mobile applications with excellent online learning experience and navigation which is visually appealing, easy to navigate and delivers an effective learning experience. This will include a team with relevant skills knowledge and expertise in designing and delivering online learning. | 25 |
|  | 1.2 | Able to bring educational expertise and creative solutions to delivery of the online learning portal to augment the clinical expertise already available to the customer | 20 |
|  | 1.3 | Proven ability to work with external partners to deliver agreed outcomes | 10 |
|  | 1.4 | Able to deliver technical solutions to statement of requirements including logins across multiple organisations and ability to upload content as need arises in accordance with specified SLA | 15 |
|  | 1.5 | Knowledge and experience of producing and delivering standard Project Management products and deliverables? | 10 |
| 2. Total Price (20%) |  | Total Fixed Price for service requirements | 20 |

| Score | Acceptability | Description |
| --- | --- | --- |
| 0 | Unacceptable | The information is omitted AND/OR No relevant details are provided AND/OR The response is relevant to the question but has not been evidenced, leaving the Contracting Authority unable to verify any element of the response AND/OR The response provides no confidence that the approach described satisfies the requirements to which the question relates AND/OR The response is not relevant |
| 1 | Poor | The response does not address in sufficient detail the needs and requirements covered by the question AND/OR The Contracting Authority has a very low level of confidence that the Bidder understands the needs and requirements covered by the question AND/OR The response provides very little confidence that the approach described satisfies the requirements to which the question relates AND/OR The Contracting Authority is not confident that the Bidder will be able to satisfactorily meet the contract requirements by delivering this element of its proposal |
| 2 | Fair | The Contracting Authority has some reservations as to whether the Bidder understands the requirements covered by the question AND/OR The response provides only limited confidence that the approach described satisfies the requirements to which the question relates AND/OR The Contracting Authority has some reservations as to whether the Bidder will be able to satisfactorily meet the contract requirements by delivering this element of its proposal |
| 3 | Satisfactory | The Contracting Authority is reasonably confident that the Bidder understands the contract requirements covered by the question AND/OR The response provides a satisfactory level of confidence that the approach described satisfies the requirements to which the question relates AND/OR The Contracting Authority is reasonably confident that the Bidder will be able to satisfactorily complete the contract requirements covered by the question to a reasonable standard by delivering this element of its proposal |
| 4 | Good | The Contracting Authority is confident that the Bidder understands the contract requirements covered by the question AND/OR The response provides a high level of confidence that the approach described satisfies the requirements to which the question relates AND/OR The Contracting Authority is confident that the Bidder will be able to complete the contract requirements covered by the question to a high standard by delivering this element of its proposal, and may deliver additional benefits |
| 5 | Excellent | The Contracting Authority is completely confident that the Bidder understands the contract requirements covered by the question AND/OR The response provides an extremely high level of confidence that the approach described satisfies the requirements to which the question relates AND/OR The Contracting Authority is completely confident that the Bidder will be able to complete the contract requirements covered by the question to a very high standard by delivering this element of its proposal, and will (or is likely to) deliver additional benefits |

The Quotation must be submitted in a PDF format, with pricing submitted in a separate file. Quotations received after the above date and time may not be considered.

It would be appreciated if you could advise, within 3 days of receiving this RFQ, if you intend to submit a bid or your reasons for not submitting a bid.

If the panel feels at any point that there is not sufficient evidence to score a bidder on any evaluation point then they may, at their discretion, seek clarification from any and all bidders. Bidder clarifications will at all times take account of the commercial confidence of bidders.

If a bidder scores a ‘0’ on any sub-section then they may be eliminated at the discretion of the panel, dependent on how service critical the panel deems that sub-section to be. If a bidder scores ‘0’ on an entire section of the evaluation, the bidder will be automatically eliminated from any further evaluation.

The pass-mark for the qualitative evaluation (Questions 1.1 – 1.5) element is 50. If a bidder does not attain this score overall then their bid will be rejected. This process ensures that NEL Commissioning Support Unit and Lewisham CCG attain a minimum acceptable service quality. Following submission of bids, a moderation / evaluation meeting may be held. Following the moderation meeting, Lewisham CCG and NELCSU will, invite the bidders scoring over 50 to a post bid submission clarification meeting / interview to establish confidence in the Evaluation Panel that you will be able to deliver what you have stated. The interview will be held on 1 June 2017.

In the event of a tie (where two or more top scoring Bidders had the same total weighted score including both quality and price), the CCG will select from amongst those Bidders, the submission of the Bidder with the highest weighted score for Price.

Your response must be valid for acceptance for 90 days from the deadline for receipt of quotations. Your response constitutes an offer and if Lewisham CCG accepts that offer then a legally binding contract will exist between us.

Respondents accept that the Lewisham CCG is subject to the Freedom of Information Act and government transparency obligations which may require Lewisham CCG to disclose information received from you to third parties.

This RFQ letter and your response do not give rise to any contractual obligation or liability unless and until such time as Lewisham CCG issues a letter referencing this Request for a Quotation with a signed contract and a valid Purchase Order number accepting your quotation. Lewisham CCG does not make any commitment to purchase and shall have no liability for your costs in responding to this Request for a Quotation.

## Canvassing and contacts

Bidders shall not in connection with this Procurement:

- Offer any inducement, fee or reward to any officer or employee of NELCSU or Lewisham CCG or any person acting as an advisor to NELCSU or Lewisham CCG in connection with this Procurement

- Do anything which would constitute a breach of the Prevention of Corruption Acts 1889-1916

- Canvass any of the persons referred to above in connection with the Procurement

No attempt should be made to contact NELCSU or Lewisham CCG staff, except the Project Team, or to contact NELCSU / Lewisham CCG or NELCSU / Lewisham CCG advisers or other NHS/DoH bodies as part of the procurement process. Any enquiries made to persons other than the NEL Commissioning Support Unit Project Team will be regarded as prima facie evidence of canvassing.

## Conflicts of interest

In order to ensure a fair and competitive procurement process, Lewisham CCG requires that all actual or potential conflicts of interest that a potential bidder may have are identified and resolved to the satisfaction of the CCG.

Potential Applicants should notify the CCG of any actual or potential conflicts of interest in their response to the RFQ. If the potential bidder becomes aware of an actual or potential conflict of interest following submission of the application it should immediately notify the CCG by completing the Conflict of Interest form (see Annex D) for this procurement. Such notifications should provide details of the actual or potential conflict of interest.

If, following consultation with the potential bidder or bidders, such actual or potential conflict(s) are not resolved to the satisfaction of the CCG, Lewisham CCG reserves the right to exclude at any time any potential Applicants(s) from the Procurement process should any actual or potential conflict(s) of interest be found by the CCG to confer an unfair competitive advantage on one or more potential bidder(s), or otherwise to undermine a fair procurement process.

Examples of potential conflicts of interest are (without limitation) as follows:

A Bidding organisation, or any person employed or engaged by or otherwise connected with a Bidding organisation, is currently carrying out any work for the CCG, NHS England and/or the Department of Health (DH), or has done so within the last six (6) months;

A Bidding organisation is providing services for more than one Potential Bidder, in respect of this Procurement.

The ‘Conflict of Interest Declaration’, provided in Annex D, must be completed by an authorised signatory, in his / her own name, on behalf of the Bidding organisation and attached in response to this section of this RFQ.

The CCG should be immediately notified, in the event that any actual or potential conflict of interest comes to a potential Bidder’s attention at any time following the submission of the potential Bidder’s ‘Conflicts of Interest Declaration’ and bid documents.

If you have any queries about this letter or the requirement, please contact the under signed at juan.carosio@nelcsu.nhs.uk

If you are unable to meet this requirement or are otherwise not intending to provide a quote, I would be grateful if you could let me know as soon as possible.

Yours sincerely,

Juan Carosio Msc. MCIPS

Senior Head of Procurement

NEL Commissioning Support Unit

Annex A

Specification / Project Brief

For

PRJ 439 Paediatric Critical Care

Introduction

# Background – Healthy London Partnership

In 2015 NHS England and London’s 32 Clinical Commissioning Groups (CCGs) launched a plan to make London the world’s healthiest global city.  This followed on from the work of the London Health Commission; an independent review of health established by the Mayor, Boris Johnson and led by Professor the Lord Darzi.  The Commission’s report (Better Health for London) contained 10 aspirations for London and over 64 recommendations on how to make London the world’s healthiest city.  The Healthy London Partnership (‘the Customer’) was established to take forward these aspirations based on 13 transformation programmes.

https://www.myhealth.london.nhs.uk/healthy-london/about-healthy-london-partnership

The Children and Young People’s (CYP) programme vision is for an integrated system for health and care that can be easily navigated by CYP, their families and health professionals delivering their care.  The aim is to achieve the best outcomes for London’s CYP. Care will be provided in high quality facilities local to families, with mental health needs treated with the same importance as physical health needs.

In order for this to happen the Customer needs to support the development of a skilled and competent workforce.

Background to this project - National Policy

Currently, general paediatric in-patient care is delivered in ward areas in 27 district general hospitals (DGHs) across London. Care that requires more intensive interventions than those delivered in a normal paediatric ward is known as High Dependency Care (HDC).  These interventions are not currently delivered consistently across all in-patient settings. This causes issues in trying to manage this cohort of patients who are acutely unwell but not requiring paediatric intensive care (PIC). In 2014 the Royal College of Paediatrics and Child Health published Time to Move On a policy document describing HDC for CYP http://www.rcpch.ac.uk/high-dependency-care which was endorsed by all other relevant professional bodies.  It described how a specific level of HDC for children should be delivered in every in-patient setting for CYP, including every District General Hospital (DGH).  The terminology to describe this level of HDC was termed Level 1 Paediatric Critical Care (PCC). Some units may in addition deliver Level 2 PCC which would enable them to manage CYP receiving Long Term Ventilation (LTV).

Background to this project – response of Healthy London Partnership

In response to this, the Customer established a CYP critical care group. In April 2016 they published a set of standards for L1 and L2 PCC https://www.healthylondon.org/children-and-young-people/hospital-care. These are linked to the Customer CYP London acute standards for inpatient care. One of the aims of the Customer over the next two years is to develop the workforce in London and train a critical mass of staff in DGHs in HDC for CYP. This will enable all in-patient paediatric units to deliver L1 PCC with a smaller number delivering care at L2 PCC.  In order to facilitate this, the Customer submitted a bid successfully to Health Education England for funding for a new educational package to achieve this aim.

To complete the full set of requirements to deliver L1 and L2 PCC in DGHs, work is on-going to develop on a commissioning framework and pricing structure as well as the development of the workforce.

Some education is currently available for training in L1 and 2 PCC in local trusts (for example at the Whittington Hospital), through outreach from both the Children’s Acute Transport service (CATS) and South Thames Retrieval Service (STRS) as well as modules delivered though Higher Education Institutions (HEIs) such as King’s College and South Bank University. These are all very good resources.  However, there is currently no consistent educational offer across London that can be delivered easily through an online portal to medical, nursing and AHP staff in all units.

How will the educational content be developed and delivered?

The Customer’s Critical Care Group will be the ongoing source of clinical expertise for the development of the content for the online learning hub. Once the Supplier is identified, membership of this Group may be augmented in conjunction with the Supplier in order to enable successful design of the educational content.

- Background

The required expertise to deliver HDC exists in tertiary centres where L3 PCC (Paediatric Intensive Care) is delivered either within a paediatric intensive care unit or a designated high dependency unit. Expertise to deliver L1 and 2 PCC is variable within local DGHs. The type of training required in DGHs differs from that required in specialist centres.  It needs to have a consistent core knowledge base accessible to all staff. The most effective way to enable this level of access to all staff will be to host this element online. The practical element needs to use locally available policies, procedures and equipment which may vary between units. This element of training is best delivered locally. .

Aim of the project

The primary requirement is the design and delivery of a high quality consistent online educational portal for L1 and L2 PCC accessible to staff in all DGHs with in-patient paediatric services for a period of five (5) years following successful go-live of the portal, comprising an initial period of three (3) years, followed by two (2) optional extension periods of one (1) year.  The Customer currently has a budget for the development of the training portal and mobile application of between £32,000 and £40,000 for the five (5) year period.

This will enable and support the development of the paediatric workforce to support safe and effective delivery of L1 PCC capability in all 25 paediatric units, and L2 PCC in a smaller number of units. This will achieve the required level of transformational change in delivery of L1 and L2 PCC across all London’s inpatient paediatric units.

Requirements in scope

The scope of the requirements shall include, but not be limited to:

- Design and development of an online resource hub to house course materials to include background information, videos and multiple choice quiz. This will have effective and user friendly navigation, be visually appealing, and provide students with an effective learning experience. This will be available via a web portal, iOS and android mobile app.

- Ability to generate secure logins for up to nine hundred (900) staff from across London (27 in-patients paediatric unites) to enable individual access to the online learning portal. This is an on-going requirement to enable newly employed staff the ability to access the portal.

- Ability to generate certificates for individuals on successful completion of a multiple choice quiz.

- Support and maintenance services to the on-line training hub for a period of five years.

- The availability of a named Account Manager to be a single point of contact for the Customer during the term, manage any change requirements and be responsible for the provision of required MI and service/contract reporting.

- Design of a Certificate of Completion of training which can be adapted and used across all participating NHS Trusts once skills and competencies have been achieved by students.

Access to the existing PCC clinical steering group will be available to support and advise the Supplier during the term of the Contract.

Requirements out of scope

Additional elements to support delivery of the development of the workforce are out-of -scope for these requirements.  The Supplier will need to understand how the online learning portal links in with the overarching educational strategy for the development of the workforce to deliver L1 and 2 PCC across London. The other out-of-scope elements include:

- Appointment of a project manager with clinical expertise to be seconded into the Customer’s team one day per week for six months to co-ordinate clinical content and liaise with supplier

- Marketing of the online learning portal

- Filming of video clips (agreement on video content is in scope)

- Appointment of a local leads for L1 and 2 PCC skills within each Sustainability and Transformation Plan area (STP)

- Training and support for the PCC leads within paediatric units to enable them to deliver training locally

- A work-based learning approach to skills acquisition – local scenario-based training to enable the acquisition of competencies

- Assessment of competencies

- Award of certificate of completion of training by individual DGHs

- Potential for RCPCH CPD points for medical staff

- Current Situation

There is currently no existing supplier of this kind of education in London. The Customer is looking for a Supplier to design and deliver the required online elements of the educational offer. The Supplier should bring the relevant educational expertise to augment the existing clinical expertise available to the programme.

Skills and Experience

This educational product is a key part of workforce development for the CYP programme in London. The Customer is looking for a Supplier who can bring the following skills and attributes to the programme:

Proven ability to develop effective online learning materials with excellent online learning experience and navigation

The Supplier shall have the capability to deliver a completed product across all three platforms which is visually appealing, easy to navigate and gives an effective learning experience. This will include the design and delivery of the completed online learning package to include hosted documents, presentations, videos, scenarios, a multiple choice quiz.  The Customer is looking for a supplier with creative ideas to bring to this project to augment the clinical expertise currently available to the Customer.

Ability to work with external partners to deliver agreed outcomes

The Customer is looking for a Supplier that can demonstrate evidence of effective partnership working to deliver products of high quality. The Supplier will work closely with the Customer CYP Project Team and with the CYP Critical Care Group. The latter group is already in existence and will be the main group where course content is agreed for inclusion on the learning platform. The group membership may need to be enhanced in order to ensure effective working with the Supplier.

The Supplier shall bring in expertise in educational methodology most appropriate to the online learning environment to enhance this group.

The Customer will be advertising for a clinical project manager from a relevant clinical background to be seconded to the Customer for a day per week to support this project. This will ensure effective liaison between the Customer and the Supplier.

In addition, a Project Manager from the core Customer team will act as the other key point of contact. These two people will form the Customer project team to link with the Supplier’s nominated Account Manager.

Educational expertise to augment the clinical expertise currently available to the Customer CYP programme

The Supplier will have demonstrable expertise in designing and delivering educational programmes. The Customer is looking for evidence of how this educational expertise may enhance or complement the clinical expertise around L1 and L2 PCC that currently exists within the Customer CYP Critical Care Group.

Ability to update materials in response to new developments

All online content requires updating to ensure it reflects current best practice in clinical care.

The Supplier will be required to demonstrate how content would be updated as the needs arises.

Solutions to generating staff log-ins and online certificates of quiz and course completion

There are 27 in-patient paediatric units in London with between 600 and 900 (estimated) staff members who would need to access the online learning and demonstrate evidence of knowledge gain through a multiple choice test.  We are looking for a Supplier who can provide a solution to managing the logins effectively.

- Scope of Requirements

3.1	An online learning hub to host core knowledge required for understanding the theory behind delivery of L1 and 2 PCC (the System).

This shall include, but not be limited to the following elements:

    - A design structure and storyboard for the System pages to contain and effectively link the required content across web based, and IOS/Android web applications

3.1.2	A design for the visual appearance and colour scheme of the System linked with the Customer’s branding

3.1.3	Interactive e-learning content including but not limited to:

- Video clips (these will be designed in conjunction with the customer. Production of the clips is out of scope):

- Expert practitioners

- Practical demonstrations of equipment use

- Child and parents describing experience

- Presentations

- National policy documents

- Reading list

- Competencies – nursing, medical, AHP

- Simulation scenarios for use locally

- MCQ to test knowledge acquisition

- Certificate of Completion of MCQ for students successfully undertaking the on-line training via the System

- The ability to generate regular monthly reports on usage of the online learning hub and mobile application.  Reports shall contain management information including, but not limited to:

- Number of hits on particular parts of the System on each platform

- Time spent on each section of the System on each platform

- No of staff successfully/unsuccessfully completing MCQ test via the System

3.1.4	The Supplier shall provide other reports as requested by the Customer.

3.1.5	Technical Service Requirements

The System shall provide:

- personal logins to staff across multiple sites and organisations

- the ability to generate new logins over the course of the contract for staff new in post

- ability to host Microsoft Office documents and video clips

- ability to host a large set of multiple choice questions

- ability to generate a random set of questions for each person undertaking a multiple choice test (MCQ) from the selection of questions

- ability to generate a certificate of successful completion of MCQ to individuals

3.1.6	Functional requirements

- The online learning hub should have the ability to be accessed from PCs, Macs, Apple and Android phones and tablet computers across both iOS and Android operating systems. The mobile application will function across iOS and android phones

- The Supplier shall upload the content agreed by the Customer’s Critical Care Group.

- The product should have virus testing and protection.

- Personal data should be protected under information governance rules.

  - Annual support and maintenance of the System (Services) for a period of up to five (5) years following successful go-live.

    - The supplier will provide the Services and maintain the System to ensure availability and user access in accordance with the specified requirements for a period of up to five (5) years post go-live.

    - The System shall be available to users on a 24 hours / 7 days per week basis (SL1)

    - Web pages should load within two (2) seconds. (SL2)

    - There should be no restriction on concurrent logins.

3.2.5	The Services shall include ten (10) additional content uploads of individual items per year.

3.2.6	Additional content shall be uploaded to the System within ten (10) working days of a Customer request (SL3)

3.3	Design / Development Services (System Developments) for a period of up to five (5) years following successful go-live.

3.3.1	The Supplier shall provide System Development services as required by the Customer during the contract term.

3.3.2	The Customer shall provide the Supplier with a specification of the required System Developments and the Supplier shall provide pricing and a target completion date for the System Developments within ten (10) working days of receipt of such a specification (SL4/).

3.3.3	Within ten (10) working days of Customer approval to progress the System Developments the Supplier shall commence work on the required System Developments (SL5).

3.3.4	All System Developments shall be provided by the Supplier in accordance with the timeframe and completion dates agreed with the Customer (SL6).

3.3.5	When requesting System Developments the Customer shall reserve the right to request a fixed price for the System Developments from the Supplier.

3.3.6	All pricing provided by the Supplier for System Developments shall be in accordance with the agreed Rate Card.

3.3.7	In the event that there is a change in the hosting arrangements of the customer, the customer will notify the supplier of the new host.

  - IPR

3.4.1 	The Customer shall retain the Intellectual Property Rights of the System.

3.4.2 	The Supplier shall ensure that if the System incorporates open source software or 3rd party software, the Supplier is an accredited partner of the software

- successful development of previous online learning tools

- educational experience associated with L1 and 2 PCC

3.4.3	If third party expertise is to be used, the supplier should demonstrate how the expertise will be used effectively within the supplier’s team

  - System Test

The supplier should provide a beta version to the customer to enable user acceptance testing and identify any bugs in the product

  - Contract / Project Management

3.6.1	The Suppliers nominated Account Manager shall provide weekly reports to the Customer during the design and build phase of the System.

3.6.2	This shall include, but not be limited to:

- the development of a proposed method for effective communication with the Customer and key stakeholders.

- a delivery timeline to include each Deliverable

- project and exception reporting

- completion of a risk and issue risk log and methods for mitigating risk

- a final report, issues log and solutions/lessons learnt on successful go-live of the System

  - Information Governance

The System and Services shall comply with local and London wide information governance requirements including any identified:

- ISO standards or IG requirements from the provider

- Information sharing protocols

3.8	Input of Third Parties

If any third party or sub-contractor is to be used by the Supplier this should be clearly identified and details on the arrangements provided.

3.9	Stakeholder management

The Supplier shall engage with a wide range of stakeholders including the existing critical care leadership group, local acute paediatric providers and HEI institutions across London. This will be supported by the Customer Project Managers plus other individuals as deemed appropriate.

- Key outputs/deliverables

4.1 	A design structure and storyboard for the pages to contain and effectively link the required content.

4.2		A design for the visual appearance and colour scheme of the learning hub linked with the Customer’s branding.

4.3     Interactive e-learning content including but not limited to:

4.3.1   Video clips (these will be designed in conjunction with the customer. Production of the clips is out of scope)

- Expert practitioners

- Practical demonstrations of equipment use

- Child and parents describing experience

4.3.2	Presentations

4.3.3	National policy documents

4.3.4	Reading list

4.3.5	Competencies – nursing, medical, AHP

    - Simulation scenarios for use locally

    - MCQ to test knowledge acquisition

4.3.8	Certificate of successful completion of MCQ for individuals

  - The ability to generate regular reports on usage of the online learning hub

4.4.1	Number of hits on particular parts of the site

4.4.2	Time spent on each section

4.4.3	No of staff successfully/unsuccessfully completing MCQ test

4.4.4	Other reports as proposed by supplier

4.5	A delivery timeline to include each deliverable

4.6	Project and exception reporting

4.7	Completion of a risk and issue risk log and methods for mitigating risk

4.8	A final report, issues log and solutions/lessons learnt on completion of the project

- Delivery Dates

| ## Dates | ## Project Phase | ## Actions | ## Primary Deliverable/ Outputs |
| --- | --- | --- | --- |
| W/C 5th June 2017 | Project initiation | Initial kick off meeting customer/supplier | Project timeline and detailed Deliverables agreed |
| June 2017 to August 2017 | Design phase | Supplier to develop learning hub structure across all three platforms Critical care group meetings to agree content - written documents - content of video clips - MCQs - Simulation scenarios | Design and structure of pages and storyboard. Visual appearance and branding format. Content agreed and available. |
| End September 2017 | Development phase | Completion of initial prototype User Acceptance Test (UAT) undertaken by Customer | Delivery of beta version. |
| October 2017 | Customer review | Final sign off of System. System Go-Live | Final version System into production |

- Reporting

6.1	The successful team will schedule regular weekly telephone calls with the Customer Lead Project Manager.

6.2	Monthly highlight reporting of exception/risks/ issues will be required for the programme and the critical care group.

6.3	An end of project report will be provided as well as an issues and solutions learning log.

- Contract Management

As previously stated, the supplier should have a named lead project manager for the lifetime of the project who can link in with the Customer project manager and team.

- Constraints

The main constraint to delivery of the programme will be access to clinicians to develop and agree the content of the programme.

If the chosen provider uses open source software, the provider should be an accredited partner of the software.

- Service Levels and Service Credits

| Service level | Service | KPI | Target | Measure | Report |
| --- | --- | --- | --- | --- | --- |
| SL1 | System Availability | 24 x 7 x 365 | 99% | Monthly | Monthly |
| SL2 | Web Page Load Speed | Within two (2) seconds | 99% | Monthly | Monthly |
| SL3 | Additional Content Upload | Within ten (10) working days of customer request | 98% | Monthly | Monthly |
| SL4 | Provision of pricing and target completion date for System Developments. | Within ten (10) working days of Customer request | 95% | Monthly | Monthly |
| SL5 | Commencement of System Developments | Within ten (10) working days of Customer approval to progress. | 95% | Monthly | Monthly |
| SL6 | Delivery of System Developments | Within timeframe agreed with the Customer | 98% | Monthly | Monthly |

The Service levels above shall be applicable with effect from one (1) month following go live of the System.

- Service Credits

Service credits shall be calculated based on the following:

| Service | Target Service Level | Calculate | Service Credit Value |
| --- | --- | --- | --- |
| SL1 | 99% | Quarterly | 1% Service Credit for every hour the System is unavailable. Excludes any agreed System downtime for upgrade/maintenance purposes. |
| SL2 | 99% | Quarterly | 1% Service Credit accrued for each percentage under the specified Target Service Level |
| SL3 | 98% | Quarterly | 1% Service Credit accrued for each percentage under the specified Target Service Level |
| SL4 | 95% | Quarterly | 0.5% Service Credit accrued for each percentage under the specified Target Service Level |
| SL5 | 95% | Quarterly | 0.5% Service Credit accrued for each percentage under the specified Target Service Level |
| SL6 | 98% | Quarterly | 1% Service Credit accrued for each percentage under the specified Target Service Level |

Service Credits shall be calculated in accordance with the following formula:

TSC = (TSL – ASL) x SCV

Where:

TSC = Total Service Credit

TSL = Target Service Level (%)

ASL = Actual Service Level achieved (%)

SCV = Service Credit Value

Within the first month following System go-live the Supplier shall provide a set of tools that will be used by the Supplier to calculate the Service Credits on a monthly / quarterly basis.

The service credit calculation tools shall be agreed with the Customer prior to being used by the Supplier.

The amount of Service Credits accrued in each monthly / quarterly period shall be capped at 30% of the monthly / quarterly service charge.

- Invoicing and Payment Profile

| ## Dates | ## Project Phase | ## Actions | ## Primary Deliverable/ Outputs | ## Invoice schedule |
| --- | --- | --- | --- | --- |
| W/C 5th June | Project initiation | Initial kick off meeting customer/supplier | Project timeline and detailed deliverables agreed | 30% |
| June to August 2017 | Design phase | Supplier to develop learning hub structure Critical care group meetings to agree content - written documents - content of video clips - MCQs - Simulation scenarios | Design and structure of pages and storyboard Visual appearance and branding format Content agreed and available | 20% contract value |
| End September 2017 | Development phase | Completion of initial prototype APEL requirements fulfilled | Delivery of beta version | 20% contract value |
| October 2017 | Customer review | Adjustments following feedback on beta version completed. Learning hub launched to external users | Final sign off | 30% contract value |
| October 2017 – June 2022 | On-going support & maintenance | On-going support & maintenance | Up to 10 uploads per year Ongoing site maintenance | Fixed annual fee / quarterly payment. |
| October 2017 – June 2022 | System Development |  |  | Subject to agreed rate card |

Annex B

NHS Terms and Conditions for Supply of Services

Annex C

Financial Submissions

Financial Envelope - The financial envelope available for this work is within the range of £32,000 – 40,000

Bidders must provide a detailed breakdown of the annual cost here (please note that there should be no heading entitled miscellaneous) and which should include the following:

- Staffing (all on costs must be included)

- Marketing

- Translation

- Management fee

- Overheads (phone, rent, etc.)

- Cost of providing any materials

- Others (if any)

| Breakdown of all Cost | Cost (£) |
| --- | --- |
| Breakdown of all costs |  |
| Management/co-ordination costs (specify staff role) |  |
| Licensing Costs |  |
| Operational Costs |  |
| Venue, Postage, Printing & Stationery, Telephone, Mobile Phones, Hire of equipment, etc. |  |
| If the work is to be broken down into specific sections, cost out each section separately. |  |
| Total |  |

The lowest price (within affordability limits) will be awarded the maximum score for price with other bidders awarded score in proportion to the lowest priced using the following formula:

Score = Lowest Tender Price x 20 (maximum score/mark available ). Other/Higher Tender Price.

All costs must be inclusive of travel and related expenses to the Base location. An estimate of the overall costs for expenses must be submitted to enable comparison of bids on an equal basis.

All prices exclude VAT.

If submitting your proposal as a pdf document, please submit your prices in a separate file.

NEL Commissioning Support Unit Lewisham CCG is requesting that bidders submit a breakdown of total cost for all the work / services as detailed in the Service Specification.

The lowest price (within affordability limits) will be awarded the maximum score for price with other bidders aggregated against that.

## Expenses

## Any expenses claimed will be:

- Reasonably and necessarily incurred as a result of carrying out the contracted services, with due regard to economy.

- Be detailed separately on the invoice and accompanied by the relevant receipts

- Have been agreed in advance with the CCG.

- Travelling time to the CCG(s) premises is non-chargeable.

### Reimbursement of expenses will be at cost and should be in line with:

### Actual rail travel costs based on standard class travel

# ANNEX D

Declaration of conflict of interests

(Bidders/Contractors)

Project Name: Paediatric Critical Care Online Education Programme

NHS Lewisham Clinical Commissioning Group Bidders/potential contractors/service providers declaration form: financial and other interests

This form is required to be completed in accordance with the CCG’s Constitution, and s140 of the NHS Act 2006 (as amended by the Health and Social Care Act 2012) and the NHS (Procurement, Patient Choice and Competition) (No2) Regulations 2013 and related guidance

Notes:

- All potential bidders/contractors/service providers, including sub-contractors, members of a consortium, advisers or other associated parties (Relevant Organisation) are required to identify any potential conflicts of interest that could arise if the Relevant Organisation were to take part in any procurement process and/or provide services under, or otherwise enter into any contract with, the CCG, or with NHS England in circumstances where the CCG is jointly commissioning the service with, or acting under a delegation from, NHS England. If any assistance is required in order to complete this form, then the Relevant Organisation should contact [specify].

- The completed form should be sent to [specify].

- Any changes to interests declared either during the procurement process or during the term of any contract subsequently entered into by the Relevant Organisation and the CCG must notified to the CCG by completing a new declaration form and submitting it to [specify].

- Relevant Organisations completing this declaration form must provide sufficient detail of each interest so that the CCG, NHS England and also a member of the public would be able to understand clearly the sort of financial or other interest the person concerned has and the circumstances in which a conflict of interest with the business or running of the CCG or NHS England (including the award of a contract) might arise.

- If in doubt as to whether a conflict of interests could arise, a declaration of the interest should be made.

Interests that must be declared (whether such interests are those of the Relevant Person themselves or of a family member, close friend or other acquaintance of the Relevant Person), include the following:

- the Relevant Organisation or any person employed or engaged by or otherwise connected with a Relevant Organisation (Relevant Person) has provided or is providing services or other work for the CCG or NHS England;

- a Relevant Organisation or Relevant Person is providing services or other work for any other potential bidder in respect of this project or procurement process;

- the Relevant Organisation or any Relevant Person has any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions.

Declarations:

| Name of Relevant Organisation: |  |
| --- | --- |
| Interests |  |
| Type of Interest | Details |
| Provision of services or other work for the CCG or NHS England |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |

| Name of Relevant Person | [complete for all Relevant Persons] |  |
| --- | --- | --- |
| Interests |  |  |
| Type of Interest | Details | Personal interest or that of a family member, close friend or other acquaintance? |
| Provision of services or other work for the CCG or NHS England |  |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |  |

Form Completion

| I declare that to the best of my knowledge and belief, the above information is complete and correct. I undertake to update as necessary the information. I understand that the information will be used in the evaluation process to assess my organisation’s suitability to be included in the tender evaluation process, and that giving false information may result in my organisation being disqualified from the process, at this or whatever stage it becomes known to the Commissioners. |  |
| --- | --- |
| Signed: |  |
| Name: |  |
| Position: |  |
| Bidder: |  |
| Date: |  |