## Option 1
MCA WELLS
Schedule of Works
Budget costs Note: All costs are subject to tendered figures and should be treated as budgetary. Costs will differ subject to works, e.g. Roof replacement vs roof refurbishment. Works undertaken in greater number are subject to economies of scale with a Contractor.
Item | Description | Qty | Unit | Rate | Cost
A | GENERAL CONDITIONS
A.1 | This Schedule of Works is to be read strictly in conjunction with the supplier’s specifications and drawings. Any discrepancies should be reported to the PM. Please note that dimensions/quantities as shown in this document and drawings are only approximate and should be checked on site by the Contractor. Any discrepancies should be reported to the PM. | Info
A.2 | In pricing these works, it is deemed that tenderers have visited the site prior to tendering in order to satisfy themselves with the scope of works. No additional costs will be payable due to contractor’s lack of knowledge of the site or specified works. | Info
A.3 | Tenderers must price each item listed in this document, where the price quoted is the total cost of completing that element of work and inclusive of all enabling, installation and making good works, unless otherwise defined. The materials provided and installed must be those specified by the supplier. Contractor to allow to pre-order all necessary equipment and materials and arrange for its availability when needed in accordance with the specification in connection with all works. The Contractor must confirm to the PM, the lead in times regarding the following materials: All products associated with the; • Hanson Steel Garage. • 2.7m Colinear aerial, lightweight pole and associated brackets. • Timber fences. This information is required within this tender document, for consideration by the PM and employer and dates must be confirmed during the pre-start meeting. | Info
A.4 | The Contractor is to price each item separately. | Info
A.5 | The Contractor is to include in his price for all associated works inferred or implied, to comply with good working practice.
A.6 | All works are to be in accordance with the relevant parts of this schedule. The Contractor is deemed to have read and become familiar with areas of the works prior to starting on site. | Info
A.7 | Prices are to include for removing all rubbish debris and waste arising from the works and site and for disposing of to a suitable Local Authority registered tip. This should include for all skip and waste disposal charges and all associated parking permits. A copy of all waste disposal certificates should be given to the PM following completion of the works. The location of skips is to be agreed with the Employer and must be positioned at least 6 meters away from any structures. | Info
A.8 | The Contractor is to limit the area of operation, at any given time, to those areas associated with the works in hand, at that stage in the works programme. NOTE - The Contractor will be required to supply more labour to the project in order to meet the PC date at no additional charge, if works fall behind programme or poor weather conditions are experienced. | Info
A.9 | Unless stated within the description for a particular item of work, all works are required to be carried out within normal working hours. Normal working hours are 8:00am and 6:00pm. Works outside normal hours and at the weekends are to be carried out by prior arrangement with the PM. | Info
A.10 | Where noisy work is to be carried out, prior planning and agreement should be coordinated with the PM to ensure disruption on site is kept to an absolute minimum. No noisy work shall be carried out outside the times permitted. The Contractor is to obtain details of such permitted times before works commence. | Info
A.11 | Adequate allowance shall be deemed included in prices for all such works in terms of programme, time, plant costs and on/off site management and supervision costs. | Info
A.12 | Where there is conflict or duplication between the requirements of the supplier information and the schedule of works then the Contractor should seek guidance from the PM. | Info
A.13 | The Contractor is to allow for detailed phasing and co-ordination on site, the works shall be undertaken to all areas and consultation must be taken between the building occupier and the contractor so the works programme does not impact on any programmed MCA/tenant activities. The Contractor should have due regard to safe and good working practice. | Info
Pre-ordering of materials and equipment
A.14 | Contractor to allow to pre-order all necessary equipment and materials and arrange for its availability when needed in accordance with the specification in connection with the all the works. | Info
Services
A.15 | The existing garage is only connected to electrical services (no water or gas connections are known – confirm on site). The Contractor shall be responsible if required, for ensuring that electricity is inspected, tested and made safe by suitably qualified professionals, i.e. NICEIC Approved Electrical Contractor and Gas Safe Registered gas engineer before associated works commence. The Contractor is to provide test certificates and describe the works that were undertaken to achieve the above. The Contractor shall be responsible for all necessary artificial lighting and power for the correct execution of the works and may be required to pay for all electricity consumed. The Contractor shall also ensure that all supplies of artificial lighting and power are terminated following completion of the works informing the PM in writing with copies of all relevant termination notices to the appropriate Electricity Board. The Contractor shall be responsible for ensuring that all aerials, cables and / or fittings connected to the outside of the building, (e.g. B.T. cables, satellite television dishes or signage) are removed / repositioned as necessary. Where works affect any such fixtures to or supplying adjacent properties, which could be affected by the works or the erection of scaffolding, should also be repositioned and / or protected as required by the adjacent occupier. Any aerials, cables and / or fittings so re-positioned shall be refitted to their original position on completion of the relevant works. The Contractor shall coordinate with all relevant suppliers of services regarding all necessary disconnection and re-connection of services, data supplies relating to works. Also allow for all costs associated. | Info
A.16 | It is anticipated that the works will not be notifiable under the CDM Regulations 2015. The Contractor is to take on the role of the Principal Contractor in accordance with the CDM Regulations 2015. The Contractor must submit a copy of the Construction Phase Plan at least one week prior to the commencement of the works, containing all necessary risk assessments and method statements for the safe execution of the works. | Info
A.17 | The Contractor should allow for providing all necessary guarding barriers, notices, warning signs, hazard tape and PPE as necessary for the safe execution of the works to be detailed more fully within the Contractor's Construction Phase Plan. Any internal areas that are to be used by the Contractor must be maintained and cleaned to a proper and reasonable standard. The Contractor shall also undertake a thorough deep clean of all areas accessed and used during the programme of works. | Info
Schedule of condition
A.18 | The Contractor will provide a schedule of condition with photos of the site, to be agreed prior to starting any works on the site. Schedule to include all areas of the site and building that may be accessed by the Contractor during works. This is to be agreed at the pre-start meeting. | Info |  |  |  | none
Co-ordination of works
A.19 | The Contractor is to allow for reviewing the Health and Safety Information and Operation and Maintenance manuals held by the client. | Info
A.20 | The Contractor is to ensure the specification for all items has been thoroughly read and understood. | Info
A.21 | The Contractor must ensure that if any work site herras fencing and site access is used that it is made secure at the end of each day. | Info
A.22 | Skips must be the enclosed lockable type and should be kept a safe distance from the building. Ideally within the site compound area, if one is provided. | Info
A.23 | Where materials are specified by Manufacturer’s name, a full set of the Manufacturer’s instructions are to be retained on site and it is the Principal Contractor’s responsibility to ensure that these are strictly observed at all times. Bring to the attention of the PM any discrepancy between the specification and any instructions that are contrary to the Manufacturer’s recommendations. | Info
A.24 | PC to allow for management and co-ordination of all other contractors. | Info
A.25 | The Contractor is to confirm hourly labour rates. These rates are applicable for 60 days following receipt of this tender by WSP for analysis. These items are not to be included within the tender submission sum and are only for reference where extra works are required; Skilled – labour rate/ hour: £ p/h General – labour rate/ hour: £ p/h | Info
B | ASBESTOS SURVEY AND REMOVAL
B.1 | The contractor is to allow for the review and full comprehension of the Management Asbestos Survey Report on the garage building prior to works occurring. | Info
B.4 | Allow to appropriately remove any none asbestos from the Garage building and to dispose of contaminated materials to a Health and Safety Executive registered site in accordance with Hazardous Waste (England and Wales) Regulations 2005. | 1
B.5 | Should the unlikely event occur that the contractor suspects asbestos containing materials (ACM’s) are present whilst works are on-going, they are instructed to stop works immediately and inform the PM. | Info
C | TIMBER AND TIMBER RELATED PRODUCTS
C.1 | The Contractor shall ensure that all timber and timber products used in connection with the Contract (including all joinery, fittings, furniture and veneers) are lawfully obtained from forests and plantations which are managed to sustain their biodiversity, productivity and vitality, and to prevent harm to other ecosystems and any indigenous or forest dependent people. All procurement by the Contractor shall also comply with all relevant international agreements (e.g. The Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES). | Info
C.2 | All timber and wood-derived products for supply or use in performance of the contract must be independently verifiable and either: from a legal and sustainable source; or From a FLEGT – Licensed or equivalent source. | Info
C.3 | Management of the forest or plantation shall be audited at intervals confirming ongoing good forest management and by organisations with appropriate forest timber harvest and/or management rights for that forest. | Info
C.4 | The Contracting Authority will accept evidence from any of the following three categories: | Info
C.5 | Category A evidence: Certification under a scheme recognised by the UK government as meeting the criteria set out in the document entitled "UK Government Timber Procurement Policy: Criteria for Evaluating Category A Evidence" (available from the Contracting Authority on request and on CPET's website). The edition current on the day the contract is awarded shall apply. A list of assessed certification schemes that currently meet the government's requirements can be found on CPET's website. Acceptable schemes must ensure that at least 70% (by volume or weight) is from a legal and sustainable source with the balance from a legal source. | Info
C.6 | Category B evidence: Documentary evidence, other than Category A evidence and FLEGT evidence, that provides assurance that the source is sustainable. In this context "sustainable" is defined in the document entitled "UK Government Timber Procurement Policy: Evaluation of Category B Evidence: Methodology" (available from the Contracting Authority on request and on CPET's website). The edition current on the day the contract is awarded shall apply. Such Category B evidence may include, for example, independent audits and declarations by the contractor or his contractors. Where Category B evidence is to be relied on, the contractor is required to notify the Contracting Authority of the source or sources of all virgin timber and wood- derived products supplied. | Info
C.7 | Source in this context means the forest or plantation where the trees were grown and all subsequent places of delivery through the supply chain prior to receipt of the timber or wood-derived product by the Contracting Authority. The contractor shall separately identify virgin timber and wood-derived products supplied from forests and plantations that are claimed to be subject to sustainable timber production and shall submit to the Contracting Authority documentation in respect of such wood to confirm that the criteria for sustainable timber production set out in this specification have been met. If mixing is unavoidable within the supply chain then sources can still be accepted provided that there are adequate controls in place and at least 70% (by volume or weight) is from a legal and sustainable source with the balance from a legal source. | Info
Treatment of Joinery
C.8 | All new timber to be used for structural purposes e.g. timber-framed ceiling joist, is to be pressure impregnated, in accordance with the Materials and Workmanship section of the specification, and the PM will require proof that this treatment has been carried out. | Info
C.9 | When required, the Contractor shall provide evidence that the timber or timber products used in connection with the Contract have come from sustainably managed forests and plantations. This evidence might, for example, take the form of a Certificate (such as Chain of Custody Certificate FSC, PEFC, SFI and CSA) issued under a credible independent, verification scheme; or other documents which demonstrate the operation of an environmental management system incorporating forest management criteria that conform with internationally recognised principles (e.g. The Helsinki Guidelines). | Info
C.10 | The Contractor should have available information about the third party who holds the valid Chain of Custody Certificate for timber and timber products procured from a supplier who is not directly certified but who claims their supply is as evidence of its legality and sustainability. | Info
C.11 | The Contractor shall ensure that all chipboard, plywood, medium density fibreboard and other wood products used in connection with the Contract shall contain the lowest formaldehyde level commensurate with the intended use. The Contractor shall offer to provide reclaimed timber or products made from reclaimed timber where it is cost effective and practicable to do so. | Info
D | INTERNAL AND EXTERNAL ACCESS
D.1 | The Contractor is responsible for ensuring that scaffold is suitable for the works and meets with the Construction (Health Safety and Welfare) Regulations 1996 (as now incorporated into the CDM Regulations 2015) and to the satisfaction of the PM. | Info
D.2 | The Contractor is to allow for all necessary edge protection etc. to be supplied and fitted to ensure the protection of the work force, public and users of the building. | Info
D.3 | All scaffolding is to be fully boarded at all times, with kick boards fitted to all elevations of all landings. (Access ladders to be removed and stored in a secure location at the end of each working day, to prevent access by the public). Access ladders are to be fully secured to the scaffold whilst in use. | Info
D.4 | Protect scaffolding and access equipment from unauthorised access throughout the duration of the works. Contractor to provide a scaffold alarm to the tower used. | Info
D.5 | The Contractor is required to provide a tender stage method statement in respect of safe access provision for the roofing works. | Info
D.6 | The scaffolding will comply with the following British Standard requirements:- *BS EN 12811-1:2003 - Temporary works equipment. Scaffolds. Performance requirements and general design; *BS 5974:2017 - Code of practice for the planning, design, setting up and use of temporary suspended access equipment; All enactments, regulations and working rules relating to Safety, Health and Welfare. | Info |  |  |  | Check these BS numbers to make sure they are the most upto date and have not been superseded.
E | SECURITY AND PROTECTION
E.1 | Provide and maintain all necessary protection, barriers, warning signs etc. around the works. | Info
E.2 | Provide and maintain adequate protection to surfaces and surrounding areas of the works that are to be retained, and reinstated to original condition upon completion. The Contractor is to ensure that areas are clean and tidy at the start and end of each working day. | Info
E.3 | Ensure that all building materials and waste emanating from the site are stored appropriately within the boundaries of the site compound. The Contractor is to ensure that all materials or waste is stored securely. Ensure that all waste is removed from site on a weekly basis. | Info
E.4 | Existing road and other surfaces including soft landscaping, must be carefully worked around. All damage is to be reinstated to original condition. | Info
E.5 | Maintain suitable security internally to prevent unauthorised access to the building and works area on completion of the works each day. Access to be agreed and approved with the PM at the pre-start meeting. | Info
E.6 | All works scheduled to be read in conjunction with works information. | Info
F | ENABLING OR PREPARATORY WORKS REQUIRED
F.1 | Prior to the commencement of works by the contractor, the MCA will allow for an initial site inspection and works coordination with the PM (site access, existing services, material storage, permitted areas, etc.). This can form part of the ‘Pre- start’ on site. | Info
F.3 | Ensure that all associated cabling and electrical connections are isolated prior to works being carried out. Terminate, remove and secure cables going into the main building and garage building and prepare them for being reinstalled in the new garage. | Info |  |  |  | Does this dwg no. match to yours?
G | DEMOLITION
G.1 | Allow for the careful removal and safe storage (on site) of 4no. wooden timber panel fences (as described on drawing 'Proposed Garage Elevations). | Info |  |  |  | Include dwg no. Have you allowed for new timber posts, if panels are being reinstated?
G.2 | Allow for demolition of associated concrete bases, posts and underground concrete haunching of timber fences (as described on drawing 'Proposed Garage Elevations). | 1 | Item |  |  | Include dwg no.
G.3 | Allow for careful removal and safe storage of additional items if required so by the Employer (to be specified during the pre- start meeting). | 1 | Item
G.4 | Allow to dismantle the existing garage (as described on drawing BL (09) 01 – EXISTING) down to the ground level. | 1 | Item
G.5 | Allow to transport the dismantled garage to Holt Police Station. | 1 | Item
G.6 | Allow for disposal of all demolished items (except those named in sections G.1 and G.3) and general cleaning of the site. Note: All metal work obtained from demolition works is to be offered to the client in the first instance. Where metal work items are not required by the client, they are then to be disposed of by the Contractor. | Info
G.7 | Generally: The Contractor should allow for making good all affected surfaces during the works. All making good works undertaken by the contractor are to match and finish flush with adjacent surfaces. | Note
H | WORKS REQUIRED
H.1 | At all times whilst works are ongoing, make sure that all the works are done in accordance to the current British Standards, Building Regulations and Approved Documents (as a minimum standard) and that all works are in line with any drawings provided with this package. It also needs to be considered that the site is located close to the coast and therefore has to resist severe weather conditions (driven rain, strong winds, etc.) | Info |  |  |  | Is there an NBS section or Works Information?
Foundations
H.2 | Principal Contractor to carry out ground investigation and buried services survey prior to excavations. | 1 | Item
H.2 | Supply and install 3 no. intermediate wooden timber panel fences to match existing as closely as possible and as per drawing 'Proposed Garage Elevations'. | 3 | Item
H.3 | Supply and install concrete for 3no. bases. Ensure the ground holes for the concrete haunching is a minimum 550mm below ground with 100mm concrete haunching all around, as per manufacturers recommendations. | 3 | Item
H.4 | Supply and install 3no. concrete posts. as per drawing 'Proposed Garage Elevations', as per manufacturers recommendations. | 3 | Item
H.5 | Supply and install 3no. concrete gravel boards. as per drawing 'Proposed Garage Elevations', as per manufacturers recommendations. | 3 | Item |  |  | What about the foundations of the garage - the concrete slab for it to sit on?
H.6 | Allow to excavate and provide a concrete slab/foundation for the new garage structure. Sizes and specification to be provided by Hansons. Contractor to allow for all necessary M&E supply's within the slab to service the building. Slab to incorporate a fall/slope to the door vehicle entrance to mitigate for ponding. | 1 | Item
| Garage Structure |  |  |  |  | Should both doors be included in the Hanson quote, is there a window, security bars will need to be fitted over the window. Both doors included, no windows included.
H.7 | 5.5m Depth x 6m Width / 18’1” x 19’8” - Steel Framed Structure with 1x 10' wide x 7'5" High Manual Up and Over Steel Door and 1x Insulated 10 point locking steel personnel door. 100mm insulation to walls and roof. All rainwater goods to be allowed for. All as per Hanson Garages Ltd quotation and drawing 'Proposed Garage Elevations'. The Contractor is to familiarise themselves with the supplier’s specification. They are to submit a price for the system specified. | 1 | Item |  |  | How are the internals of the unit finished. Will it need building control sign off? Is additional drainage needed at the foot of then roller door - ACO drain?
H.8 | Supply and install photo luminescent sign EMERGENCY EXIT ‘running man’ sign to the inner face of the door. | 1 | Item |  |  | Is there external lighting above this door and a PIR for this and the main doors? Will this side door have a thumb turn installed?
H.9 | Supply and install a weather bar to the bottom of the garage door. PC to ensure there is sufficient clearance for the garage door to close. | 2 | Item
H.10 | Principal Contractor to ensure they have the correct connection details between the building and slab in keeping with expected wind loads on the structure. | Note
INTERNALS
H.11 | Allow for an internal plaster board finish, including for security bar on all window openings. Plaster boards to be plaster skimmed and receive 1 mist coat and 3 cost of Dulux emulsion. |  | M2
FLOORING
H.12 | Allow to supply and install Flowfast Quartz Colour (Wet Area) Grey 704 to be garage floor area. Approved sub-contractor required to apply. |  | M2
AERIAL
H.13 | Allow to supply and install of Amphenol JAYBEAM 2.7m Colinear Aerial/ 5m lightweight aerial mounting, and associated brackets as per proposed information. The Contractor is to familiarise themselves with the supplier’s specification. They are to submit a price to supply and fit the system specified, with all necessary certification. | 1 | Item
H.14 | Allow to supply and install of feeder cable as per proposed information. | 1 | Item
H.15 | Allow to supply and install of Repeater as per proposed information. | 1 | Item
H.16 | Allow to supply and install of a stainless steel finish, wall shelf 1800mm x 300mm and two end stainless steel heavy duty brackets installed to wall as per proposed information. Locate shelf approx. 2m from floor to MCA office as per proposed information. | 1 | Item
SURFACE WATER DRAINAGE
H.17 | Allow for soakaway excavations to create a gravel bedded soakaway for garage rainwater goods. | 1 | Item
H.18 | Supply and install 160 mm plastic pipe to the soakaway at least 5m from the building in accordance with BS8301. | 1 | Item
H.19 | Allow for filling the soakaway with 20mm aggregate. | 1 | Item
H.20 | Alternatively, allow for all excavations and making good for the garage rainwater goods to be connected into the existing below ground drainage system | 1 | Item
ELECTRICAL WORKS - GARAGE
H.21 | Mains power supply to be taken for the main building. PC to allow for trench excavations and making good following electrical works. | 1 | Item |  |  | Where is this taken from, will a trench have to be excavated to take it into the new garage and coming up through the slab?
H.22 | Allow to supply & install a new MK 6 Way consumer unit is to be positioned in accordance with current regulations. | 1 | Item
H.23 | Allow to supply & install 4no. JCC Skypack 4ft single LED Light (or similar) ceiling mounted internal LED luminaire. | 4 | Item
H.24 | Allow to supply & install 2no. JCC Skypack 4ft single emergency LED Light (or similar) ceiling mounted internal LED luminaire. | 2 | Item
H.25 | Allow to supply & install 1 no. JCC Niteflood 15W PIR external luminaire. All external luminaire to be weatherproof / IP 65 rated. | 1 | Item
H.26 | Allow to supply and install 6 No double switched sockets to be located as required. All switches and sockets are to be surface mounted. Type – Metalclad plus. | 6 | Item
H.27 | Allow to supply and install 1 No. gang switch for the internal lighting operation. Type – Metalclad plus. | 1 | item
H.28 | Allow for supply and installation of related wiring for the new system. | 1 | Item
H.29 | Allow for supply and installation of new earthed steel galvanized conduit (all new wiring is to be placed in this conduit). | 1 | item
H.30 | Allow for supply and installation of new electrical panel heaters | 2 | Item
H.31 | The Main Contractor is to arrange for all services to be tested prior to handover: all electrical services that have been relocated or adjusted are to be connected and tested by suitably qualified professionals, i.e. NICEIC Approved electrician prior to handover and certification provided. | 1 | Item
H.32 | The contractor is to provide all relevant O&M manuals and record drawings. | Info
I | LICENCES
I.1 | The Contractor shall be responsible for obtaining all necessary licences from local authorities and for complying in all respects with Byelaws, Regulations etc. (planning permission & building control approval are to be obtained by the Employer’s Delegate). | Info
J | HANDOVER AND COMPLETION
J.1 | Upon completion, the Contractor is to clear away all debris from the site, clean all areas where works were undertaken and generally leave the premises internally and externally in a clean and tidy condition ready for use by the client/ tenant and to the satisfaction of the PM. | Info
J.2 | Prior to the presentation of the works as ‘Complete’, the Principal Contractor must provide all Test Certificates (plus any applied documents), the Health and Safety file (to include residual risks, as built and installed information, consultants used, Contractors used etc. as per the PD) and any as built drawings to the PM. | Info
Prelims, overheads and profit
Contractors management fees
Contingency
Total Cost