

**Invitation to Tender for Monitoring and Evaluation Training for Analysts**

Tender Reference Number: 2191/01/2020

Deadline for Tender Responses: 2pm 7 February 2020

**Department for Business, Energy & Industrial Strategy**

Date: 16 January 2020

The Department for Business, Energy & Industrial Strategy (“BEIS”) wishes to commission a project to BEIS Monitoring and Evaluation Training for Analysts.

Enclosed are the following sections:

* Section 1 (page 6) Instructions and Information on Tendering Procedures
* Section 2 (page 11) Specification of Requirements
* Section 3 (page 23) Further Information on Tender Procedure
* Section 4 (page 26) Declarations to be submitted by the Tenderer

Statement of Non-Collusion

Form of Tender

Conflict of Interest

Standard Selection Questionnaire

The General Data Protection Regulation Assurance Questionnaire for Contractors

* Annex A: Pricing Schedule
* Annex B: Code of Practice for Research
* Annex C: Exclusion Grounds

Please read the instructions on the tendering procedures carefully since failure to comply with them may invalidate your tender. Your tender must be returned by 14:00 pm, 7th of February 2020 clearly marked as “TENDER”.

I look forward to receiving your response.

Yours sincerely,

Caroline Booth

E:mail: caroline.booth@beis.gov.uk

**Privacy Notice**

This notice sets out how we will use your personal data, and your rights. It is made under Articles 13 and/or 14 of the General Data Protection Regulation (GDPR).

**YOUR DATA**

We will process the following personal data:

Names and contact details of employees involved in preparing and submitting the bid; Names and contact details of employees proposed to be involved in delivery of the contract;

Names, contact details, age, qualifications and experience of employees whose CVs are submitted as part of the bid.

*Purpose*

We are processing your personal data for the purposes of the tender exercise described within the remainder of this Invitation to Tender, or in the event of legal challenge to such tender exercise.

*Legal basis of processing*

The legal basis for processing your personal data is processing is necessary for the performance of a task carried out in the public interest or in the exercise of official authority vested in the data controller, such as the exercise of a function of the Crown, a Minister of the Crown, or a government department; the exercise of a function conferred on a person by an enactment; the exercise of a function of either House of Parliament; or the administration of justice.

*Recipients*

Your personal data will be shared by us with other Government Departments or public authorities where necessary as part of the tender exercise. We may share your data if we are required to do so by law, for example by court order or to prevent fraud or other crime.

*Retention*

All tenders will be retained for a period of 6 years from the date of contract expiry, unless the contract is entered into as a deed in which case it will be kept for a period of 12 years from the date of contract expiry.

**YOUR RIGHTS**

You have the right to request information about how your personal data are processed, and to request a copy of that personal data.

You have the right to request that any inaccuracies in your personal data are rectified without delay.

You have the right to request that any incomplete personal data are completed, including by means of a supplementary statement.

You have the right to request that your personal data are erased if there is no longer a justification for them to be processed.

You have the right in certain circumstances (for example, where accuracy is contested) to request that the processing of your personal data is restricted.

You have the right to object to the processing of your personal data where it is processed for direct marketing purposes.

You have the right to object to the processing of your personal data.

**INTERNATIONAL TRANSFERS**

Your personal data will not be processed outside the European Union.

**COMPLAINTS**

If you consider that your personal data has been misused or mishandled, you may make a complaint to the Information Commissioner, who is an independent regulator. The Information Commissioner can be contacted at:

Information Commissioner's Office  
Wycliffe House  
Water Lane  
Wilmslow  
Cheshire  
SK9 5AF

0303 123 1113

casework@ico.org.uk

Any complaint to the Information Commissioner is without prejudice to your right to seek redress through the courts.

**CONTACT DETAILS**

The data controller for your personal data is the Department for Business, Energy & Industrial Strategy (BEIS).

You can contact the BEIS Data Protection Officer at: BEIS Data Protection Officer, Department for Business, Energy and Industrial Strategy, 1 Victoria Street, London SW1H 0ET. Email: [dataprotection@beis.gov.uk](mailto:dataprotection@beis.gov.uk).

**Section 1**

**Instructions and Information on Tendering Procedures**

Invitation to Tender for Monitoring and Evaluation Training for Analysts

Tender Reference Number: 2191/01/2020

Deadline for Tender Responses: 2pm 7 February 2020

**Contents**

A. Indicative Timetable 6

B. Procedure for Submitting Tenders 6

C. Conflict of Interest 7

D. Evaluation of Responses 8

E. Terms and conditions applying to this Invitation to Tender 8

F. Further Instructions to Contractors 8

G. Checklist of Documents to be Returned 9

# Indicative Timetable

The anticipated timetable for this tender exercise is as follows. BEIS reserves the right to vary this timetable. Any variations will be published on contracts finder or circulated to all organisations who have registered an interest in notifications.

Supplier interviews are planned for Monday 17 February. We aim to invite suppliers to interview on the week commencing 10 February. The interviews will consist of a 15-minute presentation of the proposal by the proposed team followed by 15 minutes of questions and answers. The room has a screen the team can use for a PowerPoint presentation, but you may want to bring the appropriate adaptor for your laptop and back up hardcopies.

|  |  |
| --- | --- |
| **Tender Timeline** | **Date** |
| Full invitation to tender issued | Friday, 17 January 2020 |
| Deadline for questions relating to the tender | Wednesday, 24 January 2020 |
| Responses to questions published | Thursday, 27 January 2020 |
| Deadline for receipt of tender | 14:00 pm, Friday, 7 February 2020 |
| Invite suppliers to interview | w/c 10 February 2020 |
| Supplier interviews | Monday 17 February 2020 |
| All suppliers alerted of outcome | Wednesday 19 February 2020 |
| Inception meeting, shortly followed by Contract award on signature by both parties and contract start date | Friday 21 February 2020 |

The contract is to be for a period of 14 months, with a break point after the pilot training, unless terminated or extended by the Department in accordance with the terms of the contract.

# Procedure for Submitting Tenders

The maximum page limit for tenders is 25 pages (includes all content - CVs, project plan etc). This limit excludes declarations.

Please email your proposal to Caroline Booth ([caroline.booth@beis.gov.uk](mailto:caroline.booth@beis.gov.uk)) by 14:00pm 7 February 2020.

For questions regarding the procurement process please contact Caroline Booth ([caroline.booth@beis.gov.uk](mailto:caroline.booth@beis.gov.uk)).

Tenders will be received up to the time and date stated. Please ensure that your tender is delivered not later than the appointed time on the appointed date. The Department does not undertake to consider tenders received after that time. The Department requires tenders to remain valid for a period indicated in the specification of requirements.

BEIS shall have the right to disqualify you from the procurement if you fail to fully complete your response, or do not return all of the fully completed documentation and declarations requested in this ITT. BEIS shall also have the right to disqualify you if it later becomes aware of any omission or misrepresentation in your response to any question within this invitation to tender. If you require further information concerning the tender process, or the nature of the proposed contract, email Caroline Booth (caroline.booth@beis.gov.uk). All questions should be submitted by 24 January 2020; questions submitted after this date may not be answered. Should questions arise during the tendering period, which in our judgement are of material significance, we will publish these questions with our formal reply by the end of 27 January 2020 and circulate – unnamed - to all organisations that have expressed an interest in bidding. All contractors should then take that reply into consideration when preparing their own bids, and we will evaluate bids on the assumption that they have done so.

You will not be entitled to claim from the Department any costs or expenses that you may incur in preparing your tender whether or not your tender is successful.

# Conflict of Interest

The Department’s standard terms and conditions of contract include reference to conflict of interest and require contractors to declare any potential conflict of interest to the Secretary of State.

For research and analysis, conflict of interest is defined the presence of an interest or involvement of the contractor, subcontractor (or consortium member) which could affect the actual or perceived impartiality of the research or analysis.

Where there may be a potential conflict of interest, it is suggested that the consortia or organisation designs working arrangements such that the findings cannot be influenced (or perceived to be influenced) by the organisation which is the owner of a potential conflict of interest. For example, consideration should be given to the different roles which organisations play in the research or analysis, and how these can be structured to ensue maintain an impartial approach to the project is maintained.

The process by which this is managed in the procurement process is as follows:

1. **During the bidding process, organisations may contact BEIS to discuss whether or not their proposed arrangement is likely to yield a conflict of interest.** Any responses given to individual organisations or consortia will be published on contract finder (in a form which does not reveal the questioner’s identity). Any organisation thinking of submitting a bid, should share their contact details with the staff member responsible for this procurement, to ensure they receive an update when any responses to questions are published.
2. **Contractors are asked to sign and return Declaration 3 p30 to indicate whether or not any conflict of interest may be, or be perceived to be, an issue.** If this is the case, the contractor or consortium should give a full account of the actions or processes that it will use to ensure that conflict of interest is avoided. In any statement of mitigating actions, contractors are expected to outline how they propose to achieve a robust, impartial and credible approach to the research.
3. **When tenders are scored, this declaration will be subject to a pass/fail score**, according to whether, on the basis of the information in the proposal and declaration, there remains a conflict of interest which may affect the impartiality of the research.

Failure to declare or avoid conflict of interest at this or a later stage may result in exclusion from the procurement competition, or in the Department exercising its right to terminate any contract awarded.

# Evaluation of Responses

The tender process will be conducted to ensure that bids are evaluated fairly and transparently, in accordance with agreed assessment criteria. Further details are provided in the specification.

# Terms and conditions applying to this Invitation to Tender

The Department’s Standard Terms and Conditions of Contract will apply to this contract. These can be downloaded from Contracts Finder.

# Further Instructions to Contractors

The Department reserves the right to amend the enclosed tender documents at any time prior to the deadline for receipt of tenders. Any such amendment will be numbered, dated and issued by 27 January 2020. Where amendments are significant, the Department may at its discretion extend the deadline for receipt of tenders.

The Department reserves the right to withdraw this contract opportunity without notice and will not be liable for any costs incurred by contractors during any stage of the process. Contractors should also note that, in the event a tender is considered to be fundamentally unacceptable on a key issue, regardless of its other merits, that tender may be rejected. By issuing this invitation the Department is not bound in any way and does not have to accept the lowest or any tender and reserves the right to accept a portion of any tender unless the tenderer expressly stipulates otherwise in their tender.

# Checklist of Documents to be Returned

* Proposal (maximum 25 pages)
* Annex A: Pricing Schedule
* Declaration 1: Statement of non-collusion
* Declaration 2: Form of Tender
* Declaration 3: Conflict of Interest
* Declaration 4: Standard Selection Questionnaire
* Declaration 5: The General Data Protection Regulation Assurance Questionnaire for Contractors

**Section 2**

**Specification of Requirements**

Invitation to Tender for Monitoring and Evaluation Training for Analysts

Tender Reference Number: 2191/01/2020

Deadline for Tender Responses: 2pm 7 February 2020

**Contents**

1. Summary of requirements 11

2. Introduction 11

3. Background 11

4. Aims and Objectives 11

4. Methodology 12

5. Outputs Required 14

6. Ownership and Publication 15

7. Quality Assurance 16

8. Timetable 16

9. Challenges 16

10. Working Arrangements 16

11. Data Protection 16

12. Skills and experience 16

13. Consortium Bids 17

14. Budget 18

15. Market engagement briefing slides and Q&A 18

16. Evaluation of Tenders 18

# Summary of requirements

BEIS has a need to develop evaluation analytical capability, particularly in relation to the evolving range of theory-based evaluation techniques. Training is being procured to equip our analysts with a good understanding of the different evaluation approaches and methods used in BEIS and how to use them appropriately given the policy context and design. This training offer is aimed at analysts who are responsible for designing and commissioning evaluations and may have a limited knowledge and experience of leading evaluations.

We envisage three modules over a total of three days covering:

1) Evaluation background, planning and approaches

2) Experimental approach, methods and quality assurance

3) Theory-based approach, methods and quality assurance.

The work includes scoping, designing content, piloting the training and rolling out the training over a further minimum of four sessions.

# Introduction

The Department for Business, Energy & Industrial Strategy (BEIS) is responsible for a range of policy areas including science and innovation, business and enterprise, competitiveness, labour markets, energy and decarbonisation. Across these areas we are progressing to meet our four headline priorities: getting businesses ready for Brexit and the opportunities beyond; leading the world in tackling climate change; solving the Grand Challenges facing our society; making the UK the best place to work and grow a business.

There are two main reasons for carrying out evaluation: learning and accountability. Learning helps to improve current policy to gain a general understanding of what types of things work for whom, when and to develop the evidence to inform future policy development. The department also needs to be accountable for how it spends taxpayer’s money. For more information on UK government’s approach to monitoring and evaluation see the Magenta Book and the Green Book.

Due to the range of work undertaken in the department BEIS needs to understand the different approaches available for monitoring and evaluation, including theory-based and experimental and quasi-experimental approaches.

# Background

There is a need to continue developing evaluation analytical capability in BEIS, particularly in relation to the evolving range of theory-based evaluation techniques. The purpose of the training is to equip our analysts with a good understanding of the different evaluation approaches and methods used in BEIS and how to use them appropriately given the policy context and design.

Large numbers of new staff and existing staff are moving within and outside the department, requiring a regular training programme to maintain our capability and capacity. This training offer is aimed at analysts who are responsible for designing and commissioning evaluations and may have a limited knowledge and experience of leading evaluations. Our evaluation analysts include Social Researchers, Statisticians, Operational Researchers and Economists, with varying expertise in evaluation.

# Aims and Objectives

The learning outcomes of the training are to have a better understanding of:

1. how to design, commission and quality assure evaluations

2. approaches and methods for monitoring and evaluating policies, projects and programmes.

Managing evaluations, data collection methods, reporting and presenting findings, and using evidence to have impact for policy development will be out of scope for this training, but sources of further information should be sign posted.

# Methodology

The contractor will be required to design the format and materials of the training programme. This will include some initial scoping work with BEIS to understand our specific requirements and the evaluation challenges within the department.

We envisage the training to cover three-day long modules over three weeks.

We have proposed a content outline below, **which we expect to be reviewed based on the scoping work and we welcome suggestions from tenders in their proposals.**

In the pricing schedule please provide prices for delivery of the courses in parts A-E. The pricing evaluation will be based on A+B only.

*Module 1: Background, planning ​and approaches (1 day)*

This module covers the following.

* Why we need monitoring and evaluation​ in the context of government policy evaluation with the aim of learning and accountability
  + Use, purpose and impact
* Examples of where evaluation​ have informed decision making, design and implementation
* Introduction to theory of change as a means of understanding the policy and facilitating monitoring and evaluation
* Group activity – constructing a theory of a change​ using a simple example
* Evaluation objectives: learning and accountability
  + e.g. testing a pilot, learning from a phased roll out, informing policy milestones, filling evidence gaps, attribution and/or contribution of a project and/or programme, a regulatory post implementation review, value for money
* Monitoring
* Understanding the purpose of monitoring, including examples
* How to plan and specify indicators, milestones and targets
* Data collection challenges including planning, access and permissions for use
* Forming baseline
* Reporting and uses of monitoring outputs, including examples
* Brief overview of the types of evaluation and their purpose
* Process – purpose, use and high-level designs
* Impact – purpose, use and high-level designs
* VfM – purpose, use and high-level method ​
* Needs driven and proportionate approach, based on scale of investment, risk and uncertainty, high-profile, statutory commitment, resource requirement considerations
* Evaluation questions
* What are evaluation questions and what are the different types?
  + what do we want to learn from this intervention?
  + What do we need to learn from policy development?
  + what specific evidence gaps does the evaluation need fill?
* Best practice for developing evaluation questions
* Activity – forming evaluation objectives and questions​
* Approaches​: understanding approaches and choosing the most appropriate and proportionate approach
* Experimental/quasi-experimental
* Theory-based including realist evaluation
* Outcome evaluation/monitoring performance/benefits management ​
* Activity – assigning an appropriate approach​ to different scenarios
* Introductions to other considerations for evaluation and signposting to resources and training on:
  + Procurement and commissioning
  + Managing evaluations
  + Data collections methods
  + Use and dissemination
  + Further information on evaluation approaches and methods (e.g. Magenta Book and annexes, Betterevaluation.org etc.)

*Module 2: Experimental approach, methods and quality assurance (1 day)*

This module covers the following elements:

* Introduction
  + Revisiting theory of change and key impact of interest
  + What is experimental/quasi-experimental design
  + Establishing a counterfactual​
* How and when to apply the following methods:
  + Randomised Control Trial​s including what you need to run an RCT, issues to consider in implementation and design (actual examples) and different RCT designs inc. ethics of randomisation
  + Difference-in-differences analysis​
  + Propensity score matching
  + Instrumental variables: regression discontinuity and interrupted time series analysis​
  + Before-and-after comparisons​
* For each of these methods: pros, conditions required for successful use and implementation, limitations and resource requirements
* Appropriate additional/supplementary research in order to understand the impacts measured
* Activity – assigning an appropriate experimental evaluation method using real BEIS scenarios
* Quality assurance​ and peer review – general considerations and specifically for experimental and quasi-experimental
  + Why and how to quality assure throughout an evaluation e.g. design including evaluation objectives and questions, approaches, analytical and data collection methods, deliverables including findings and technical reporting
  + Overview of dimensions of quality assurance e.g. framing, transparency, appropriateness, validity, credibility, transferability, robustness and structure​
  + Introduction to and appropriate use of Maryland scale for experimental methods​
  + Peer review process

*Module 3: Theory-based approach, methods and quality assurance (1 day)*

* Introduction

Theory-based approaches, appropriateness (research question and epistemological framework

* + What is theory-based evaluation
  + What is realist evaluation
  + Revisiting the theory of change and key impact of interest
* How and when to apply the following methods:
  + Developing hypotheses (including alternatives) using Context-Mechanism-Outcome (CMO) Configurations
    - Optional activity to construct a CMO
  + Qualitative comparative analysis​
  + Contribution analysis​
  + Process tracing​ (also with Bayesian updating)
* For each of these methods: pros, conditions required for successful use and implementation, limitations and resource requirements
* Activity – assigning an appropriate theory-based evaluation method using real BEIS scenarios
* Quality assurance​ and peer review – general considerations and specifically for experimental and quasi-experimental
  + Why and how to quality assure throughout an evaluation e.g. design including evaluation objectives and questions, approaches, analytical and data collection methods, deliverables including findings and technical reporting
  + Overview of dimensions of quality assurance e.g. framing, transparency, appropriateness, validity, credibility, transferability, robustness and structure​
  + Introduction to and appropriate use of Maryland scale for experimental methods​
  + Peer review process

# Outputs Required

The outputs and deliverables expected at each stage of the project are provided below. These are based on the approach provided above.

**Design phase (including sign off of content) – mid-Feb to early April 2020**

* Content of the training to be delivered
* Clear and accessible explanation of the suggested content described above.
* Content should be visually engaging
* Should include BEIS/government specific examples which will be provided by BEIS
* In an electronic format for presenting to participants, e.g. PowerPoint
* Materials to accompany training
* A more detailed explanation of the content.
* This should complement and be used alongside the presentation, with space for notes
* To include signposting to other resources and examples related to the content.
* Clearly indexed for ease of reference.
* Provided in an electronic format, e.g. pdf
* Material for activities
* Used to facilitate activities.
* Tasks clearly explained
* Participant and stakeholder feedback on pilot training
* Design an online form to capture feedback on content, delivery and learning outcomes.

Draft versions of all material to be sent to BEIS for comment, which will include a few rounds of comments. Once BEIS comments have been responded to, BEIS will sign off the final version.

**Delivery of Pilot Training – w/c 20 April to w/c 4 May 2020**

* Delivery of the three pilot one day modules, over three weeks.
* It is envisaged the three training modules will be delivered by more than one. facilitator, to reflect the specialist knowledge required for each module.
* The training team should have the capacity to provide expert trainers on a flexible basis to meet demand
* BEIS evaluation representatives will attend throughout the pilot training.
* We would suggest a maximum of 15 to 20 participants per module
* Training will take place in London at a location sourced by BEIS.
* **Review of pilot training – May 2020**
* A review will take place with BEIS and the contractor on the delivery of the pilot training modules based on feedback from participants and stakeholders.
* Based on the review, if required, amendments will be made to the content material and delivery format.
* Approval by BEIS of any changes made.
* **Delivery of rolling training programme – early June 2020 to March 2021**
* The number of training courses will depend on demand; we require a front-loaded rollout and envisage a minimum of four (up to eight) courses over the period.
* Delivered in line with the suggested content set out above, taking account of changes based on the review.

BEIS will assess future training needs and decide on any tendering for future waves of training. On the basis of current recruitment levels, we envisage an ongoing training need.

# Ownership and Publication

Unless otherwise stated in the tender, all outputs from the evaluation training will assume to be owned by BEIS. The outputs and tools developed for the training will be transferred to BEIS at times agreed with BEIS and cannot therefore be used by contractors for purposes other than our work. Bidders should be explicit if they intend to use outputs and tools that they have intellectual property rights over and that will not be owned by BEIS.

# Quality Assurance

Please outline your internal quality assurance processes for this training. BEIS expects to provide comments on iterations of the content and delivery plans.

# Training Timetable

A high-level timetable is outlined below. Please provide a more detailed timetable in your proposal. Please provide explanatory text if you believe a deviation from the high level timetable is required.

|  |  |
| --- | --- |
| **Deliverables** | **Date** |
| Design phase (including sign off of content) | late-Feb to early April 2020 |
| Delivery of pilot training | w/c 20 April to w/c 4 May 2020 |
| Review of pilot training | May 2020 |
| Delivery of rolling training programme | early June 2020 to March 2021 |

BEIS will assess future training needs and decide on extending or retendering the contract. Based on current recruitment levels, we envisage an ongoing training need.

# Challenges

We have outlined below an initial list of the challenges we foresee in designing and delivering this training. In the proposal, please suggest your approach to addressing each of these and include any additional challenges;

* Targeting the content at the right level to meet the needs of both analysts for whom monitoring, and evaluation is new or only part of their role.
* Covering all the approaches and methods of monitoring and evaluation in this brief in enough depth to be able to proficiently commission and quality assure projects.
* The successful team will need to have the capacity, skills, experience and availability to deliver the training on continuing basis covering the full brief.
* Communicating the practical application of monitoring and evaluation in a government policy context.
* Delivering an engaging course.

Reflecting the bespoke nature of this training and module three’s focus on theory-based method, sufficient thought will need to be invested in developing this training.

# Working Arrangements

The successful contractor will be expected to identify one named point of contract through whom all enquiries can be filtered. A BEIS project manager will be assigned to the project and will be the central point of contact.

# **Data Protection**

The Contractor will be compliant with the Data Protection Legislation, as defined in the terms and conditions applying to this Invitation to Tender. A guide to The General Data Protection Regulation published by the Information Commissioner’s Office can be found [here.](https://ico.org.uk/for-organisations/guide-to-the-general-data-protection-regulation-gdpr/lawful-basis-for-processing/)

# **Skills and experience**

BEIS would like you to demonstrate that you have the experience and capabilities to undertake the project. Your tender response should include a summary of each proposed team members experience and capabilities.

The following skills and capabilities are considered important for this work:

* Expert knowledge of evaluation approaches and methods and their practical application, preferably in government.
* Within the team there must be expertise to cover experimental *and* theory-based approaches, as outlined in the content.
* Designing and delivering training.
* High quality, engaging written and presentational communication skills.
* It is desirable to have knowledge of monitoring and evaluation in either UK energy and climate change policy and/or business and industrial strategy.
* Understanding the use of evaluation within government policy e.g. policy development, spending reviews, post implementation reviews, informing policy decisions, communicating impact

We welcome consortium bids, to cover the range of expertise and experience required.

Contractors should propose named members of the project team and include the tasks and responsibilities of each team member. This should be clearly linked to the work programme, indicating the grade/ seniority of staff and number of days allocated to specific tasks.

Contractors should identify the individual(s) who will be responsible for managing the project.

# **Consortium Bids**

In the case of a consortium tender, only one submission covering all of the partners is required but consortia are advised to make clear the proposed role that each partner will play in performing the contract as per the requirements of the technical specification. We expect the bidder to indicate who in the consortium will be the lead contact for this project, and the organisation and governance associated with the consortia.

Contractors must provide details as to how they will manage any sub-contractors and what percentage of the tendered activity (in terms of monetary value) will be sub-contracted.

If a consortium is not proposing to form a corporate entity, full details of alternative proposed arrangements should be provided in the Annex. However, please note the Department reserves the right to require a successful consortium to form a single legal entity in accordance with Regulation 28 of the Public Contracts Regulations 2006.

The Department recognises that arrangements in relation to consortia may (within limits) be subject to future change. Potential Providers should therefore respond in the light of the arrangements as currently envisaged. Potential Providers are reminded that any future proposed change in relation to consortia must be notified to the Department so that it can make a further assessment by applying the selection criteria to the new information provided.

# Budget

The budget for this project is £70k to £110k excluding VAT.

Contractors should provide a full and detailed breakdown of costs (including options where appropriate). This should include staff (and day rate) allocated to specific tasks.

Cost will be a criterion against which bids will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments is as follows:

* Delivery and BEIS sign off of course content and pilot, including review
* Successful completion of each course (or set of courses if run concurrently)

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The Department aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Market engagement briefing slides and Q&A

Copies of the market engagement briefing slides and Q&A that took place on 8 January can be found below.

 

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 25 pages, excluding declarations. Tenders will be evaluated by at least three BEIS staff.

BEIS will select the bidder that scores highest against the criteria and weighting listed below:

* **Conflict of interest:** pass/fail. See page 7 of the ITT for further information

**EVALUATION CRITERIA AND SCORING METHODOLOGY**

Contractors are invited to submit full tenders of no more than 25 pages with 11-point font, excluding declarations. Tenders will be evaluated by at least three BEIS staff. BEIS will select the bidder that scores highest against the criteria and weighting listed below:

|  |  |  |
| --- | --- | --- |
| ***Criterion*** | ***Description*** | ***Weighting*** |
| 01 | Completed declarations including: Statement of non-collusion, Form of Tender, Conflict of Interest, Standard Selection Questionnaire, The General Data Protection Regulation Assurance Questionnaire for Contractors | Pass/Fail |
| 02 | **Understanding the requirements:**Demonstrated an understanding of the monitoring and evaluation training requirements for BEIS to support government policy. | 5% |
| 03 | **Design and delivery of training in line with the specification:**Quality of the structure and content of the training, including the delivery approach, to meet BEIS’s monitoring and evaluation requirements and deliver high quality and engaging training within the specified timetable. | 25% |
| 04 | **Project team and ability to deliver:**Evidence of how the research team meet the skills and capabilitiesset out in the specification. | 25% |
| 05 | **Specification of project management and quality assurance:**outline project plan and timetable, quality assurance and sign off arrangements. Provide consideration of risk including a risk register. | 10% |
| 06 | **Cost**: Price will be marked proportionately to the lowest bid for the total cost (excluding VAT) of the training (design, pilot and delivery of up to 8 courses). Please complete the pricing schedule in Annex A. Parts A and E will be included in the price evaluation. | 20% |
| 07 | **Supplier interview:** Evidence of how the proposal, communication and presentational skills of the team meets the training needs set out in the specification, including any clarifications. | 15% |
|  | | 100% |

**Scoring Method**

*Non-Price elements*

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100. Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

|  |  |
| --- | --- |
| **Score** | **Description** |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

*Scoring for Pricing Evaluation*

Price will be marked using proportionate pricing. Please see the example below.

Marking will be conducted proportionate to the lowest price.

There will be a maximum of 20 marks.

The lowest priced bid will receive the full 20 marks, all other bids will then be marked as set out below.

Proportionate Pricing scoring example

If 20% = 20 marks

|  |  |  |
| --- | --- | --- |
| Supplier | Price | Marks |
| 1 (lowest bid) | £50,000 | 20 |
| 2 | £60,000 | 50/60 \* 20 = 16.7 |
| 3 | £75,000 | 50/75 \* 20 = 13.3 |

**Structure of Tenders**

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above. Complete the price schedule attached at Annex A, specifying the daily rates (ex-VAT) you will charge for each level of your staff.

**Bid Clarification**

After reviewing and evaluating the written proposals, BEIS will hold bid clarification interviews with suppliers.

**Feedback**

Feedback will be given in the unsuccessful letters or emails.

**Section 3**

**Further Information on Tender Procedure**

Invitation to Tender for Monitoring and Evaluation Training for Analysts

Tender Reference Number: 2191/01/2020

Deadline for Tender Responses: 2pm 7 February 2020

**Contents:**

A. [Definitions](#_Definitions) 24

B. [Data security](#_Data_security) 24

C. [Non-Collusion](#_Non-Collusion) 25

# Definitions

Please note that references to the "Department" throughout these documents mean The Secretary of State for Business, Energy and Industrial Strategy acting through his/her representatives in the Department for Business, Energy & Industrial Strategy.

The Freedom of Information Act 2000 (“FOIA”) and the Environmental Information Regulations 2004 (“EIR”) apply to the Department. You should be aware of the Department’s obligations and responsibilities under FOIA or EIR to disclose, on written request, recorded information held by the Department. Information provided in connection with this procurement exercise, or with any contract that may be awarded as a result of this exercise, may therefore have to be disclosed by the Department in response to such a request, unless the Department decides that one of the statutory exemptions under the FOIA or the exceptions in the EIR applies. If you wish to designate information supplied as part of this response as confidential, of if you believe that its disclosure would be prejudicial to any person’s commercial interests, you must provide clear and specific detail as to the precise information involved and explain (in broad terms) what harm may result from disclosure if a request is received, and the time period applicable to that sensitivity. Such designation alone may not prevent disclosure if in the Department’s reasonable opinion publication is required by applicable legislation or Government policy or where disclosure is required by the Information Commissioner or the First-tier Tribunal (Information Rights).

Additionally, the Government’s transparency agenda requires that tender documents (including ITTs such as this) are published on a designated, publicly searchable web site. The same applies to other tender documents issued by the Department (including the original advertisement and the pre-qualification questionnaire (if used)), and any contract entered into by the Department with its preferred supplier once the procurement is complete. By submitting a tender, you agree that your participation in this procurement may be made public. The answers you give in this response will not be published on the transparency web site (but may fall to be disclosed under FOIA or EIR (see above)). Where tender documents issued by the Department or contracts with its suppliers fall to be disclosed the Department will redact them as it thinks necessary, having regard (inter alia) to the exemptions/exceptions in the FOIA or EIR.

# Data security

The successful tenderer must comply with all relevant Data Protection Legislation, as defined in the terms and conditions applying to this Invitation to Tender.

Section 4 contains a “The General Data Protection Regulation Assurance Questionnaire for Contractors” (Declaration 5) to evidence the extent of readiness. The Authority may ask the Contractor to provide evidence to support the position stated in the questionnaire. The Authority may require the successful Contractor to increase their preparedness where the Authority is not satisfied that the Contractor will be in a position to meet its obligations under the terms and conditions. If the Contractor fails to satisfy the Authority that it will be in a position to meet its obligations under the terms and conditions in the event that the Contractor is successful, the Authority reserves the right to exclude the bidder from this procurement.

# Non-Collusion

No tender will be considered for acceptance if the contractor has indulged or attempted to indulge in any corrupt practice or canvassed the tender with an officer of BEIS. Section 4 contains a "Statement of non-collusion" (declaration 1); any breach of the undertakings covered under items 1 - 3 inclusive will invalidate your tender. If a contractor has indulged or attempted to indulge in such practices and the tender is accepted, then grounds shall exist for the termination of the contract and the claiming damages from the successful contractors. You must not:

* Tell anyone else what your tender price is or will be, before the time limit for delivery of tenders.
* Try to obtain any information about anyone else's tender or proposed tender before the time limit for delivery of tenders.
* Make any arrangements with another organisation about whether or not they should tender, or about their or your tender price.

Offering an inducement of any kind in relation to obtaining this or any other contract with the Department will disqualify your tender from being considered and may constitute a criminal offence.

**Section 4**

**Declarations to be submitted by the Tenderer**

Invitation to Tender for Monitoring and Evaluation Training for Analysts

Tender Reference Number: 2191/01/2020

Deadline for Tender Responses: 2pm 7 February 2020

**Contents**

Declaration 1: Statement of non-collusion 26

Declaration 2: Form of Tender 27

Declaration 3: Conflict of Interest 28

Declaration 4: Standard Selection Questionnaire 30

Declaration 5: The General Data Protection Regulation Assurance Questionnaire for Contractors 52

Declaration 6: Code of Practice 53

# Declaration 1: Statement of non-collusion

To: The Department for Business, Energy & Industrial Strategy

1. We recognise that the essence of competitive tendering is that the Department will receive a bona fide competitive tender from all persons tendering. We therefore certify that this is a bona fide tender and that we have not fixed or adjusted the amount of the tender or our rates and prices included therein by or in accordance with any agreement or arrangement with any other person.

2. We also certify that we have not done and undertake not to do at any time before the hour and date specified for the return of this tender any of the following acts:

1. communicate to any person other than the Department the amount or approximate amount of our proposed tender, except where the disclosure, in confidence, of the approximate amount is necessary to obtain any insurance premium quotation required for the preparation of the tender;
2. enter into any agreement or arrangement with any other person that he shall refrain for submitting a tender or as to the amount included in the tender;
3. offer or pay or give or agree to pay or give any sum of money, inducement or valuable consideration directly or indirectly to any person doing or having done or causing or having caused to be done, in relation to any other actual or proposed tender for the contract any act, omission or thing of the kind described above.

3. In this certificate, the word “person” shall include any person, body or association, corporate or unincorporated; and “any agreement or arrangement” includes any such information, formal or informal, whether legally binding or not.

……………………………………………………………………………….….

Signature (duly authorised on behalf of the tenderer)

……….………………………………………………………………………….

Print name

…………………………………………………………….…………………….

On behalf of (organisation name)

…………………………………………………………………….…………….

Date

# Declaration 2: Form of Tender

To: The Department for Business, Energy & Industrial Strategy

1. Having considered the invitation to tender and all accompanying documents

(including without limitation, the terms and conditions of contract and the Specification) we confirm that we are fully satisfied as to our experience and ability to deliver the goods/services in all respects in accordance with the requirements of this invitation to tender.

2. We hereby tender and undertake to provide and complete all the services required to be performed in accordance with the terms and conditions of contract and the Specification for the amount set out in the Pricing Schedule.

3. We agree that any insertion by us of any conditions qualifying this tender or any unauthorised alteration to any of the terms and conditions of contract made by us may result in the rejection of this tender.

4. We agree that this tender shall remain open to be accepted by the Department for 8 weeks from the date below.

5. We understand that if we are a subsidiary (within the meaning of section 1159 of (and schedule 6 to) the Companies Act 2006) if requested by the Department we may be required to secure a Deed of Guarantee in favour of the Department from our holding company or ultimate holding company, as determined by the Department in their discretion.

6. We understand that the Department is not bound to accept the lowest or any tender it may receive.

7. We certify that this is a bona fide tender.

…………………………………………………………………………........

Signature (duly authorised on behalf of the tenderer)

…………………………………………………………………………………

Print name

………………………………………………………………………….

On behalf of (organisation name)

………………………………………………………………………….

Date

# Declaration 3: Conflict of Interest

I have nothing to declare with respect to any current or potential interest or conflict in relation to this research (or any potential providers who may be subcontracted to deliver this work, their advisers or other related parties). By conflict of interest, I mean, anything which could be reasonably perceived to affect the impartiality of this research, or to indicate a professional or personal interest in the outcomes from this research.

Signed …………………………………….

Name …………………………………….

Position …………………………………….

***OR***

I wish to declare the following with respect to personal or professional interests related to relevant organisations\*;

* X
* X

*Where a potential conflict of interest has been declared for an individual or organisation within a consortia, please clearly outline the role which this individual or organisation will play in the proposed project and how any conflict of interest has or will be mitigated.*

* X
* X

Signed …………………………………….

Name …………………………………….

Position …………………………………….

Please complete this form and return this with your ITT documentation - Nil returns **are** required.

**\*** These may include (but are not restricted to);

* A professional or personal interest in the outcome of this research
* For evaluation projects, a close working, governance, or commercial involvement in the project under evaluation
* Current or past employment with relevant organisations
* Payment (cash or other) received or likely to be received from relevant organisations for goods or services provided (Including consulting or advisory fees)
* Gifts or entertainment received from relevant organisations
* Shareholdings (excluding those within unit trusts, pension funds etc) in relevant organisations
* Close personal relationship or friendships with individuals employed by or otherwise closely associated with relevant organisations

***All of the above apply both to the individual signing this form and their close family / friends / partners etc.***

If your situation changes during the project in terms of interests or conflicts, you must notify the Department straight away.

A DECLARATION OF INTEREST WILL NOT NECESSARILY MEAN THE INDIVIDUAL OR ORGANISATION CANNOT WORK ON THE PROJECT; BUT IT IS VITAL THAT ANY INTEREST OR CONFLICT IS DECLARED SO IT CAN BE CONSIDERED OPENLY.

# Declaration 4: Standard Selection Questionnaire

**Potential Supplier Information and Exclusion Grounds: Part 1 and Part 2.**

The standard Selection Questionnaire is a self-declaration, made by you (the potential supplier), that you do not meet any of the grounds for exclusion[[1]](#footnote-2). If there are grounds for exclusion, there is an opportunity to explain the background and any measures you have taken to rectify the situation (we call this self-cleaning).

A completed declaration of Part 1 and Part 2 provides a formal statement that the organisation making the declaration has not breached any of the exclusions grounds. Consequently we require all the organisations that you will rely on to meet the selection criteria to provide a completed Part 1 and Part 2. For example these could be parent companies, affiliates, associates, or essential sub-contractors, if they are relied upon to meet the selection criteria. This means that where you are joining in a group of organisations, including joint ventures and partnerships, each organisation in that group must complete one of these self-declarations. Sub-contractors that you rely on to meet the selection criteria must also complete a self-declaration (although sub-contractors that are not relied upon do not need to complete the self-declaration).

When completed, this form is to be sent back to the contact point given in the procurement documents along with the selection information requested in the procurement documentation.

**Note for Contracting Authorities: The following paragraph is optional for inclusion, authorities can delete it** if **they prefer to receive** only **Word/ PDF versions of the standard Selection Questionnaire**. [*Alternatively you can submit the completed Exclusion Grounds of the* [*EU ESPD*](https://ec.europa.eu/tools/espd) *(Part III) as a downloaded XML file to the buyer contact point along with the selection information requested in the procurement documentation*.]

**Supplier Selection Questions: Part 3**

The procurement document will provide instructions on the selection questions you need to respond to and how to submit those responses. If you are bidding on behalf of a group (consortium) or you intend to use sub-contractors, you should complete all of the selection questions on behalf of the consortium and/or any sub-contractors.

If the relevant documentary evidence referred to in the Selection Questionnaire is not provided upon request and without delay we reserve the right to amend the contract award decision and award to the next compliant bidder.

**Consequences of misrepresentation**

If you seriously misrepresent any factual information in filling in the Selection Questionnaire, and so induce an authority to enter into a contract, there may be significant consequences. You may be excluded from the procurement procedure, and from bidding for other contracts for three years. If a contract has been entered into you may be sued for damages and the contract may be rescinded. If fraud, or fraudulent intent, can be proved, you or your responsible officers may be prosecuted and convicted of the offence of fraud by false representation, and you must be excluded from further procurements for five years.

**Invitation to Tender for Monitoring and Evaluation Training for Analysts**

**2191/01/2020**

**OPEN**

**Notes for completion**

1. The “authority” means the contracting authority, or anyone acting on behalf of the contracting authority, that is seeking to invite suitable candidates to participate in this procurement process.
2. “You” / “Your” refers to the potential supplier completing this standard Selection Questionnaire i.e. the legal entity responsible for the information provided. The term “potential supplier” is intended to cover any economic operator as defined by the Public Contracts Regulations 2015 (referred to as the “regulations”) and could be a registered company; the lead contact for a group of economic operators; charitable organisation; Voluntary Community and Social Enterprise (VCSE); Special Purpose Vehicle; or other form of entity.
3. Please ensure that all questions are completed in full, and in the format requested. If the question does not apply to you, please state ‘N/A’. Should you need to provide additional information in response to the questions, please submit a clearly identified annex.
4. The authority recognises that arrangements set out in section 1.2 of the standard Selection Questionnaire, in relation to a group of economic operators (for example, a consortium) and/or use of sub-contractors, may be subject to change and will, therefore, not be finalised until a later date. The lead contact should notify the authority immediately of any change in the proposed arrangements and ensure a completed Part 1 and Part 2 is submitted for any new organisation relied on to meet the selection criteria. The authority will make a revised assessment of the submission based on the updated information.
5. For Part 1 and Part 2 every organisation that is being relied on to meet the selection must complete and submit the self-declaration.
6. **Note for Contracting Authorities: The following paragraph is optional for inclusion if a decision has been made to request a self-declaration of the exclusion grounds from sub-contractors.** *All sub-contractors are required to complete Part 1 and Part 2[[2]](#footnote-3).*
7. For answers to Part 3 -If you are bidding on behalf of a group, for example, a consortium, or you intend to use sub-contractors, you should complete all of the questions on behalf of the consortium and/ or any sub-contractors, providing one composite response and declaration.

The authority confirms that it will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the regulations, or pursuant to an order of the court or demand made by any competent authority or body where the authority is under a legal or regulatory obligation to make such a disclosure.

**Part 1: Potential Supplier Information**

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

|  |  |  |
| --- | --- | --- |
| Section 1 | Potential supplier information | |
| Question number | Question | Response |
| 1.1(a) | Full name of the potential supplier submitting the information |  |
| 1.1(b) – (i) | Registered office address (if applicable) |  |
| 1.1(b) – (ii) | Registered website address (if applicable) |  |
| 1.1(c) | Trading status   1. public limited company 2. limited company 3. limited liability partnership 4. other partnership 5. sole trader 6. third sector 7. other (please specify your trading status) |  |
| 1.1(d) | Date of registration in country of origin |  |
| 1.1(e) | Company registration number (if applicable) |  |
| 1.1(f) | Charity registration number (if applicable) |  |
| 1.1(g) | Head office DUNS number (if applicable) |  |
| 1.1(h) | Registered VAT number |  |
| 1.1(i) - (i) | If applicable, is your organisation registered with the appropriate professional or trade register(s) in the member state where it is established? | Yes ☐  No ☐  N/A ☐ |
| 1.1(i) - (ii) | If you responded yes to 1.1(i) - (i), please provide the relevant details, including the registration number(s). |  |
| 1.1(j) - (i) | Is it a legal requirement in the state where you are established for you to possess a particular authorisation, or be a member of a particular organisation in order to provide the services specified in this procurement? | Yes ☐  No ☐ |
| 1.1(j) - (ii) | If you responded yes to 1.1(j) - (i), please provide additional details of what is required and confirmation that you have complied with this. |  |
| 1.1(k) | Trading name(s) that will be used if successful in this procurement |  |
| 1.1(l) | Relevant classifications (state whether you fall within one of these, and if so which one)   1. Voluntary Community Social Enterprise (VCSE) 2. Sheltered Workshop 3. Public service mutual |  |
| 1.1(m) | Are you a Small, Medium or Micro Enterprise (SME)[[3]](#footnote-4)? | Yes ☐  No ☐ |
| 1.1(n) | Details of Persons of Significant Control (PSC), where appropriate: [[4]](#footnote-5)  - Name;  - Date of birth;  - Nationality;  - Country, state or part of the UK where the PSC usually lives;  - Service address;  - The date he or she became a PSC in relation to the company (for existing companies the 6 April 2016 should be used);  - Which conditions for being a PSC are met;  - Over 25% up to (and including) 50%,  - More than 50% and less than 75%,  - 75% or more. [[5]](#footnote-6)  (Please enter N/A if not applicable) |  |
| 1.1(o) | Details of immediate parent company:    - Full name of the immediate parent company  - Registered office address (if applicable)  - Registration number (if applicable)  - Head office DUNS number (if applicable)  - Head office VAT number (if applicable)  (Please enter N/A if not applicable) |  |
| 1.1(p) | Details of ultimate parent company:  - Full name of the ultimate parent company  - Registered office address (if applicable)  - Registration number (if applicable)  - Head office DUNS number (if applicable)  - Head office VAT number (if applicable)  (Please enter N/A if not applicable) |  |

Please note: A criminal record check for relevant convictions may be undertaken for the preferred suppliers and the persons of significant in control of them.

Please provide the following information about your approach to this procurement:

|  |  |  |
| --- | --- | --- |
| Section 1 | Bidding model | |
| Question number | Question | Response |
| 1.2(a) - (i) | Are you bidding as the lead contact for a group of economic operators? | Yes ☐  No ☐  If yes, please provide details listed in questions 1.2(a) (ii), (a) (iii) and to 1.2(b) (i), (b) (ii), 1.3, Section 2 and 3.  If no, and you are a supporting bidder please provide the name of your group at 1.2(a) (ii) for reference purposes, and complete 1.3, Section 2 and 3. |
| 1.2(a) - (ii) | Name of group of economic operators (if applicable) |  |
| 1.2(a) - (iii) | Proposed legal structure if the group of economic operators intends to form a named single legal entity prior to signing a contract, if awarded. If you do not propose to form a single legal entity, please explain the legal structure. |  |
| 1.2(b) - (i) | Are you or, if applicable, the group of economic operators proposing to use sub-contractors? | Yes ☐  No ☐ |
| 1.2(b) - (ii) | If you responded yes to 1.2(b)-(i) please provide additional details for each sub-contractor in the following table: we may ask them to complete this form as well.   |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | Name |  |  |  |  |  | | Registered address |  |  |  |  |  | | Trading status |  |  |  |  |  | | Company registration number |  |  |  |  |  | | Head Office DUNS number (if applicable) |  |  |  |  |  | | Registered VAT number |  |  |  |  |  | | Type of organisation |  |  |  |  |  | | SME (Yes/No) |  |  |  |  |  | | The role each sub-contractor will take in providing the works and /or supplies e.g. key deliverables |  |  |  |  |  | | The approximate % of contractual obligations assigned to each sub-contractor |  |  |  |  |  | | |

**Contact details and declaration**

I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

I declare that, upon request and without delay I will provide the certificates or documentary evidence referred to in this document.

I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

I understand that the authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

I am aware of the consequences of serious misrepresentation.

|  |  |  |
| --- | --- | --- |
| Section 1 | Contact details and declaration | |
| Question number | Question | Response |
| 1.3(a) | Contact name |  |
| 1.3(b) | Name of organisation |  |
| 1.3(c) | Role in organisation |  |
| 1.3(d) | Phone number |  |
| 1.3(e) | E-mail address |  |
| 1.3(f) | Postal address |  |
| 1.3(g) | Signature (electronic is acceptable) |  |
| 1.3(h) | Date |  |

**Part 2: Exclusion Grounds**

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

|  |  |  |
| --- | --- | --- |
| Section 2 | Grounds for mandatory exclusion | |
| Question number | Question | Response |
| 2.1(a) | **Regulations 57(1) and (2)**  The detailed grounds for mandatory exclusion of an organisation are set out on this [web page](https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/551130/List_of_Mandatory_and_Discretionary_Exclusions.pdf), which should be referred to before completing these questions.  Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below and listed on the [webpage](https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/551130/List_of_Mandatory_and_Discretionary_Exclusions.pdf). | |
|  | Participation in a criminal organisation. | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
|  | Corruption. | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
|  | Fraud. | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
|  | Terrorist offences or offences linked to terrorist activities | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
|  | Money laundering or terrorist financing | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
|  | Child labour and other forms of trafficking in human beings | Yes ☐  No ☐  If Yes please provide details at 2.1(b) |
| 2.1(b) | If you have answered yes to question 2.1(a), please provide further details.  Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction,  Identity of who has been convicted  If the relevant documentation is available electronically please provide the web address, issuing authority, precise reference of the documents. |  |
| 2.2 | If you have answered Yes to any of the points above have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion ? (Self Cleaning) | Yes ☐  No ☐ |
| 2.3(a) | **Regulation 57(3)**  Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | Yes ☐  No ☐ |
| 2.3(b) | If you have answered yes to question 2.3(a), please provide further details. Please also confirm you have paid, or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

Please Note: The authority reserves the right to use its discretion to exclude a potential supplier where it can demonstrate by any appropriate means that the potential supplier is in breach of its obligations relating to the non-payment of taxes or social security contributions.

|  |  |  |
| --- | --- | --- |
| Section 3 | Grounds for discretionary exclusion | |
|  | Question | Response |
| 3.1 | **Regulation 57 (8)**  The detailed grounds for discretionary exclusion of an organisation are set out on this [web page](https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/551130/List_of_Mandatory_and_Discretionary_Exclusions.pdf), which should be referred to before completing these questions.  Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation. | |
| 3.1(a) | Breach of environmental obligations? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1 (b) | Breach of social obligations? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1 (c) | Breach of labour law obligations? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(d) | Bankrupt or is the subject of insolvency or winding-up proceedings, where the organisation’s assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(e) | Guilty of grave professional misconduct? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(f) | Entered into agreements with other economic operators aimed at distorting competition? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(g) | Aware of any conflict of interest within the meaning of regulation 24 due to the participation in the procurement procedure? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(h) | Been involved in the preparation of the procurement procedure? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(i) | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? | Yes ☐  No ☐  If yes please provide details at 3.2 |
| 3.1(j)  3.1(j) - (i)  3.1(j) - (ii)  3.1(j) –(iii)  3.1(j)-(iv) | Please answer the following statements  The organisation is guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria.  The organisation has withheld such information.  The organisation is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015.  The organisation has influenced the decision-making process of the contracting authority to obtain confidential information that may confer upon the organisation undue advantages in the procurement procedure, or to negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award. | Yes ☐  No ☐  If Yes please provide details at 3.2  Yes ☐  No ☐  If Yes please provide details at 3.2  Yes ☐  No ☐  If Yes please provide details at 3.2  Yes ☐  No ☐  If Yes please provide details at 3.2 |

|  |  |  |
| --- | --- | --- |
| 3.2 | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self Cleaning) |  |

**Part 3: Selection Questions**[[6]](#footnote-7)

|  |  |  |  |
| --- | --- | --- | --- |
| **Section 4** | **Economic and Financial Standing** | | |
|  | Question | Response | |
| **4.1** | Are you able to provide a copy of your audited accounts for the last two years, if requested?  If no, can you provide **one** of the following: answer with Y/N in the relevant box. | | Yes ☐  No ☐ |
| (a) A statement of the turnover, Profit and Loss Account/Income Statement, Balance Sheet/Statement of Financial Position and Statement of Cash Flow for the most recent year of trading for this organisation. | | Yes ☐  No ☐ |
| (b) A statement of the cash flow forecast for the current year and a bank letter outlining the current cash and credit position. | | Yes ☐  No ☐ |
|  | (c) Alternative means of demonstrating financial status if any of the above are not available (e.g. forecast of turnover for the current year and a statement of funding provided by the owners and/or the bank, charity accruals accounts or an alternative means of demonstrating financial status). | | Yes ☐  No ☐ |
| **4.2** | Where we have specified a minimum level of economic and financial standing and/ or a minimum financial threshold within the evaluation criteria for this procurement, please self-certify by answering ‘Yes’ or ‘No’ that you meet the requirements set out. | | Yes ☐  No ☐ |

|  |  |  |
| --- | --- | --- |
| **Section 5** | **If you have indicated in the Selection Questionnaire question 1.2 that you are part of a wider group, please provide further details below:** | |
| **Name of organisation** | |  |
| **Relationship to the Supplier completing these questions** | |  |

|  |  |  |
| --- | --- | --- |
| **5.1** | Are you able to provide parent company accounts if requested to at a later stage? | Yes ☐  No ☐ |
| **5.2** | If yes, would the parent company be willing to provide a guarantee if necessary? | Yes ☐  No ☐ |
| **5.3** | If no, would you be able to obtain a guarantee elsewhere (e.g. from a bank)? | Yes ☐  No ☐ |

|  |  |
| --- | --- |
| **Section 6** | **Technical and Professional Ability** |
| **6.1** | **Relevant experience and contract examples**  Please provide details of up to three contracts, in any combination from either the public or private sector; voluntary, charity or social enterprise (VCSE) that are relevant to our requirement. VCSEs may include samples of grant-funded work. Contracts for supplies or services should have been performed during the past three years. Works contracts may be from the past five years.  The named contact provided should be able to provide written evidence to confirm the accuracy of the information provided below.  Consortia bids should provide relevant examples of where the consortium has delivered similar requirements. If this is not possible (e.g. the consortium is newly formed or a Special Purpose Vehicle is to be created for this contract) then three separate examples should be provided between the principal member(s) of the proposed consortium or Special Purpose Vehicle (three examples are not required from each member).  Where the Supplier is a Special Purpose Vehicle, or a managing agent not intending to be the main provider of the supplies or services, the information requested should be provided in respect of the main intended provider(s) or sub-contractor(s) who will deliver the contract.  If you cannot provide examples see question 6.3 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Contract 1** | **Contract 2** | **Contract 3** |
| **Name of customer organisation** |  |  |  |
| **Point of contact in the organisation** |  |  |  |
| **Position in the organisation** |  |  |  |
| **E-mail address** |  |  |  |
| **Description of contract** |  |  |  |
| **Contract Start date** |  |  |  |
| **Contract completion date** |  |  |  |
| **Estimated contract value** |  |  |  |

|  |  |
| --- | --- |
| **6.2** | Where you intend to sub-contract a proportion of the contract, please demonstrate how you have previously maintained healthy supply chains with your sub-contractor(s)  Evidence should include, but is not limited to, details of your supply chain management tracking systems to ensure performance of the contract and including prompt payment or membership of the UK Prompt Payment Code (or equivalent schemes in other countries) |
|  |  |

|  |  |
| --- | --- |
| **6.3** | If you cannot provide at least one example for questions 6.1, in no more than 500 words please provide an explanation for this e.g. your organisation is a new start-up or you have provided services in the past but not under a contract. |
|  |  |

|  |  |  |
| --- | --- | --- |
| **Section 7** | **Modern Slavery Act 2015:** **Requirements under Modern Slavery Act 2015[[7]](#footnote-8)** | |
| **7.1** | Are you a relevant commercial organisation as defined by section 54 ("Transparency in supply chains etc.") of the Modern Slavery Act 2015 ("the Act")? | Yes ☐  N/A ☐ |
| **7.2** | If you have answered yes to question 1 are you compliant with the annual reporting requirements contained within Section 54 of the Act 2015? | Yes ☐  Please provide relevant the url …  No ☐  Please provide an explanation |

|  |  |  |
| --- | --- | --- |
| **Section 8** | **The General Data Protection Regulation (GDPR)[[8]](#footnote-9)** | |
| **8.1** | Compliance with the GDPR is a mandatory requirement for all contracts or agreements that involve the transfer and processing of personal data from 25th May 2018. Will your organisation be compliant with the GDPR and all Data Protection Legislation (as defined in the terms and conditions applying to this Invitation to Tender) in regards to the processing required under this contract by the time of contract award?  Contractors are also required to complete Declaration 5: The General Data Protection Regulation Assurance Questionnaire for Contractors, to evidence the extent of readiness. The Authority may ask the Contractor to provide evidence to support the position stated in the questionnaire. The Authority may require the successful Contractor to increase their preparedness where the Authority is not satisfied that the Contractor will be in a position to meet its obligations under the terms and conditions. If the Contractor fails to satisfy the Authority that it will be in a position to meet its obligations under the terms and conditions in the event that the Contractor is successful, the Authority reserves the right to exclude the bidder from this procurement. | Yes ☐  No ☐ |

**9. Additional Questions**

Suppliers who self-certify that they meet the requirements to these additional questions will be required to provide evidence of this if they are successful at contract award stage.

|  |  |
| --- | --- |
| **Section 9** | **Additional Questions** |
| **9.1** | **Insurance** |
| a. | Please self-certify whether you already have, or can commit to obtain, prior to the commencement of the contract, the levels of insurance cover indicated below:  Y/N  Employer’s (Compulsory) Liability Insurance = £x  Public Liability Insurance = £x Professional Indemnity Insurance = £x  Product Liability Insurance = £x  \*It is a legal requirement that all companies hold Employer’s (Compulsory) Liability Insurance of £5 million as a minimum. Please note this requirement is not applicable to Sole Traders. |

|  |  |  |
| --- | --- | --- |
| **9.2** | **Skills and Apprentices[[9]](#footnote-10) – (please refer to supplier selection guidance)** | |
| **a.** | Public procurement of contracts with a full life value of £10 million and above and duration of 12 months and above should be used to support skills development and delivery of the apprenticeship commitment. This policy is set out in detail in Procurement Policy Note 14/15.Please confirm if you will be supporting apprenticeships and skills development through this contract. | Yes ☐  No ☐ |
| **b.** | If yes, can you provide at a later stage documentary evidence to support your commitment to developing and investing in skills, development and apprenticeships to build a more skilled and productive workforce and reducing the risks of supply constraints and increasing labour cost inflation? | Yes ☐  No ☐ |
| **c.** | Do you have a process in place to ensure that your supply chain supports skills, development and apprenticeships in line with PPN 14/15 (see guidance) and can provide evidence if requested? | Yes ☐  No ☐ |

|  |  |
| --- | --- |
| **9.3** | **Steel[[10]](#footnote-11) – (please refer to supplier selection guidance)** |
| **a.** | Please describe the supply chain management systems, policies, standards and procedures you currently have in place to ensure robust supply chain management |
|  | |
| **b.** | Please provide details of previous similar projects where you have demonstrated a high level of competency and effectiveness in managing of all supply chain members involved in steel supply or production so that there was a sustainable and safe supply of steel. |
|  | |
| **c.** | Please provide all the relevant details of previous breaches of health and safety legislation in the last 5 years, applicable to the country in which you operate, on comparable projects, for both:  (i) Your company  (ii) All your supply chain members involved in the production or supply of steel. |

|  |  |  |
| --- | --- | --- |
| **9.4** | **Suppliers’ Past Performance[[11]](#footnote-12) - (please refer to supplier selection guidance - this question should only be included by central government contracting authorities)** | |
| **a.** | Can you supply a list of your relevant principal contracts for goods and/or services provided in the last three years? | Yes ☐  No ☐ |
| **b.** | On request can you provide a certificate from those customers on the list? | Yes ☐  No ☐ |
| **c.** | If you cannot obtain a certificate from a customer can you explain the reasons why? | Yes ☐  No ☐ |
| **d.** | If the certificate states that goods and/or services supplied were not satisfactory are you able to supply information which shows why this will not recur in this contract if you are awarded it? | Yes ☐  No ☐ |
| **e.** | Can you supply the information in questions a. to d. above for any sub-contractors [or consortium members] who you are relying upon to perform this contract? | Yes ☐  No ☐ |

# Declaration 5: The General Data Protection Regulation Assurance Questionnaire for Contractors

****

# 

**Annex A: Pricing Schedule**

Please provide prices for the delivery of courses in parts A-E. The pricing evaluation will be based on A+B only.

**Part A – Staff/project team charges – training content development and pilot delivery and any resulting content updates**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **\*Grade/level of staff** | **Daily rate**  **(ex VAT)** | **No. days offered over course of contract** | **Tasks to be undertaken on this project** | **Total price offered per staff member** |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
| **Any non-staff charges** | | |  | £ |
| **Sub-total** | | |  | **£** |

[\*Suppliers should also include sub-contractors]

**Part B – Staff/project team charges – further 8 courses delivered following pilot**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **\*Grade/level of staff** | **Daily rate**  **(ex VAT)** | **No. days offered over course of contract** | **Tasks to be undertaken on this project** | **Total price offered per staff member** |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
| **Any non-staff charges** | | |  | £ |
| **Sub-total** | | |  | **£** |

[\*Suppliers should also include sub-contractors]

**Part C – Staff/project team charges – further 4 courses delivered following pilot**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **\*Grade/level of staff** | **Daily rate**  **(ex VAT)** | **No. days offered over course of contract** | **Tasks to be undertaken on this project** | **Total price offered per staff member** |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
| **Any non-staff charges** | | |  | £ |
| **Sub-total** | | |  | **£** |

[\*Suppliers should also include sub-contractors]

**Part D – Staff/project team charges – per additional course following pilot**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **\*Grade/level of staff** | **Daily rate**  **(ex VAT)** | **No. days offered over course of contract** | **Tasks to be undertaken on this project** | **Total price offered per staff member** |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
| **Any non-staff charges** | | |  | £ |
| **Sub-total** | | |  | **£** |

[\*Suppliers should also include sub-contractors]

**Part E – Full price offered**

|  |  |
| --- | --- |
| **Sub-total (Part A + Part B)** | **£** |
| **VAT** | **£** |
| **TOTAL (Sub-total + VAT)** | **£** |

**Annex B: Code of Practice for Research**

**CODE OF PRACTICE FOR RESEARCH**

***Issued by the Department for Business, Energy & Industrial Strategy***

The Department has developed this Code of Practice from the Joint Code of Practice issued by BBSRC; the Department for Environment, Food and Rural Affairs (Defra); the Food Standards Agency; and the Natural Environment Research Council (NERC) which lays out a framework for the proper conduct of research. It sets out the key aspects of the research process and the importance of making judgements on the appropriate precautions needed in every research activity.

The Code applies to all research funded by BEIS. It is intended to apply to all types of research, but the overriding principle is fitness of purpose and that all research must be conducted diligently by competent researchers and therefore the individual provisions must be interpreted with that in mind.

***PRINCIPLES BEHIND THE CODE OF PRACTICE***

Contractors and consortia funded by BEIS are expected to be committed to the quality of the research process in addition to quality of the evidence outputs

The Code of Practice has been created in order to assist contractors to conduct research of the highest quality and to encourage good conduct in research and help prevent misconduct.

Set out over 8 responsibilities the code of practice provides general principles and standards for good practice in research.

Most contractors will already have in place many of the measures set out in the

Code and its adoption should not require great effort.

***COMPLIANCE WITH THE CODE OF PRACTICE***

All organisations contracting to the Department (including those sub-contracting as part of a consortium) will be expected to commit to upholding these responsibilities and will be expected to indicate acceptance of the Code when submitting proposals to the Department.

Contractors are encouraged to discuss with BEIS any clauses in the Code that they consider inappropriate or unnecessary in the context of the proposed research project. The Code, and records of the discussions if held, will become part of the Terms and Conditions under which the research is funded.

Additionally, BEIS may conduct (or request from the Contractor as appropriate) a formal risk assessment on the project to identify where additional controls may be needed.

***MONITORING OF COMPLIANCE WITH THE CODE OF PRACTICE***

Monitoring of compliance with the Code is necessary to ensure:

* Policies and managed processes exist to support compliance with the Code
* That these are being applied in practice.

In the short term, BEIS can require contractors to conduct planned internal audits although BEIS reserve the right to obtain evidence that a funded project is carried out to the required standard. BEIS may also conduct an audit of a Contractor’s research system if deemed necessary.

In the longer term it is expected that most research organisations will assure the quality of their research processes by means of a formal system that is audited by an impartial and competent third party against an appropriate internationally recognised standard that is fit for purpose.

A recommended checklist for researchers can be found on the UK Research Integrity Office (UKRIO) website at http://www.ukrio.org/what-we-do/code-of-practice-for-research

***SPECIFIC REQUIREMENTS IN THE CODE OF PRACTICE***

***1. Responsibilities***

All organisations contracting to the Department (including those sub-contracting as part of a consortium will be responsible for the overall quality of research they conducted. Managers, group leaders and supervisors have a responsibility to ensure a climate of good practice in the research teams, including a commitment to the development of scientific and technical skills.

The Principal Investigator or Project Leader is responsible for all the work conducted in the project including that of any subcontractors. All staff and students must have defined responsibilities in relation to the project and be aware of these responsibilities.

***2. Competence***

All personnel associated with the project must be competent to perform the technical, scientific and support tasks required of them. Personnel undergoing training must be supervised at a level such that the quality of the results is not compromised by the inexperience of the researcher.

***3. Project planning***

An appropriate level of risk assessment must be conducted to demonstrate awareness of the key factors that will influence the success of the project and the ability to meet its objectives. There must be a written project plan showing that these factors (including research design, statistical methods and others) have been addressed. Projects must be ethical and project plans must be agreed in collaboration with BEIS, taking account of the requirements of ethical committees[[12]](#footnote-13) or the terms of project licences, if relevant.

Significant amendments to the plan or milestones must be recorded and approved by BEIS if applicable.

***4. Quality Control***

The organisation must have planned processes in place to assure the quality of the research undertaken by its staff Projects must be subjected to formal reviews of an appropriate frequency. Final and interim outputs must always be accompanied by a statement of what quality control has been undertaken.

The authorisation of outputs and publications shall be as agreed by BEIS, and subject to senior approval in BEIS, where appropriate. Errors identified after publication must be notified to BEIS and agreed corrective action initiated.

***5. Handling of samples and materials***

All samples and other experimental materials must be labelled (clearly, accurately, uniquely and durably), and retained for a period to be agreed by BEIS. The storage and handling of the samples, materials and data must be as specified in the project plan (or proposal), and must be appropriate to their nature. If the storage conditions are critical, they must be monitored and recorded.

***6. Documentation of procedures and methods***

All the procedures and methods used in a research project must be documented, at least in the personal records of the researcher. This includes analytical and statistical procedures and the generation of a clear audit trial linking secondary processed information to primary data.

There must be a procedure for validation of research methods as fit for purpose, and modifications must be trackable through each stage of development of the method.

***7. Research/work records***

All records must be of sufficient quality to present a complete picture of the work performed, enabling it to be repeated if necessary.

The project leader is accountable for the validity of the wok and responsible for ensuring that regular reviews of the records of each researcher are conducted[[13]](#footnote-14)

The location of all project records, including critical data, must be recorded. They must be retained in a form that ensures their integrity and security, and prevents unauthorised modification, for a period to be agreed by BEIS

A recommended checklist for researchers can be found on the UK Research Integrity Office (UKRIO) website at http://www.ukrio.org/what-we-do/code-of-practice-for-research

**Annex C**

**Mandatory Exclusion Grounds**

**Public Contract Regulations 2015 R57(1), (2) and (3)**

**Public Contract Directives 2014/24/EU Article 57(1)**

**Participation in a criminal organisation**

Participation offence as defined by section 45 of the Serious Crime Act 2015

Conspiracy within the meaning of

* section 1 or 1A of the Criminal Law Act 1977 or
* article 9 or 9A of the Criminal Attempts and Conspiracy (Northern Ireland) Order 1983

where that conspiracy relates to participation in a criminal organisation as defined in Article 2 of Council Framework Decision 2008/841/JHA on the fight against organised crime;

**Corruption**

Corruption within the meaning of section 1(2) of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906;

The common law offence of bribery;

Bribery within the meaning of sections 1, 2 or 6 of the Bribery Act 2010, or section 113 of the Representation of the People Act 1983;

**Fraud**

Any of the following offences, where the offence relates to fraud affecting the European Communities’ financial interests as defined by Article 1 of the convention on the protection of the financial interests of the European Communities:

* the common law offence of cheating the Revenue;
* the common law offence of conspiracy to defraud;
* fraud or theft within the meaning of the Theft Act 1968, the Theft Act (Northern Ireland) 1969, the Theft Act 1978 or the Theft (Northern Ireland) Order 1978;
* fraudulent trading within the meaning of section 458 of the Companies Act 1985, article 451 of the Companies (Northern Ireland) Order 1986 or section 993 of the Companies Act 2006;
* fraudulent evasion within the meaning of section 170 of the Customs and Excise Management Act 1979 or section 72 of the Value Added Tax Act 1994;
* an offence in connection with taxation in the European Union within the meaning of section 71 of the Criminal Justice Act 1993;
* destroying, defacing or concealing of documents or procuring the execution of a valuable security within the meaning of section 20 of the Theft Act 1968 or section 19 of the Theft Act (Northern Ireland) 1969;
* fraud within the meaning of section 2, 3 or 4 of the Fraud Act 2006;
* the possession of articles for use in frauds within the meaning of section 6 of the Fraud Act 2006, or the making, adapting, supplying or offering to supply articles for use in frauds within the meaning of section 7 of that Act;

**Terrorist offences or offences linked to terrorist activities**

Any offence:

* listed in section 41 of the Counter Terrorism Act 2008;
* listed in schedule 2 to that Act where the court has determined that there is a terrorist connection;
* under sections 44 to 46 of the Serious Crime Act 2007 which relates to an offence covered by the previous two points;

**Money laundering or terrorist financing**

Money laundering within the meaning of sections 340(11) and 415 of the Proceeds of Crime Act 2002

An offence in connection with the proceeds of criminal conduct within the meaning of section 93A, 93B or 93C of the Criminal Justice Act 1988 or article 45, 46 or 47 of the Proceeds of Crime (Northern Ireland) Order 1996

**Child labour and other forms of trafficking human beings**

An offence under section 4 of the Asylum and Immigration (Treatment of Claimants etc.) Act 2004;

An offence under section 59A of the Sexual Offences Act 2003

An offence under section 71 of the Coroners and Justice Act 2009;

An offence in connection with the proceeds of drug trafficking within the meaning of section 49, 50 or 51 of the Drug Trafficking Act 1994

An offence under section 2 or section 4 of the Modern Slavery Act 2015

**Non-payment of tax and social security contributions**

Breach of obligations relating to the payment of taxes or social security contributions that has been established by a judicial or administrative decision.

Where any tax returns submitted on or after 1 October 2012 have been found to be incorrect as a result of:

* HMRC successfully challenging the potential supplier under the General Anti – Abuse Rule (GAAR) or the “Halifax” abuse principle; or
* a tax authority in a jurisdiction in which the potential supplier is established successfully challenging it under any tax rules or legislation that have an effect equivalent or similar to the GAAR or “Halifax” abuse principle;
* a failure to notify, or failure of an avoidance scheme which the supplier is or was involved in, under the Disclosure of Tax Avoidance Scheme rules (DOTAS) or any equivalent or similar regime in a jurisdiction in which the supplier is established

**Other offences**

Any other offence within the meaning of Article 57(1) of the Directive as defined by the law of any jurisdiction outside England, Wales and Northern Ireland

Any other offence within the meaning of Article 57(1) of the Directive created after 26th February 2015 in England, Wales or Northern Ireland

**Discretionary exclusions**

**Obligations in the field of environment, social and labour law.**

Where an organisation has violated applicable obligations in the fields of environmental, social and labour law established by EU law, national law, collective agreements or by the international environmental, social and labour law provisions listed in Annex X to the Directive (see copy below) as amended from time to time; including the following:-

* Where the organisation or any of its Directors or Executive Officers has been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years.
* In the last three years, where the organisation has had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds of alleged unlawful discrimination.
* In the last three years, where any finding of unlawful discrimination has been made against the organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or incomparable proceedings in any jurisdiction other than the UK).
* Where the organisation has been in breach of section 15 of the Immigration, Asylum, and Nationality Act 2006;
* Where the organisation has a conviction under section 21 of the Immigration, Asylum, and Nationality Act 2006;
* Where the organisation has been in breach of the National Minimum Wage Act 1998.

**Bankruptcy, insolvency**

Bankrupt or is the subject of insolvency or winding-up proceedings, where the organisation’s assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State;

**Grave professional misconduct**

Guilty of grave professional misconduct

**Distortion of competition**

Entered into agreements with other economic operators aimed at distorting competition

**Conflict of interest**

Aware of any conflict of interest within the meaning of regulation 24 due to the participation in the procurement procedure

**Been involved in the preparation of the procurement procedure.**

**Prior performance issues**

Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions.

**Misrepresentation and undue influence**

The organisation has influenced the decision-making process of the contracting authority to obtain confidential information that may confer upon the organisation undue advantages in the procurement procedure, or to negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award.

Additional exclusion grounds

**Breach of obligations relating to the payment of taxes or social security contributions.**

**ANNEX X Extract from Public Procurement Directive 2014/24/EU**

**LIST OF INTERNATIONAL SOCIAL AND ENVIRONMENTAL CONVENTIONS REFERRED TO IN ARTICLE 18(2) —**

* ILO Convention 87 on Freedom of Association and the Protection of the Right to Organise;
* ILO Convention 98 on the Right to Organise and Collective Bargaining;
* ILO Convention 29 on Forced Labour;
* ILO Convention 105 on the Abolition of Forced Labour;
* ILO Convention 138 on Minimum Age;
* ILO Convention 111 on Discrimination (Employment and Occupation);
* ILO Convention 100 on Equal Remuneration;
* ILO Convention 182 on Worst Forms of Child Labour;
* Vienna Convention for the protection of the Ozone Layer and its Montreal Protocol on substances that deplete the Ozone Layer;
* Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal (Basel Convention);
* Stockholm Convention on Persistent Organic Pollutants (Stockholm POPs Convention)
* Convention on the Prior Informed Consent Procedure for Certain Hazardous Chemicals and Pesticides in International Trade (UNEP/FAO) (The PIC Convention) Rotterdam, 10 September 1998, and its 3 regional Protocols.

**Consequences of misrepresentation**

A serious misrepresentation which induces a contracting authority to enter into a contract may have the following consequences for the signatory that made the misrepresentation:-

* The potential supplier may be excluded from bidding for contracts for three years, under regulation 57(8)(h)(i) of the PCR 2015;
* The contracting authority may sue the supplier for damages and may rescind the contract under the Misrepresentation Act 1967.
* If fraud, or fraudulent intent, can be proved, the potential supplier or the responsible officers of the potential supplier may be prosecuted and convicted of the offence of fraud by false representation under s.2 of the Fraud Act 2006, which can carry a sentence of up to 10 years or a fine (or both).
* If there is a conviction, then the company must be excluded from procurement for five years under reg. 57(1) of the PCR (subject to self-cleaning).

1. For the list of exclusion please see https://www.gov.uk/government/uploads/system/uploads/attachment\_data/file/551130/List\_of\_Mandatory\_and\_Discretionary\_Exclusions.pdf [↑](#footnote-ref-2)
2. See PCR 2015 regulations 71 (8)-(9) [↑](#footnote-ref-3)
3. See EU definition of SME: http://ec.europa.eu/enterprise/policies/sme/facts-figures-analysis/sme-definition/ [↑](#footnote-ref-4)
4. UK companies, Societates European (SEs) and limited liability partnerships (LLPs) will be required to identify and record the people who own or control their company. Companies, SEs and LLPs will need to keep a PSC register, and must file the PSC information with the central public register at Companies House. [See PSC guidance](https://www.gov.uk/government/publications/guidance-to-the-people-with-significant-control-requirements-for-companies-and-limited-liability-partnerships). [↑](#footnote-ref-5)
5. Central Government contracting authorities should use this information to have the PSC information for the preferred supplier checked before award. [↑](#footnote-ref-6)
6. [See Action Note 8/16 Updated Standard Selection Questionnaire](https://www.gov.uk/government/collections/procurement-policy-notes) [↑](#footnote-ref-7)
7. [Procurement Policy Note 9/16 Modern Slavery Act 2015](https://www.gov.uk/government/collections/procurement-policy-notes) [↑](#footnote-ref-8)
8. [Procurement Policy Note 02/18 Changes to Data Protection Legislation & General Data Protection Regulation](https://www.gov.uk/government/publications/procurement-policy-note-0218-changes-to-data-protection-legislation-general-data-protection-regulation) [↑](#footnote-ref-9)
9. [Procurement Policy Note 14/15– Supporting Apprenticeships and Skills Through Public Procurement](https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/456805/27_08_15_Skills__Apprenticeships_PPN_vfinal.pdf) [↑](#footnote-ref-10)
10. [Procurement Policy Note 16/15– Procuring steel in major projects](https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/473545/PPN_16-15_Procuring_steel_in_major_projects.pdf) [↑](#footnote-ref-11)
11. [Procurement Policy Note 04/15 Taking Account of Suppliers’ Past Performance](https://www.gov.uk/government/publications/procurement-policy-note-0415-taking-account-of-suppliers-past-performance) [↑](#footnote-ref-12)
12. Please note ethical approval does not remove the responsibility of the individual for ethical behaviour. [↑](#footnote-ref-13)
13. Please note that this also applies to projects being undertaken by consortia. [↑](#footnote-ref-14)