# Annex A

| Title of Project | Ocean Country Partnership Programme: Sri Lanka Necropsy training and capacity building to support conservation and management of protected, endangered and threatened mobile marine species in Sri Lanka |
| --- | --- |
| Date and Time for Return of Bids | Monday 6th January 2025 @ 14:00 (UK) |
| Contract Reference Number | C24-0604-1990 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO HANNAH LAWSON, JAMIE SMALL OR PROCUREMENT VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 00 44 1733 866987 |
| Proposed Start Date | Wednesday 15 January 2025 |
| Proposed End Date | Monday 31 March 2025 |

Ocean Country Partnership Programme: Sri Lanka

Necropsy training and capacity building to support conservation and management of protected, endangered and threatened mobile marine species in Sri Lanka.

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims	4

4.	Project Objectives	5

5.	Contractor Requirements	7

6.	Potential Follow-On Work	7

7.	Product Specification	7

8.	Timescale	8

9.	Health and Safety	8

10.	Project Management	8

11.	Instructions for Bid Submission	8

12.	Evaluation Criteria	9

13.	Payment	10

14.	Additional Requirements	11

18.  Procurement Timetable (which may be subject to change)	11

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC has a responsibility to protect the people we work with, and who work for us, and we will continuously strive to prevent bullying, harassment, exploitation and abuse and child abuse from happening.

JNCC takes a Gender Equality and Social Inclusion (GESI) approach across all elements of our work (under the OCPP) to address unequal power relations and inequalities, reduce disparities and ensure equal rights, responsibilities, opportunities and respect for all individuals. JNCC also takes all reasonable steps to safeguard the people we come into contact with (including staff and the communities in which programmes are delivered) from sexual exploitation, abuse and harassment (SEAH).  JNCC will work with the successful bidder to meet GESI and safeguarding expectations, including the collection of data to evaluate GESI under this project.

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

Through the OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution: supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood: supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity: supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

Many protected, endangered and threatened (PET) species in Sri Lanka perform ecologically important roles within the marine environment (e.g. birds, sharks, rays, marine mammals and marine turtles). As such, the presence and abundance of PET marine species are important indicators of marine ecosystem health. In addition to this, local coastal communities can benefit from the presence of PET species as important sources of income through sustainable ecotourism.

There is a need to increase awareness and address knowledge gaps related to the condition and distribution of these species in Sri Lanka, as well as to better understand the impact and nature of the threats to them. Necropsies of stranded PET marine species can provide significant information regarding the health of individual animals, the species and, in turn, the health of the marine ecosystem. For example, samples and data collected from stranded animals can provide information on marine pollution and implications on human health through the analysis of chemical contaminants.

By improving knowledge and understanding of Sri Lanka’s PET marine species, effective conservation and management measures may be developed, with benefits for the target species, local coastal communities and the wider marine environment.

## Project Aims

This contract aims to increase the knowledge, skills and capacity of government and university wildlife vets and veterinary students within Sri Lanka to confidently conduct necropsies of PET marine species (marine mammals, sea turtles and seabirds) through the delivery of a bespoke necropsy training programme.

Necropsy training will contribute to the conservation management of Sri Lanka’s PET marine species and support the development of standardised operating procedures for marine wildlife emergency response.

The outputs of this project include:

- The development of standard operating procedures for marine mammal, turtle and seabird strandings in Sri Lanka, including first response and necropsy.

- A multi-day in person necropsy training capacity building workshop for up to 30 vets and veterinary students based in Sri Lanka.

## Project Objectives

Work Package 1 Technical advice and recommendations for supporting Sri Lanka’s preparedness and response capabilities to PET marine species strandings

- Undertake a needs assessment to identify Sri Lanka’s current capacity to respond to stranding events, including training requirements to inform work package 2 and recommendations for key equipment and facility requirements to support necropsy from specimen collection through to analysis of collected samples. Compilation of a post-training report with recommendations for further training and capacity building in these topics based on your findings in country

- Development of Standard Operating Procedures for live marine mammal, turtle and seabird strandings in Sri Lanka and sampling/ necropsy methodologies for dead animals

- Facilitate networking opportunities for the Sri Lanka government and NGOs to build relationships with regional and international strandings response support networks.

Work Package 2 Basic necropsy training workshop for approx. 30 veterinary practitioners and students in Sri Lanka.

- A needs assessment should be undertaken to shape the content of the workshop and ensure it is at an appropriate level for participants. We encourage bidders to use their experience to suggest how best to design and deliver this training over a suggested period of 2-3 weeks in country. This could be a mixture of theoretical sessions and practical sessions and a mix of both remote and in person is possible (e.g., remote pre-training sessions, or higher numbers of students could dial into/ observe certain sections).

- The following content requirements should be considered:

  - Basic biology and physiology of marine mammals, turtles and seabirds found in Sri Lanka

  - Major threats to these species in Sri Lankan waters

  - Response to strandings

    - Key steps involved in responding to marine mammal, turtle and seabird strandings, sharing of key response procedures and SOPs of relevance and inclusion of responder health and safety principles

    - Euthanasia of PET species including principles, techniques and SOPs (noting there are legal considerations for this process in the country which Government officials can cover)

    - Logistical considerations – equipment, resources, transportation, and disposal

- Collection and storage of tissue and blood data samples

    - Outline the purpose and importance of data collection during stranding response efforts

    - Explain the necessary data fields and protocols for recording stranding information

    - Address health and safety considerations, handling, storage, and transportation of biological samples for further analysis

    - Describe the tiered sampling approach – basic information, photos and measurements; basic sample collection (skin, feather, blubber, muscle), full necropsy.

- Practical exercise to demonstrate how to collect basic data and samples from dead marine mammals, turtles and seabirds.

- Practical exercise to ascertain possible cause of death of dead marine mammals, turtles and seabirds including measurements, photographs, and biological samples.

  - Please note this is subject to available specimens, please provide an alternative approach if carcasses aren’t available.

- Necropsy report writing and post collection analysis considerations in the context of Sri Lanka e.g., availability of diagnostic laboratories.

- Inclusion of theoretical training/ discussion on how such data and information can feed into understanding of wider ecosystem and human health.

- Training materials to support the content of the workshop, which can be referred to by training participants into the future.

- Include estimated costs related to the delivery of the workshop in your bid e.g., venue hire, travel and subsistence for delivery team and training participants, potential need for translation services (the workshop can be delivered in English but translation support may be required to provide explanations on technical aspects) etc.

- Include exact specifications of what PPE, equipment and associated ancillaries you require to be in country to deliver this training. The training can take place within a university in central Sri Lanka (Kandy) which has access to dial-in technology, large lecture halls and a post-mortem/ dissection room. Further details on the training facilities can be provided to the successful bidder.

- Subject to funds there is potential to also include advanced necropsy training in this programme. Please outline an approach for advanced training, including content and any additional requirements to support delivery, and a separate quote for this element.

## Contractor Requirements

The successful contractor should:

- Have demonstrable expert knowledge of marine mammals, turtles and seabirds, ideally in Sri Lankan waters, including species ID and taxonomy.

- Be experienced in marine mobile species monitoring including strandings monitoring design, data collection (both directly and via citizen science), analysis and quality assurance procedures.

- Have extensive experience in undertaking necropsy for marine mammals, turtles and seabirds.

- Be a confident communicator with experience of developing and delivering clear and accessible training programmes focused on the biology/physiology, monitoring and necropsy of marine mammals, turtles and seabirds.

- Have experience of successfully collaborating with Governments, NGOs, Universities and local communities.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 15th January 2025 |
| Proposed workplan | 24th January 2025 |
| Completed rapid, remote needs assessment to inform training content | 10th February 2025 |
| Draft workshop itinerary, training materials and SOPs developed | 24th February 2025 |
| Final workshop materials developed | 5th March 2025 |
| Workshop logistics and associated risk assessments etc completed | 28th February 2025 |
| Necropsy training workshop delivered | Completed by 20th March 2025 |
| Final outputs | 31st March 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

General Duty of care: The organiser shall commit to exercise reasonable care and take necessary precautions to ensure the safety and well-being of attendees during the event (s) / Workshop (s).

Emergency Procedures: Outline the steps the organiser will take in the event of an emergency, including evacuation procedures, medical assistance, and communication protocols. This may include conducting risk assessments and providing necessary safety equipment and ensuring compliance with the relevant Health and Safety regulations.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Hannah Lawson

Email: Hannah.lawson@jncc.gov.uk

Telephone: +44 (0) 1224 083511

Name: Jamie Small

Email: Jamie.small@jncc.gov.uk

Telephone: +44 (0) 1733 259687

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract.

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective.

A detailed project plan (including a Gantt chart) and an estimate of time required to achieve each objective.

Details of the Project Team including their roles and experience.

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team.

  - Costs and time allocation should be clearly allocated to specific tasks under each work package within this contract/project, including all costs associated with workshop delivery (e.g., facility hire) and contractor’s travel and subsistence to undertake stakeholder workshops/stakeholder meetings. Note, if flights are required they should be economy or premium economy class only, with suitable justification for the use of premium economy.

  - Please refer to the contractors travel and subsistence rates document for all travel (these rates are analogous to the UK civil service rates).

  - If submitting a joint proposal, bidders should clearly outline the lead contractor on their bid.  Please ref to PS4a Instructions to Tenderers email submission, Group Bids (14) for more details.

  - The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates or equivalence which is the legal requirement in your jurisdiction;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 12.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation shall be undertaken by JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (40% of the total for the three assessment categories) |  |  |  |
| 1 | Clarity and effectiveness of proposal, particularly training programme outline | 15 |  |
| 2 | Understanding of the requirements, adequacy of outputs and effective plan for delivery by end of contract date | 15 |  |
| 3 | Identification and proposed solutions to potential risks/issues to the project which threaten success | 10 |  |
|  | Sub Total | 40 |  |
| 2. Details of Contractor (50% of the total for the three assessment categories) |  |  |  |
| 4 | Relevant expertise and experience of marine mammal, turtle and seabird species ID, taxonomy and necropsy | 20 |  |
| 5 | Experience developing and delivering accessible training workshops focused on necropsy techniques and strandings response protocols for marine mammals, sea turtles and seabirds | 20 |  |
| 6 | Evidence of existing relationships with regional and international strandings response networks, particularly networks in the Indian Ocean region. | 10 |  |
|  | Sub Total | 50 |  |
| 3. Cost (10% of the total for the three assessment categories) |  |  |  |
| 7 | Transparency and correctness of presentation | 5 |  |
| 8 | Fairness/reasonableness for the level of work and expertise required, including split of staff and allocated days of work | 5 |  |
|  | Sub Total | 10 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

Any communications or social media statements to be released by the successful bidder on this work must be signed off by the OCPP team first. Reports, presentations and documents must use our branding and logo to be discussed with the project team.

## 18.  Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 11 December 2024 |
| Last date for receipt of clarification questions | 17 December 2024 |
| JNCC Procurement Office Closed | 20 December 2024 – 2 January 2025 |
| Final submission date for bids | 6 January 2025 |
| Evaluation of bids | w/c 6 January 2025 |
| Post-tender negotiation/clarification and or presentation if required | w/e 10 January 2025 |
| Successful Bidder Notified & Contract award | w/c 13 January 2025 |
| Unsuccessful bidders notified | w/e 17 January 2025 |
| Start of project | 15 January 2025 |