Change Request Overview:

| Contract Title & Contract Reference: | Digital Debt Services Project (DDSP) – Legal Advice on Procurement of new IT system |
| --- | --- |
| Supplier Name & Registered No: | TLT LLP |
| Contract Change Title: | Date only extension from “30th November 2018” to “31st March 2020” |
| Change Request No: | 001 |
| Contract Change Implementation Date: | 1st December 2018 |

Details of Change:

DWP Customer Lead – Name and Position:

REDACTED, Senior Lawyer GLD

Summary of proposed contract change required:

Date only extension from 30th November 2018 to 31st March 2020 for TLT LLP to continue to provide support to DWP on the Digital Debt Services Project (DDSP).

Details of any changes or adjustments to charges resulting from this Contract change and confirmation of funding stream:

None, this is a date only extension.

Amended/New Contract Wording – must include details of cross referencing to original Contract Documents:

Clause 1.5 Expiry Date is amended from “30th November 2018” to “31st March 2020.”

Required delivery date, with rationale:

None, this is a date only extension.

In consideration of the rights and obligations created, granted and assumed by each party to the other party pursuant to this Change Authorisation Note, the parties have agreed to enter into this Change Authorisation Note.

The provisions of the Contract shall, save as amended in this Change Authorisation Note, continue in full force and effect, and shall be read and construed as one document with this Change Authorisation Note.

Change Authorisation:

| Signed on Behalf of the Supplier: |  |
| --- | --- |
| Signature: |  |
| Print Name: | REDACTED |
| Position: | PARTNER |
| Date: | 12/08/2019 |

| Signed on Behalf of the Contracting Authority: |  |
| --- | --- |
| Signature: |  |
| Print Name: | REDACTED |
| Position: | Commercial Practitioner |
| Date: | 13/08/2019 |