# Annex A

| Title of Project | Ocean Country Partnership Programme: Belize Belize Coastal Zone Management Authority and Institute (CZMAI) Spatial Data and Geographic Information System (GIS) Processing |
| --- | --- |
| Date and Time for Return of Bids | Thursday 11 July 2024 17:00 UK BST |
| Contract Reference Number | C24-0604-1902 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO HANNAH LAWSON, SARAH BLANCHARD, OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below:00 44 1733866988 |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +44 (0) 1733 866897 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +44 (0) 1733 866897 |
| Proposed Start Date | 19 July 2024 |
| Proposed End Date | 31 March 2025 |

Ocean Country Partnership Programme: Belize

Belize Coastal Zone Management Authority and Institute (CZMAI) Spatial Data and Geographic Information System (GIS) Processing

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aim	4

4.	Project Objectives: Detailed Tasks	4

5.	Contractor Requirements	6

6.	Potential Follow-On Work	6

7.	Product Specification	6

8.	Timescale	7

9.	Health and Safety	7

10.	Project Management	8

11.	Instructions for Bid Submission	8

12.	Evaluation Criteria	8

13.	Payment	10

14.	Additional Requirements	10

18.	Procurement Timetable (which may be subject to change)	10

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/.

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

Through OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution:- supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood: - supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity: - supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

JNCC, on behalf of the OCPP, is working in collaboration with the Government of Belize providing technical assistance focused on Marine Protected Areas (MPAs) and marine biodiversity.

This contract is being delivered on behalf of the Coastal Zone Management Authority and Institute (CZMAI) in Belize. CZMAI is the leading authority in the management and sustenance of Belize’s coastal resources. More information about CZMAI can be found here:
https://www.coastalzonebelize.org/.

## Project Aim

This contract focuses on three key aims.

1) The development of a Geospatial data Curation Guideline for CZMAI’s Coastal and Marine Data Centre.

2) Spatial data curation of historic, and recent spatial datasets hosted at CZMAI’s Coastal and Marine Data Centre.

3) Data Call Campaign for coastal and marine datasets to be used to support spatial planning.

4) Capacity development for CZMAI’s technical staff on data management including spatial and non-spatial data curation.

## Project Objectives: Detailed Tasks

The project objectives include:

- Develop a Geospatial data curation Guideline for CZMAI’s Coastal and Marine Data Centre on metadata development of CZMAI's spatial data, focusing on data from recent projects and data created by CZMAI.

  - The guidelines should be developed based on current practices and any recommended best practices for data curation.

  - Guidelines must include, but not limited to, technical procedures of geospatial data curation and procedures for data dissemination and publication.

  - The criteria for curation must include, but not limited to, system coordinates, and geographical projection, metadata, attribute table, topology errors, and statistical information.

  - Review the existing spatial metadata structure and current data storage system and provide recommendations.

- Spatial data curation of historic, and recent spatial datasets hosted at CZMAI’s Coastal and Marine Data Centre.

  - Using the guidelines, curate recent and historic coastal and marine spatial data collated by CZMAI.

  - The curation of data stored at CZMAI which include data from projects, hosted datasets, historic spatial data, and data from the Integrated Coastal Zone Management Plan (ICZMP),

  - The curation of spatial data being developed for the ICZMP and Belize’s Marine Spatial Plan - Belize Sustainable Ocean Plan (BSOP).

  - Use the processed and newly acquired data to create easy to understand spatial maps (especially for priority use areas and marine spatial data).

  - Update CZMAI’s Data Catalogue as needed.

- Data Call Campaign for coastal and marine datasets to be used to support spatial planning.

  - Develop templates to be used during a Data Call campaign for the collection of coastal and marine datasets.

    - Development of templates to be used by other organisations including Government of Belize, Universities, and Non-Governmental Organisations in Belize, to submit their spatial data to CZMAI.

    - Templates should be created in English and be available to translate to Spanish by JNCC or their sub-contractors.

  - Collaborate with in country partners to identify and collate historic data and/or recent data from the data call.

  - Curate data received from the Data Call campaign and upload into CZMAI’s spatial database and data catalogue.

- Training/Capacity development for CZMAI’s technical staff on spatial and non spatial data curation and data management.

  - Develop and implement training session(s) for CZMAI staff on the management and maintenance of data.

  - Development of training materials and implementation of training at a range of knowledge levels, to ensure staff can build expertise and capacity around spatial data. Including spatial data management, meta data creation, processing and quality assurance. Training materials should be appropriate for audiences with different skill levels.

## Contractor Requirements

The successful contractor should:

- Have knowledge and evidence of experience in data management, including data processing and management of large datasets, quality control, uploading and manipulating data on spatial data platforms.

- Have a good understanding of Belize’s marine environment, ideally with previous experience working in Belize.

- Have experience of successfully collaborating with a range of stakeholders, such as Governments, NGOs, and Universities.

- Have demonstrated experience with ESRI’s ArcGis Pro Software, ArcOnline, or similar applications, ideally with experience using GIS for natural resource management or marine resources management.

- Have experience in providing training using various methods, such as the development of templates/ materials and executing training in workshop settings.

- Be willing to travel to Belize as required and able to work from the CZMAI office 2 – 3 times a week, where appropriate.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/2026.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 19 July 2024 |
| Proposed workplan provided by contractor | 31 July 2024 |
| Objective 1: Copy of Guidelines (Both raw document and finalized PDF) | 02 September 2024 |
| Objective 2: Data Processing Progress Report 1 with accompanying files (Guidelines), copy of Catalogue and accompanying datasets curated, and maps created | 04 November 2024 |
| Objective 2: Data Processing Progress Report 2 (Data call & Data curation) with accompanying files (data curated, data call needs) | 06 January 2025 |
| Objective 3: Templates and materials for new data call drafted, including data sharing protocol. | 27 January 2025 |
| Objective 3: New data call completed | 10 February 2025 |
| Objective 2 & 3: Data Processing Progress Report 3 (Data call & Data Curation) with accompanying files (At least 4 datasets received from external organizations, data curated) | 24 February 2025 |
| Objective 3: Additional processing and maps created from the data curated. | 03 March 2025 |
| Objective 4: Training Report. Copy of Training Material developed (Documents, photos, meeting minutes etc) | 24 March 2025 |
| Objective 4: Developed and delivery of training | 31 March 2025 |
| Final Report | 31 March 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Hannah Lawson

Email:  Hannah.Lawson@jncc.gov.uk

Telephone: +44 (0) 1224 083511

OR

Name: Sarah Blanchard

Email:  Sarah.Blanchard@jncc.gov.uk

Telephone: +44 (0) 1733 866925

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract.

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective.

A project plan and an estimate of time needed to achieve each objective.

Details of the Project Team including their roles and experience

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project.

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy.

  - Copies of current public and employer liability insurance certificates or equivalence which is the legal requirement in your jurisdiction.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

Bids will be evaluated using the criteria in the table below. Each received bid will be evaluated by both JNCC and CZMAI to assess the application against the criteria and score the information provided accordingly. By submitting a bid for this contract, you agree to the documents submitted for this contract to be provided to CZMAI, as JNCC’s project partner, to complete the evaluation process.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (30% of the total for the three assessment categories) |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 10 |  |
| 2 | Understanding of the requirements and adequacy of outputs | 10 |  |
| 3 | Soundness and logicality of methods | 5 |  |
| 4 | Identification and proposed solutions to potential risks/issues which threaten success | 5 |  |
|  | Sub Total | 30 |  |
| 2. Details of Contractor (55% of the total for the three assessment categories) |  |  |  |
| 5 | Experience and knowledge of data management including data processing, management and quality control | 15 |  |
| 6 | Good understanding of Belize’s coastal and marine environment | 15 |  |
| 7 | Experience with ESRI’s ArcGis Pro Software, ArcOnline and data management for natural resource management or marine resources management | 20 |  |
| 8 | Ability to work in Belize | 5 |  |
|  | Sub Total | 55 |  |
| 3. Cost (15% of the total for the three assessment categories) |  |  |  |
| 9 | Transparency and correctness of presentation | 10 |  |
| 10 | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Sub Total | 15 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## 18.	Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 20 June 2024 |
| Last date for receipt of clarification questions | 4 July 2024 |
| Final submission date for bids | 11 July 2024 |