[image: image1.jpg]


The Big Lottery Fund is a Non Departmental Public Body and therefore subject to the
disclosure requirements of the Freedom of Information Act 2000
Invitation to Tender (ITT)

Reference BIG ref BIG 001-0621

1 December 2016
Dear Sir or Madam:

Invitation to Tender (ITT):
HELP THROUGH CRISIS – LEARNING,  SUPPORT AND EVALUATION CONTRACT 
Reference: BIG001-0621
You are invited by the Big Lottery Fund, to tender for the above referenced Contract. Our requirements are contained in this ITT document.
The Big Lottery Fund is seeking a Service Provider to capture learning, to enable implementation of learning and development of beneficiary voice and to provide a range of networking and support services to the grant holders of the Help Through Crisis programme. 
The Contract Terms and Conditions that you will be required to sign up to are available to view at our procurement webpage under this tender reference: BIG001-0621: http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm. 
The Preferred Bidder will not be permitted to enter into any negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Bidder being excluded from the tender process. In such circumstances the Fund reserves the right to invite the next highest scoring Bidder to enter into the Contract.
Kindly note the Big Lottery Fund offices will close on 23 December 2016 and reopen on 3rd January 2017 therefore there would be no responses to clarification questions issued over this period.
You must follow all the instructions set out in this Invitation to Tender when responding to it. The deadline for submission is 12.00 (Noon) on 8 February 2017.  Failure to provide all information required will result in rejection of the tender.

Yours faithfully,

Procurement Team
Big Lottery Fund
Email: Procurement@biglotteryfund.org.uk
CONTENTS:
SECTION ONE 
Instructions to Bidders

SECTION TWO
Scope of Work
SECTION THREE
Annex 1 - 
Response to Tender and Evaluation Criteria 

Annex 2 – 
Schedule of Charges 

Annex 3 -
Bidder’s Details 

Annex 4 - 
Form of Tender



Part I: Declaration


Annex 5-


Part I: Transparency Requirements



Part II Parent Company Guarantee (where appropriate)



Part III: Regulation 57 (1) Declaration 



Part IV: Regulation 57 (8) Declaration 

SECTION ONE

INSTRUCTIONS TO BIDDERS
1. General Information                                                                                    


1.1 This is an invitation only.  The Big Lottery Fund reserves the right to vary any or all parts of the information contained in the Invitation to Tender.

1.2 The Big Lottery Fund intends to accept the tender which scores the most marks against the criteria set out below.  The Big Lottery Fund at its sole discretion, reserves the right to accept or reject any tender.  The Big Lottery Fund does not bind itself to accept the lowest priced or any tender and shall not be liable for any costs incurred in the production of your submission.

1.3 The Big Lottery Fund reserves the right to change the timing or any other aspect of the procurement process or to cancel the procurement process at any stage or not to proceed with the procurement for any reason whatsoever without prior notice. Under no circumstances will the Big Lottery Fund or any of its advisers be liable for any costs or expenses incurred by Bidders and/or their members in this procurement.

1.4 The Big Lottery Fund reserves the right not to disclose information that it feels would put them at a commercial or unacceptable contractual disadvantage. 
1.5 Tenders, all documents and all correspondence relating to the tender must be written in English.
2. Tender Documents


2.1 seq level0 \h \r0 

seq level1 \h \r0 

seq level2 \h \r0 

seq level3 \h \r0 

seq level4 \h \r0 

seq level5 \h \r0 

seq level6 \h \r0 

seq level7 \h \r0 Tenders shall be submitted in accordance with the following instructions.

2.2 All pages of the tender shall be sequentially numbered (including any forms to be signed and returned). 

2.3 The bidder is expected to examine all of the instructions, forms, Contract and specifications that comprise the tender documents. Unless the bidder provides all of the information required the tender will be rejected. If you have any queries about the information that must be submitted then you must raise them prior to the tender deadline in accordance with 3 (clarification) below.

2.4 All information issued in connection with the Invitation to Tender remains the property of the Big Lottery Fund and are to be used solely for the purpose of tendering.

2.5 The Preferred Bidder will not be permitted to enter into any post tender negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Bidder being excluded from the tender process.  In such circumstances the Fund reserves the right to invite the next highest scoring bidder to enter into the Contract.
3. Clarification


3.1 If you require clarification with respect to the contents of this ITT or this ITT process, please email procurement@biglotteryfund.org.uk Questions or requests for clarification must be submitted prior to the closing date for the submission of questions. 
3.2 The Big Lottery Fund will publish questions and responses (without identifying the author of the question) save where the Big Lottery Fund considers the question and response to be commercially sensitive. The Big Lottery Fund will upload responses to clarification questions on the following site regularly and it is bidder’s responsibility to review it regularly: http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm 
3.3 Kindly note the Big Lottery Fund offices will close on 23 December 2016 and reopen on 3rd January 2017 therefore there would be no responses to clarification questions over this period. If you require clarifications prior to shut down endeavour to send your questions in by 21 Dec to give the Fund ample time to respond. All other questions will be picked up on 3rd January 2017.
4. Bidders’ Open Day

4.1 A Bidders’ Open day will be held on Wednesday 15th December 2016 from 13:00pm – 16:00pm. 1 - 4pm Shelter, 4 Garrett Street, London, EC1Y 0TY
4.2 Bidders are invited to register their interest in attending by sending an email with the subject line ‘Bidders’ Open Day: BIG001-0621 Help Through Crisis Learning, Evaluation and Support Contract to procurement@biglotteryfund.org.uk. The email should give the names of the delegates, their job titles as well as their email addresses. 
5. Schedule of Charges


5.1 Bidders shall complete Section Three, against each capitalised description, detailing a total and full cost for the service provision. 

5.2 The rates and or percentage charges entered in Section Three shall be deemed to include complete provision for full compliance with the requirements of the Contract.

5.3 The rates and or percentage charges contained within Section Three are, unless otherwise expressly agreed between the parties, firm and fixed and will not be subject to any variation.

5.4 The Charges must be quoted in pounds sterling and inclusive of VAT and expenses.
5.5 ANY ATTEMPT TO QUALIFY PRICING OR INCLUDE ASSUMPTIONS IN THE SCHEDULE OF CHARGES THAT YOU ARE REQUIRED TO SUBMIT WILL RESULT IN THE REJECTION OF YOUR TENDER.

6. Timetable
The indicative timetable for the procurement is as follows: 

	Key Actions
	Dates*

	(Publish OJEU Notice and) Issue of Invitation to Tender
	1 December 2016

	Bidders Open Day
	15 December 2016, 
1 - 4pm Shelter, 4 Garrett Street, London, EC1Y 0TY

	Closing Date for Questions
	12.00 Noon, 25 January 2017
The Fund will upload responses to clarification questions on the Contracts Finder website and its procurement site regularly and it is bidder’s responsibility to review it regularly. http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm


	Tender Return Deadline

	12.00 Noon, 8 February 2017


	Evaluation Period
	9 – 24 February 2017

	Clarification meetings **
	Week Commencing 27 February 2017

	Notification of Outcome and Identification of Preferred Bidder
	Week Commencing  27 February 2017

	Standstill Period
	3 March – 13 March 2017

	Contract Award 
	Week Commencing  13 March 2017

	Contract signed and work commencement Date
	Week Commencing 20 March 2017


*The Big Lottery Fund may vary these dates.

**The Fund reserves the right to carry out clarifications via email or by inviting Bidders to a clarification meeting. 

Scores will be moderated based on any clarifications provided during this meeting. 

7. Legal Documentation

7.1 Achieving greater transparency of public sector procurement and contracting

Government has set out the need for greater transparency across its operations to enable the public to hold public bodies and politicians to account. This includes commitments relating to public expenditure, intended to help achieve better value for money. 

As part of the transparency agenda, Government has made the following commitments with regard to procurement and contracting:

· All new central government tender documents for contracts over £10,000 and Contracts over £10,000 to be published on a single website from September 2010, with this information to be made available to the public free of charge. 
Bidders should be aware that if your organisation is awarded this contract, the resulting contract between you and the Big Lottery Fund will be published.  In some circumstances, limited redactions will be made to some contracts before they are published in order to comply with existing law and for the protection of national security.

7.2 Bidders must complete and return all documents in Section 3

· Annex 1
Response to Tender and Evaluation Criteria

· Annex 2
Schedule of Charges 

· Annex 3
Bidders Detail
· Annex 4 
Form of Tender

         
Part 1 Declaration

· Annex 5


         


Part I: Transparency Requirements





Part II Parent Company Guarantee (where appropriate)





Part III: Regulation 57 (1) Declaration




Part IV: Regulation 57 (8) Declaration 
Bidders shall notify The Big Lottery Fund of any errors, omissions or details contained within the documents, which precludes them from tendering for this service.

7.3 We recognise the potential need for consortia to provide experience and deliver the range of services outlined and have allowed more time to enable that to happen, if necessary. Where it is a consortia bid, the bid will need to identify a lead bidder and outline the individual roles and responsibilities of each company in relation to the delivery of the Contract. The Big Lottery Fund will enter into a contract with the lead organisation, and the lead organisation will ultimately be accountable for overall contract delivery. The lead organisation will be required to enter into a sub-contract with its partners on terms mirroring those of the main contract with the Big Lottery Fund (i.e. back-to-back contracts).   
7.4 Bidders are required to detail within their tender submission if it is their intention to sub contract any element of the services detailed in section 2, ‘Scope of Works’.

7.5 NB: Bidders must declare any known or potential conflicts of interest.
8. Submission Of Tenders
8.1 Bidders must submit an electronic copy of their tender submissions in a zip folder to procurement@biglotteryfund.org.uk  no later than 12.00 Noon on 
8 February 2017.    The subject line should be as follows:
“BIG001-0621 HELP THROUGH CRISIS LEARNING, SUPPORT AND EVALUATION CONTRACT”
Tenders received after that time will not be considered and it is your responsibility to ensure the tender is submitted in a zip file and that we have received it. If you do not submit the information in this way it may be too large for our email inbox and we will not receive it. Please ensure your emails are not larger than 7MB. 
8.2 By submitting a tender, the bidder agrees to keep that tender open for acceptance by the Big Lottery Fund for 90 days following the closing date for submission of tenders.

8.3 The Big Lottery Fund does not bind itself to award a contract or contracts and shall not be liable for any costs incurred in the production or submission of ITT. Under no circumstances will the Big Lottery Fund or any of its advisers be liable for any costs or expenses incurred by Bidders and/or their members in this procurement.
9. Notification Of Award Of Contract
9.1 Following the notification of outcome and the intention to award, a mandatory standstill period of TEN (10) calendar days will be observed. The Fund will not enter into a contract before the end of the standstill period. At the l end of the standstill period the contract will be awarded.  The issue of a signed Contract shall constitute the Big Lottery Fund’s acceptance of the tender.

SECTION TWO - SCOPE OF WORK
1. Background
1.1 Big Lottery Fund

The Big Lottery Fund (“the Fund”) is a non-departmental public body sponsored by the Department for Culture, Media and Sport. We operate across all countries in the UK. 

The Fund’s Mission and Values state that it is committed to bringing real improvements to communities, and to the lives of people most in need. To achieve this, we have three values that underpin all our work:
1. Making the best use of Lottery money

2. Using knowledge and evidence

3. Being supportive and helpful

1.2 The Fund’s Vision and Principles

The Big Lottery Fund’s vision is that people should be in the lead in improving their lives and communities.  Our approach will focus on the skills, assets and energy that people can draw upon and the potential in their ideas.

We feel that strong, vibrant communities can be built and renewed by the people living in them – making them ready for anything in the face of future opportunities and challenges.


Our work and the choices will be guided by the following principles:

· Confidence, not control - we trust in people’s ability to make great things happen, believing that our funding should enable rather than control. 

· Simple processes, good judgements - we use simple, proportionate processes which enable us to make good judgements. 

· The strengths people bring - we start with what people can contribute, and the potential in their idea. 

· A catalyst for others - we listen to, learn from, act on and facilitate the things that matter to people, communities and our partners. 

· Shared direction, diverse approaches - we value the diversity of communities we work with across the UK, are consistent in the quality and opportunities we offer, and support people to tackle inequalities. Using resources well - we make informed choices about the resources given to us by National Lottery players: with knowledge, with people and with money, and in an environmentally sustainable way. 
More detailed information about the Fund, including our vision and principles is available at www.biglotteryfund.org.uk/about-big/strategic-framework/our-vision
2. Help Through Crisis Programme
    2.1
Overview

A significant number of people continue to experience poverty (13 million across the UK, Joseph Rowntree Foundation, 2014). Over the last few years, one of the key trends is the significant increase in people experiencing a situation where their basic needs such as food, shelter, fuel and basic health and/or social care are not being met.
The Fund has invested £30 million in 59 local area partnerships* across England to focus on supporting people to move on from hardship crisis (Help through Crisis programme (HTC)). The programme’s overall aims are to better enable those people experiencing, or at high risk of experiencing, hardship crisis to move on and avoid being in this situation in the future. By hardship crisis we mean people having a lack of basic needs (for example, those things necessary to sustain life, including shelter, food and health care). 
Partnerships will provide tailored support, advice and advocacy, including legal advice, to enable people to address their immediate crisis and be in a better position to improve their circumstances and plan for the future. The partnerships are in different localities in England involving a combination of Voluntary, Community and Social Enterprise (VCSE) organisations that are targeted to support those who have the most difficulty accessing mainstream services and that take a person-centered, holistic approach. Partnerships will enable people to access and navigate the services they need to address their immediate difficulty, and help prevent it happening again by tackling the more underlying causes.
The Help through Crisis Programme (hereafter – Programme) was launched in June 2015 in two stages:

· Stage one - in December 2015, 84 grant applicants were invited to submit a Stage two application. 

· Stage two – in March 2016, 59 awards were made to grant applicants (details available here). We have funded partnerships in all nine regions across England to work with more than 35,000 people - 51 funded for five years, six of four year duration and two of three years.  Grant funding will end in 2021.  
We have not been prescriptive on how the individual partnerships respond to the programme outcomes (see 2.2) but projects will deliver a range of services and interventions that will draw on the strengths and personal experience of people facing hardship crisis so that they can overcome immediate difficulties and be ready for opportunities and challenges ahead. We have funded collaborative projects that will provide a broad range of interventions, including hands-on advocacy and advice, to better enable people to deal with the problems they are experiencing. 
Responsiveness to change is a key requirement of the Programme. It is expected that projects will need to respond rapidly to changes in the external environment and changing needs of beneficiaries.
*Note – throughout this ITT document words such as grant holders, partnerships and projects are used interchangeably and mean the 59 partnerships that were awarded at Stage two under the Help through Crisis programme.

The terms beneficiaries, clients, users and service users are used interchangeably throughout the ITT document and mean people supported by the project who have experienced hardship crisis or risk experiencing hardship crisis. For example, the term ‘user-led’ refers to the beneficiaries and not the grant holders. 

2.2
HTC Programme principles and outcomes
The programme has four outcomes, all of which need to be met by the partnerships:

· People who have experienced hardship crisis are better able to improve their circumstances
· People who are at high risk of experiencing hardship crisis are better able to plan for the future

· Organisations are better able to support people to effectively tackle hardship through sharing learning and evidence
· Those experiencing, or who are at high risk of experiencing, hardship crisis, have a stronger, more collective, voice, to better shape a response to their issues
In order for the programme to achieve its full potential and to put people in the lead in improving their lives and communities, local partnerships also need to adopt the following principles:

· Ensure those that have experienced hardship crisis themselves are fully engaged in the design and delivery of services and are actively encouraged to help shape solutions in order to influence change

· Commit to supporting those who have experienced, or risk experiencing, hardship crisis, to have a stronger, more collective voice to better shape a response to their issues

· Be led by, or involve, smaller scale grassroots community organisations that reach out to those who may not easily engage with mainstream services

· Demonstrate effective collaborative working to ensure holistic support including strong links with statutory and other support services
· Commit to capturing learning about what works to tackle hardship crisis and the impact of the services to enable projects to share and respond to changing circumstances and environment.
You will find more information about the Programme on our website https://www.biglotteryfund.org.uk/global-content/programmes/england/help-through-crisis  and in the attached Stage 2 application form (please see Appendix A to this ITT)
3.  Scope of Learning, Support and Evaluation Contract
A significant strand to the HTC programme is learning and support that will be provided to ensure projects develop to their full potential by capturing, sharing and implementing learning and enabling those who experience hardship crisis to have a greater say in the development of services that address their needs. 
The chosen Service Provider will work with all 59 grant holders, who will have different delivery approaches. Anecdotal evidence from stakeholders and the Fund’s existing grant holders tell us they find little evidence available to identify what works best in addressing hardship, which approaches are most effective at preventing recurrence and what strategies have the greatest impact. In addition there is a lack of collective beneficiary voice in this field. The Fund is looking to address these issues through this contract.
The HTC programme has a ‘test and learn’ ethos with emphasis on real-time learning and implementation throughout. This has been encouraged at application and set-up, with the learning aspect highlighted at all stages and embedding of user engagement strongly encouraged. All projects have a monitoring and evaluation budget, with some aspects of the project evaluations being completed by independent evaluators.  Due to the varied nature of the projects, approaches will vary between partnerships.   

The Service Provider will be key to identifying what works, facilitating networking between projects, supporting continuous improvement of service delivery and enabling partnerships and beneficiaries to have a stronger voice to broker improvements for the beneficiaries. 
The Fund’s detailed requirements are set out below and the Fund expects all bidders to confirm, explain and provide costs for how they would meet the deliverables listed in Sub-section 9.  All bidders are welcome to submit innovative approaches and suggestions on how the objectives of this contract can be achieved and on how our detailed requirements can be met. 
4. Aims and Objectives of the Contract

The aims of the learning, support and evaluation contract cover four interlinked strands of work:

1. Learning and evaluation – to capture and identify learning around impact, access and service user engagement

2. Support – with partnership working, evaluation approaches, service user engagement and identification/implementation of suitable new approaches.

3. Networking/Dissemination – to enable projects to engage, share and learn from each other’s experiences in all areas

4. Beneficiary Voice – to enable a stronger, collective voice to influence policy and practice both locally and nationally.
The objectives of the contract are as follows:
1. To support and empower grant holders to robustly evaluate and measure the impact of their projects (to capture learning about what does and doesn’t work, and why this is the case) 

2. To help grant holders to support beneficiaries in having more influence on service delivery within their individual projects and more widely with other partnerships and local stakeholders.

3. To identify good practice and critical success factors (such as method of intervention/service user engagement/collaboration) in order to enable a comparison of approaches and their effectiveness in different scenarios that can be used by the grant holders and others to implement ongoing improvements in the delivery of projects.

4. To support grant holders to replicate or scale-up approaches from elsewhere to help meet the needs of their beneficiaries.

5. To identify research gaps regarding the tackling and prevention of hardship crisis and ensure that learning from the programme on impact and efficacy of models contributes to the development of the evidence base. 

6. To enable a stronger, collective voice for beneficiaries to influence policy and practice both locally and nationally.

5. The Detailed Requirements

The Service Provider will support the awarded partnerships to consolidate the learning from their own partnership as well as others. This will include an initial detailed scoping to map the projects and to determine the main thematic issues of the programme both in terms of approaches used and target groups. Through the scoping exercise with the partnerships, and ongoing consultations with clusters of partnerships and their independent evaluators, the final key questions for shared learning should be suggested and developed.
5.1 
The following activities will be required to be carried out by the Service Provider as a minimum:

· Direct support with partnerships (including project-level independent evaluators) to appraise and support their impact measurement techniques and approaches (support may include range of face to face, telephone and/or workshops as appropriate)

· Direct support with partnerships to enable involvement of service users at all stages (including range of face to face, telephone and/or workshops as appropriate)

· Stakeholder engagement and awareness raising activities including establishment of a national steering/advisory group in collaboration with The Fund, to maximise impact of communications and support influencing

· Qualitative and quantitative research with 59 grant holders and other stakeholders to gather learning around impact and access to hardship crisis support
· Analysis of information and data to produce a range of materials clearly communicating which approaches work best – or do not work so well - and why 

· Enabling the sharing and implementation of learning amongst grant holders, through a combination of remote and face to face activities and learning tools, in accessible formats that can be disseminated to grant holders and more widely.

5.2 
The key questions that the Fund will expect the learning, support and evaluation Service Provider to address will include:
· Which approaches are most effective at preventing recurrence of hardship?
· What factors influence how successful, or not, partnerships are in addressing hardship? 

· How best to engage and empower people with lived experience to influence and shape projects in order to respond to changing circumstances?

· What can be learned about how to engage effectively with beneficiary groups that don’t engage well with mainstream services and how can this be implemented throughout the lifetime of the programme?

· How can this learning be shared between partnerships to maximise implementation of best practise?
For avoidance of doubt, the final key questions for shared learning should be suggested and developed with the input of the partnerships. All bidders are welcomed to suggest their sample questions in the tender response. 

5.3 
General requirements 

A strategic approach is expected, that sets out the way that evidence and learning will be gathered, analysed, shared and implemented so that continuous improvement can be incorporated throughout the lifetime of the programme to shape delivery and to use in influencing policy and practice with practitioners, policy makers, commissioners and other funders.   
This approach needs to be adapted on an on-going basis to ensure responsiveness to the changing needs of grant holders and service users as well as a rapidly changing external environment.
The Service Provider will be required to engage with all 59 partnerships and ensure that they are able to participate in the continuous sharing of learning as appropriate. Resources to develop and continue engagement need to be incorporated. The Service Provider will need to have an understanding of the national policy context in which the partnerships are operating and it is likely that regional and local policy understanding will be developed through contact with the partnerships.
A majority of the projects will have engaged independent project evaluators and these will be an important source of information for this contract. Many of these evaluators will engage with frontline workers and beneficiaries to identify what makes a difference in addressing hardship crisis. The Service Provider will need to collate evidence for a programme wide view of impact.

5.4
Role of the Fund

The Fund recognises that circumstances change and the external environment is volatile, therefore it will work flexibly with the Service Provider throughout to respond and adjust to changes. The Fund believes in a co-production approach and intends to encourage close working between the Service Provider, the Fund’s project management team, programme funding staff and the partnerships. 

It will work with the successful Service Provider to develop relationships and ensure consistent messages to partnerships to frame the importance of this work and emphasise on-going expectations. 

The Fund will collaborate with the Service Provider in establishment of a national steering/advisory group.
It will assist the Service Provider’s own fieldwork with access to information/data collected by the Fund as part of the management of grants and any other relevant internal documentation. Up-to-date programme information and contact details will be shared via a secure document store. This will include close communication and interaction throughout the contract with Fund staff as required.

5.5
Role of Partnerships

Partnerships are aware that they need to interact and engage with the Service Provider and build in capacity for this and cost for attending events. Additionally they have agreed to share monitoring data as required by the Service Provider within data protection guidelines. 

5.6 
Communications

The Fund will require the Learning, Support and Evaluation Service Provider to provide a programme of varied communication activity for a range of audiences (including the partnerships, frontline workers, service users, other agencies and stakeholders) that makes best use of the information, evidence and learning generated by the projects and the contract and involves service users with lived experience in developing these communications wherever possible. 

Communication channels and communication methods should reach all the partnerships and stakeholders by utilising a range of platforms and methods to facilitate learning as the study progresses. In providing this contract the successful bidder should demonstrate how they will use a range of audience appropriate media including websites, social media, film and illustrated reports as well as face-to-face events to ensure learning is easily accessible and engaged with by partnerships, other practitioners, stakeholders and service-users alike. Products should have a clear, well-evidenced message and be produced in response to partnerships’ needs with audience – and practical application – in mind.

A communications protocol will be developed at the outset setting out how the Service Provider will work with the Fund on all communications activity.  They will be required to involve the Fund’s External Relations department when planning and producing materials. 

6. Constraints and dependencies

Any web-based deliverables must comply with the Fund’s standard digital requirements, which are available to download from http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm. 

There will be a total of 59 partnerships and the Service Provider should be aware that contacts with partners as well as lead organisations may change over the period of the contract, as will service users, and every effort should be made to keep up to date and engaged over the period of the Contract.

7. Monitoring performance 

The Service Provider will provide quarterly progress reports to the Fund detailing, as a minimum:

· An overview of the meetings held

· An overview of progress achieved by contract holder (against the delivery plan and deliverables list)

· An overview of progress against Key Performance Indicators (KPIs)

· An overview of expenditure to date.

The structure of the reports will be agreed with the Fund and need to be written in plain English.


Bidders are asked to propose appropriate KPIs to evaluate their performance.  The final KPIs will be agreed by the Fund and the Service Provider at the start of the contract but may address the following:

· Extent, quality and impact of evaluation/beneficiary engagement support to partnerships

· Extent, quality and impact of engagement with beneficiaries

· Quality and adoption of learning papers and recommendations

· Evidence of analysis of learning with recommendations

· Evidence of implementation and impact of learning by partnerships

· Evidence of adapting to changing needs of projects and changing environment

· Evidence of continuous improvement

· Customer service levels and response times

· Partnership satisfaction.
8. Contract Term

The Contract is for a term of three years from February 2017 to February 2020, with the option to extend up to a further 2 years. (Subject to the Fund’s right to terminate it earlier).
The value of the contract for its full five year duration will be up to a maximum of £1,100,000 (including VAT and any associated expenses). Bids in excess of this limit will be excluded.  Bidders are required to set out their charges in the Table A and B, Schedule of Charges at Annex 2 of this ITT.

9. Communication with the Fund and Accountability
The Service Provider will maintain excellent communications with the Fund at all times ensuring that it is well informed, aware of issues and central to decision making in relation to progress.  The successful bidder will:

· Identify a single named contact acting as Service and Contract Manager. The designated person will carry prime responsibility for the successful delivery and implementation of services under this contract 

· The Service and Contract Manager will liaise with and take instruction from the Fund’s Contract Manager.
The Fund intends to publish data as a commitment to open data. This contract should be transparent about its data and methods. Suitably anonymised original data and all computer code needed to prepare and perform an analysis should be included in electronic accessible form so that others can understand, replicate and extend.

10. Deliverables
The Service Provider must provide the following deliverables to the Fund as a minimum:
	Contract Management
	Due date*

	Face to face inception meeting with the Fund’s Help Through Crisis team to agree plans and discuss requirements and roles of each team member.
	Within 10 working days of the contract start date

	Submit detailed delivery plan for all services required for the Fund’s approval, including KPIs, communications plan and invoicing schedule, to be updated at least annually in response to needs of grant holders and the user-led/national steering groups.
	Within 15 days of the inception meeting

	Provide quarterly progress reports and attend quarterly meetings, or other meetings requested by the Fund, to discuss progress against delivery plans and KPIs with contract manager and internal stakeholders.
	Quarterly – dates to be agreed with the Fund – until 2020-22

	Annual report on delivery and impact of the contract, including effectiveness review of contract.
	Annual

	Scoping of Partnerships
	

	Survey partnerships to map range of activities and beneficiary groups to identify common themes and approaches for shared measurement opportunities appropriate for clusters of partnerships. (Include communication with project evaluators as appropriate)
	First quarter

	Survey the partnerships to understand their evaluation and learning priorities and needs in order to scope opportunities for maximising learning and impact across the programme.
	First quarter and annually (to respond to changing needs)

	Survey partnerships to understand their service user engagement strategy, to identify best practice and to help scope support needed to enhance and develop service user involvement in management, design, delivery and evaluation. 
	First quarter

	Report on existing evidence and research in this field of work to identify what partnerships need to improve their service delivery.
	As per approved delivery plan

	Set-up and Support
	

	Organise and facilitate an event with all partnerships to explore and agree the nature and shape of networking, shared learning, support and dissemination to be provided – between Service Provider, partnerships and independent evaluators.  


	First six months

	Plan and deliver one to one evaluation support to each partnership to support their impact measurement approach and project evaluation plans. Consider shared measurement opportunities in collaboration with the partnerships and their independent evaluators, and continue to offer support throughout the period of the contract. (Approx. 60 days in year one across the partnerships)
	As per approved delivery plan

	Set-up, coordinate and facilitate a national level steering/advisory group in collaboration with the Fund. Membership to include key sector stakeholders, partnership representatives and participants with lived experience.
	Annual meetings and as per approved delivery plan

	Plan a programme of audience appropriate activities to facilitate networking, disseminate shared learning, and impact and to support grant holders to replicate or scale-up approaches from elsewhere to help meet the needs of their beneficiaries. Establish suitable communication platform(s) to do so, including a website, social media, events, etc.

	As per approved delivery plan

	Beneficiary Voice 


	

	Set-up ,coordinate and facilitate a user-led steering group, in collaboration with the partnerships, with representation from a range of projects and equality groups, and plan their contribution to the learning activities delivered in fulfilment of this contract. Continue to develop throughout contract.
	Biannual meetings and as per approved delivery plan.



	Plan and deliver service user involvement support in collaboration with the partnerships and co-design training/workshops to help develop involvement strategy and facilitate co-production. Produce guidance materials as appropriate. (Average 60 days of support in year one across the partnerships on a one-to-one basis or in groups)
	As per approved delivery plan

	Coordinate local and national connections, including training and support for beneficiaries, to help them develop an individual and collective voice for the purpose of influencing future services both locally and nationally.


	As per approved delivery plan

	Shared Learning/Networking
	

	Analyse and aggregate data received from the grant holders and their project evaluators - factoring in any additional research conducted by the Service Provider or obtained from networking, beneficiary or stakeholder events – to produce a range of materials communicating findings and best practice recommendations.

	As per approved delivery plan

	Publicise and communicate good practice and critical success factors enabling a comparison of approaches and their effectiveness in different scenarios to be used by the partnerships and others to implement ongoing improvements in the delivery of projects. (number and frequency to be finalised in delivery plan)


	As per approved delivery plan

	Identify research gaps regarding the tackling and prevention of hardship crisis and ensure that learning from the programme on impact and efficacy of models is shared widely and contributes to the development of the evidence base. 


	As per approved delivery plan

	Produce a package of responsive practice-orientated outputs to support implementation of learning and best practice 
	As per approved delivery plan

	Co-produce real-time learning focussed policy commentaries over the course of the contract for dissemination to partnerships and local and national stakeholders
	As per approved delivery plan

	Manage, develop and maintain communication platforms (including website or other platform as agreed with the Fund)
	As per approved delivery plan

	Plan and deliver a series of face to face network events, (regional and/or national and 2-4 per annum based on demand) for partnerships and beneficiaries to share learning and experiences. These will be developed in collaboration with the partnerships. 
	As per approved delivery plan


	Plan and deliver three national/regional conferences during the lifetime of the programme. Timings and content to be agreed with the Fund, the user-led and national steering groups, partnerships and external stakeholders.
	As per approved delivery plan

	Present evidence and learning at non-programme funded events in this field, and support partnerships to do likewise (minimum 2 per annum)
	As per approved delivery plan

	Produce four accessible annual interim reports and one final report, with stand-alone and partnership-friendly executive summaries, to report on key learning throughout the year and topics identified by the partnerships and the Fund for dissemination to partnerships and wider stakeholders. Including evidence of embedded learning and impact.
	As per approved delivery plan


* The Fund reserve the right to amend this timetable where required. Dates dependent on 2 year extension after the initial contract term. 
The deliverables set out above represent our minimum requirements. All deliverables must be adapted on an ongoing basis in response to the user-led steering group and to the changing needs of partnerships. We encourage bidders to consider how they may provide additional and appropriate services to these within their overall tender proposals.
11. Payment Schedule
This is a payment by deliverables contract. Payment will be made by the Fund upon  acceptance of deliverables, quarterly. 
SECTION THREE

ANNEX 1

Response to Tender & Evaluation Criteria

You are required to respond to ALL of the criteria below.  To assist our evaluation of your tender submission, please ensure you clearly cross-refer your responses to the assigned numbers. Any relevant supporting tender documentation must also be clearly identifiable by a criteria number. 

Initially we will evaluate your tender to see if you meet our minimum PASS/FAIL CRITERIA set out below.

Bidders who do not pass all the Pass/Fail criteria (A-F) below will be excluded from further consideration in the competition (i.e. their tenders will not be evaluated further and will be excluded from the competition).

Pass/Fail Criteria 

	Pass Fail Criteria A


	PASS/FAIL

	The Fund requires bidders or in the case of consortia, the  Lead Organisation to have a minimum of 2 years relevant experience successfully delivering similar projects. Please provide evidence of 2 years’ experience of undertaking projects (similar in scale, value and complexity) successfully and supporting references demonstrating this.
In your tender response, please confirm when each contract commenced and concluded, its value as well as contact details. The customer contact should be prepared to speak to us to confirm the accuracy of the information provided.

	

	Pass Fail Criteria B
	

	Financial PASS/FAIL TEST (Where the bidder is a consortium, this test will be carried out on the lead organisation who the Fund will enter into a contract with and the Lead Organisation should submit the information requested below)

Please submit a copy of your annual accounts for the last two years. We will review these to ensure you have adequate financial standing to perform the services without putting the Fund at risk. Where we have concerns we may request further information/comfort from you. Where our concerns are not addressed you will be excluded from further participation in the tender process. 

In order for us to carry out this assessment please provide copies of the last two years audited accounts and annual reports to include: 

· Balance Sheet

· Profit & Loss Account and Cost of Sales 

· Full notes to the accounts 

· Director’s report/auditor’s report 

If you are unable to submit the information requested above because your organisation is below the threshold for which audited accounts are required, please submit the following documents instead:

· Balance Sheet
· Profit and Loss Statement

If you are unable to submit the information requested above for the most recent financial year because such information is not yet audited, please submit management accounts for that period. 


	

	Pass Fail Criteria C

	

	Bidders must confirm they either have: 

1. Hold an accredited independent third party certificate of compliance in accordance with BS EN ISO 9001 (or equivalent); or 

2. Have documented procedures for periodically reviewing, correcting and improving quality performance including processes for ensuring that the bidder’s quality management is effective in reducing/preventing incidents of sub-standard delivery, this must include the quality of output and general performance.
The winning bidder will be required to provide documentary evidence upon contract award
	

	Pass Fail Criteria D 


	

	Bidder has submitted a complete tender that accords with every instruction and requirement set out in this ITT.


	

	Pass Fail Criteria E


	

	Bidder has completed Parts III and IV of Annex 5 and confirmed none of the circumstances set out there in apply. 


	

	Pass Fail Criteria F  
	

	The Tender must not exceed £1,100,000 (including VAT and expenses) for the whole of the contract term of 3 years plus 2 years extension in meeting all the Fund’s requirements specified in the ITT. Tenders that exceed this will be considered unaffordable and will be excluded from further consideration in the tender process


	


If you pass all of the pass/fail criteria set out above, we will evaluate your tender response using quality and price criteria which are set out below.  

Your Bid will be scored out of 100. 70% of the marks will be allocated to your responses to the Quality Questions Below. Each question will be scored using the methodology in the Table below. 

Your overall score for each question will be calculated by multiplying the quality score you receive with the weighting for that question, set out below. This score will then be divided by the maximum available score for this Quality Criterion (425) and multiplied by (70) to get your final score for that question.
Example: assume Bidder A scores 3 for Question 1: the formula is 3 x 20 = 60, 60/425 x 70 = 9.88 out of 100.
30% of the marks will be available for your Price Proposal. The methodology for scoring price is set out further below.

Your responses should be supported by evidence/previous successful implementation of proposed solution for meeting our requirements.

Please note – Though criteria are numbered, this does not relate to any order of importance

	
	Evaluation Criteria 
Quality: 70%
	Weighting
	Maximum score available

	Question 1
	Please set out your proposal for meeting all our requirements set out in Section 2 ‘Scope of Work’ (from Sub-section 3 onwards).
	20
	100

	Question 2
	Please detail your proposed delivery team, their proposed role including each member’s relevant skills and expertise and how relevant they are for delivering the services required. In particular, their experience and skills of delivering networking, learning, beneficiary engagement and support activities similar to those outlined in Section 2 ‘Scope of Work’. Please identify any specialist organisations or services that you would link up with to provide specialist support as required.
	10
	50

	Question 3
	Provide a clear and realistic delivery plan (including methodology and estimate timeline) that responds to the aims and constraints set out in Section 2.Please explain the reasoning for your approach.

Your response should include an explanation on your resource allocation.
	15
	75

	Question 4
	Please set out your plans to capture and analyse learning from the partnerships in order to identify and share the most effective means of tackling and preventing hardship crisis and building stability and resilience.
	10
	50

	Question 5
	Please explain how you will ensure the learning is shared between the partnerships and how you will support them to maximise implementation of best practice to improve their own project delivery.
	10
	50

	Question 6
	Please explain how you will enable partnerships and beneficiaries to have a stronger, more collective voice to influence policy and practice both locally and nationally.
	10
	50

	Question 7
	Please detail your approaches to quality assurance for the service and how you will monitor quality on an ongoing basis. Please include your suggested KPIs (as requested in Sub-section 7 of Section 2 ‘Scope of Work’) and measurement plans in response to this question.
	5
	25

	Question 8
	Please identify the main risks to the delivery of this contract to time and budget and your proposals for mitigating/managing them.
	5
	25

	Total

	
	
	425


Responses to each question above will be allocated a score based on the methodology contained in the table below. This score will then be multiplied by the weighting in the column on the right. 

Quality Questions scoring methodology
	0
	Poor


	No response or partial response and poor evidence provided in support of it.  Does not give the Fund confidence in the ability of the Bidder to deliver the Contract.

	1
	Weak


	Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract.

	2
	Satisfactory


	Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract.

	3
	Good


	Response is comprehensive and supported by good standard of evidence. Gives the Fund confidence in the ability of the Bidder to deliver the contract. Meets the Fund’s requirements.

	4
	Very good


	Response is comprehensive and supported by a high standard of evidence. Gives the Fund a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in some respects. 

	5
	Excellent
	Response is very comprehensive and supported by a very high standard of evidence. Gives the Fund a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in most respects.


Price scoring methodology: 30% overall

Price: The evaluation of price will be carried out on the Schedule of charges you provide in response to Annex 2 Table A 

	Price Criterion


	30% will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in Table A will be used to score this question.

For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30-2.4 = 27.6 marks) 
	30%


The scores for quality and price will be added together to obtain the overall score for each Bidder. The Bidder with the highest score will be the preferred Bidder.

ANNEX 2 - Schedule of Charges  

Bidders are required to submit the following costs tables as part of their bids:

1. Table A – Total firm and fixed Fees for delivering the Contract
2. Table B – Cost Plan per year 
Bidders must complete the Schedule of Charges table A and B below estimating the number of days and travel and subsistence costs associated with their bid. The total fixed price will be inclusive of VAT and inclusive of expenses and all costs to be incurred.

	TABLE A*:

(firm and fixed costs)


	e.g. Partnership Manager/ Director
	e.g. Senior Consultant/manager/researcher 
	Junior 

Consultant/equivalent 


	Total days
	Total Fees

(£)

	
	e.g. £500
	e.g. £300
	e.g. £200
	
	

	
	Quantity
	
	
	

	E.g. Inception meeting to agree plans and finalise requirements with the Fund
	1
	e.g. 0.5
	1
	1.5
	3
	850

	Insert additional rows 
	
	
	
	
	
	

	[Add as necessary]
	
	
	
	
	
	

	Expenses
	
	
	
	
	
	

	Travel and subsistence
	
	
	
	
	
	

	Other (non-staff) costs – 

Please specify
	
	
	
	
	
	

	Sub-total
	£

	VAT
	£

	Total Costs including VAT and expenses (this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements ) 
	£


* The Fund reserve the right to amend this timetable where required.

Notes: 

The Fund reserves the right to reject abnormally low tenders.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this tender.
Bids in excess of £1,100,000 (including VAT and expenses) for the whole of the contract term i.e. 3 years plus 2 years will be considered unaffordable and will be excluded from further consideration in the tender process. 
Please note any contract awarded will be based on the Fund’s standard terms and conditions of contract and you will be required to sign up to these if successful.
Table B:  Cost Plans per year

The completed Table A must be accompanied by a separate cost plan for each year of Contract term including the Extension Years 2021 and 2022, setting out how the above costs have been arrived at. 
Please expand columns as required.
Cost Plan: Year One 2017/18
	TABLE B:

Cost Plan for Year 1


	e.g. Partnership Manager/ Director
	e.g. Senior Consultant/manager/researcher 
	Junior 

Consultant/equivalent 


	Total days
	Total Fees

(£)

	
	e.g. £500
	e.g. £300
	e.g. £200
	
	

	
	Quantity
	
	
	

	Inception meeting to agree plans and finalise requirements with the Fund
	1
	e.g. 0.5
	1
	1.5
	3
	850

	[Add as necessary]
	
	
	
	
	
	

	[Add as necessary]
	
	
	
	
	
	

	Expenses
	
	
	
	
	
	

	Travel and subsistence
	
	
	
	
	
	

	Other (non-staff) costs – 

Please specify
	
	
	
	
	
	

	Sub-total
	£

	VAT
	£

	Total Costs including VAT and expenses for Year 2017/2018
	£


Cost Plan: Year Two 2018/19 etc.

ANNEX 3
Bidder’s Details
	Company Details

	1.
	Registered Company Name:

	2.
	Company Registration Number:

	3.
	Main Operational address for the service:

	
	Tele:

	
	Fax:

	
	Email:

	
	

	4.
	Address for all contractual correspondence –

	
	(If one of the above, please specify)

	
	

	
	

	
	

	5.
	Address for all service management correspondence

	
	(If one of the above, please specify)

	
	

	
	

	
	

	6.
	Contacts:

	
	a. Responsible Person for the Contract

	
	Tele: 

	
	Fax: 

	
	Mobile:

	
	Email: 

	
	

	
	b.  Responsible Person for the Service:

	
	(If different to the above)

	
	Tele: 

	
	Fax: 

	
	Mobile

	
	Email: 

	
	

	7.
	VAT registration Number (if applicable)

	
	

	8.
	Payment Details

	
	Account Name:

	
	Bank Name: 

	
	Address:

	
	Sort Code:

	
	Account Number:

	
	


ANNEX 4

Form of Tender

Part I – Declaration

Note: The Bidder is to type the following on its own letter headed paper

Dear Big Lottery Fund 

CONTRACT: HELP THROUGH CRISIS – LEARNING, SUPPORT AND EVALUATION CONTRACT; BIG001 - 0621 (‘the Contract’)
Having examined the proposed Contract comprising, we do hereby offer to enter into a Contract with THE FUND on the terms and conditions in the said Contract.
We undertake to keep the Tender open for acceptance by THE FUND for a period of 90 days from the return date.
We declare that this is a bona fide Tender, intended to be competitive, and that we have not fixed or adjusted the amount of the Tender by, or under, or in accordance with, any agreement or arrangement with any other person.  We further declare that we have not done, and we undertake that we will not do, any of the following acts prior to award of this Contract:

a) Collude with any third party to fix the price of any number of Tenders for this Contract; 
b) Offer, pay, or agree to pay any sum of money or consideration directly or indirectly to any person for doing, having done, or promising to be done, any act or thing of the sort described herein and above.

We understand that you are not bound to accept the lowest priced, or any, Tender.

Signed:



Date:



Name:



In the capacity of: 


Duly authorised to sign tenders for and on behalf of:


ANNEX 5

Part I: Transparency
Note: In compliance with the Government’s transparency agenda, all Big Lottery Fund contracts over £10,000 (net of recoverable VAT) issued on or after 1 January 2011 will be published on the Government’s Contracts Finder website. We are required to publish contracts in full, and as a minimum must publish the specification, terms and conditions and associated schedules (which may include the winning bidder’s bid).

In limited circumstances redactions can be made prior to publication to protect certain types of information. Redactions are permitted in line with the exemptions set out by the Freedom of Information Act 2000. Examples of information which may be exempt under the FOIA include: personal data; information amounting to a trade secret; and information which if disclosed would or would be likely to prejudice the commercial interests of any person.

If the Bidder believes redactions ought to be made, these should be identified by the Bidder in the following table on their own letter headed paper. Bidders must provide explicit justification and reasoning for each redaction requested. The Big Lottery Fund is responsible for determining in its absolute discretion whether any information is exempt from publication.

CONTRACT FOR Tender Title: Help Through Crisis – Learning, Support and Evaluation Contract BIG001 - 0621
	Contract clause or section of tender to be redacted
	Justifications for redaction

	
	


Part II: Parent Company Guarantee
Note:  To be submitted in full on Service Provider's ultimate Holding Company's headed notepaper.

Dear Big Lottery Fund 
Help Through Crisis – Learning, Support and Evaluation Contract BIG001 - 0621
With reference to the Tender for the above services submitted by [insert name of Bidder] (hereinafter referred to as "the Contractor"), as a condition precedent for and in consideration of the Big Lottery Fund (a non departmental Public Body sponsored by the Cabinet Office) (hereinafter referred to as "THE FUND") entering into a contract (hereinafter referred to as "the Contract") with the Contractor for the above services, we, as the Contractor's ultimate holding company do hereby enter into the following unconditional and irrevocable undertakings with THE FUND. These undertakings being on condition that THE FUND enters into the Contract with the Contractor for the above services and in consideration of the same:

· The Contractor shall perform all its obligations contained in the Contract;

· If the Contractor shall in any respect fail to perform the said obligations contained in the Contract or commits any breach thereof we shall ourselves perform on simple demand by THE FUND, or take whatever steps may be necessary to achieve performance of the obligations under the Contract of the Contractor, and shall indemnify and keep indemnified the Authority against any loss, damages, costs and expenses howsoever arising from the said failure or breach for which the Contractor may be liable;

· We shall not be discharged or released from our undertakings hereunder by any waiver or forbearance by THE FUND, whether as to payment, time, performance or otherwise;

· This guarantee shall be unconditional and irrevocable and shall continue in force, notwithstanding any variations or additions to or deletions from the scope of services to be performed under the Contract, until all the Contractor's obligations there under have been performed; and,

· This document shall be construed and take effect in accordance with English Law and, furthermore, we submit to the jurisdiction of the English Courts.

Yous faithfully

Signed:



Date:



Name:



In the capacity of: 


Duly authorised to sign tenders for and on behalf of:

Part III: Regulation 57 (1) Declaration
Important Notice: 

In some circumstances the Fund is required by law to exclude you from participating further in procurement. If you cannot answer ‘no’ to every question in this section it is very unlikely that your application will be accepted, and you should contact us for advice before completing this form. 

	2.1 Within the past five years, has your organisation (or any member of your proposed consortium, if applicable), Directors or partner or any other person who has powers of representation, decision or control been convicted of any of the following offences?
	Please indicate your answer by marking ‘X’ in the relevant box.

	
	Yes
	No

	a) conspiracy within the meaning of section 1 or 1A of the Criminal Law Act 1977 or article 9 or 9A of the Criminal Attempts and Conspiracy (Northern Ireland) Order 1983 where that conspiracy relates to participation in a criminal organisation as defined in Article 2 of Council Framework Decision 2008/841/JHA on the fight against organised crime;
	
	

	b) corruption within the meaning of section 1(2) of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906;
	
	

	c) the common law offence of bribery;
	
	

	d) bribery within the meaning of sections 1, 2 or 6 of the Bribery Act 2010; or section 113 of the Representation of the People Act 1983;
	
	

	e) any of the following offences, where the offence relates to fraud affecting the European Communities’ financial interests as defined by Article 1 of the Convention on the protection of the financial interests of the European Communities:
	
	

	(i) the offence of cheating the Revenue;
	
	

	(ii) the offence of conspiracy to defraud;
	
	

	(iii)
fraud or theft within the meaning of the Theft Act 1968, the Theft Act (Northern Ireland) 1969, the Theft Act 1978 or the Theft (Northern Ireland) Order 1978;
	
	

	(iv) fraudulent trading within the meaning of section 458 of the Companies Act 1985, article 451 of the Companies (Northern Ireland) Order 1986 or section 993 of the Companies Act 2006;
	
	

	(v) fraudulent evasion within the meaning of section 170 of the Customs and Excise Management Act 1979 or section 72 of the Value Added Tax Act 1994;
	
	

	(vi) an offence in connection with taxation in the European Union within the meaning of section 71 of the Criminal Justice Act 1993;
	
	

	(vii)
destroying, defacing or concealing of documents or procuring the execution of a valuable security within the meaning of section 20 of the Theft Act 1968 or section 19 of the Theft Act (Northern Ireland) 1969;
	
	

	(viii) fraud within the meaning of section 2, 3 or 4 of the Fraud Act 2006; or
	
	

	(ix)
the possession of articles for use in frauds within the meaning of section 6 of the Fraud Act 2006, or the making, adapting, supplying or offering to supply articles for use in frauds within the meaning of section 7 of that Act;
	
	

	f) any offence listed—
	
	

	(i)
in section 41 of the Counter Terrorism Act 2008; or
	
	

	(ii)
in Schedule 2 to that Act where the court has determined that there is a terrorist connection;
	
	

	g) any offence under sections 44 to 46 of the Serious Crime Act 2007 which relates to an offence covered by subparagraph (f);
	
	

	h) money laundering within the meaning of sections 340(11) and 415 of the Proceeds of Crime Act 2002;
	
	

	i) an offence in connection with the proceeds of criminal conduct within the meaning of section 93A, 93B or 93C of the Criminal Justice Act 1988 or article 45, 46 or 47 of the Proceeds of Crime (Northern Ireland) Order 1996;
	
	

	j) an offence under section 4 of the Asylum and Immigration (Treatment of Claimants etc.) Act 2004;
	
	

	k) an offence under section 59A of the Sexual Offences Act 2003;
	
	

	l) an offence under section 71 of the Coroners and Justice Act 2009
	
	

	m) an offence in connection with the proceeds of drug trafficking within the meaning of section 49, 50 or 51 of the Drug Trafficking Act 1994; or
	
	

	n) any other offence within the meaning of Article 57(1) of the Public Contracts Directive—
	
	

	(i)
as defined by the law of any jurisdiction outside England and Wales and Northern Ireland; or
	
	

	(ii)
created, after the day on which these Regulations were made, in the law of England and Wales or Northern Ireland.
	
	

	Non-payment of taxes (Regulation 57(3))
Has it been established by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which your organisation is established (if outside the UK), that your organisation is in breach of obligations related to the payment of tax or social security contributions?
If you have answered Yes to this question, please use a separate Appendix to provide further details. Please also use this Appendix to confirm whether you have paid, or have entered into a binding arrangement with a view to paying, including, where applicable, any accrued interest and/or fines?
	
	


Part IV: Regulation 57 (8) Declaration
Important Notice. 
The Fund is entitled to exclude you from consideration if any of the following apply but may decide to allow you to proceed further. If you cannot answer ‘no’ to every question it is possible that your application might not be accepted. In the event that any of the following do apply, please set out (in a separate Annex) full details of the relevant incident and any remedial action taken subsequently. The information provided will be taken into account by the Authority in considering whether or not you will be able to proceed any further in respect of this procurement exercise. 

	Within the past three years, please indicate if any of the following situations have applied, or currently apply, to your organisation.
	Please indicate your answer by marking ‘X’ in the relevant box.

	
	Yes
	No

	a) your organisation has violated applicable obligations referred to in regulation 56 (2) of the Public Contracts Regulations 2015 in the fields of environmental, social and labour law established by EU law, national law, collective agreements or by the international environmental, social and labour law provisions listed in Annex X to the Public Contracts Directive as amended from time to time;
	
	  

	b) your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State;
	
	

	c) your organisation is guilty of grave professional misconduct,  which renders its integrity questionable;
	
	

	d) your organisation has entered into agreements with other economic operators aimed at distorting competition;
	
	

	e) your organisation has a conflict of interest within the meaning of regulation 24 of the Public Contracts Regulations 2015 that cannot be effectively remedied by other, less intrusive, measures;
	
	

	f) the prior involvement of your organisation in the preparation of the procurement procedure has resulted in a distortion of competition, as referred to in regulation 41, that cannot be remedied by other, less intrusive, measures;
	
	

	g) your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions;
	
	

	h) your organisation—

(i)
has been guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria; or
(ii)
has withheld such information or is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015; or
	
	

	i) your organisation has undertaken to
	
	

	(aa)
unduly influence the decision-making process of the contracting authority, or
	
	

	(bb)
obtain confidential information that may confer upon your organisation undue advantages in the procurement procedure; or
	
	

	j) your organisation has negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award.
	
	


Page 2 of 39

