# Expression of interest

# Title: Evaluation of the Master’s Degree Loan

Project reference: 2016/054

Deadline for expressions of interest: Friday 24th February 2017

## Summary

Expressions of interest are sought for evaluation of the impact of the first year’s availability of postgraduate master’s degree loans. This is likely to involve a combination of secondary data analysis of existing data sources, analysis of Student Loan Company management information, primary quantitative and qualitative research with postgraduate students (loan takers and non-loan takers) and qualitative research with higher education institutions.

## Background

This government has a long-term commitment to enhancing support for postgraduate study. That is why, in summer 2016, a new postgraduate master’s loan scheme was launched, with the overarching aims of:

- helping to remove the financial barrier often faced by those wishing to step up to achieving a master’s level qualification, and consequently stimulating increased take-up in postgraduate master’s degree study; and

- in turn, improving the supply of highly skilled individuals to the UK economy and increasing our global competitiveness.

The new scheme enables postgraduate master’s students under the age of 60 to access a loan of up to £10,000 as a contribution towards the cost of their studies.  The loan is available to full-time and part-time students, as well as those undertaking distance learning. As with the undergraduate loan system, repayment of the loan is income-contingent and borrowers will only begin repaying when they are earning over £21,000 per year.

The loan scheme was launched in June 2016, to provide support for students commencing their studies in Academic Year 2016/17 onwards. Research is now required to assess the initial impacts of the introduction of the loans.

## Evaluation aims

A full measure of the impact of the introduction of the new master’s loans will not be possible in the time available for this research due to the longer timescales required of some output and outcome impacts. The work will therefore involve (i) an initial assessment of activities, outputs and progress towards longer term outcomes and (ii) scoping a longer term assessment of impact.

This will involve the following:

- Determining appropriate measures of impact - including both output and outcome measures. Consideration must be given to existing measures where appropriate.

- Providing an assessment of impacts based on these metrics. This is likely to involve analysis of available secondary data and management information and qualitative and quantitative primary research.

- Providing an estimate of deadweight (that is, the outcomes that might have been expected without the loan).

- Outlining measures for longer term outcomes and set  up requirements of the project to enable longer term outcomes to be examined in the future (e.g. collection of permission to re-contact survey participants and collection of contact details).

### Key research questions

Management information and existing statistical sources will provide a range of data of relevance to this research including:

- The number of students undertaking postgraduate master’s education

- The characteristics of students undertaking postgraduate master’s education

- The courses being taken and institutions at which they are provided

- The numbers and characteristics of students taking up the loans

- All major sources of student funding (including the balance of multiple sources)

Bespoke research is required to determine the following:

For students:

- How much of an enabler was the loan?

  - Has the loan enabled more students to take up master’s study? What role has the loan played in the student’s decision to study?  Did they start the master’s course earlier as a result of the loan? Why did students not take up the loan?

- What were the motivations for studying and for taking the loan?

  - Was it to further their career, academic interest etc.?

- What role did the loan play in the decision to study?

  - Was it used to pay for fees or living costs? What other sources of funding did they use to top up the £10K loan amount? Did this differ with student characteristics e.g. age? What impact did the repayment terms have on their decision i.e. was concurrent repayment a deterrent? Did it affect the type of course they chose (e.g. course length, cost, study intensity?) How did they hear about the loan? Where did they go to find funding information?

- Is the loan crowding in funding rather than crowding it out?

  - If the loan hadn’t been available, how would they have funded the master’s / would they have studied? What other sources of funding did they consider? Is the loan duplicating funding? Has the loan enabled loan takers to increase/decrease use of other sources of finance (e.g. paid work, credit, bank loans)?

For institutions:

- How has the introduction of the loan impacted their institution?

- Has the loan opened up new opportunities for their postgraduate provision?

## Methodology

The research is likely to involve a mixture of quantitative and qualitative research:

- Analysis of Student Loan Company management information

- Secondary data analysis (for example of HESA statistics and Performance Indicators)

- Quantitative survey of around 2,500 postgraduate students (to include loan takers and non-loan takers)

- Qualitative research with approximately 40 loan takers and non-loan takers

- Qualitative research with approximately 10 higher education institutions

## Timing

- Expression of interest 		Feb 2017

- Invitation to tender			March 2017

- Contract awarded/project start	End March 2017

- Fieldwork				April – June 2017

- Draft final report			July 2017

- Proposed end date			August 2017

## Assessment criteria

Expressions of interest will be assessed against the following criteria:

- Experience of research topics to be covered

- Experience of research methodologies to be used

- Experience of research with higher education students and higher education institutions

- Capacity and capability to deliver the project in the timescales indicated

Expressions of interests submitted must be no more than 1000 words overall; this includes any website links. Anything longer will be disregarded.

Closing date for EOIs: Friday 24th February 2017 Send your EOI form to: liz.pendry@education.gov.uk

## How to submit an expressions of interest

You must submit an expression of interest (EOI) in order to be considered to be invited to tender. To do so, please complete the Expression of Interest Research template found on the Department’s research website. A submission of an EOI does not guarantee an invitation to tender and the Department does not routinely advise organisations that they have not been successful in being invited to tender. Feedback is however available on request.

In order to express an interest you must be registered with us and you will need your ID number. If you need to register then please do so using the online supplier registration form. If you have already registered and have forgotten your ID number, please send an email to Enquiries.RBU@education.gov.uk

All contracts are let on the basis of the Department’s Terms and Conditions. You are encouraged to check these before submitting your expression of interest, as these form part of your contractual obligations.

© Crown copyright 2017