## Summary Page
Council of the Isles of Scilly
Bryher Fire Station
SUMMARY PAGE
Ref | Description | Element Total
1 | FROM COLLECTION PAGE | 16500
2 | OVERHEAD & PROFIT | 0
3 | DAYWORKS & RISK ALLOWANCE | 0
TOTAL TO FORM OF TENDER |  | 16500
8
8
8

## Collection Page
Council of the Isles of Scilly
Bryher Fire Station
TENDER RETURN COLLECTION PAGE
Ref | Description | Element Total
1 | SCOPE OF WORKS
2 | PRELIMARIES | 0
3 | ACCESS | 0
4 | SCHEDULE OF WORKS | 1500
5 | CONTINGENCY | 15000
6 | CONTRACTOR DESIGN ITEMS | 0
7 | COMPLETION | 0
TOTAL TO SUMMARY PAGE |  | 16500
8
8
8

## Schedule of Works
Council of the Isles of Scilly
Bryher Fire Station
SCHEDULE OF WORKS
Ref | Description | Unit | Qty | Total | Comments
Note: The Contractor is to ensure the schedule of works is read in conjunction with the drawings, specification and all other tender documents supplied.
1 | SCOPE OF WORKS
1.1 | This schedule of works and specification predominately consists of asbestos removals and the associated roof recovering, along with removal of the timber suspended floor; replacing with a concrete slab. External and internal repairs and redecoration are also detailed in isolation. The aim of these works are to prevent further damage to the internal and external fabric due to failed/life expired elements, the removal of health and safety hazards and also providing the opportunity to implement thermal improvements.
2 | PRELIMINARIES
2.1 | The Contractor is to review the tender package in full and provide a breakdown of the preliminary price to complete the works and provide this within their tender response.
2.2 | The below is to be read in conjunction with the Preliminaries document.
2.3 | The Contractor is to allow for an appropriate site set up to ensure compliance with all Health, Safety and Welfare Legislation relating to Health & Safety at Work Act and CDM Regulations 2015.
2.4 | The Contractor is to allow for a site set up to provide for all welfare facilities and access required to undertake the works
2.5 | Formal induction procedures are to be agreed and briefed prior to any employees starting work on site.
2.6 | The Contractor shall allow access for progress visits and health & safety audits to be undertaken by the Contract Administrator (CA). Access for visits shall not be unreasonably denied. Any information collated from health & safety audits shall be given to the Contractor for action to assist in the promotion of a positive health & safety culture.
2.7 | The Contractor shall allow for appropriate protection and security to work areas during and outside of working hours.
2.8 | Any skips located within 5 meters of a building that contain combustible materials must be a fully enclosed and lockable. Contractor must obtain all relevant permits dependant on the location of the highway. Rubble chutes will not be permitted on site.
2.9 | Before any works commence the Contractor is responsible for providing a photographic schedule of condition of the parts of the site affected by the works. The record is to highlight any areas of existing damage and must be provided to the CA in PDF. Costs to repair damage caused during the works, not previously identified in the photographic record of condition, shall be borne by the Contractor.
2.1 | The building will be primarily unoccupied during the works (refer to Pre-Construction Information for further details) and all fire fighting equipment and loose furniture/fittings shall be removed by the client prior to commencement.
2.11 | The Contractor is to handle, store and fix materials and accessories in accordance with manufacturers' recommendations and the relevant British Standard for each work task; ensuring compliance with design and performance requirements.
2.12 | Mechanical, electrical and plumbing items are to be covered by Contractors Design Portion (CPD). These have been listed seperately towards the bottom of this Schedule of Works.
3 | ACCESS
3.1 | Access considerations to be read in conjunction with preliminaries.
3.2 | As per the preliminaries, access to be the responsibility of the Contractor.
4 | SCHEDULE OF WORKS
4.1 | ENABLING WORKS / DEMOLITION
4.1.1 | The Contractor is to commission a Refurbishment & Demolition Survey and await the findings prior to any works commencing on site. This report shall be made available to the Client and Contract Administrator.
4.1.2 | Upon the results of the above survey, the Contractor is to employ a licensed asbestos removal contractor to remove the existing cement slates above the Lounge and the corrugated roof sheets above the Office, WC and Lobby. All work is to be undertaken in accordance with the HSE Approved Codes of Practice and guidance. Allow to install all protection required, signage, area isolation etc. to undertake the asbestos removal work. All removed materials are to be categorised as hazardous waste and disposed of in accordance with statutory requirements.
4.1.3 | Following removal of the above items, remove temporary access, cart away all protection facilitating the asbestos removal and clean site ready for the below items of work. Removed protection is to be categorised as hazardous waste and disposed of in accordance with statutory requirements.
4.1.4 | Undertake air testing and provide certification to the CA before proceeding with the below items of works to confirm that the work area is safe to access. The below works will not be allowed to proceed until certification is provided.
4.2 | ROOF - LOUNGE (CREW ROOM)
4.2.1 | Prior to commencing the below removals, the Contractor is to identify, trace, isolate and make safe electrical installations associated with the solar panels or any other installations that the Contractor deems necessary in order to undertake the following works safely.
4.2.2 | Carefully remove the 8nr solar panels including all associated framing, fixings, conduit and cabling; ensuring they are adequately stored, protected and secure. This is to be maintained throughout the works. The Contractor will repair/replace any panels/fittings that suffer damage or theft as a result of poor protection or security and costs shall be borne by the Contractor in such an event. Cost to include reinstatement, testing and certification upon completion of the below roof recovering works.
4.2.3 | All remaining fixings, roofing felt, etc are all to be removed and disposed of ensuring minimal disturbance to the retained fabric.
4.2.4 | Carefully break out the enclosed verge detail to the gable elevations of the Lounge to enable an overhanging verge detail to be installed (See item 4.2.10). All broken out material is to be disposed of.
4.2.5 | When all structural roof elements (rafters, purlins etc) are exposed, the Contractor is to inspect their condition and advise the Contract Administrator of any defective (i.e., rotten, insect attack etc.) areas that require repair or replacement. The extent of works to the structure will be subject to these further investigations and their findings.
4.2.6 | Allow the provisional sum of £750.00 to remove/repair/replace all defective structural roof timbers identified in the above investigations. | 750 | 1 | 750
4.2.7 | Supply and install the Tyvek Supro Breathable Membrane in accordance with Specification Clause H62/240 and manufacturers guidance.
4.2.8 | Supply and install new eaves ventilation and treated softwood battens in accordance with Specification Clauses H62 and manufacturers guidance.
4.2.9 | Supply and install a new natural slate covering and ridge tiles to match those installed to the Garage. The natural slates are to be installed in accordance with Specification Clause H62/275. The Contractor is to submit proposals to the CA prior to order.
4.2.10 | During the above recovering, the Contractor is to implement a new mortar bedded verge with a natural slate under cloak in accordance with Specification Clause H62/455. Slates are to be butt jointed and fixed riven side up. Mortar for bedding; 1:3 cement/sand pigmented to match colour of slates.
4.2.11 | Install 270mm of Knauf glass mineral wool insulation between and over the ceiling joists. Specification reference P10/125.
4.3 | ROOF - WC/LOBBY & OFFICE
4.3.1 | When all structural roof elements (rafters, purlins etc) are exposed, the Contractor is to inspect their condition and advise the Contract Administrator of any defective (i.e., rotten, insect attack etc.) areas that require repair or replacement. The extent of works to the structure will be subject to these further investigations and their findings.
4.3.2 | Allow the provisional sum of £750.00 to remove/repair/replace all defective structural roof timbers identified in the above investigations. | 750 | 1 | 750
4.3.3 | For tender purposes, allow to supply and install 120mm of Thermapitch TP10 insulation between the existing rafters. Final insulation thickness is subject to confirmation of rafter depth upon opening up. Specification reference P10/140.
4.3.4 | Supply and install the Tyvek Supro Breathable Membrane in accordance with Specification Clause H62/240 and manufacturers guidance.
4.3.5 | Supply and install new eaves ventilation and treated softwood counter battens and battens in accordance with Specification Clause H62 and manufacturers guidance.
4.3.6 | Supply and install a new Eternit UrbanPro fibre cement roof covering in accordance with Specification Clause H30 and in strict accordance with manufacturers guidance.
4.3.7 | Leadwork Note: All lead weatherproofing details are to be installed in accordance with BS EN 14783 and BS EN 12588 and to BS 6915 and latest edition of 'Rolled lead sheet. The complete manual' published by the Lead Sheet Training Academy. Lead welding not permitted.
4.3.8 | Install new soakers and cover flashings to the 2nr side abutments using Code 4 lead.
4.4 | GARAGE ROOF
4.4.1 | Allow to replace 15nr slipped/damaged slates with new natural slates. The natural slates are to be installed in accordance with Specification Clause H62/275. The Contractor is to submit proposals to the CA prior to order.
4.4.2 | Carefully clean the loose moss/vegetation from the Garage roof using water and a soft bristle brush only.
4.4.3 | Temporarily remove the vertical hung slates to facilitate works access; allow to reinstate upon completion. Remove the existing defective lead flashing and redress using Code 4 lead.
4.5 | ROOF JOINERY & RAINWATER GOODS
4.5.1 | The existing timber fascia boards and UPVC rainwater goods throughout are to be removed and disposed of.
4.5.2 | Supply and install new UPVC fascia and 100mm half round gutters & downpipes to the relevant parts of BS EN 607 and BS EN 1462, Kitemark certified. Gutters are to be true to line and event gradient to prevent ponding or backfall. Position high points of gutters as close as practical to the roof and low points not more than 50mm below the roof. Align connections to below ground drainage. Fascia: White Guttering's & Downpipes: White
4.6 | WINDOWS
4.6.1 | Remove the existing timber frame windows including all ironmongery and fittings and dispose of.
4.6.2 | Install new PVCu windows and ironmongery within the existing openings. The opening arrangements are to match that of the existing. For pricing purposes the Contractor is to refer to Drawing PL_4101565_Bryher Fire Station_002_Proposed Floor Plan. The Contractor is responsible for confirming final sizes prior to order. Specification Reference: L10.
4.6.3 | Allowance to make good window openings externally where damaged and re-render with 20mm sand and cement render finish. Specification Reference: M20 110
4.7 | EXTERNAL PEDESTRIAN DOORS
4.7.1 | Carefully remove and replace the 2nr timber rain deflectors at the base of the doors. The Contractor is to inform the Contract Administrator of any rotten/decayed/defective timbers that require replacement.
4.7.2 | All existing painted timber framed doors and frames are to be redecorated using Dulux Trade Weathershield Exterior Quick Drying Gloss. Colour to match existing. Preparation and redecoration to be in strict accordance with manufacturer’s instructions and Specification Reference M60.
4.7.3 | Allow to ease and adjust existing ironmongery to the 2nr entrance doors to ensure effective operation.
4.8 | EXTERNAL GARAGE DOORS
4.8.1 | Cost Option A: Doors and frames are to be redecorated using Dulux Trade Weathershield Exterior Quick Drying Gloss. Colour to match existing. Preparation and redecoration to be in strict accordance with manufacturer’s instructions and Specification Reference M60.
4.8.2 | Allow to ease and adjust existing ironmongery to ensure effective operation.
4.8.3 | Cost Option B: Remove and dispose of the existing timber doors, frame and all associated ironmongery. Supply and install the Seceurosheifd 75 Traditional Shutter Tube door with solid galvanised steel slats, surface mounted wall switch and including crank handle. Website: https://www.arrowsecurityshutters.co.uk Contractor responsible for determining, designing and installing appropriate connections to facilitate the installation.
4.9 | EXTERNAL WALLS
4.9.1 | The Contractor is to include an allowance for cutting back vegetation surrounding the building to facilitate the below repair and redecoration works.
4.9.2 | Make good the render with 20mm sand and cement render finish where previously broken out to facilitate the implementation of the overhanging verges and removal of the airbricks to the Lounge. Specification Reference: M20/110
4.9.3 | The Contractor is to undertake isolated render repairs elsewhere prior to redecoration. Allow for the provisional quantity of 2m², in areas not exceeding 0.5m².
4.9.4 | To all previously prepared and decorated surfaces, allow to wash down and remove any mould and lichen by scraping and brushing. Apply 1nr coat of Dulux Trade Weathershield Multi-Surface Fungicidal Wash, followed by redecoration using 2nr coats of Dulux Trade Weatherfield Maximum Exposure Smooth Masonry Paint in accordance with Specification Reference M60 and manufacturer’s instructions. Colour to match existing.
4.1 | TIMBER FLOOR REPLACEMENT (Lounge & Store 2)
4.10.1 | To facilitate the below floor replacement, carefully remove the internal stud partition and door to Store 2. Set aside the door for reinstatement following the below works.
4.10.2 | Remove the timber suspended floor throughout the Lounge and Store 2 including skirtings, floorboards, joists and all associated fixtures and fittings and dispose of.
4.10.3 | Following the above removals, carefully break out the existing sleeper walls and dispose of.
4.10.4 | Carefully remove the existing airbricks and block up using masonry and mortar in a 3:1 mix.
4.10.5 | Excavate sub-soil to the reduced level and compact. The overall floor build-up is to achieve a level threshold with existing lobby and kitchen floor.
4.10.6 | Install clean, inert well compacted 150mm hardcore layer.
4.10.7 | Install 50mm sand blinding layer over hardcore. Sand for blinding in accordance with BS EN 12620.
4.10.8 | Install Visqueen R400 Radon Membrane over blinding in strict accordance with manufacturers recommendations using approved system components. Joints to have a minimum of 150mm overlap and sealed. DPM to be extended/lapped up the internal wall and fixed behind the skirting; ensuring enough excess is left that it can be accessed should it need to be lapped with a DPC in future. Ensure membrane is protected from sharp edges and damage to ensure required seal is achieved. Manufacturer: - Visqueen Product: - R400 Radon Membrane - Zedex CPT High-Performance Damp-Proof Course Contact: - Web: www.visqueen.com - Email: enquiries@visqueen.com
4.10.9 | Install 120mm of Thermafloor TF70 insulation above the DPM, ensuring a 25mm insulation strip is returned to the perimeter edges and is terminated above the proposed slab height.
4.10.10 | A 1200 gauage vapour control layer is to be installed, ensuring 150mm overlap between sheets and sealed with vapour tape. Turn VCL at wall upstands by concrete slab thickness.
4.10.11 | Install A252 reinforcement mesh on top of plastic (membrane safe) spacers to provide a 50mm minimum cover to concrete.
4.10.12 | Pour 150mm RC20/25 concrete mix and vibrate particularly around reinforcement to remove air bubbles and allow to cure.
4.10.13 | Pour self leveling screed in accordance with manufacturers guidance ready to receive vinyl floor covering.
4.10.14 | Re-construct new timber studwork to Store 2 where previously removed. Fix back to substrate and board with 12.5mm plasterboard including plaster skim finish. Plasterboard and plaster installation in accordance with Specification Clause K10.
4.10.15 | Install new MDF timber skirting to the Lounge and Store 2, to match size and profile of existing surroundings. Specification Reference: P20 200A.
4.10.16 | Reinstall the previously set aside door including frame, architrave etc, to Store 2 ensuring it is fully operational.
4.10.17 | Install new vinyl flooring throughout the Lounge and Store 2 in strict accordance with manufacturers recommendations and Specification Clause M50.
4.10.18 | Decorate new timber skirtings, door frames and architraves. Specification Reference: M60.
4.10.19 | Decorate new plastered internal partitions. Specification reference: M60
4.11 | FLOOR COVERINGS
4.11.1 | Re-seal the Lobby, Kitchen, Store 1 and Garage using Concrete Floor Sealer by Floorseal. Preparation and application to be undertake in strict accordance with manufacturers guidance. Colour to match existing.
4.11.2 | Apply Watco Step Marker anti-slip pain to the nosing's of internal step nosing's.
4.11.3 | Install new vinyl flooring within the WC and Office in strict accordance with manufacturers recommendations. Vinyl within the WC only is to be returned up the internal walls to create 100mm skirting upstand. Specification Clause M50.
4.12 | INTERNAL DECORATIONS
4.12.1 | Redecorate timber clad ceiling within the Lounge. Specification Reference M60.
4.12.2 | Redecorate ceilings and and walls throughout. Specification Reference M60.
4.12.3 | Redecorate all existing timber doors and frames and ease and adjust to ensure effective operation. Specification Reference M60.
4.13 | MECHANICAL, ELECTRICAL & PLUMBING (Contractors Design Portion)
WC
4.13.1 | Isolate, remove and dispose of existing wash hand basin, toilet, instaneous hot water heater and all of the above ground pipework including fixtures and fittings supplying these systems. NB: The mirror and toilet roll dispenser are to be set aside for reinstatement upon completion. Cost to include reinstatement.
4.13.2 | Design, supply and install new above ground hot and cold water supply and foul water drainage pipework to suit proposed the below sanitary appliances (positioning to be as previously removed). New pipework, fixtures and fittings throughout. Pipework to be copper and insulated. Hot water is to be provided to the handwash basin by localised electric point-of-use heater. Contractor to submit proposal for CA approval.
4.13.3 | Supply and install new Armitage Shanks Vitreous China Contour 21 Raised Height Closed Couple Pan Toilet (or similar approved) in accordance with manufacturers recommendations. Specification reference N13
4.13.4 | Supply and install new Armitage Shanks Vitreous China wall hung hand basin and chrome plated basin mixer taps (or similar approved) in accordance with manufacturers recommendations. - Sandringham 21 Handrinse Washbasin 45cm 1 Taphole - Water saving basin mixer taps Specification reference N13
4.13.5 | Design, supply and install a new direct extract fan within the WC. Extract fan to achieve a flow rate of 15l/s.
4.13.6 | Install new ceramic tile splashback to kitchenette walls. Spec Reference: M40 110.
Kitchen
4.13.8 | Remove the existing instatenous hot water heater and dispose of. Replace with new localised electric point-of-use heater to match that of the WC. Contractor to submit proposal for CA approval.
4.13.9 | Remove all blue MDPE pipework from above ground water distribution; replacing with copper. All pipework to be insulated.
General
4.13.10 | Supply and install replacement to plastic distribution board. Replace with metal fire resistant distribution board in line with BS 7671.
4.13.11 | Supply a backflow prevention valve to the external hose connection.
4.13.12 | Replace 4nr missing tubular light diffusers to the existing light fittings within the Kitchen, Store and Garage.
4.13.13 | Remove and dispose of the existing electric panel heaters within the Lounge and Office; replacing with modern alternatives that have the same (or higher) output.
4.13.14 | Design, supply and install replacement external low-energy LED lighting in line with BS 7671.
4.13.15 | Contractor to undertake testing and commissioning of installed services and provide relevant certification for documentation within O&M manual.
5 | CONTINGENCY
5.1 | A contingency of £15,000.00 has been allowed for any unforeseen works not already listed above. To be expended as required by the Contract Administrator. | Prov |  | 15000
6 | CONTRACTOR DESIGN ITEMS
6.1 | Provide cost for completing all design work on Contractors Design Portion mechanical and electrical works listed above.
7 | COMPLETION
7.1 | The Contractor is to make good any damage caused during the works.
7.2 | The Contractor is to remove all temporary protection and cart away.
7.3 | All work areas are to be left clean and tidy upon completion and all work areas and components are to be thoroughly cleaned.
7.4 | The Contractor is to dispose of any waste materials including cut offs and packaging.
7.5 | Collate and send all information required for the Health & Safety File to the CA two weeks before Practical Completion. Note: this information will be required in order for the CA to issue a Certificate of Practical Completion.
7.6 | The above is to include all warranties and commissioning certificates.
7.7 | Building Control final certificate, electrical certificate are to be obtained/provided prior to handover.
TOTAL ELEMENTAL BUILDING COST (To Main Summary) |  |  |  | 0
8
8
8
0
0
0