## Sheet1
Highways England Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Highways England Lorry Parking – Study 1 – Individual Site Assessment
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | Lorry Park Feasibility Studies | Sub Pin: | 9 |  | PIN No.: | Redacted
HE Reference: | SE 26 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.409 | Consultant Contact: |  |  | Redacted
Start & End Date: | 25/06/2018 - 29/10/2018 | CTO Authorisation No.
Task Overview
Overview A draft Highways England Lorry Parking draft scope study 1 v.1 was provided by Highways England on 24 May 2018. In summary: •Highways England has been asked by DfT to consider sites in its ownership that have the potential to be brought forward as lorry parking. •Highways England is taking forward 3 pieces of inter-related work to consider this: oStudy 1 - Individual site assessment: Site feasibility work on those sites initially considered by Highways England and not ruled-out as having the potential to be lorry parks in the future. oStudy 2 - Disposal Strategy: A disposal strategy for sites in Highways England ownership relevant to lorry parking. oStudy 3 - Strategic Spatial Planning considerations: A wider study looking at what, from a Highways England perspective, would constitute an appropriate location / size / scale for lorry parking. This would be something that could be used to inform strategic planning and input to strategic spatial planning. This CTO covers work elements related to Study 1 Individual site assessment. •It is proposed that the individual feasibility site studies are delivered through the regional spatial planning contracts. At this stage there will be 3 studies in South East and 1 study in Yorkshire North East. This work is being led by Network Planning Division within Strategy & Planning Directorate but procured via the SE Spatial Planning Contract. •The three study sites that form the basis of the SE assessment comprise: oChigwell, Essex – ex Olympics freight consolidation site oMerstham – Surrey (Reigate and Banstead) oGerrards Cross – Buckinghamshire Information Available •AECOM will support Study 1 with incorporation of the work and data they produced from the 2017 lorry parking audits, recently published by DfT. The following reports have been provided by Highways England: oLorry Parking Highways England Sites Review (DfT - September 2017) - The original piece of work done for DfT that looked across 16 sites. oLorry Park feasibility study – site summary Briefing Note – (31 May 2018) - A summary of the 4 sites being considered. This was recently prepared to support one of the Ministerial updates. •We have assumed Highways England will provide: oAccess to operational data held via CPS / DBFO contractor oAccess to the HAGIS system if required Methodology Following an Inception meeting we will produce a Project Plan, outlining project Governance, scope, key contacts, methodology, programme. Delivery of Study 1 will be a single report for Highways England that provides all the necessary elements of a pre-application / Feasibility study with regard the sites identified as possible lorry parks. AECOM will provide strategic spatial planning advice and reporting (not included in this fee proposal). A facilitated workshop(s) is to be programmed and arranged by Highways England in order to ensure all relevant information is considered at an early stage in order to guide initial findings. A single draft Initial Findings Report will provide an assessment for each site with specific details set out in the Task Brief (Highways England Lorry Parking draft scope - study 1 v.1): Milestone 1 - Physical Site Characteristics, Planning Factors Milestone 2 - Market Assessment, Financial Assessment, Indicative Layout Drawings (concept level design) Following receipt of Highways England comment we will produce a Final Findings Report.
Task Objectives and Milestones
Objectives •To establish if any of the identified SE region site are viable as potential lorry park locations. •To establish the likely planning context and requirements for site delivery. Milestones An indicative programme is outlined below (dates all week-beginning). This is not prescriptive but is intended to provide guidelines for key milestones, in particular for reporting back to DfT. •11th June: Commission starts •18th June: Inception meeting / call •25th June: Facilitated workshops •2-4th July: Initial findings •20th August: Final findings Assumptions To meet demanding timescales all three SE sites are to be analysed and progressed together. •Activation of Milestone 2 works by site to be agreed with the Highways England PM •The work does not require stakeholder engagement - key stakeholders are primarily Highways England, however, engagement with DfT and some regional delivery partners (LA’s) may be required. •No formal meeting facilitation is needed as a part of the commission – the facilitated workshop(s) will be handled within the Highways England team and are assumed to take place at Bridge House Guildford. The workshop could be a single session covering all three sites or one for each site. •Limited engagement is required with the NE lorry park site consultants (CH2M) - co-ordination will be via Strategy and Planning team lead (Redacted). •Where possible Highways England will further supply identified key site data and information via Operational teams (via Redacted). •There will be a probable need to identify the statutory planning process requirements for the development of each site i.e. whether by DCO or for progression via the Highways Act. •There will be value in analysing ‘previous use’ documentation if available – i.e. for Chigwell site consolidation reports (ODA) and / or for Merstham site. •Limited analysis of site development costs / BCR calculation will be possible – the work will probably have to be based on different development scenario assumptions. •For Air quality the scope is to identify existing AQ (e.g. AQMAs, monitoring data, Defra PCM modelled road links exceeding EU limit values) and constraints (e.g. nearby housing, other sensitive receptors) and recommendations for next steps. CONTINUED UNDER TASK OUTCOMES...
Task Outcomes
CONTINUED... •We have estimated expenses of £3,000 required to undertake C2 Statutory Undertaker surveys as well as nominal estimated expenses of £1,500 to cover travel costs associated with attendance of 5 staff at 3 workshops •No costs / provisions are assumed for: oGIS data and CAD mapping files access to be provided by Highways England or separate GIS team. oGeo technical surveys or bridge survey work. oNo vertical design required at this stage – horizontal alignments only – any gradient issues to be raised as risks/constraints only. In addition land referencing information is not priced for – we understand HA GIS should provide adequate land ownership data. We have access to specialist land referencing expertise but we have not assumed this is a requirement at this stage of this work. •Deliverables will be a Project Plan and an Initial and Final report (including one iteration each) to consider client comments. Any additional project related outputs that could require specialist graphics for presentational purposes would incur additional costs. •Site survey work will be desktop in nature (via use of HAGIS and other supporting sites for e.g. Google Earth , http://www.magic.gov.uk, and other sites for the assessment of noise, air quality, flooding etc ). Where necessary further analysis requirements will, with the agreement of Highways England be identified and investigated. Although at this stage unlikely to be required, any site visits and/or access could be possible for some sites via Highways England (operational leads) and could require additional budget. •AECOM work associated with Study 1 has not been included in this CTO. Outcomes • Highways England will be able to have an informed view on all the necessary elements of a pre application / Feasibility study with regard the sites identified as possible lorry parks. •For each site Highways England will be able to answer the question – Could there be lorry parking on this site?
Project Risk and Management
Risks •Our fee estimate assumes a 16 week programme. The programme is challenging and the indicative milestones will be confirmed in the Project Plan. •A risk register will be developed for each site as a means for managing the costs and challenges likely to be associated with site viability assessment. •It is possible that initial findings rule out any further work at a given site(s) which would result in a reduced scope of works. •Any additional work outside of the agreed scope could affect the project cost and programme. Any changes will be identified and agreed with Highways England as an early warning / change control. •No communications relating to the task should be sent outside of DfT, Highways England or identified contacts at AECOM & CH2M owing to the commercial and political sensitivity of this work. •Additional staff could be drawn onto the project (including from our sub-consultants WSP) to support specific tasks as required. All new staff will need to adhere to confidentiality requirements. •Reporting could be subject to multiple sets of comments from various Highways England stakeholders. For efficiency these comments need to be communicated centrally from Highways England using a comments and response log to ensure that all are addressed. •Insufficient data available to enable effective site surveying and analysis. •Lack of clarity re reporting requirements – note the opportunity to liaise with CH2M (we understand that they are undertaking the Doncaster site study in the north) to ensure knowledge transfer and consistency across projects. •Inability to test lorry park viability / operational issues. Management •Contract management – Chris Cary •Task management – Alistair Bradley •Project Director - Andy Cleaver •Project Manager / Assistant Project Manager – Alistair Bradley / Alex Pye •Physical Site works lead – Richard Clarke •Market Assessment lead – Graham James •Planning Factors lead – Sarah Wallis •Financial Assessment lead – Fayyaz Qadir A full breakdown of staff roles and responsibilities will be outlined in the Project Plan and will be shared within one week of project inception.
Project Title: | Highways England Lorry Parking – Study 1 – Individual Site Assessment |  |  |  | HE Reference: | SE 26 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 26 18/19ATK | 188415.14 | 0 |  |  | 188415.14 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 188415.14
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 188415.14
Total Project Fee Estimate |  |  |  |  | 188415.14
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Director | 201 | @ | Redacted | 22612.5
Redacted | Associate Director | 20 | @ | Redacted | 1663.8
Redacted | Director | 66 | @ | Redacted | 6050.22
Redacted | Planner/ Engineer | 334 | @ | Redacted | 14983.24
Redacted | Principal Planner / Engineer | 328 | @ | Redacted | 21615.2
Redacted | Associate Director | 128 | @ | Redacted | 10648.32
Redacted | Director | 24 | @ | Redacted | 2700
Redacted | Director | 253 | @ | Redacted | 23134.32
Redacted | Senior Planner/Engineer | 108 | @ | Redacted | 5671.08
Redacted | Principal Planner / Engineer | 36 | @ | Redacted | 2372.4
Redacted | Director | 45 | @ | Redacted | 4366.35
Redacted | Senior Planner/Engineer | 55 | @ | Redacted | 2768.15
Redacted | Planner/ Engineer | 40 | @ | Redacted | 1676
Redacted | Principal Planner / Engineer | 228 | @ | Redacted | 14110.92
Redacted | Technician | 256 | @ | Redacted | 6625.28
Date Produced: | 2018-07-23 |  | Works Total |  | Redacted
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  |  |  | 0
|  |  | Sub Total |  | Redacted
|  |  | Expenses |  | Redacted
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 145497.78