
PROVISION OF QUALITY ASSURANCE TO THE ARMED FORCES COMPULSORY DRUG TESTING (AFCDT) PROGRAMME
INDICATIVE PROCUREMENT TIMETABLE
Issue Advert (EOI/DPQQ)


25 Jun 19
Closing Date




25 Jul 19
DPQQ Evaluation

(2 Wks)
26 Jul – 9 Aug 19
Results/DEF 157



12 Aug 19
Issue ITT


(35 Days)
14 Aug 19
Site Visit






Clarification period/extension request


Response to clarification Q/Ext



ITT due




18 Sep 19
Reverse auction



N/A
Tender evaluation

(3 Wks)
19 Sep – 9 Oct 19
SMS approval




19 Sep – 9 Oct 19
Start standstill/award notice
(10 Days)
10 Oct 19
Standstill ends (11:59pm)


21 Oct 19
Contract entry




22 Oct 19
Lead-in


(3 Months)
23 Oct 19 – 31 Jan 20
Contract start




01 Feb 20
Contract expiry



31 Jan 23
Options (1 x 1 yr)






