## Batch Order Template
National Salt Saturator & Associated Equipment Assets Contract Batch Order Form (Lot 2)
To | Wintertech Systems
From | REDACTED
Contract Area | Contract 2 (South)
Batch Order Number | 3
Batch Order Name | East Region (Area 8) Sandy Depot
Agreement Number | 4103509
Agreement Line Number | TBC
Project Identification Number | 600588
Client Contact details for this Batch Order
Name | REDACTED
Address | Woodlands, Manton Lane, Bedford, MK41 7LW
Telephone | REDACTED
email | REDACTED@highwaysengland.co.uk
Health & Safety (only when CDM applies)
duty holders | principal designer |  |  | principal contractor
| REDACTED (Highways England) |  |  | REDACTED
pre-construction information | The site will be cleared and the old equipment will be disposed of by a contractor chosen by REDACTED. This will be under instruction from HE as part of their AD M&R Contract duties, and does not form part of this batch order. The site will be clear by November 2019 Drainage, water pipes and power will remain in situ, and no alterations or improvement works are required.
Part A - For completion by the Client
In accordance with both the Goods Information and Price Schedule you are hereby required to provide the following Goods. The Batch Order shall be undertaken in accordance with Para 1.2.7, Para 2 and the additional requirements detailed herein:
Description | For the supply and installation REDACTED 20,000 litre Salt Saturator with REDACTED 40,000 litre additional storage tank together with training and associated instruction manuals. To be located in the area as shown during the site visit on 17.06.2019 at Sandy Depot (area 8) In addition the supplier shall provide annual commissioning and decommissioning for each unit installed (REDACTED Saturator and REDACTED Brine Storage Tank) for a period of three years. A programme confirming the manufacturing, delivery and installation of required infrastructure is to be provided to the Client by the Supplier on return of task order.
Starting Date | 2019-09-26
Completion Date | 2019-10-10
Delay Damages per day | REDACTED
Summary of Order
Equipment Type | Size (x,000ltrs) |  | Quantity | Unit Price | Cost
Salt Saturator item 3 | 20000 |  | REDACTED | REDACTED | REDACTED
Storage tank item 9 | 40000 |  | REDACTED | REDACTED | REDACTED
Technical Advice 1 |  |  | REDACTED | REDACTED | REDACTED
Technical Advice 2 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 10 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 11 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 12 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 13 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 14 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 15 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 16 |  |  | REDACTED | REDACTED | REDACTED
Commissioning / Training 17 |  |  | REDACTED | REDACTED | REDACTED
Total Batch Order Value |  |  |  |  | 0
Signed (for the Employer) | Name: REDACTED |  |  | Date: 25/09/2019
Part B - For completion by the Supplier
Supplier |  | WinterTech Systems
Total of the Prices for the Batch Order |  | 80371.93
The Supplier's plan for this Batch Order is |  | Project Plan Rev A provided in PDF Format - "BATCH ORDER 003 (Lot 2) Sandy (6&8) - Project Plan Rev A.pdf"
The Supplier's additional comments for this plan/instruction |  | Although this batch order is treated as a single event in terms of the project plan provided, internally in WinterTech Systems, we will be running the associated batch orders 002 and 003 concurrently during the manufacturing stage and consecutively during the delivery, installation and commissioning phases. Gaps noticed in one project plan will be where works in being done in another plan.
Signed (for the Supplier) | Name: REDACTED |  |  | Date: 27/09/2019
Part C1 - For completion by the Client
I accept the above price and plan and instruct you to carry out the Batch Order. Please see attached Purchase Order
Signed (for the Client) | Name: REDACTED |  |  | Date: 27/11/2019
Or
Part C2 - For completion by the Client
I do not accept the above price and/or plan and you are not required to carry out the Batch Order
Signed (for the Client) | Name: |  |  | Date:

## Price List
National Salt Saturators Supply Contract - Price Schedule
| Tenderer's Name: | Wintertech Systems Ltd
The following items are Batch Order Goods that may be ordered by Purchaser's Instructions:
Lot 2 - South
REDACTED
Item no. | Item Description | Unit | Estimated Quantity | Rate £ | Amount
Note 1 | For all Saturator and Brine Storage Tank item descriptions below, the Supplier is to include for in the Rate the cost of all delivery and installation of necessary equipment, such as: pumps, control system and panels, all cabling, drainage and pipework services for the connection to existing services provided by others, frost protection, support steelwork, ladders, metalwork such as handrails, so as to provide operational equipment. The Supplier shall include in the Rate the cost of providing a three year warranty for each newly installed Saturator and Brine Storage Tank. This will commence from the initial commissioning date.
TECHNICAL ADVICE
1 | For each supplied saturator and brine tank installed, provide technical advice and liaise with the HE and HE employed third parties to programme and co-ordinate the timely installation of the new equipment, in accordance with the Goods Information (2.1.1) | Nr. | REDACTED | REDACTED | REDACTED
2 | For each supplied saturator and brine tank to be installed, provide to the HE a comprehensive specification document, that details all dimensions and services requirements for power, water and drainage, in accordance with the Goods Information. | Nr. | REDACTED | REDACTED | REDACTED
SATURATORS
3 | Provide and install fully operational Saturator with minimum capacity requirement of 20,000 litres but not exceeding 24,999 litres in accordance with the Goods Information, at various Area locations. | Nr. | REDACTED | REDACTED | REDACTED
STORAGE TANKS
4 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 10,000 litres but not exceeding 14,999 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
5 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 15,000 litres but not exceeding 19,999 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
6 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 20,000 litres but not exceeding 24,999 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
7 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 25,000 litres but not exceeding 29,999 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
8 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 30,000 litres but not exceeding 34,999 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
9 | Provide and install fully operational Brine Storage Tank with minimum capacity requirement of 35,000 litres but not exceeding 41,000 litres in accordance with the Goods Information at various area locations. | Nr. | REDACTED | REDACTED | REDACTED
COMMISSIONING / TRAINING
10 | Provide set of manuals consisting of: two hard copies and one electronic PDF format of instructions manual and operation / maintenance manual and repair manual for each salt saturator at various Area locations, in accordance with the Goods Information. | Manual Set | REDACTED | REDACTED | REDACTED
11 | Provide commissioning on an annual basis of any size, newly installed saturator and associated equipment in accordance with the Goods Information, Switching on for winter period. | Nr. | REDACTED | REDACTED | REDACTED
12 | Provide commissioning on an annual basis of any size, newly installed brine storage tank and associated equipment in accordance with the Goods Information, Switching on for winter period. | Nr. | REDACTED | REDACTED | REDACTED
13 | Provide annual de-commissioning of any size, newly installed saturator and associated equipment and provide associated report in accordance with the Goods Information, switching off for summer period or putting the unit into summer maintenance / store position. | Nr. | REDACTED | REDACTED | REDACTED
14 | Provide annual de-commissioning of any size, newly installed brine storage tank and associated equipment and provide associated report in accordance with the Goods Information, switching off for summer period or putting the unit into summer maintenance / store position. | Nr. | REDACTED | REDACTED | REDACTED
15 | Following installation and commissioning of new saturator or brine storage tank provide initial one day training Operational Training sessions for the HE and HE's Contractor's employees based at the various area locations in accordance with the Goods Information. | Training day | REDACTED | REDACTED | REDACTED
16 | Following installation and commissioning of new saturator or brine storage tank provide initial one day training Supervisor's Maintenance Training sessions for the HE and HE's Contractor's employees based at the various area locations in accordance with the Goods Information. | Training day | REDACTED | REDACTED | REDACTED
17 | Provide ad-hoc one day training sessions for the HE and HE's Contractor's employees based at the various area locations in accordance with the Goods Information. | Training day | REDACTED | REDACTED | REDACTED