## Tender Query Log
All queries received relating to the below tender will be logged and log re-uploaded to Contracts Finder with responses.
Please refer all queries to: James Hardy james.hardy@penzance-tc.gov.uk
Tender Name: | Coach House Conversion Tender
Tender Reference: | PTC-02-25
Published Date: | 06.03.2025
Deadline for Queries | 03.03.2025
Deadline for Responses | 07.03.2025
Version Number: | 1
Query Number | Date Received | Query | Response | Response Date
1 | 21.02.2025 / 24.02.2025 | Is there 3 phase electrical | 3 phase electrical will be installed for the building , outside the scope of the tender | 24.02.2025
2 | 24.02.2025 | Are there landscaping plans | Landscaping plans were included in the tender paackage. These were resent to the enquirer | 24.02.2025
3 | 27.02.2025 | Is there an asbestos report for the building | Asbestos report was added to the tender package on contracts finder and sent to all attending site visits | 27.02.2025 \ 06.03.2025
4 | Multiple | Will the roof need replacing | Expectation is that roof will be replaced - listed in tender package - two faces are asbestos tile and one face will require the install of a skylight - detailed in tender package | multiple
5 | Multilple | What access is there to the site? | Access will be through the rear gate of the park with access down lane (detailed in tender documentation) | multiple
6 | Multiple | Will the electrical panels for Penlee Centre require moving by contractor | The electrical panels will be moved outside of the confines of this tender, and therefore bidders do not need to cost for this | 06.03.2025
7 | Multiple | What drainage is there | CCTV drainage survey sent to all those who undertook site visit | 26.02.2025 / 06.03.2025