## Sheet1
WHEATHAMPSTEAD PAVILION
Tender Item Ref | Category | Schedule of Works | Comment | Tender Price
1 | Site strip | Erect Heras fencing as tree protection to north and east sides of proposed pavilion. Fencing to remain in position until Practical Completion
2 |  | Excavate over the footprint of the new building and cart away to east end of site no further than 50m
3 |  | Leave ready for piling contractor - no piling mat required
4 |  | Grade and spread excavated material mounds to an even profile
5 | External Works | Excavate for and lay 150mm consolidated hardcore and 600 x 600 precast concrete paving slabs to front and side of pavilion as shown
6 |  | Excavate for and lay 150mm consolidated hardcore and 600 x 600 precast concrete paving slabs to form disabled access ramp as shown
7 |  | Thoroughly sweep all hard surfacing to car park, prepare and white line car parking bays as shown, Disabled parking bays to be marked in yellow (Exclude overflow car park) | To be carried out by others | do not price | Planning requirement
8 |  | Provide and fix KeyClamp handrail to one side of ramp
9 |  | Provide and fix 5 x double wall mounted cycle racks as shown | To be carried out by others | do not price | Planning requirement
10 |  | Grade excavated rear and side areas to finished levels after completion of pavilion construction works. Leave ready for seeding/planting | To be carried out by others | do not price
11 |  | Planting | To be carried out by others | Do not price | Cost of trees and shrubs
12 | Utility Connections | Water and Electricty connections to be provided at the boundary of the site by relevent utility suppliers - Include here for common NJUG compliant Services trench to site boundary - Individual site service to be allowed for below
13 | Foul Drainage | Excavate for and lay 63mm MDPE as indicated on the sketch plan and site plan serving the pavilion and extending to new septic tank only for future connection if required
14 |  | Excavate for and form 2 no inspection chambers for connection of internal drainage. Supply and install medium duty covers
15 |  | Supply and delivery of a Clearwater Alpha 2800 litre septic tank
16 |  | Excavate for and install septic tank in accordance with manufacturer's recommendations inclusive finalisation of design and drain runs to drainage field
17 | Internal drainage | Supply and lay internal drains as shown inclusive of SVP and stub stacks with 4 automatic air vents ready for connection of internal waste pipes
18 | Rainwater | Excavate and lay 110 surface water drainage and gullies connecting 6 No downpipes to new soakaway
19 |  | Excavate for and form 2 No Polystorm crate soakaways totalling approx 5 3 cu m no closer than 5m to the building
20 |  | Note. Final location of soakaway to be determined on site |  |  | Design being finalised
21 | Water supply | Utilizing NJUG compliant trenching for drain, supply and lay 50mm MDPE pipe to connect pavilion to new metered supply by others |  |  | Possible omission
22 |  | Allow for pressure testing and chlorination of new pipe
23 | Electrical Supply | Excavate for and lay concrete base and entry ducting for electrical service chamber to be located adjacent to car park entrance. Make off connections internally and leave ready for main electric connection and meter installation by others |  |  | Possible omission of Energy Co brings supply direct into building
24 |  | Utilizing NJUG compliant trenching for drain, supply and lay 90mm dia SWA cable to connect pavilion to new service chamber |  |  | Possible omission of Energy Co brings supply direct into building
25 | Foundations | Piling Contractor to be directly employed and paid by the Client - Allow for coordination and supervision of piling contractor
26 |  | Cut down pile caps, excavate for and lay clayboard and form reinforced concrete ring beam as Structural Engineers details. | do not need to include - this will be part of the piling contractors scope of work |  | Final design still under review
27 |  | Supply and lay brickwork and concrete block up to and including dpc. Back fill with selected hardcore. All as per Structural Engineers drawing
28 | Floor | Allow for the design and installation of the beam and block suspended flooring as per the Structural Engineers drawing
29 | External Walls | External where clad walls to be 2 skins 100mm blockwork with solid 95mm cavity fill and ties at 450 vertical centres and 900 horizontal centres, staggered.
30 |  | Supply and install Catnic lintels over all new openings
31 |  | External walls to have render finish
32 | Roof trusses | Allow for the design, supply and delivery of timber roof trusses inclusive of all bracing, wall plates and holding down straps
33 |  | Lift into position and fix roof trusses as recommended by manufacturer
34 | Roofing | Supply and lay breathable roofing felt and treated timber battens
35 |  | Supply and lay Marley Modern interlocking concrete roof tiles in anthracite
36 | Sundries | Allow for forming penetrations and flashings for SVP at head of internal drain run
37 | Rainwater disposal | Supply and fix Alumac hoppers, gutters and downpipes to front and rear elevations
38 |  | Connect up rainwater downpipes to new drains leading to new soakaway as shown
39 | Internal Partitions | Internal blockwork partitions both sides of Club Training Room to be 100mm full height blockwork as shown to underside of finished roof covering inclusive of fire stopping
40 |  | Remaining partitions to be 90mm metal stud with solid Rockwool slab infill and 12.5mm plasterboard both sides or 75mm blockwork, plastered (Contractors choice)
41 | Ceilings | Supply and fix 12.5mm taper edge foil backed plasterboard taped and jointed to underside of roof trusses including all noggins
42 |  | Allow for cutting, forming and inserting 3 No proprietary roof access hatches
43 | Plastering & Screeding | All internal walls to be12.5mm plasterboard (moisture resistant in shower areas) taped and jointed
44 |  | Floor slab to have 100mm solid insulation
45 |  | Lay 80mm floor screed to all areas for inclusion of Under Floor Heating pipes by specialist contractor
46 |  | Note that changing room shower areas to have a minimum of 50mm fall from perimeter to shower gullies.
47 | Doors & Windows | Supply and install powder coated aluminium entrance doors inclusive of all ironmongery and glazing (D01 & D04)
48 |  | Note. External doors to have minimum clear opening of 864mm
49 |  | Supply and install 2 sets powder coated aluminium external double door, each leaf 900 wide as shown inclusive of frames, ironmongery and glazing
50 |  | Supply and install 7 powder coated high level opening aluminium windows as shown inclusive of frames, ironmongery and glazing
51 |  | Supply and install powder coated horizontal sliding aluminium window as shown to kitchen inclusive of frames, ironmongery and glazing
52 |  | Supply and fix solid core ply faced internal doors as shown inclusive of all frames and ironmongery
53 |  | Note. Internal doors D19 & D21 to have minimum clear opening of 864mm
54 |  | All doors to be lockable.
55 | Glazing | All windows and doors to have double glazed units with laminated safety glass all to relevant BS.
56 | Joinery | All skirtings included in flooring
57 |  | All architraves to be ex 50 x 25 pencil rounded and left ready for painting
58 |  | Provide 25mm bull nose window boards to all windows
59 |  | Allow the Provisional Sum of £1,000 for the supply and fix of kitchen units | Minimum Requirement (Sink Unit) |  | Required by Football Foundation
60 | Decorations | All ceilings to be white eggshell |  |  | Paint only
61 |  | All walls including to be magnolia eggshell paint finish
62 |  | All internal woodwork to have white gloss paint
63 |  | Supply and fix Altro Whiterock or equal approved 2mm white PVC wall cladding to all shower areas inclusive of 2 pack adhesive and all trims.
64 |  | Allow for Altro Whiterock or equal approved 2mm white PVC wall cladding to all splash backs above work tops and sinks inclusive of 2 pack adhesive and all trims.
65 | Electrical installation | Allow for the design and installation of electrical services by a specialist subcontractor inclusive of electric heating, fire and intruder alarm systems all as per the Schedule |  |  | Value Engineering can be discussed with appointed subcontractor
66 | Security alarm | Please show here the saving to be achieved if the security alarm system is omitted
67 |  | Allow for all builders work in connection with the electrical works
68 | Heat pump | Air source heat pump installation |  |  | Under review
69 |  | Allow for all builders work in connection with the ASHP works
70 |  | Underfloor heating installation |  |  | Under review
71 |  | Allow for all builders work in connection with the UFH works
72 | Plumbing installation | Allow for the plumbing installation by a specialist subcontractor all as per the Schedule
73 |  | Allow for all builders work in connection with the plumbing works
74 | Ventilation | Allow for the ventilation installation by a specialist subcontractor all as per the Schedule
75 |  | Allow for all builders work in connection with the ventilation works
76 | Other works not listed
Guards to 3no external doors
2no External door Security shutters
Kitchen shutter
shower cubicles
loft insulation
silicone
Removal of obstructions in ground inc. roots
PRELIMS
77 | Hoarding | Allow for maintaining for the duration of the project around the perimeter of the building, Heras style demountable hoardings double clipped together
78 | Compound | Allow here for providing all suitable offloading and storage facilities, The compound may be located on the car park area subject to making good on completion
79 | Welfare facilities | Allow for all welfare facilities to meet statutory requirements
80 | Other Prelims | Allow here for any other prelims and provide a full breakdown of the costs. |  |  | Assumes free use of water and electric on site
skips
Skips, Clearing & cleaning
scaffold
deck scaffold
telehandler
Site set up
Supervision
Distribution
Plant
Temporary services
Protection
Total Sum of Prices