## Table 1
Beaconsfield public Toilet Refurbishment Costing Document |  |  | 2025-03-19
When costing the following document, please note the existing DDA WC is to be refurbished last and it will remain open to stall holders on market days only, or to allow them access to the portaloo would be appreciated. This being the case it is the contractor’s responsibility to keep access to a toilet clear of building supplies and accessible to traders on those dates.
All works to be carried out in line with Building Control/and all certification to be issued at the end of the project with O&M Manual. It is the contractors responsibility to liaise with the relevant authority and /or organisation for permits and permissions.
There will be time made available for all contractors to visit site prior to costing, please call Jeannette Buckle to arrange a visit. Full access to all of the site can only be gained via an arranged appointment.
Phase 1 - Toilet Works
Item | Description | Cost £ | Option Cost £
Demolition | Remove a small section of the front wall (Shown in Blue dotted on Drawing 5067-02 Rev C) and supply and install a new supporting steel where the external wall has been removed, the calculations of steel to be approved by Building Regs. The contractor is reponsible for obtaining this. | 0
| Remove internal walls shown in red on drawing 5067-02 Rev C. | 0
| Remove all existing sanitaryware and doors. | 0
| Remove all existing wall tiles where needed. | 0
| Remove DDA door safety bollard from outside exsitng DDA WC and make good floor area. | 0
Electrical work | Relocate existing electrical cupboard to new location as shown on drawing 5067-02 Rev C. | 0
| All redundant wiring to existing services to be removed and new wiring installed where required. | 0
| All electrics to comply with current regulations and relevant certificates to be issued by the electrical contractor. | 0
Extraction | Supply and install Extraction system to all new toilets. | 0
Plumbing | Strip out and cap off redundant water supplies. | 0
| All new waste/services for the new sinks, toilets and urinal to run in service duct behind the cubicle IPS panels as shown on drawing 5067-02 Rev C. | 0
| Supply and Install 1 new 50L dora2050 water heater. Heater to be installed in the Storeroom as shown in the drawing. | 0
Flooring | Repair floor where needed after demolition works and screed all floors with self-levelling screed. | 0
| For the DDA toilet only the floor needs to be dug up and taken down to be a flat level entrance and made good ready to take flooring option A or B. | 0
| Option A – Supply and install Altro Classic R11 Anti Slip Flooring with coved skirting to all WCs. | 0
| Option B – Supply and install Altro Grip 1.25mm Resin to all WCs. |  | 0
| The new external floor area outside store / in front of unisex toilet shown on drawing 5067-02 Rev C requires ground preparation ready to take a resin floor. If an alternative hardwearing flooring solution is suggested please specify. | 0
| Paint store room floor with Anti Slip industrial floor paint. | 0
New walls | Make good exernal walls to accomodate new door arrangment to match existing walls. | 0
| New internal walls shown in pink on drawing 5067-02 Rev C to be either breezeblock or 100mm partitions systems with internal reinforcements to take all the fittings in agreement with building regulations. | 0
| New external walls shown in Orange on drawing 5067-02 Rev C to be brick to match existing. | 0
| Install new IPS walls to the rear of all WCs. Allow for removable access hatch for maintenance. | 0
| Storeroom walls to be made good. Please specify if leaving tiles and filling or other. | 0
Finishes | All existing walls to WCs to be made good after demolition. Then select following options: | 0
| Option A - Paint remaining walls that are not part of the IPS system. | 0
| Option B - All WCs to have IPS panels. |  | 0
| Option C - An alternative solution to remaining walls - please specify. | 0
| All finishes to comply with DDA Regulations and have appropriate 30 LV difference. All finishes to be approved by client and designer before ordering. | 0
Doors | All toilet doors including DDA to match. Supply and Install DDA weatherproof doors to the new DDA toilet. Please confirm type of external door and/or provide an alternative and specify. | 0
| Supply and install 3 new single weatherproof doors to small unisex WC, Male and Female WCs. Please confirm type of external door and/or provide an alternative and specify. | 0
| Supply and install external access door to the electrics cupboard. | 0
| Supply and install 2 new wide access/hospital weatherproof doors to Storeroom. | 0
| DDA door to have DDA approved door handles and latches.The 3 unisex, female and male toilet doors to be fitted with a vacant/engaged thumb latch. | 0
| Supply and install Coat hooks to back of all toilet doors. | 0
| All toilet doors need to be timer controlled, and self closing to ensure they shut after exiting. | 0
Ceilings | Make good ceilings after demolition works and remove existing lighting. Install new MF ceiling on hangers below existing wood ceiling within all toilet areas and Store (Unless upon site inspection/demolition there is good cause to remove the existing ceiling) All ceilings to be painted matt white. | 0
| Replace existing soffit and install new weatherproof ceiling to the outside of the smaller unisex WC and Store lobby and to the front overhang. Note - There are currently trickle vents in place in the existing soffit, if found to be redundant these do not need to be replaced in new soffit. Also note - You will need to move the gutter down pipe by the new DDA toilet to the left. | 0
Lighting | New LED Round backlight panels 12w 170mm diameter fittings to be installed within the new MF ceiling to all WCs and storeroom as per drawing. Lux levels to be checked to make sure compliant but to a level that will give minimum glare off the wall panels and reduce antisocial behaviour. | 0
| Lighting to be on a system set for a minimum of 20 minutes then to turn off ie PIR or other). Storeroom lighting to be switch controlled (See drawing for location of switch). Level of lighting to be set to make sure minimum glare off the wall panels. | 0
| New exterior grade white spotlights to exterior ceiling to be timer controlled. | 0
| New exterior LED wall lights to be installed as per drawing 5067-02 Rev C to run off the same timer as the exterior ceiling spotlights. https://www.lights.co.uk/p/lucande-led-outdoor-wall-light-akira-anthracite-metal-23cm-9617034.html | 0
Sanitary ware for DDA | Supply and install the following sanitaryware to the DDA toilet - Back to wall Doc M pack in Red including grab rails. Back to wall Toilet with with hidden cistern and push plate flush with red contrast buttons and red contrast toilet seat (no cover). DTUK24 Stainless Steel Twin Toilet Roll Holder. | 0
| Dementia Friendly wall hung basin & Taps with Red Edge detail such as Franke ANMW502-RED 550mm VariusCare wheelchair accessible washbasin. The tap to be similar to DTUK52 Dementia Friendly Basin Mixer Tap ie with red detail. | 0
| Dryflow EcoWave Hand dryer with HEPA Filter is Satin Finish. Dementia Friendly Soap Dispensor and 2 coat hooks to back of door at 2 levels. Alarm pull cord and exterior red Beacon. | 0
| Supply and install a wall hung baby changing unit and nappy bin. | 0
All dementia friendly products can be found on the following sites - https://www.disabled-toilets-uk.co.uk/dementia-bathroom-products-98-c.asp https://www.notjusttaps.co.uk/dementia-care.html
Sanitary ware for remaining toilets | To the remaining 3 toilets install – Ideal Standard i.lfe B Back to wall toilet with hidden cisten, push plate flush in chrome and WC Seat (no cover). | 0
| HBN 00-10 HTM64 (LB G M) Contour 21+ 50cm Back Outlet Washbasin and Contour 21+ Outline 1 Hole mixer tap. | 0
| Supply and install a cancelled waste urinal to the male toilet only. | 0
| Dryflow EcoWave Hand dryer with HEPA Filter is Satin Finish. | 0
| DTUK23 Stainless Steel Soap Dispenser and DTUK24 Stainless Steel Twin Toilet Roll Holder. | 0
| Option B to supply Dementia friendly sanitary wear as per DDA toilet - Back to wall Doc M pack in Red. Back to wall Toilet with with hidden cistern and push plate flush with red contrast buttons and red contrast toilet seat (no cover). |  | 0
| Each WC to have 1 no 400mm wide x 600mm high Mirror above sink. | 0
External works | Install new outside tap with drainer. Water to be drinkable and also used to fill a Bowser. 2 strong bolts to be fixed to wall to secure a chain for the Bowser. | 0
| Existing entrance gates need to be retained, as in a conservation area. Install a system mounted on the gates or underneath to enable at least one side to be on a timer to allow access to the public when the toilets are open, but no access when closed. Self closing at a set time when the toilets are closed for the evening.The gates or the other half of the gates need to be accessible to our grounds staff to open to allow wheelbarrows etc to the rear store. The overall aim is to automatically open and close the toilets without requiring staff to visit the site to unlock/close. Existing bollard lighting within the shrub beds to be on timers/sensors. | 0
Signage | For DDA supply and install Dementia friendly door signs to include the word 'toilet' and a picture of a toilet on the outside to include a disabled sign and baby changing sign. For the remaining 3 toilets to also include the appropriate symbols/words for male, female and unisex. Also for the DDA toilet a “Way Out / Exit” sign on the inside to the toilet door. | 0
| Supply and Install new dementia friendly sign to main entrance. Sign to have the word Toilet, a picture of a toilet and the opening times. Location of sign to be on or left side of gate (tbc). (Designs, material and colour for all signs to be approved with the designer before manufacture). | 0
Bench | Supply and install 1 new composite benches to form a seating area. https://www.earth-anchors.com/products#!/Forest-Saver-seat- 321/p/69605915/category=20528860 | 0
| Total Project Cost | 0 | 0