SCHEDULE 5:

MOBILISATION

| Version number | Issue Date | Comment |
| --- | --- | --- |
| 1.0 | February 2022 | Execution Version |

CONTENTS

1	Definitions	3

2	Purpose	6

3	Preparation for Service Period	6

4	Ramp-Up	8

5	Services Commencement	8

6	Availability of Prisoner Places	9

7	Practical Completion	10

8	The Mobilisation Assurance Plan	11

9	Initial Custodial Service Delivery Plan	13

10	Initial Operating Procedures	16

11	Approval of Operating Procedures	16

12	Reporting	17

13	Checkpoint Meetings	17

14	Stability Threat Assessment Meetings	19

15	Contractor's Staff Information	20

16	Authority Package of Support	20

Appendix 1 – Mobilisation Strategy	22

Appendix 2 –Glen Parva New Build Operator Interface Requirements	23

DEFINITIONS

For the purpose of this Schedule 5 (Mobilisation), unless the context otherwise requires:

| "Assurance Checklist" | means the assurance checklist set out in the Mobilisation Strategy at Annex D (Assurance Checklist) to the Mobilisation Strategy; |
| --- | --- |
| "Authority Package of Support" or "APOS" | has the meaning given in paragraph 16 (Authority Package of Support); |
| "Change Confirmation" | has the meaning given in Schedule 16 (Change Protocol); |
| "Checkpoint Meeting" | means the meetings required pursuant to paragraph 13 (Checkpoint Meetings) and section 2 of the Mobilisation Strategy; |
| "Construction Plan" | means the plan prepared by the Constructor setting out its fundamental activities in the management and execution of the Construction Contract Works; |
| "Delay Costs" | means reasonable, unavoidable, evidenced-based costs suffered in the Delay Period which are justified by supporting information and which are derived using the cost basis included in the Base Case; |
| "Delay Notification" | means a notice issued by the Authority to the Contractor that a Delay to Practical Completion is likely to occur (or that following an earlier such delay notice, a further delay is likely to occur) and providing an estimate of the expected Practical Completion Date and any resulting required revision of the Services Commencement Date; |
| "Delay Period" | means the period from the Original Practical Completion Date or any Revised Practical Completion Date to the expected Practical Completion Date (as applicable); |
| "Delay to Practical Completion" | means a delay to Practical Completion which results in the Practical Completion Date occurring later than the Original Practical Completion Date or any Revised Practical Completion Date (as applicable); |
| "Existing and Remedial Works" | has the meaning given in Schedule 11 (Property and Facilities Management); |
| "Glen Parva New Build Operator Interface Requirements" | means the document entitled 'Glen Parva New Build Operator Interface Requirements' set out in Appendix 2 (Glen Parva New Build Operator Interface Requirements) which provides further details about how the Prison will be handed over to the Contractor and the obligations of the Constructor with regards to any such handover to the Contractor; |
| "FF&E" | has the meaning given to it in Schedule 11 (Property and Facilities Management); |
| "Government Soft Landings" | means the Government strategy for ensuring a smooth transition from design and construction phase to the operational phase of a built asset including the completion of a post occupancy assessment to compare the required or projected performance outcomes with actual performance outcomes of the built asset; |
| "Initial Custodial Service Delivery Plan" or "ICSDP" | has the meaning given to it in paragraph 8.2.11 (Initial Custodial Service Delivery Plan); |
| "Local Security Strategy" | has the meaning given to it in Part 1 (Custodial Services) of Schedule 4 (Authority’s Custodial Service Requirements); |
| "MAP Approval Certificate" | has the meaning given to it in paragraph 9.3.1.1 (Approval of the Mobilisation Assurance Plan); |
| "MAP Notice of Non-Compliance" | has the meaning given to it in paragraph 9.3.1.2 (Approval of the Mobilisation Assurance Plan); |
| "MAP Reports" | has the meaning given to it in paragraph 9.4.1.1 (Updates to the Mobilisation Assurance Plan); |
| "Maximum Available Prisoner Places" | has the meaning given to it in Schedule 14 (Payment Mechanism); |
| "Mobilisation Action Plan" | has the meaning given to it in paragraph 16.1 of Annex D to the Mobilisation Strategy; |
| "Mobilisation Assurance Plan" | has the meaning given in paragraph 8 (The Mobilisation Assurance Plan); |
| "Mobilisation Strategy" | means the document entitled 'Prison Operator Competition Mobilisation Strategy' set out in Appendix 1 (Mobilisation Strategy) which details the key elements of Mobilisation that: (a) the Contractor shall comply with where the Prison is an Existing Prison; and (b) how the Authority requires Mobilisation to be carried out by the Contractor where the Prison is a New Prison; |
| "Mobilisation" or "Mobilisation Period" | means the period commencing on the Commencement Date and ending on either: (a) the completion of the Preparation for Service Period if an Existing Prison; or (b) the completion of the Ramp-Up Period (if a New Prison) and covers all activity undertaken by the Contractor to prepare to deliver, and then deliver, all Services within the Prison; |
| "Original Practical Completion Date" | means 31st January 2023; |
| "Preparation for Service Period" | means, in respect of New Prisons and Existing Prisons, the period between the Commencement Date and the Services Commencement Date; |
| "Ramp-Up Period" | has the meaning given in Schedule 14 (Payment Mechanism); |
| "Ramp-Up Rate" | means, in respect of any New Prison, the addition of forty (40) Available Prisoner Places per week; |
| "Revised Practical Completion Date" | means any date for Practical Completion later than the Original Practical Completion Date set as a consequence of an Authority Change resulting from a Delay to Practical Completion under paragraph 3.4 of this Schedule 5 (Mobilisation); |
| "Stability Threat Assessment Meeting" or "STAM" | means the meeting carried out in accordance with paragraph 14 (Stability Threat Assessment Meetings) and section 3 of the Mobilisation Strategy; and |
| "Transformation Plan" | means, in respect of Existing Prisons, the transformation plan prepared by the Contractor in accordance paragraph 8.3 (The Mobilisation Assurance Plan) that forms part of the Mobilisation Assurance Plan. |

PURPOSE

The Authority wishes to ensure that the Services to be delivered by the Contractor pursuant to the Authority's Requirements are mobilised in a timely manner that is safe, secure and decent for Prisoners, staff and delivery partners at all times.

This Schedule 5 (Mobilisation) sets out the various elements of Mobilisation, the phases of its delivery and the terms of support offered by the Authority when accessed by the Contractor to enable effective delivery of the Services.

PREPARATION FOR SERVICE PERIOD

Payment for the Preparation for Service Period shall be made in accordance with Schedule 14 (Payment Mechanism).

The Preparation for Service Period includes the following:

the period from the Commencement Date to the Practical Completion Date; and

the period from the Practical Completion Date to the Services Commencement Date.

Handover of the Site from the Constructor to the Contractor will take place on the Practical Completion Date.

For the avoidance of doubt, the Contractor acknowledges that the Practical Completion Date may be subject to amendment under and in accordance with the requirements of the Construction Contract, provided that Delay to Practical Completion shall be dealt with in accordance with the following provisions of this paragraph 3.4:

the Authority may from time to time provide to the Contractor information relating to the progress of the Construction Contract Works;

the Authority may, as part of the information provided under paragraph 3.4.1 or independent of it, issue to the Contractor a Delay Notification;

where the Authority issues to the Contractor a Delay Notification, such Delay Notification shall be accompanied by an Authority Change Notice pursuant to paragraph 4 of Schedule 16 (Change Protocol) which may include any proposed amendment to the Services Commencement Date as a result of the Delay to Practical Completion;

the Contractor shall respond to the Authority Change Notice issued under paragraph 3.4.2 in accordance with the Change procedure in Schedule 16 (Change Protocol), provided that the provisions of paragraphs 8.1.1 to 8.1.4, 8.1.9 and 8.1.10 (Estimates) of Schedule 16 (Change Protocol) shall not apply and the "Estimate" required to be submitted under paragraph 8 (Estimates) of Schedule 16 (Change Protocol) shall be in the form of the Base Case;

the Contractor's rights in respect of a Delay to Practical Completion shall be as determined pursuant to the procedure for an Authority Change and shall not be treated as a Compensation Event;

the Contractor shall take all reasonable and commercial steps to agree contracts with its staff and supply chain which exclude or minimise additional charges and/or costs resulting from a Delay to Practical Completion and/or any amendment to the Services Commencement Date;

any adjustment to the Base Case and/or Contract Price shall be in accordance with paragraph 12 (Adjustments to the Base Case and/or Contract Price Following Changes) of Schedule 16 (Change Protocol) and be determined by reference to the Base Case as an when accepted by the Authority pursuant to Schedule 16 (Change Protocol);

no Authority Change shall take effect in relation to a Delay to Practical Completion until a Change Confirmation is concluded in accordance with paragraph 11 (Implementation of Changes) of Schedule 16 (Change Protocol); and

the Authority may, at its option, request as part of the Authority Change that the Initial Contract Period may be extended to take into account a Delay to Practical Completion and/or any amendment to the Services Commencement Date if it considers that such extension would provide a better economic outcome for the Authority than agreeing to an Authority Change based upon the Expiry Date applicable at the date of the Delay Notice.

Notwithstanding any other provision of this Contract, from the Practical Completion Date until the Services Commencement Date the Contractor will be responsible for:

the Required Insurance covering the responsibilities and liabilities of the Contractor during this period in accordance with Schedule 19 (Required Insurances) and Schedule 14 (Payment Mechanism);

the payment for utilities in accordance with Schedule 14 (Payment Mechanism);

the provision of facilities management services commensurate with the responsibilities and liabilities on the Contractor during this period and in accordance with Schedule 11 (Property and Facilities Management) which includes but is not limited to the following:

security of the Prison and the Site;

any required maintenance of the Prison and the Site;

cleaning of the Prison and the Site; and

undertaking the 'fit out' of Contractor-provided FF&E.

- The services described in this paragraph 3.5 shall be performed to an equivalent standard as is required for the performance of the Services under this Contract (save as otherwise specifically provided in this Contract).

RAMP-UP

This paragraph 4 (Ramp-Up) applies to New Prisons only.

The Contractor shall comply with the Ramp-Up timetable in Schedule 14 (Payment Mechanism).

The Contractor shall notify the Authority if additional accommodation will not or is unlikely to be available to meet the average Ramp-Up Rate over any one (1) Month period.

The Contractor shall add no more or less than twenty (20) Additional Prisoner Places above or below the Ramp-Up Rate in any one week without prior approval of the Authority.

The Authority reserves the right to pause or reduce the volume of new Prisoners transferred into the Prison.

Payment for Ramp-Up shall be made in accordance with Schedule 14 (Payment Mechanism).

SERVICES COMMENCEMENT

On and from the Practical Completion Date the Authority shall, subject to and in accordance with the terms and conditions of this Contract, hand over control of the Prison to the Contractor and the Contractor shall commence provision of the services in accordance with paragraph 3.5 (Preparation for Service Period) of this Schedule 5 (Mobilisation).

On and from the Services Commencement Date the Contractor shall, subject to and in accordance with the terms and conditions of this Contract, commence provision of the Services that have not already commenced pursuant to paragraph 5.1 (Services Commencement).

The Contractor shall measure its performance from the Services Commencement Date in accordance with Schedule 15 (Performance Mechanism) (including in respect of any Ramp-Up Period (if applicable)).

Subject to the provisions of paragraph 13 (Prison Specific Information) of Schedule 14 (Payment Mechanism), the Contractor shall at all times on and from the Services Commencement Date provide to the Authority no less than the Maximum Available Prisoner Places.

Subject to clause 12 (Compensation Events), the Authority may, by giving written notice to the Contractor, postpone the Services Commencement Date until the date specified in such notice provided that such postponement shall not be a Compensation Event if it is required as a result of an act or omission of the Contractor or as a result of a Delay to Practical Completion (which in the latter case shall be dealt with in accordance with paragraph 3.4 (Preparation for Service Period)).

The Authority shall ensure that any necessary Statutory Certificates in respect of the Prison are current and valid as at the Practical Completion Date.

In the event that, after the Practical Completion Date, the Existing and Remedial Works prevent the Contractor from commencing the relevant Services on the Services Commencement Date, the Authority may postpone the Services Commencement Date by a reasonable period to remove the obstruction preventing the commencement of the relevant Services.

AVAILABILITY OF PRISONER PLACES

A Prisoner Place shall not be capable of constituting an Available Prisoner Place until the Authority has approved all Initial Operating Procedures in accordance with paragraph 11.3 (Approval of Operating Procedures).

If a Prisoner Place has not satisfied the requirements at paragraph 6.1 (Availability of Prisoner Places) prior to the Services Commencement Date, the Prisoner Place in question shall not be deemed to be an Available Prisoner Place and the Contractor shall not be entitled to payment for such Prisoner Place until such time as the provisions of paragraph 6.1 (Availability of Prisoner Places) are satisfied.

PRACTICAL COMPLETION

The Contractor shall work collaboratively with the Authority and the Constructor to facilitate the efficient and effective handover of the Prison on the Practical Completion Date and enable the Constructor to deliver its obligations to the Authority under the Construction Contract.

The Authority shall procure the first Checkpoint Meeting includes attendance by a representative of the Constructor, as further detailed in paragraph 13.6.1 (Attendance at Checkpoint Meetings).

The Contractor shall, working in good faith with the Authority and the Constructor, ensure that the contents of the Mobilisation Strategy and the Glen Parva New Build Operator Interface Requirements are developed and incorporated into a memorandum of understanding as to how these arrangements will operate in practice.  The Contractor shall not act or fail to act where the relevant act or failure would:

cause, contribute to or otherwise give rise to any breach by the Authority of any of its obligations pursuant to the Glen Parva New Build Operator Interface Requirements; and/or

prejudice or lead to the diminution or loss of any other rights, entitlements or other benefits of the Authority under the Construction Contract.

In addition to the Mobilisation Strategy, the Authority shall ensure that the Constructor's Construction Plan is issued to the Contractor to provide details of completion and the proposed hand-over dates of all Buildings and support facilities.

The Contractor shall, working in good faith with the Constructor and Authority to ensure effective and efficient handover in accordance with Government Soft Landings contribute to a detailed programme of works for each building type including:

the Built Environment and M&E Assets Verification Report process;

commissioning for Contractor FF&E;

familiarisation training; and

system-specific training.

The Contractor shall be responsible for (including the Contractor ensuring that satisfactory facilities are available and that it provides reasonable assistance) facilitating access by the Constructor to any parts of the Site for any Constructor access for commissioning demobilisation activity or in order to undertake any Existing and Remedial Works.

Should any issues materialise between the Contractor and Constructor in implementing the Mobilisation Strategy and Glen Parva New Build Operator Interface Requirements which cannot be resolved between the Contractor and the Constructor, the Contractor shall immediately notify the Authority.  The Contractor shall act in good faith to resolve the issue with both the Constructor and Authority, complying with any requirements of the Authority to resolve the issue.

THE MOBILISATION ASSURANCE PLAN

Within one (1) Month following the Commencement Date, the Contractor shall provide to the Authority the Mobilisation Assurance Plan.

The Mobilisation Assurance Plan shall show all activities and milestones (including all key activities, critical activities and resources and any requirements of the Mobilisation Strategy) covering the whole Mobilisation Period and shall include at least the following Assurance Checklist headings as a minimum (as further described in Annex D of Appendix 1 (Mobilisation Strategy) of this Schedule 5 (Mobilisation)):

leadership, project governance and organisation;

risk governance/scheduled review meetings;

shared vision, respect, values and goals;

communication, partner and stakeholder engagement strategies (including community engagement and public relations procedures);

recruitment and retention during the Contract Period, including a resourcing plan for the entire mobilisation period;

organisational staffing requirements;

training, personal development and 'setting the right workplace culture';

delivery and any transitioning of ICT and documentation (in accordance with the requirements of Schedule 2 (Digital));

details on the mobilisation of the Property and Facilities Management Services (in accordance with the requirements of paragraph 11.1.3 (Mobilisation Period) of Schedule 11 (Property and Facilities Management));

Prison Industries and (where applicable) resettlement service plans for current and future (in accordance with the requirements of Part 3 (Prison Industries) of Schedule 1 (Authority’s Custodial Service Requirements));

operational and quality assurance requirements for the delivery of Custodial Services (in accordance with the requirements of Part 1 (Custodial Services) of Schedule 1 (Authority's Custodial Service Requirements)) including an initial plan detailing how the Contractor intends to prepare for providing and provide the Services during the Mobilisation Period (the "Initial Custodial Services Delivery Plan");

adherence to the National Security Framework (as applied through the Local Security Strategy);

first night, induction and discharge procedures prior to Prisoner arrival;

Third Party engagement;

Ramp-Up (if relevant);

Transformation Plan (if relevant);

provision of a safe, secure, and decent environment (safeguarding);

Mobilisation Action Plan; and

any Mobilisation activities provided by the Contractor and included within the Contractor's Proposals.

Where relevant, the Mobilisation Assurance Plan shall also include the Contractor's Transformation Plan. This shall detail the delivery and integration of the Contractor's Proposals for delivering improvements in efficiency and effectiveness of the Services from the Services Commencement Date. If required, the Transformation Plan shall also be prepared in accordance with the requirements of the Mobilisation Strategy.

The Contractor shall maintain the Mobilisation Assurance Plan and shall make copies available to the Authority at each Checkpoint Meeting and Stability Threat Assessment Meeting held during the Mobilisation Period. The Authority reserves the right to audit and request additional information regarding any element of the Mobilisation Assurance Plan (including the Transformation Plan) from the Contractor at any point during the Mobilisation Period.

INITIAL CUSTODIAL SERVICE DELIVERY PLAN

The Contractor shall provide to the Authority the Initial Custodial Service Delivery Plan for submission as part of the Mobilisation Assurance Plan pursuant to paragraph 8 (The Mobilisation Assurance Plan).

The Contractor shall ensure that the Initial Custodial Service Delivery Plan contains:

a staff handbook;

the dates by which the Initial Operating Procedures are to be delivered to the Authority's Representative as set out in paragraph 10 (Initial Operating Procedures);

the OSP Partnership and Enabling Plan, including any Partnering Agreements (including, for example, those entered into pursuant to clause 14.6 (Working with the Healthcare Provider, Social Care Service Provider and Probation Provider));

details of the requirements for training on the Authority's ICT System pursuant to clause 9.6 (Training);

the Contractor's plan on providing appropriate employment opportunities for certain Prisoners including Prison Industries, Prison Work and under ROTL (as further detailed in paragraph 2 (Aims and Objectives of Work in Prisons) of Part 3 (Prison Industries) of Schedule 1 (Authority's Custodial Service Requirements));

the Contractor's plan on the minimum number of Work Places (as such term is defined in Part 3 (Prison Industries) of Schedule 1 (Authority's Custodial Service Requirements)) (as further detailed in paragraph 5 (Prisoner Work) of Part 3 (Prison Industries) of Schedule 1 (Authority's Custodial Service Requirements));

the Contractor's plan on delivering the full Purposeful Activities offer to Prisoners, including an update to the details set out in Schedule 7 (Contractor's Proposals);

details of the Contractor's proposed incentives and earned privileges scheme (as further described in paragraph 6 (Performance Management and Incentivisation) of Part 3 (Prison Industries) of Schedule 1 (Authority's Custodial Service Requirements));

the Contractor’s plans to set up their Property and Facilities Management Services;

the Exit Plan; and

where applicable, the Contractor’s plan for Prison Industries and resettlement services for current and future Prisoners, to include a working Prison plan for each purposed industry/service, a plan for the set-up of each new industry/service to be introduced to the Prison, detailing the approach to steady state identifying activity arrangements. This shall include an update to the details set out in Schedule 7 (Contractor's Proposals).

APPROVAL OF THE MOBILISATION ASSURANCE PLAN

Within twenty (20) Business Days after receipt of the Mobilisation Assurance Plan, the Authority's Representative shall either:

issue a certificate (the "MAP Approval Certificate") confirming that they are satisfied that the Mobilisation Assurance Plan (and ICSDP contained within) is in accordance with the requirements of the Contract; or

issue a notice (a "MAP Notice of Non-Compliance") stating that the MAP Approval Certificate has not been issued, specifying the grounds on which the MAP Notice of Non-Compliance is based (provided that such grounds shall be one or more of those set out in paragraph 2.4 (Grounds for Amendment) and paragraphs 4.2.2.1 to 4.2.2.5 (Grounds of Objection) of Schedule 17 (Review Procedure)) and specifying any matters that must be attended to before the MAP Approval Certificate can be issued.

Following receipt of a MAP Notice of Non-Compliance, the Contractor shall attend to such outstanding matters referred to in the MAP Notice of Non-Compliance and shall deliver the revised Mobilisation Assurance Plan to the Authority within ten (10) Business Days after receipt of the MAP Notice of Non-Compliance so that the procedure in paragraph 9.3.1 (Approval of Mobilisation Assurance Plan) is repeated as often as necessary to ensure that all outstanding matters in relation to the Mobilisation Assurance Plan are attended to and the MAP Approval Certificate can be issued in accordance with paragraph 9.3.1 (Approval of Mobilisation Assurance Plan).

If the Parties are unable to agree the Mobilisation Assurance Plan, the Dispute Resolution Procedure shall apply.

Without prejudice to the Contractor's obligations pursuant to paragraph 5 (Services Commencement), no Prisoner Places shall constitute Available Prisoner Places until the Authority's Representative has approved the Mobilisation Assurance Plan.

UPDATES TO THE MOBILISATION ASSURANCE PLAN

The Contractor shall:

for the duration of the Mobilisation Period, produce progress updates ("MAP Reports") to the Mobilisation Assurance Plan each Month for each Checkpoint Meetings no later than one (1) Business Day in advance of each Checkpoint Meeting up to the end the Mobilisation Period; and

ensure that the MAP Reports contain details of the Contractor's progress against the Mobilisation Assurance Plan (and Initial Custodial Service Delivery Plan contained within).

The Parties acknowledge that the production of a MAP Report may require the Mobilisation Assurance Plan (and Initial Custodial Service Delivery Plan contained within) to be amended. If the Mobilisation Assurance Plan requires amendment, the Contractor shall:

amend the Mobilisation Assurance Plan accordingly; and

issue it to the Authority's Representative for approval,

and the procedure outlined in paragraph 9.3 (Approval of Mobilisation Assurance Plan) shall be repeated until the amended Mobilisation Assurance Plan is approved by the Authority.

INITIAL OPERATING PROCEDURES

- The Contractor shall provide to the Authority and the Authority's Representative details of each core operating procedure for each service requirement area contained in the Competition Operator Requirements ("Initial Operating Procedure") at least sixty (60) Days prior to the Services Commencement Date (or, if earlier, the date for delivery specified within the Initial Custodial Service Delivery Plan).

APPROVAL OF OPERATING PROCEDURES

Within twenty (20) Business Days after receipt of each Initial Operating Procedure, the Authority's Representative shall either:

issue a certificate (an "Operating Procedure Approval Certificate") confirming that they are satisfied that the Initial Operating Procedure in question is in accordance with the requirements of this Contract; or

issue a notice (an "Operating Procedure Notice of Non-Compliance") stating that the Operating Procedure Approval Certificate has not been issued, specifying the grounds on which the Operating Procedure Notice of Non-Compliance is based (provided that such grounds shall be one or more of those set out in paragraph 2.4 (Grounds for Amendment) and paragraphs 4.2.2.1 to 4.2.2.5 of Schedule 17 (Review Procedure)) and specifying any matters that must be attended to before the Operating Procedure Approval Certificate can be issued.

Following receipt of an Operating Procedure Notice of Non-Compliance, the Contractor shall attend to such outstanding matters referred to in the Operating Procedure Notice of Non-Compliance and shall deliver such revised Initial Operating Procedure to the Authority's Representative within five (5) Business Days after receipt of the Operating Procedure Notice of Non-Compliance so that the procedure in paragraph 11.1 (Approval of Operating Procedures) is repeated as often as necessary to ensure that all outstanding matters in relation to the Initial Operating Procedure are attended to and the Operating Procedure Approval Certificate can be issued in accordance with paragraph 11.1  (Approval of Operating Procedures).

Without prejudice to the Contractor's obligations pursuant to paragraph 5 (Services Commencement), no Prisoner Places shall constitute Available Prisoner Places until all of the Initial Operating Procedures have been approved by the Authority's Representative.

Once so approved, the Initial Operating Procedures shall constitute the Operating Procedures for the purposes of this Contract and shall be reviewed on an annual basis on every twelve (12) Month anniversary of the relevant date for the provision of such Initial Operating Procedure or as otherwise specified by the Authority in writing.

REPORTING

Based on the requirements of paragraph 13 (Utility (energy and water) Monitoring and Reporting) of Schedule 12 (Sustainability), and specifically in respect of the Mobilisation Period, the Contractor shall prepare a Monthly Usage Report (as such term is defined in Schedule 12 (Sustainability)) regarding utility consumption for each Building forming part of the Prison and the Site during the Mobilisation Period.

The Monthly Usage Report prepare pursuant to paragraph 12.1 (Reporting) shall be made available to the Authority each Month during the Mobilisation Period within fifteen (15) Business Days after the end of the previous Month.

CHECKPOINT MEETINGS

Checkpoint Meetings shall aim to ensure all Mobilisation work streams are on track to deliver the outputs and timescales set within the Mobilisation Assurance Plan and Assurance Checklist, in accordance with the MAP Report and provide information and advice to the Authority. Checkpoint Meetings shall not constitute an executive decision-making group and any decisions are made without prejudice to the Authority's rights and obligations under this Contract.

Checkpoint Meetings shall consider the outcomes of any other meetings held pursuant to this Contract during Mobilisation including those concerning the Healthcare Provider, Social Care Service Provider and Probation Provider pursuant to clause 14 (Working with the Healthcare Provider, Social Care Service Provider and Probation Provider).

Checkpoint Meetings shall be chaired by the Authority or a representative of the Authority.

The first occurrence of the Checkpoint Meeting shall take place no later than ten (10) Business Days after the Commencement Date.

Following the first Checkpoint Meeting, each subsequent Checkpoint Meeting shall take place on at least a Monthly basis throughout the Mobilisation Period.

Attendance at Checkpoint Meetings

The Authority shall procure that the first Checkpoint Meeting is attended by a representative of the Constructor and the aim of the meeting shall be to seek an agreed approach to managing the early engagement and Site handover (including activities relating to the commissioning and fitting of any FF&E in accordance with the Mobilisation Strategy and the Glen Parva New Build Operator Interface Requirements).

The Contractor shall ensure that each Checkpoint Meeting is attended, as a minimum, by the following individuals or representatives of the following parties:

the Director and any other persons responsible for Mobilisation;

the person responsible for human resources within the Prison;

the person responsible for Regime and activities within the Prison;

the person responsible for the relationship with drug service providers within the Prison;

the person responsible for the relationship with Healthcare Providers within the Prison;

the person responsible for the relationship with Social Care Services Providers within the Prison;

the person responsible for the relationship with Probation Providers within the Prison; and

the person responsible for the Property and Facilities Management Services within the Prison.

The Authority shall ensure that each Checkpoint Meeting is attended, as a minimum, by representatives of the following parties:

an Authority representative to chair the meeting and set the agenda;

the Controller; and

the Constructor.

As a minimum, the Checkpoint Meeting agenda shall cover progress against the Mobilisation Assurance Plan (including the ICSDP), and progress against the following contractual obligations:

Operating Procedures;

Contractor's key personnel (as set out in Schedule 6 (Contractor Key Personnel));

Equipment Register;

Built Environment and M&E Assets Condition Verification Report (including any construction manuals, BIM system documentation and warranties in respect of the Built Environment and M&E Assets); and

Contractor's Staff (pursuant to clause 36 (The Contractor's Staff), in particular clause 36.11 (Sufficient Contractor's Staff)).

STABILITY THREAT ASSESSMENT MEETINGS

Stability Threat Assessment Meetings aim to ensure the Contractor is supported during the Ramp-Up Period in accordance with the Ramp-Up timetable whilst maintaining a safe, decent and secure environment.

Each STAM shall:

be chaired by a representative of the Authority;

take place at least quarterly (every three (3) Months) throughout the Ramp-Up Period; and

monitor the stability and safety of the Prison during the Ramp-Up Period drawing upon whichever metrics and information is deemed relevant by the Authority.

The Contractor shall ensure that each STAM is attended, as a minimum, by the following individuals or representatives of the following parties:

the Director; and

the individual in the Prison responsible for security.

The Authority shall ensure that each STAM is attended, as a minimum, by the following individuals or representatives of the following parties:

an Authority representative to chair the meeting; and

the Controller.

Pursuant to clause 19.1 (Built Environment and M&E Assets Condition Verification) the Contractor shall inspect the Built Environment and M&E Assets at the Prison and Site and shall no later than thirty (30) Days after the Practical Completion Date provide to the Authority's Representative the Built Environment and M&E Assets Condition Verification Report.

CONTRACTOR'S STAFF INFORMATION

Pursuant to clause 13.5.1 (Contractor's Staff Information), at least three (3) Months prior to the Services Commencement Date, the Contractor shall submit to the Authority's Representative:

the names of, and such other information as the Authority's Representative may require about, the proposed members of the senior management of the Prison and all other persons requiring certification or approval, as specified in clauses 35 (Certification of Prisoner Custody Officers) and 36 (The Contractor's Staff); and

any other evidence reasonably required by the Authority's Representative to demonstrate that the Contractor is and will be capable of providing sufficient properly trained and certified Contractor's Staff,

## together the "Contractor's Staff Information".

AUTHORITY PACKAGE OF SUPPORT

Subject to paragraph 16.2 (Authority Package of Support), the Authority may make available certain packages of support (as further described in the Data Room document "APOS Offer for the new prison at Glen Parva" (the "APOS Offer")) (each an "Authority Package of Support" or "APOS"). These are:

Additional Vetting Support (as further set out in the APOS Offer); and

Priority Access to "FOCUS: Foundations of Custodial Success" Training Package (as further set out in the APOS Offer).

Pursuant to the Contractor’s Proposals, the Contractor shall:

not make use of the Additional Vetting Support (as described at paragraph 16.1.1) unless otherwise agreed by the Parties as a Change; and

be entitled to Priority Access to "FOCUS: Foundations of Custodial Success" Training Package (as described at paragraph 16.1.2), which shall be made available to one hundred and twenty-eight (128) operational support staff during the Ramp-Up Period.

APOS Charging Policy

The Contractor shall pay the Authority for the use of APOS as follows:

The Contractor shall pay the Authority or its sub-contractors for any use of APOS in accordance with the relevant charges and invoicing terms as set out in the APOS Offer.

Appendix 1 – Mobilisation Strategy

The Mobilisation Strategy is set out overleaf.

[Rest of page intentionally blank]

Appendix 2 – Glen Parva New Build Operator Interface Requirements

The Glen Parva New Build Operator Interface Requirements document is set out overleaf.

For the purpose of this Appendix 2, unless the context otherwise requires the term "Operator" means the Contractor and the term "Client" means the Authority.

[Rest of page intentionally blank]