Prison Operator Competition Mobilisation Strategy

February 2022

Contents

Statement of Purpose	3

Section 1: Mobilisation Overview	4

Section 2: Preparation for Service	6

Section 3: Ramp Up	12

Section 4: Mobilisation, Transition and Transformation (MTT)	16

Annex A to Prison Operator Competition Mobilisation Strategy: Glen Parva Practical Completion Strategy	18

Statement of Purpose	20

Section 1: Mobilisation Overview	21

Section 2: Preparation for Service	23

Section 3: Ramp Up	26

Annex A to Glen Parva Practical Completion Handover Strategy: Process Map - Asset Verification & Handover, Changes, Issues & Dispute Resolution	27

Annex B to Glen Parva Practical Completion Handover Strategy: Roles and Responsibilities:	28

Annex C to Glen Parva Practical Completion Handover Strategy: Key Meetings	29

Annex D to Prison Operator Competition Mobilisation Strategy: Assurance Checklist	30

# Statement of Purpose

The Prison Operator Competition Mobilisation Strategy sets out what is considered to be the key elements of successful prison mobilisation for new and existing prisons. Given that the second Mini-Competition is for a new Resettlement Prison at Glen Parva, this version of the strategy focuses more on the mobilisation of new prisons and should be used by bidders to assist the development of their mobilisation strategy and bid responses.  This document will be updated for future Mini-Competitions taking into account continued lessons learned and the need to focus more on Mobilisation Transition and Transformation where it relates to existing prisons. Our experience of mobilisation - both in the public and private sector - is that it is a critical time and is an inherently challenging period for new prisons, when many staff may be new and relatively inexperienced. The leadership team, officers and non-operational staff will all be adapting to the new site, at the same time as trying to create and embed a culture, regime and set of processes for the prison. In contrast, the prisoners that transfer in may be comparatively experienced and could seek to exploit teething issues in the regime. As such, mobilisation requires careful planning and monitoring to ensure the prison remains safe, decent and stable throughout.

For new-build prisons mobilisation comprises two phases – Preparation for Service (set out in section 2) and Ramp Up (set out in section 3). For existing prisons, mobilisation will form part of the previously-used Mobilisation, Transition and Transformation (MTT) approach set out in section 4. The appropriate focus and detail to be provided against assurance headings in the Mobilisation Assurance Plan should be tailored depending on whether the prison is new or existing.

Some of the content in this strategy is also set out as requirements in the mobilisation schedule in the call off contract. Others are recommended but non-mandatory features that we would expect to see covered in some way in a Mobilisation Assurance Plan. Although both the Mobilisation Strategy and Mobilisation Assurance Plan broadly set out the actions, we would expect the Operator and Authority to take during mobilisation, these should not be considered exhaustive.

The Contractor will be responsible for the successful mobilisation of the prison, but this strategy and the emphasis we have placed on successful mobilisation in the contract demonstrates that – possibly more than any other period in a contract’s lifecycle – it should be a period of close partnership between the Contractor and the Authority. The scheduling of regular checkpoint meetings, informed by equally close relationships with other delivery partners, should help to shape the development of the prison’s culture and allow a timely, joint response to issues as they arise. This approach has also influenced our thinking in respect of any Authority Package of Support which may be provided at each call off, details of which can be found in the competition data room ‘APOS Offer for the new prison at Glen Parva’ in the Glen Parva-specific documents section.

As part of the Authority’s internal handover during Mobilisation, the Authority shall make available to its ‘BAU’ operations team:

- all clarification questions submitted as part of the Glen Parva Mini-Competition;

- the Authority’s reviewed version of the Contractor’s operational assumptions;

- all relevant documents included on the Jaggaer (Bravo) data room site for the Glen Parva Mini-Competition; and

- a link to the ‘Viewpoint’ data room.

# Section 1: Mobilisation Overview

This section provides an overview of the mobilisation for a new prison, the key requirements within the mobilisation period and how the Authority will hold the Contractor to account through a Mobilisation Assurance Plan. Sections 2 and 3 then detail the actions expected to be seen in the distinct periods of mobilisation in a new prison.

These sections should also be read in conjunction with:

- Glen Parva New Build Operator Interface Requirements (appendix 2 to Schedule 5 (Mobilisation) of the call off contract); and the

- Glen Parva Practical Completion Strategy (Annex A of this document).

Both are needed to understand the full requirements of developing a coherent strategy if developing a bid for the new Resettlement Prison at Glen Parva.

Mobilisation Assurance Plan

Within one month of the Commencement Date the Contractor must provide the Mobilisation Assurance Plan. This will be the key document for managing the programme of work to successfully mobilise a full custodial and maintenance service. The Authority will monitor progress against the plan and will be a central consideration for Checkpoint meetings that will be established throughout the mobilisation period.

As a minimum, the Mobilisation Assurance Plan should set out the actions the Contractor will take under each heading of the Assurance Checklist at Annex D, along with timescales and resources. Sections 2 and 3 of this strategy give more detail on the two phases of mobilisation (including further detail on several key assurance checklist headings) and these should inform the production of the Mobilisation Assurance Plan.  The Mobilisation Assurance Plan will contain the Initial Custodial Services Delivery Plan.

Custodial Service Delivery Plans

Within one month of the Commencement Date, as part of the Mobilisation Assurance Plan, the Contractor is expected to have provided an Initial Custodial Service Delivery Plan (ICSDP) which will cover the whole period of mobilisation, until the prison is fully operational.

The ICSDP will include:

- The staff handbook

- The dates by which the Initial Operating Procedures will be delivered to the Authority's Representative

- The OSP Partnership and Enabling Plan, including any relevant Partnering Agreements (as well as including any emergency services contingency planning)

- Requirements for training on the Authority’s ICT System

- The Contractor’s plan to deliver appropriate employment opportunities

- The Contractor’s plan to deliver at least the minimum number of work places

- The Contractor’s plan on delivering the full Purposeful Activities offer

- The Contractor’s proposed Incentives Scheme

- Where applicable, Industries and Resettlement service plans for current and future

The Contractor will provide ICSDP Reports that give an update of progress against the ICSDP throughout the Mobilisation period. The appropriate focus and detail to be provided against each item in the ICSDP should be tailored to the type of mobilisation (i.e. whether the prison is new or existing).

Once the prison is fully operational, the Contractor will be expected to work to an Annual Custodial Service Delivery Plan (ACSDP). If the ICSDP is likely to continue into the start of a new Financial Year then the ACSDP should cover just the period of time after the prison becomes fully operational.

In addition to items (i) and (iii) of the ICSDP, the ACSDP will cover:

- Operating Procedures, along with proposed review dates

- The public relations procedures

- Annual Interventions Plan

- Annual Interventions Costs

- Annual Resourcing Plan

- The Exit Plan

- Sustainability Plan

- The overarching strategy for education and work

- Appropriate Prisoner Employment Plan

- Prisoner Work Plan

- Annual Purposeful Activity Plan

- Annual ROTL Delivery Plan

- Incentives Scheme

# Section 2: Preparation for Service

This section sets out the actions that are expected to be seen during the Preparation for Service phase of mobilisation. It is not exhaustive, and a Contractor may decide to approach certain elements differently to the way it is set out below. It is intended to demonstrate what elements make up a credible Mobilisation Assurance Plan, but not dictate how that plan should be delivered. It also sets out what the Authority will do to enable and support the Contractor to establish an effective custodial and maintenance service.

This section should also read – for Glen Parva – in conjunction with:

- Glen Parva New Build Operator Interface Requirements (appendix 2 to schedule 5 Mobilisation of the call off contract); and the

- Glen Parva Practical Completion Strategy (Annex A of this document)

Both are needed to understand the full requirements of developing a coherent strategy if developing a bid for the first call off at the new Resettlement Prison at Glen Parva.

Checkpoint meetings between the Authority and Contractor should commence early on in the Preparation for Service phase and will be used to plan and monitor activity, as well as identifying and rectifying issues as they arise. A Controller will be available from the start of the contract and they will also be able to work with the Contractor, MoJ Estates delivery teams and, where necessary, the Constructor to help keep progress on track.

2.1 Shared vision

An Operator and its suppliers should seek to develop a shared understanding of the core partnership values, transformation agenda and the benefits of early community engagement, specific to mobilisation. This will prevent a culture of silo working and ensure all stakeholders fully understand how their areas impact on mobilisation and the required outputs that need to be achieved.

Commitments should include: 
•    improving safety and security standards
•    increasing rehabilitation
•    reducing reoffending
•    transforming the nature of time spent in prison

And have a particular focus on: 
•    tackling suicide, self-harm and levels of violence

•    improving the recruitment and retention of prison custody officers and other staff
•    improving resettlement outcomes and lowering reoffending rates.

Authority actions:

HMPPS will provide clarity on its organisational priorities and engage with potential operators to detail our values, shared vision and the significance of added value in the new prison design and how this is expected to be operated within a resettlement regime. We will test how well these values and priorities have been applied when evaluating proposals.

Contractor actions:

Develop values in line with the prison transformation agenda and develop a shared vision and understanding of a resettlement prison design which would showcase the importance of providing a resettlement culture within all aspects of delivery, including early engagement with the local community and the benefits this can bring.

2.2 Leadership

Authority actions:

A dedicated controller will be in place and available from the point of contract award and a mobilisation lead will oversee the entire Mobilisation process (Preparation for Service and Ramp Up).

Checkpoint Meetings will be established shortly after the Commencement Date and will continue for the duration of mobilisation on an at-least-monthly basis (and probably more frequently at the start of mobilisation). They will be chaired by an Authority representative. This body will monitor the Mobilisation Assurance Plan as part of the Contractor’s ICSDP Reports, using the Authority’s assurance checklist to keep mobilisation on track.

Contractor actions:

Operators should provide evidence in their bids that leadership will be in place at the earliest opportunity from the contract being awarded. The Senior Management Team should be present on site from the earliest possible point in the mobilisation period.

Attendees with the right level of authority to cover key elements of the Mobilisation Assurance Plan will be expected to attend checkpoint meetings throughout the mobilisation period. This will include attendees with the relationships with partners in Health, drug services, emergency services and Local Authorities. Representatives from these third parties may be invited by the Contractor or Authority to attend checkpoints if appropriate.

Strong leadership is required from the start of the contract. Leaders in key posts need the experience and capability to build sound business infrastructure and operational processes, as well as inspire staff, to create a stable, safe regime that is balanced between control and rehabilitation.  Leadership needs to be established quickly and key Senior Management put in place well before officer recruitment to provide both consistency and accountability.

2.3 Recruitment and Retention

Authority actions:

As part of Authority Package of Support (APOS – see Data Room document “APOS Offer for the new prison at Glen Parva”), we will make available additional vetting support which may be drawn on by the Operator to help them ensure the vetting process for their staff is streamlined and not subject to unnecessary delays.

Contractor actions:

Operators will need to evidence in their bids how they have considered the geography and economics of the area demonstrating a clear understanding to the timeline of both its own and partner agency recruitment.

Prison Custody Officer recruitment will need to commence in good time before the Service Commencement Date. The Contractor will need to demonstrate in their recruitment planning how new prison custody officers will gain live experience and build confidence and resilience in their face-to-face interactions.

The Contractor should demonstrate how they will mentor and manage new staff. This should include how they intend to mitigate the risks of running a new prison with a potentially less experienced workforce. They should evidence strategies to embed a supportive culture that enables resilience to develop, with the intention that newly trained staff retention is high, and attrition is low.

The Contractor should demonstrate how they will mentor and manage experienced staff, whether recruited directly or brought in via a loan or secondment opportunity from an existing prison.  They should evidence strategies to embed a supportive culture that enables adaptation to this unique environment, with the intention that experienced staff retention is high, and attrition is low.

Staff profiles will need to have the right mix of experience to support delivery. Operators should demonstrate an understanding of what this means for different roles, and how they intend to meet this need.

Whether drawing on additional vetting support under APOS, employing similar support from another provider, or using a different approach entirely, the Contractor should demonstrate understanding of how their chosen provisions will ensure a robust approach to recruitment, vetting and training that mitigates potential challenges to avoid potential delays and deliver the required workforce ready and able to ramp up according to project timescales.

It is vital that Operators recruit, train and retain the right staff to deliver a good service. When mobilising a new prison all staff will require time to gain an understanding of their new surroundings and should help to form the culture of the site.  Recruitment and retention can be challenging, and other prisons have faced difficulties in retaining staff, especially when environmental or cultural issues have not been tackled.

The training and induction process should provide staff with the necessary knowledge and skills, ensuring all are aware of and bought in to the core values of the prison.  Both the operational and non-operational staff profile needs to include experienced staff and managers with the right skills to model the culture and mentor the less experienced. Supporting and developing staff is vital if the prison is to retain staff and keep attrition low.

2.4 Training and setting the right culture for a Resettlement Prison

Training and creating the right balance of culture between rehabilitation, control and security is essential to successful mobilisation ensuring that this culture is a key theme in all staff training. This balance should be the thread that links everything that staff do in their day-to-day interactions and interventions.

Themes for achieving the balance between rehabilitation culture and dynamic security:

- The attitudes and thinking that enable effective use of soft skills to:

  - Achieve a supportive rehabilitative environment

  - Maximise the use of dynamic security

- A focus on building staff-prisoner relationships with openness and transparency

- Staff professionalism (‘staff confidence and competence in the use of authority’)

- Opportunities for prisoners to exercise some degree of autonomy

- The importance of relationships and strong family links

- Forming or renewing positive, supportive relationships

- Strengthened community links and opportunities for prisoners’ self-development

- Preparation and support for release and resettlement

- Developing a pro-social identity, sense of purpose and self-determination

- The development and maintenance of hope and motivation

- Recognition and celebration of positive change

- Mental health awareness

Authority actions:

As part of the Authority Package of Support (APOS – see Data Room document “APOS Offer for the new prison at Glen Parva”), we will offer a foundation training package that is focused on preparing new staff of all grades and functions for the custodial environment, and embedding a balance between rehabilitative culture, security and control. This may be drawn on as part of a wider approach to training and induction.

Contractor actions:

The Contractor must evidence understanding that any training is a starting point, and should have a strategy in place for ensuring staff continue to develop the necessary knowledge, confidence and skills to enable resettlement outcomes introduced through any training course or exercise. They should identify and address any potential gaps in these essential attributes in their workforce.

The Contractor is responsible for ensuring that the training, induction and subsequent processes provide employees with the necessary knowledge, language, confidence and skills to enable resettlement outcomes. For Prison Custody Officers this includes the most up-to-date POELT training as a minimum, but also the capability of all operational and non-operational staff should be considered by the Contractor.

Whether drawing on training under APOS, using another existing training package or devising something new, the Contractor should demonstrate understanding of how their chosen provisions will provide employees with the necessary knowledge, language, confidence and skills to be developed on the job to enable resettlement outcomes.

  - Assurance

Post contract award, the Contractor will provide assurance on how mobilisation is progressing via updates against the Mobilisation Assurance Plan, including ICSDP Reports. This will enable emerging problems to be recognised and addressed in a timely manner. Assurance measures must be in place to support the achievement of the prison’s policies, values and targets at all levels. Annex D details delivery expectations at each milestone, ensuring:

- proper internal controls are in place

- that those controls are operating effectively

- key risks are being managed to enable the mobilisation of resettlement prison

- a formal early warning system alerts is in place to recognise emerging issues that may affect successful mobilisation.

Authority actions:

Provide Assurance Checklist milestone guidance for the readiness assessment document (see Annex D below).

Contractor actions:

The Contractor should provide readiness assessment information within agreed timescales, capturing robust evidence and achievements of all key milestones, giving consideration to both their internal and external supply chain, allowing additional time in order to rectify any issues before final sign off to go live is approved.

2.6 Engagement and communications

Throughout mobilisation the importance of strong working relationships within and beyond the prison between the Constructor and project/operational team are key.  Ensuring that communication remains an effective two-way process with the flexibility to address risk at its earliest opportunity.  The right people with the right levers need to be available throughout the mobilisation period.

Authority Action:

Consult early and often with potential operators to ensure all requirements are understood and agreed. Build relationships, support and provide transparency throughout the competition process and ensure actions are carried out in a timely manner.

Contractor action:

The communication expectation should be built into bids as part of the communication strategy, including attendance of required meetings and up-to-date completion of readiness assessments, ensuring that any key stakeholders and third-party engagement is also included. This communication expectation will be tested as part of the evaluation process.

# Section 3: Ramp Up

The Ramp Up phase will begin shortly after the Service Commencement Date and end at the point at which the prison can reasonably be considered to be at ‘steady state’, with all planned capacity made available for use. In the case of the new Resettlement Prison at Glen Parva, our assumption is that will be 10-12 months after the service commencement date (based on an average Ramp Up rate of 40 additional available places per week), but the actual end date will be agreed by parties at the Stability Threat Assessment Meeting (STAM) and signed off by the Authority.

This section should also read in conjunction with:

- Glen Parva New Build Operator Interface Requirements (appendix 2 to schedule 5 Mobilisation of the call off contract); and the

- Glen Parva Practical Completion Strategy (Annex A of this document)

Both are needed to understand the full requirements of developing a coherent strategy if developing a bid for the first call off at the new Resettlement Prison at Glen Parva.

3.1 Ramp Up Principles

Ramp Up is a key period where many of the risks of running a prison are more likely to manifest. Leaders and staff will be acclimatising to the new prison and the rhythm of the regime may take a while to settle. A proportion of staff is likely to be relatively new, and some prisoners transferred in may have more experience of prison life and seek to test new officers and processes. The experience of both operation and non-operational staff can impact on the sustainability of the Ramp Up rate in a new prison. Equally, teething issues with the regime may have an impact on individuals’ experience of the prison, the effects of which may be most acute with more vulnerable prisoners.

The Contractor and Authority will therefore need to be vigilant during Ramp Up to ensure that the prison remains safe, secure and decent as its population grows. If Ramp Up has to be scaled back in order to stabilise the regime then this is preferable to allowing problems to worsen, particularly as long term instability is more likely to have a sustained impact on capacity and pressure across the estate.

First impressions of the prison are vital and to a certain extent the Ramp Up plan could succeed or fail on the effectiveness of the reception function and first night centre. Similarly, the smooth running of the prison will rely on there being in place an initial cohort of prisoners able to deliver key functions.

We have established the following principles that should apply during the Ramp Up phase:

- The focus of Ramp Up should be on achieving stability, with the process supporting the ability of the Authority and Contractor to prevent rather than respond to serious disruption

- Overall site-level progress should be regularly monitored by stakeholders at the right level of authority, with a focus on progress against the Ramp Up plan as well as levels of security, order, control and stability

- The Authority and Contractor should be confident that they can be transparent about progress and risks throughout Ramp Up

- The Authority and Contractor should be able to instigate a pause in Ramp Up if the prison falls outside of performance tolerances – especially safety and security

- Operators should not Ramp Up at a rate that is unsustainable or puts performance (particularly safety) at significant risk.

Authority actions:

The Authority will work with the Contractor to ensure they can select some prisoners in early Ramp Up such as kitchen workers, peer mentors and listeners to establish these vital functions.

In addition to Checkpoint meetings, which will continue to meet at least monthly, Stability Threat Assessment Meetings (STAM) will convene at least quarterly throughout the Ramp Up phase and be chaired by an Authority representative. These meetings will allow the Authority and Contractor to formally assess the stability of the prison, drawing on metrics and operational intelligence to decide whether to pause, slow down or speed up the rate of intake to the prison. It does not replace the day-to-day dialogue on stability between the Director and Controller. An extraordinary STAM may be called by either party if circumstances demand a formal decision on Ramp Up.

Contractor actions:

The Contractor should work in partnership with the Authority by providing attendees with the right level of authority, covering the key membership requirements at both Checkpoint meetings and STAMs. They should take a flexible approach throughout the mobilisation period, identifying and communicating risk at the earliest opportunity that may cause a delay to Ramp Up or the Service Commencement Date.

The Contractor's Mobilisation Assurance Plan should include a Ramp Up schedule in line with the recommended Ramp Up principles. This should detail:

- sourcing of the initial cohort to fulfil critical hotel function; and

- approach to housing subsequent cohorts in line with proportions established by the resettlement prison model, including men convicted of sexual offences.

All partners and planned contracted services should be aligned to the planned Ramp Up and opening of the prison and engagement with Prison Escort Services will be essential.

Special emphasis should be placed on making sure staff are familiar with booking in processes relating to reception and first night induction.

3.2 Construction Handover

We want to ensure there is time and space for the Contractor to work closely with the Constructor to ensure that the prison is fitted out in line with how it will be used. The Preparation for Service phase will give the Contractor time to develop a good understanding of the building whilst parts of the building are being completed and to agree a programme for the operator to fit out the areas of the prison it is responsible for. The period between the Practical Completion Date and Service Commencement Date shall be used by the Contractor for the purposes of completing their fit out. Detailed Construction Handover processes are outlined in the Practical Completion Handover Strategy (Annex A of this document).

Authority actions:

The Authority will provide details of the Construction Plan and will ensure all manuals and warranties will be made available digitally on a platform compatible with end user requirements at the point of handover to the Contractor. This ensures safe systems of work can be put into practice accordingly from day one without delay and contribute to the requirements of Government Soft Landings.

Contractor actions:

The Contractor should be mindful when planning that handover will not be accepted without warranties being in place and the Contractor will need to agree a programme to fit out the areas of the prison it is responsible for.

3.3 Compatibility of ICT

Authority Actions:

Digital solutions will be available for NOMIS to be cloud based by 2021, allowing easier compatibility of ICT systems.

Contractor actions:

The Contractor will need to provide evidence that software is compatible with HMPPS IT systems (Quantum and NOMIS). The core offender record system – NOMIS – incorporates the new role of the key worker under Offender Management in Custody (OMiC).  Consideration should also be given to the installation and usage of all hardware and server requirements, including all third-party suppliers and partner agencies.

Incompatibility of ICT can cause delays to mobilisation. All IT and telecommunication systems must be operational and capable of performing the required functions ensuring they are also compatible and interpretable with HMPPS and any third partner agencies.

3.4 Other Service Providers

Authority Actions:

If the Contractor calls off HMPPS contracts, the Authority will give advance notice to partners/suppliers in order to allow for any "transition time" to a change in current contracts along with managing the increase in demand within the required lead-times.

Contractor actions:

Contractor to notify suppliers and place an order with sufficient warning as to when goods/services are required, ensuring that this is within the required mobilisation timelines.

If operators source their own suppliers for contracts, they must ensure they meet HMPPS required standards and lead times must be factored into the mobilisation timeline to ensure this does not impact on the Service Commencement Date.

# Section 4: Mobilisation, Transition and Transformation (MTT)

The mobilisation approach set out above will be significantly different for the mobilisation of an existing prison. In such cases the Contractor will not be building a new service from scratch but taking on an existing prison, usually without any gap in provision, and making the improvements in efficiency and effectiveness set out in their bid. Although the Contractor will need to go through a preparation for service phase, just as it would for a new prison, instead of a Ramp Up phase there will be a short period of transition from one contract to another and then a period of transformation as the Contractor implements the service it has set out in its bid. This structure will be needed even where the same provider as currently running the prison wins the contract as the contract will have been agreed on different terms.

Mobilisation (under MTT)

As with new prisons, the period of mobilisation starts at the point of Contract Award (Commencement Date) and ends when the prison makes available its full capacity. Unlike new prisons, we would expect a re-competed prison to be at full capacity on the Services Commencement Date, even if there will still be a brief period of transition after this point.

During this period, mobilisation will cover the planning and delivery of all activities that are essential to the successful handover and operation of the prison including the development and integration of all of the Contractor’s proposals for delivering the Contract requirements. As with all competed prisons, we will expect this to be set out in a Mobilisation Assurance Plan under the terms of the Initial Custodial Service Delivery Plan set out in the contract.

Transition

Under MTT, Transition is defined as the relatively short period spanning two weeks leading up to and two weeks after the Services Commencement Date, during which time the incumbent will hand over all essential services, property, assets, data and policy to the new Contractor to ensure a successful transition to the new contract. Although Transition is a relatively short period of time the successful implementation of the Transition phase is key to the whole handover process.

To fully understand the bidder’s proposals for this essential element of the handover process, the Authority needs an in-depth understanding of the Bidder’s proposals for this period.  Attention to detail will be vital to assure a successful handover.  The Transition period can best be explained and interpreted as holding a magnifying glass over the planning and delivery activities that surround the actual handover of the prison.

Due to the sensitive nature of some elements of transition, and the criticality of this period, the Authority needs to ensure there are robust management processes in place and that there is close dialogue between the Contractor and the Authority.

Transformation

The primary objectives of competition are to secure marked improvements in the efficiency and effectiveness in the delivery of custodial services at the prison, which lead to improved outcomes, including a reduction in re-offending.

The key element of Transformation will be the delivery and integration of the Contractor’s proposals for delivering these improvements in efficiency and effectiveness. To ensure these improvements last, it is essential that clear planning, organisation, coordination and management are in place during the Transformation phase to deliver these benefits. We would expect these plans for transformation to form a critical part of the Contractor’s first Annual Custodial Service Delivery Plan, building on the progress made in the Initial Custodial Service Delivery Plan submitted for the mobilisation phase.

# Annex A to Prison Operator Competition Mobilisation Strategy: Glen Parva Practical Completion Strategy

Glen Parva

Practical Completion Handover Strategy

February 2022

Contents

Statement of Purpose	3

Section 1: Mobilisation Overview	5

Section 2: Preparation for Service	7

Section 3: Ramp Up	13

Section 4: Mobilisation, Transition and Transformation (MTT)	17

Annex A to Prison Operator Competition Mobilisation Strategy: Glen Parva Practical Completion Strategy	19

Statement of Purpose	21

Section 1: Mobilisation Overview	22

Section 2: Preparation for Service	24

Section 3: Ramp Up	27

Annex A to Glen Parva Practical Completion Handover Strategy: Process Map - Asset Verification & Handover, Changes, Issues & Dispute Resolution	28

Annex B to Glen Parva Practical Completion Handover Strategy: Roles and Responsibilities:	29

Annex C to Glen Parva Practical Completion Handover Strategy: Key Meetings	30

Annex D to Prison Operator Competition Mobilisation Strategy: Assurance Checklist	31

# Statement of Purpose

This Glen Parva Practical Completion Strategy should be read in conjunction with:

- The Mobilisation Strategy (appendix 1 of schedule 5 (Mobilisation) of the call off contract)

- The Glen Parva New Build Operator Interface Requirements (appendix 2 of schedule 5 Mobilisation of the call off contract)

This document contains specific information relating to the completion and handover of the new build prison at Glen Parva. It sets out, at a high level, the following:

- Process for the handover of the new prison including asset verification (Annex A);

- Process for changes, issues and dispute resolution - this does not seek to alter or differ from the provision in each contract for dispute resolution (Annex A);

- Process for dealing with Construction Contract Works Defects following handover and during the life of the building (Annex A)

- Roles and Responsibilities for key parties in delivering mobilisation and the successful handover of the prison (Annex B);

- Key Meetings – a descriptor of key meetings, attendees and purpose during the mobilisation period (Annex C).

In addition, there will be a significant amount of documentation available to bidders in the competition data room under the Glen Parva-specific documents section which will help them not only develop their bids but gain an understanding of the build specification.

# Section 1: Mobilisation Overview

This section provides an overview of the mobilisation for a new prison, the key requirements within the mobilisation period and how the Authority will hold the Contractor to account through a Mobilisation Assurance Plan.

Sections 2 (Preparation for Service) and 3 (Ramp up) then detail the actions we would expect to see in the distinct periods of mobilisation in a new prison.

Key stages relating to the contractual requirements for the Contractor set out in the table below:

| Stage | Definition and key activities | Mobilisation Stage |
| --- | --- | --- |
| Commencement Date | - The point at which the contract is signed between the Authority and Contractor - Preparation for Service commences - Payment begins as per the payment schedule for Preparation for Service - Within one month, Contractor to submit their Mobilisation Assurance Plan (which includes their Initial Custodial Service Delivery Plan (ICSDP)) - Initial Interface Meeting between the Authority, Contractor and Constructor (agree MOU) - Agree the detailed programme of work by building type - Each programme of work will include: - Build programme and expected date of completion - Asset Verification inspection process - Building familiarisation process - System familiarisation process - Develop ‘train the trainer’ programme on the above processes. | Preparation for Service |
| Practical Completion Date | - The point at which the construction of the prison is complete, is verified by the Authority, is handed over to the Contractor, the lease commences and the Contractor assumes legal responsibility for the site - As outlined in schedule 5 Mobilisation of the contract the Contractor is responsible for: - The Lease of the property subject to schedule 9 Leases - Required Insurances commensurate with the responsibilities and liabilities on the Contractor during this period and in accordance with schedule 19 Required Insurances and schedule 14 Payment Mechanism - Payment of Utilities in accordance with schedule 14 Payment Mechanism - Provision of the Facilities Management Services in accordance with schedule 11 Property and Facilities Management which includes but is not limited to the following: - Security of the asset - Any required daily Maintenance of the asset - Cleaning of the asset - Fit out of Contractor provided FF&E | Preparation for Service |
| Service Commencement Date | - End of Preparation for Service - First day of ramp up and arrival of the first prisoner | Ramp up |

# Section 2: Preparation for Service

Preparation for Service for the new prison at Glen Parva will be delivered in two distinct phases, these are:

- Preparation for Service – Constructor Managed site (prior to Practical Completion)

- Preparation for Service – Operator Managed site (post Practical Completion)

A high-level process map for the process of handover and asset verification can be found in this document at Annex A.

2.1 Preparation for Service – Constructor Managed Site

Throughout the construction of the prison and up to the Practical Completion Date the Constructor is responsible for the site including but not limited to:

- Site security

- Site safety

- Site access

- Site construction as per the Contract

During this phase there is no right of general access by the Contractor and access to the site by the Operator will comply with the following:

- Access is agreed by all parties through the Interface meeting(s)

- Access is managed/controlled by the Constructor as reasonably required to ensure the security and safety of the site and all persons within it

- Attendance by the Operator or their representatives will not hinder the delivery of the Construction Contract

- Activity on the site undertaken by the Operator or their representative during this period will be subject to the agreement of parties through the Interface meeting(s)

During this phase a detailed programme of activity will set out the process and activity for the completion, verification and handover of each building type, system and finally the residual site. Whilst driven by the construction timetable, the detailed programme of activity should be agreed by parties through the Interface meeting(s).

Asset verification processes of a building or system type could commence as early as 12 months prior to the Practical Completion Date. The Operator should be prepared and able to discharge its responsibilities in relation to the asset verification and handover process in line with the timetable agreed through the Interface meeting(s). It is anticipated that any snagging issues should be identified and rectified within the asset verification processes. Though the Contractor will participate in the asset verification and snagging processes the responsibility and authority to accept works arising from the construction contract remain solely with the Authority.

Prior to Practical Completion the Operator’s responsibilities in relation to the site are:

- Contribute to the asset verification process; acceptance of the asset will be based on:

  - Assets meet the requirements specified in the Construction Contract;

  - Assets meet the required standards subject to any accepted derogations;

  - Assets meet the operational requirements; Where the build meets conditions 1 and 2 above the Contractor will accept the assets as meeting the operational requirements.

- Facilitate the training of agreed numbers of appropriate staff in relation to buildings and systems for the purposes of ensuring delivery of Government Soft Landings and the preparation of their facilities management and maintenance services

- Facilitate the orientation training of appropriate staff on a ‘train the trainer’ basis for the purposes of preparation of their custodial services

2.2 Preparation for Service – Contractor Managed Site

Post Practical Completion and handover of the prison the Operator is responsible for the site including but not limited to:

- Site security;

- Site safety;

- Site maintenance and cleaning;

- Site commissioning activity and ‘fit out’ of FF&E (Excluding Group 1 & 2). Details of FF&E provided under groups 1 & 2 can be found in the data room. The Contractor is responsible for all FF&E they require to deliver the services not listed therein;

- Delivery of BREEAM requirements (see BREEAM Contractor Requirements in the data room);

- Delivery of any planning requirements falling to the Contractor (see Contractor Planning Permission Requirements document in the data room);

- Legal and financial responsibility as per the lease and Contract requirements;

- Delivery of site-specific training for staff (orientation, systems and operations) (as per their mobilisation plan);

- Enabling third party access for FF&E ‘fit out’ i.e. NHSE provision of healthcare;

- Timely notification by the Contractor to the Authority of Construction Contract Works Defects; and

- Accommodating site access by the Constructor as required for demobilisation works, referred to as "Permitted Post-Completion Works" in the Construction Contract during the "Permitted PCW Period".

Access to the site by the Constructor or their representatives during this period and beyond the Services Commencement Date will comply with the following:

- Access will be granted by the Contractor for the purposes of the assessment or rectification of issues, snagging or Construction Contract Works Defects (Annex A contains high level process) in line with the proscribed timescales contained in table 1 below during the 104 week period following Practical Completion and during which the Constructor is required to rectify such Construction Contract Works Defects in accordance with the Construction Contract (and also during any further period that the Authority may notify to the Contractor from time to time);

- Access will be managed in accordance with the requirements of the contract with due regard to the safety and security of the site and all those within it;

- The Operator will not obstruct the Constructor access to the area(s) falling within that identified as ‘Permitted Post-Completion Construction Works’ in accordance with the Glen Parva New Build Operator Interface Requirements.

Table 1.

| Type of Defect | Rectification Period |
| --- | --- |
| "Routine Defects" (as defined in the Construction Contract) | - Rectify as soon as possible but no later than 28 days of notification by the Authority. |
| "Emergency Defects" (as defined in the Construction Contract" | - Rectify as soon as possible but no later than 48 hours from the notification of the Authority (noting that this period may be extended in certain circumstances in accordance with the terms of the Construction Contract where it is not possible for the Constructor to rectify such defect within this period but can make it safe as a temporary measure). |

# Section 3: Ramp Up

Ramp up commences on the Services Commencement Date and will be managed in accordance with schedule 5 Mobilisation of the call off contract and the Operators Mobilisation Strategy and Assurance Plan.

It is anticipated that the operator FF&E fit out will continue beyond the Services Commencement Date and the Contractor will be required to detail how it will manage and mitigate any risks associated with this.

The asset verification process is expected to identify [almost] all snagging issues and will be rectified by the Constructor during this process period. Any snagging issues identified by the Contractor after the Practical Completion and handover will be reported to the Authority who will liaise with all parties to facilitate rectification.

In respect of Construction Contract Works Defects the Contractor will comply with the requirements and timescales contained in the notification, access and rectification protocol detailed in the table 1 (contained in section 2 of this document) as set out in the Construction Contract and as notified by the Authority to the Contractor from time to time.

The contractual relationships with both the Constructor and Contractor are held by the Authority unless otherwise instructed.

# Annex A to Glen Parva Practical Completion Handover Strategy: Process Map - Asset Verification & Handover, Changes, Issues & Dispute Resolution

# Annex B to Glen Parva Practical Completion Handover Strategy: Roles and Responsibilities:

# Annex C to Glen Parva Practical Completion Handover Strategy: Key Meetings

# Annex D to Prison Operator Competition Mobilisation Strategy: Assurance Checklist

1.0 Leadership, project governance and organisation

1.1 Identify Key Leadership roles, experience and responsibilities providing evidence where required.

1.2 Identify the Contractor’s key individuals or roles to be present at meetings, including the Checkpoint and Stability Threat Assessment meetings.

2.0 Risk governance/scheduled review meetings

2.1 Mechanism to manage and monitor progress of mobilisation as well as providing a forum to identify/manage risks during that period of the contract.

2.2 Strategic, operational, communication and progress meetings are in place with Contractor and Authority during Phase 1 and Phase 2 of mobilisation process.

3.0 Shared vision, respect, values and goals

3.1 Develop the vision, values and goals of the prison to be communicated to all staff, stakeholders and 3rd party suppliers.

4.0 Communication, partner and stakeholder engagement strategies

4.1 Plan and produce internal and external communication and engagement demonstrating how all relevant parties will receive key communication.

5.0 Recruitment and retention during the life of the contract

5.1 Develop recruitment plan to meet the mobilisation timescales demonstrating a clear understanding of the geography and economics of the area and local employment market.

5.2 Develop retention plan, staff engagement and approach to achieve a balance mix of experienced staff with the right skill set.

6.0 Organisational staffing requirements

6.1 Plan and produce operating procedures and processes including performance evaluation.

7.0 Training, personal development and setting the right workplace culture

7.1 Delivery of training, real time experience and mentoring including mandatory training from HMPS outlining training to be delivered and timescales.

8.0 Delivery and transitioning of ICT (Compatibility)

8.1 Deliver and Transition ICT, which must be compatible with Authority's system.

8.2 The usage of ICT including telephony, E-mail and Video Conferencing systems.

9.0 Property, facilities and life-cycle management

9.1 Detail Facilities Management (FM) requirements and provide what is necessary to mobilise FM services within the prison during this period, including annual health checks.

9.2 Identify procedures to report hard and soft FM services - to include comprehensive hand-over and highlight any outstanding work.

9.3 Detail performance management and delivery management information.

10.0 Operational and quality assurance requirements for the delivery of custodial services

10.1 Develop the Initial Custodial Service Delivery Plan, including timelines for production of initial operating procedures and handbooks.

11.0 Adherence to the National Security Framework, (Local Security Strategy)

11.1 Adhering to National Security Framework, plan, produce and implement Local Security Strategy to ensure Public Protection, a Safe, Decent and Secure Environment is achieved.

12.0 First night, induction and discharge procedures prior to prisoner arrival.

12.1 Detail operational procedures together with timing and testing with third party providers, including full induction and security awareness training for all staff and 3rd party operators.

13.0 Third party engagement

13.1 Plan the approach for establishing and maintaining third party relationships, including who the critical partners are, anticipated outcomes (including reduction in re-offending and successful resettlement) and partnership working processes.

14.0 Ramp Up

14.1 Demonstrate transparent and flexible approach to Ramp Up, meeting the principles of the Authority's Ramp Up model (see section 2.1 of Mobilisation Strategy), identifying and communicating risks at the earliest opportunity.

14.2 Plan to manage and meet the initial required hotel function and subsequent cohort of prisoners throughout Ramp Up, reflecting mix of prisoners in line with the Resettlement model.

15.0 Provide a Safe, Secure, and Decent environment (Safeguarding)

15.1 Detail provision for prisoners at risk, foreign national prisoners, healthcare arrangements, substance misuse services and mental health services.

15.2 Detail provision for maintaining a safe, secure and decent regime and environment that supports health, well-being, rehabilitation and reduces re-offending.

16.0 Mobilisation Action Plan

16.1 Detailed Gantt chart timeline expanding on the MAP submitted as part of the bid, detailing every aspect of mobilisation delivery from contract award to service commencement including critical milestones and full interdependencies across the programme.

17.0 Any Mobilisation activities provided by the Contractor and included within the Contractor's Proposals