## Sheet1
ITT Clarifications Register
EFM015LTU | Clarifications IN |  | Clarifications OUT
Clarification reference number | Date received | Query | Date issued | Response
1 | Wed 24/04/2019 11:19 | Please can you let me know when we can meet up to take a look at the project | 2019-04-25 | Site visits will be hosted at 1000h on Wednesday 1st May. Please report to the main reception desk.
2 | University initiated | clarification required in tender timetable for site visits and to correct previous timetable discrepancy regarding days and dates not matching. | 2019-04-25 | A new tender timetable has been published. Please see attached. The timetable is also uploaded to the TenderDocuments section of the portal
End of ITT Clarifications v1
3 | University initiated | Revision to tender documents | 2019-04-30 | Tenderers are advised that five revised documents have been uploaded to the tender documents section of this website. The documents are LTU-DR-004A, 005A, 006A, 007A, and Schedule of Works Bede Works 2019, all annotated Rev A. Due to this, the tender deadline has been extended to 10.00am on Tuesday 28th May 2019. A revised timetable has also been added to the tender documents section of this website.
End of ITT Clarifications v2