## CWF Contractor Guidance
Guidance Notes
Application For Payment (AfP) Worksheet
Guidance Notes
1 | Select 'Application for Payment' from the drop-down in cell C5. The HE QS will change this to 'HE Assessment' when they return the certified amount.
2 | Complete all blue shaded cells in rows 7 -30
3 | For second/third etc applications ensure the previous certified figures are entered into Column K (Rows 36-50)
4 | Selecting Option E from cell E9 will remove pain/gain calculations from the bottom of the sheet
Cost Information Worksheets
1 | If additional rows are needed copy existing empty rows and paste underneath
2 | Choose an activity series from the drop-down for every cost item entered. This data is required for HE Cost Intelligence (ABS Analysis)
3 | For People costs enter names of people column B and the role of people column C
4 | Enter fee uplift on the 'People Staff' WS only. The other cost sheets will autopopulate
PAF Calculation
1 | Enter the agreed value of compensation events into tab 'EWs CEs'.
2 | Adjust task starting date in tab 'PAF Calculation' cell D5,D6 and D9. This can be done at any point from the 1st AFP onward but will only affect the final account.
C.Es Worksheet
1 | Will uplift the agreed target regardless of whether the CE is implemented yet. This is intended for interim application purposes only to ensure Contractors are not negatively affected by delay to agreeing C.Es.
PC Role Worksheet
1 | Enter agreed % on tab 'PC role' as necessary. This will only affect the final account.
Forecast Worksheet
1 | Enter forecast data. This will not affect any payment assessements but will be used to inform HE monthly business reporting.
Data Dump Worksheet
1 | To be used for Contractors own purposes. Eg Can be used to populate Cost worksheets using Vlookup/Sumif formula
Share Ranges Worksheet
1 | Autopopulated based on choices in drop-downs, used for Final Account calculations. Does not required any amendment or data entry.

## AfP
Application for Payment |  |  | use dropdown
Contract: | [5 empty] | enter manually
Scheme PIN No: |  |  | enter manually
NEC Option: |  |  | use dropdown
Principle Contractor:
Contractor: | [5 empty] | use dropdown
Lot No: |  |  | use dropdown
Contractor Task Order No: |  |  | enter manually
Contractor Task Order Value: |  |  | enter manually
Agreed CE Value: | 0 |  | lookup
Application For Payment No : |  |  | enter manually
Application Status: | Interim |  | use dropdown
Period End Date: |  |  | enter manually
Programmed Commencement Date: |  |  | enter manually
Actual Commencement Date: |  |  | enter manually
Programmed Completion Date: |  |  | enter manually
Actual Completion Date: |  |  | enter manually
Final Account | N/A |  | lookup
The following table shows the Suppliers Defined Cost incurred for Providing the Services to Date claimed by and assessed by the Service Manager in accordance with the Contract.
SCC Head | Applied |  | Disallowed |  | Assessed | Previously Certified | Change in Month
| lookup |  | lookup |  | lookup | enter manually | lookup
People - Staff | 0 |  | 0 |  | 0 | 0 | 0
People - Labour | 0 |  | 0 |  | 0 | 0 | 0
Equipment - Plant | 0 |  | 0 |  | 0 | 0 | 0
Equipment - Other | 0 |  | 0 |  | 0 | 0 | 0
Materials | 0 |  | 0 |  | 0 | 0 | 0
Charges | 0 |  | 0 |  | 0 | 0 | 0
Other & Subcontractors | 0 |  | 0 |  | 0 | 0 | 0
Sub-total | 0 |  | 0 |  | 0 | 0 | 0
Pain/Gain | 0 | 0 |  | 0 | 0 | 0 | 0
Gain share - released at final account only | 0 | 0 |  | 0 | 0 | 0 | 0
Pain Share - taken at interim & final | 0 | 0 |  | 0 | 0 | 0 | 0
Total | 0 |  |  |  | 0 | 0 | 0

## People Staff
A10 - Defined Cost - (People) Staff | [6 empty] | Fee
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
[7 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Staff Name | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## People Labour
A10 - Defined Cost - (People) Labour | [6 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[7 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Labour Name | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## Equipment Plant
A10 - Defined Cost - Plant | [7 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Plant | Company | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## Equipment Other
A10 - Defined Cost - Equipment | [7 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Plant | Company | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## Materials
A10 - Defined Cost - Materials | [7 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Materials | Company | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## Charges
A10 - Defined Cost - Charges | [7 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Charges | [7 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Charges | Company | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## Other and SubCon
A10 - Defined Cost - Other & Subcontractor | [7 empty] | Direct Fee | 0%
Note: Actual Cost Should Be In Accordance With The Schedule Of Cost Components
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[8 empty] | Applied |  |  | Disallowed |  |  |  |  | Assessed
MMHW Series | Other / Subcontractors | Company | CBS Code | Date | Rate | UoM | Quantity | Net Total | Fee | Gross Total | Quantity | Value | Fee | Total | Reason | Gross Total
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0

## CBS
Commodity Breakdown Structure (CBS)
CBS Code | Resource Type | Category | Sub Category | Description | Coverage and Guidance Notes | Unit
01.100.1000.10 | Labour | Directly Employed Labour | Directly employed unskilled Labour | Labourer/General Operative | Includes cleaner, gateman, groundworker, apprentices, etc. | hr
01.100.2000.05 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Security guard | includes CCTV monitoring staff, excludes traffic safety. | hr
01.100.2000.10 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Banksman |  | hr
01.100.2000.15 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Storesperson |  | hr
01.100.2000.20 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Concreter | Includes concrete finishers, "rubber-up" | hr
01.100.2000.25 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Fencer |  | hr
01.100.2000.30 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Pipe layer |  | hr
01.100.2000.40 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Kerb layer | Includes paver | hr
01.100.2000.50 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Plant operator | (machine driver) | hr
01.100.2000.60 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Scaffolder |  | hr
01.100.2000.70 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Welder |  | hr
01.100.2000.80 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Structural steel erector |  | hr
01.100.2000.90 | Labour | Directly Employed Labour | Directly employed semi-skilled Labour | Steel fixer | includes NIP hands | hr
01.100.3000.10 | Labour | Directly Employed Labour | Directly employed skilled Labour | Ganger |  | hr
01.100.3000.20 | Labour | Directly Employed Labour | Directly employed skilled Labour | Bricklayer |  | hr
01.100.3000.30 | Labour | Directly Employed Labour | Directly employed skilled Labour | Carpenter | (joiner) | hr
01.100.3000.40 | Labour | Directly Employed Labour | Directly employed skilled Labour | Plumber |  | hr
01.100.3000.50 | Labour | Directly Employed Labour | Directly employed skilled Labour | Electrician |  | hr
01.100.3000.60 | Labour | Directly Employed Labour | Directly employed skilled Labour | Skilled labourer unnamed | Skilled labour where trade is not given | hr
01.100.4000.10 | Labour | Directly Employed Labour | Directly Employed Labour Extra over Costs | Subsistence |  | LS
01.100.4000.20 | Labour | Directly Employed Labour | Directly Employed Labour Extra over Costs | Travel | includes mileage rates, fares, other travel costs | LS
01.100.4000.30 | Labour | Directly Employed Labour | Directly Employed Labour Extra over Costs | Overtime & Night working where paid or claimed as an extra cost |  | LS
01.200.1000.10 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed unskilled Labour | Labourer/General Operative | Includes cleaner, gateman, groundworker etc. | hr
01.200.2000.05 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Security guard | includes CCTV monitoring staff, excludes traffic safety. | hr
01.200.2000.10 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Banksman |  | hr
01.200.2000.15 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Storesperson |  | hr
01.200.2000.20 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Concreter | Includes concrete finishers, "rubber-up" | hr
01.200.2000.25 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Fencer |  | hr
01.200.2000.30 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Pipe layer |  | hr
01.200.2000.40 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Kerb layer | Includes paver | hr
01.200.2000.50 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Plant operator | (machine driver) | hr
01.200.2000.60 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Scaffolder |  | hr
01.200.2000.70 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Welder |  | hr
01.200.2000.80 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Structural steel erector |  | hr
01.200.2000.90 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed semi-skilled Labour | Steel fixer | includes NIP hands | hr
01.200.3000.10 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Ganger |  | hr
01.200.3000.20 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Bricklayer |  | hr
01.200.3000.30 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Carpenter | (joiner) | hr
01.200.3000.40 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Plumber |  | hr
01.200.3000.50 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Electrician |  | hr
01.200.3000.60 | Labour | Labour Only Sub contract or Agency Labour | Indirectly employed skilled Labour | Skilled labourer unnamed | Skilled labour where trade is not given | hr
01.200.4000.10 | Labour | Labour Only Sub contract or Agency Labour | Indirectly Employed Labour Extra over Costs | Subsistence |  | LS
01.200.4000.20 | Labour | Labour Only Sub contract or Agency Labour | Indirectly Employed Labour Extra over Costs | Travel | includes mileage rates, fares, other travel costs | LS
01.200.4000.30 | Labour | Labour Only Sub contract or Agency Labour | Indirectly Employed Labour Extra over Costs | Overtime & Night working where paid or claimed as an extra cost |  | LS
01.300.1000.10 | Staff | Staff | Project Management | Project Director |  | hr
01.300.1000.20 | Staff | Staff | Project Management | Project Manager | Includes all grade of Project / Programme Manager | hr
01.300.1000.30 | Staff | Staff | Project Management | Construction Manager (or Agent) | Includes Works Manager, all grades of Agent, etc. | hr
01.300.1000.40 | Staff | Staff | Project Management | Technology Integration & Commissioning Manager |  | hr
01.300.1000.50 | Staff | Staff | Project Management | Temp Works Co-ordinator |  | hr
01.300.1000.60 | Staff | Staff | Project Management | Planning Manager | Includes Senior Planner or Senior Planning Engineer | hr
01.300.1000.70 | Staff | Staff | Project Management | Planning Engineer | includes or grades of planner, programmer, Logistics Manager and the like | hr
01.300.1000.80 | Staff | Staff | Project Management | Safety Health & Environment Manager |  | hr
01.300.1000.90 | Staff | Staff | Project Management | Safety Health & Environment Trainer or advisor |  | hr
01.300.2000.10 | Staff | Staff | Design & Engineering | Design Manager | includes Design Co-ordinator | hr
01.300.2000.20 | Staff | Staff | Design & Engineering | Technology Design Integration Manager |  | hr
01.300.2000.30 | Staff | Staff | Design & Engineering | Senior Engineer | State type of Engineer. Includes all specialisms | hr
01.300.2000.40 | Staff | Staff | Design & Engineering | Engineer | State type of Engineer. Includes all specialisms and grades below Senior Engineer; includes technician grades | hr
01.300.2000.50 | Staff | Staff | Design & Engineering | IVQT Engineer | State type of Engineer or inspector. Includes Works Superintendent | hr
01.300.2000.60 | Staff | Staff | Design & Engineering | Survey Manager/Senior Land Surveyor |  | hr
01.300.2000.70 | Staff | Staff | Design & Engineering | Setting out engineer/land surveyor |  | hr
01.300.2000.80 | Staff | Staff | Design & Engineering | Chain man |  | hr
01.300.3000.10 | Staff | Staff | Site Supervision | Technology Commissioning Supervisor |  | hr
01.300.3000.20 | Staff | Staff | Site Supervision | Foreman | State type of Foreman / Supervisor | hr
01.300.3000.30 | Staff | Staff | Site Supervision | Traffic Safety Control Officer (TSCO) | Includes Traffic Safety CCTV staff | hr
01.300.3000.40 | Staff | Staff | Site Supervision | Occupational HealthNurse | Inc First Aider if full time occupation | hr
01.300.4000.10 | Staff | Staff | Commercial, QS & Accountancy | Commercial Manager | State grade | hr
01.300.4000.20 | Staff | Staff | Commercial, QS & Accountancy | Quantity Surveyor | State grade | hr
01.300.4000.30 | Staff | Staff | Commercial, QS & Accountancy | Buyer | State grade | hr
01.300.4000.40 | Staff | Staff | Commercial, QS & Accountancy | Accountant/Auditor | State grade | hr
01.300.4000.50 | Staff | Staff | Commercial, QS & Accountancy | Estimator | State grade | hr
01.300.4000.60 | Staff | Staff | Commercial, QS & Accountancy | Other Manager | includes Risk Manager, Performance improvement manager, Public Relations Manager, etc. State grade | hr
01.300.5000.10 | Staff | Staff | Administration, including IT & QA | QA Manager |  | hr
01.300.5000.20 | Staff | Staff | Administration, including IT & QA | IT Systems Manager |  | hr
01.300.5000.30 | Staff | Staff | Administration, including IT & QA | Office Manager |  | hr
01.300.5000.40 | Staff | Staff | Administration, including IT & QA | Administrator | includes Clerk, Typist, Secretary, Receptionist, Document Controller, Accounts Clerk, etc. | hr
01.300.5000.50 | Staff | Staff | Administration, including IT & QA | Admin Assistant | includes all other clerical roles | hr
01.300.6000.10 | Staff | Staff | Staff Extra over Costs | Subsistence |  | LS
01.300.6000.20 | Staff | Staff | Staff Extra over Costs | Travel | includes mileage rates, fares, other travel costs | LS
01.300.6000.30 | Staff | Staff | Staff Extra over Costs | Overtime & Night working where paid or claimed as an extra cost |  | LS
01.300.6000.40 | Staff | Staff | Staff Extra over Costs | Other Expenses |  | LS
01.300.6000.50 | Staff | Staff | Staff Extra over Costs | Professional Fees |  | LS
01.300.6000.60 | Staff | Staff | Staff Extra over Costs | Partnering Events |  | LS
01.990.1000.10 | Staff | Other | Other - people | Unallocated people | Include here new or otherwise non-standard items | LS
01.990.1000.15 | Staff | Other | Other - people | People not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories (e.g. gang rates) | LS
01.990.1000.20 | Staff | Other | Other - people | Arithmetic errors |  | LS
02.100.1000.10 | Plant and Equipment | Excavation Equipment | Excavators | 360o tracked or wheeled Mini excavator up to 3 tonnes |  | hr
02.100.1000.20 | Plant and Equipment | Excavation Equipment | Excavators | 360o tracked or wheeled Mini excavator3.01 - 6.00 tonnes |  | hr
02.100.1000.30 | Plant and Equipment | Excavation Equipment | Excavators | 360o tracked excavator 6.01 - 17 tonnes |  | hr
02.100.1000.40 | Plant and Equipment | Excavation Equipment | Excavators | 360o tracked excavator 17.01 - 26 tonnes |  | hr
02.100.1000.50 | Plant and Equipment | Excavation Equipment | Excavators | 360o tracked excavator 26.01 tonnes and above |  | hr
02.100.1000.60 | Plant and Equipment | Excavation Equipment | Excavators | 360o wheeled excavator 6.01 - 17 tonnes | i.e. Rubber duck | hr
02.100.1000.70 | Plant and Equipment | Excavation Equipment | Excavators | 360o wheeled excavator 17.01 - 26 tonnes | i.e. Rubber duck | hr
02.100.1000.80 | Plant and Equipment | Excavation Equipment | Excavators | 360o wheeled excavator 26.01 tonnes and above | i.e. Rubber duck | hr
02.100.1000.90 | Plant and Equipment | Excavation Equipment | Excavators | Excavator with integral breaker or pile cruncher or similar | To be used where excavator and attachment are not separated. State size of excavator. | hr
02.100.1000.95 | Plant and Equipment | Excavation Equipment | Excavators | Suction / vacuum excavator | (e.g. Vac Ex) | hr
02.100.2000.10 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Breaker attachment for Mini excavator up to 6 tonnes | State type of attachment | hr
02.100.2000.20 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Breaker attachment for excavator over 6 tonnes | State type of attachment | hr
02.100.2000.30 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Pile cruncher for Mini excavator up to 6 tonnes | State type of attachment | hr
02.100.2000.40 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Pile cruncher for excavator over 6 tonnes | State type of attachment | hr
02.100.2000.50 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Pallet fork adaptor for excavator over 6 tonnes | (includes kerb lifter). State type of attachment | hr
02.100.2000.60 | Plant and Equipment | Excavation Equipment | Excavator Ancillary Equipment | Other non-mechanical attachements | (e.g. ripper tooth). State type of attachment | hr
02.100.3000.05 | Plant and Equipment | Excavation Equipment | Loading Shovels | Tracked loaders up to 3 tonnes |  | hr
02.100.3000.15 | Plant and Equipment | Excavation Equipment | Loading Shovels | Tracked loaders 3.01 - 6tonnes |  | hr
02.100.3000.20 | Plant and Equipment | Excavation Equipment | Loading Shovels | Tracked loaders 6.01 - 17 tonnes |  | hr
02.100.3000.25 | Plant and Equipment | Excavation Equipment | Loading Shovels | Tracked loaders 17.01 - 26 tonnes |  | hr
02.100.3000.30 | Plant and Equipment | Excavation Equipment | Loading Shovels | Tracked loaders 26.01 tonnes and above |  | hr
02.100.3000.35 | Plant and Equipment | Excavation Equipment | Loading Shovels | Compact Wheeled loaders up to 3.00 tonnes | (e.g. Bobcat, skid steer) | hr
02.100.3000.40 | Plant and Equipment | Excavation Equipment | Loading Shovels | Wheeled loaders 3.01 - 6 tonnes |  | hr
02.100.3000.45 | Plant and Equipment | Excavation Equipment | Loading Shovels | Wheeled loaders 6.01 - 17 tonnes |  | hr
02.100.3000.50 | Plant and Equipment | Excavation Equipment | Loading Shovels | Wheeled loaders 17.01 - 26 tonnes |  | hr
02.100.3000.55 | Plant and Equipment | Excavation Equipment | Loading Shovels | Wheeled loaders 26.01 tonnes and above |  | hr
02.100.3000.60 | Plant and Equipment | Excavation Equipment | Loading Shovels | Wheeled loader with 180o backhoe excavator | i.e. JCB 2, JCB 3 | hr
02.100.4000.10 | Plant and Equipment | Excavation Equipment | Crawler Dozers | Small dozer up to 10 tonnes |  | hr
02.100.4000.20 | Plant and Equipment | Excavation Equipment | Crawler Dozers | Medium dozer 10.01 to 25 tonnes |  | hr
02.100.4000.30 | Plant and Equipment | Excavation Equipment | Crawler Dozers | Large dozers 25.01 tonnes and above |  | hr
02.100.5000.10 | Plant and Equipment | Excavation Equipment | Other Bulk Earthworks | Scrapers |  | hr
02.100.5000.20 | Plant and Equipment | Excavation Equipment | Other Bulk Earthworks | Graders |  | hr
02.100.6000.10 | Plant and Equipment | Excavation Equipment | Piling equipment - powered | Pile Boring auger machine | State type | hr
02.100.6000.20 | Plant and Equipment | Excavation Equipment | Piling equipment - powered | Pile Boring shell, auger, tripod, cables & pullies | i.e. gravity powered | hr
02.100.6000.30 | Plant and Equipment | Excavation Equipment | Piling equipment - powered | Pile Hammering / Extracting machine | State type | hr
02.100.6000.40 | Plant and Equipment | Excavation Equipment | Piling equipment - powered | Pile Cropping machine | i.e. hire of Machine(excavator) and attachment complete. State type. | hr
02.200.1000.10 | Plant and Equipment | Compaction Equipment | Plate compactors | Pedestrian operated vibration rammer or trench compactor up to 200 Kg |  | hr
02.200.1000.20 | Plant and Equipment | Compaction Equipment | Plate compactors | Pedestrian operated vibrating plate compactor (all sizes) |  | hr
02.200.2000.10 | Plant and Equipment | Compaction Equipment | Pedestrian guide rollers | Vibratory pedestrian operated single trench roller up to 600 mm wide | includes radio controlled rollers. State if sheep's foot type | hr
02.200.2000.20 | Plant and Equipment | Compaction Equipment | Pedestrian guide rollers | Vibratory pedestrian operated twin trench roller 601mm wide and above | includes radio controlled rollers. State if sheep's foot type | hr
02.200.3000.10 | Plant and Equipment | Compaction Equipment | Self propelled sit on rollers | Self propelled vibratory tandem rollers 800 - 1199 mm wide | e.g. Bomag 80. State if sheep's foot type | hr
02.200.3000.20 | Plant and Equipment | Compaction Equipment | Self propelled sit on rollers | Self propelled vibratory tandem rollers 1200 -2399 mm wide | e.g. Bomag 120. State if sheep's foot type | hr
02.200.3000.30 | Plant and Equipment | Compaction Equipment | Self propelled sit on rollers | Self propelled vibratory tandem rollers 2400 mm wide and above | e.g. Bomag 240. Includes three point roller. State if sheep's foot type | hr
02.200.4000.10 | Plant and Equipment | Compaction Equipment | Towed rollers | Towed Vibrating roller up to 7 tonnes | State type and size | hr
02.200.4000.20 | Plant and Equipment | Compaction Equipment | Towed rollers | Towed Vibrating roller 7.01 tonnes and above | State type and size | hr
02.200.4000.30 | Plant and Equipment | Compaction Equipment | Towed rollers | Towed dead weight roller | State type and size | hr
02.300.1000.10 | Plant and Equipment | Transport | Dumpers | Small dumpers 2 wheel drive | State capacity in Tonnes | hr
02.300.1000.20 | Plant and Equipment | Transport | Dumpers | Small dumpers 4 wheel drive | State capacity in Tonnes | hr
02.300.1000.30 | Plant and Equipment | Transport | Dumpers | Small dumpers 4 wheel drive side tipping | State capacity in Tonnes | hr
02.300.2000.10 | Plant and Equipment | Transport | Articulated Dump Trucks | Articulated dump trucks up to 23 tonnes |  | hr
02.300.2000.20 | Plant and Equipment | Transport | Articulated Dump Trucks | Articulated dump trucks 23.01 -32 tonnes |  | hr
02.300.2000.30 | Plant and Equipment | Transport | Articulated Dump Trucks | Articulated dump trucks 32.01 tonnes and above |  | hr
02.300.3000.10 | Plant and Equipment | Transport | Rear Dump Trucks | Rear dump trucks up to 23 tonnes |  | hr
02.300.3000.20 | Plant and Equipment | Transport | Rear Dump Trucks | Rear dump trucks 23.01 - 32 tonnes |  | hr
02.300.3000.30 | Plant and Equipment | Transport | Rear Dump Trucks | Rear dump trucks 32.01 tonne and above |  | hr
02.300.4000.05 | Plant and Equipment | Transport | Road Tipper Lorries | Tipper lorry up to 7.5 tonnes | include Transit tipper or similar | hr
02.300.4000.10 | Plant and Equipment | Transport | Road Tipper Lorries | Tipper lorry 7.51 - 20 tonnes |  | hr
02.300.4000.20 | Plant and Equipment | Transport | Road Tipper Lorries | Tipper lorry 20.01 - 30 tonnes |  | hr
02.300.4000.30 | Plant and Equipment | Transport | Road Tipper Lorries | Tipper lorry 30.01 tonnes and above |  | hr
02.300.5000.10 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Road Lorry up to 20 tonnes with or without lifting equipment | State type of equipment, e.g. Hiab crane, grab bucket, off-loading platform ( e.g. "beaver tail") | hr
02.300.5000.20 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Road Lorry 20.01 - 44 tonnes with or without lifting equipment | State type of equipment, e.g. Hiab crane, grab bucket, off -oading platform ( e.g. "beaver tail") | hr
02.300.5000.30 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Articulated lorry tractor unit with 12m trailer (up to 44t) |  | hr
02.300.5000.40 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Articulated lorry tractor unit with Low loader trailer (up to 44t) |  | hr
02.300.5000.50 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Trailer up to 10 tonnes |  | hr
02.300.5000.60 | Plant and Equipment | Transport | Other Road Lorries (inc trailers) | Trailer 10.01 tonnes and above |  | hr
02.300.6000.10 | Plant and Equipment | Transport | Tractors | Tractor up to 75 KW |  | hr
02.300.6000.20 | Plant and Equipment | Transport | Tractors | Tractor 75.01 - 92 KW |  | hr
02.300.6000.30 | Plant and Equipment | Transport | Tractors | Tractor 92.01 KW and above |  | hr
02.300.6000.40 | Plant and Equipment | Transport | Tractors | Add to tractor for trailer | State type | hr
02.300.6000.50 | Plant and Equipment | Transport | Tractors | Add to tractor for Hiab |  | hr
02.300.6000.60 | Plant and Equipment | Transport | Tractors | Add to tractor for fencing auger |  | hr
02.300.6000.70 | Plant and Equipment | Transport | Tractors | Fresco broom |  | hr
02.300.7000.10 | Plant and Equipment | Transport | Vans | Vans - up to 1.50 tonnes |  | wk
02.300.7000.20 | Plant and Equipment | Transport | Vans | Vans - over 1.50 tonnes |  | wk
02.300.8000.10 | Plant and Equipment | Transport | Personnel Transport etc. | Mini-bus | including MPVs, personnel carriers, etc. | wk
02.300.8000.20 | Plant and Equipment | Transport | Personnel Transport etc. | Welfare van | including mess facilities, etc. | wk
02.300.8000.30 | Plant and Equipment | Transport | Personnel Transport etc. | 4 Wheel Drives and Pick-ups | 4WD, Landrover, Hilux, etc | wk
02.300.8000.40 | Plant and Equipment | Transport | Personnel Transport etc. | Cars - Small | Ka or equivalent | wk
02.300.8000.50 | Plant and Equipment | Transport | Personnel Transport etc. | Cars - Medium | Focus or equivalent | wk
02.300.8000.60 | Plant and Equipment | Transport | Personnel Transport etc. | Cars - Large | Mondeo or equivalent | wk
02.300.8000.85 | Plant and Equipment | Transport | Personnel Transport etc. | Spares, servicing and maintenance for vehicles |  | LS
02.300.9000.10 | Plant and Equipment | Transport | Vehicle Recovery Service for live Public Highway | Rear Impact Protection Vehicle (RIPV) | includes IPV | hr
02.300.9000.20 | Plant and Equipment | Transport | Vehicle Recovery Service for live Public Highway | Light recovery vehicle |  | hr
02.300.9000.30 | Plant and Equipment | Transport | Vehicle Recovery Service for live Public Highway | Heavy recovery vehicle |  | hr
02.400.1000.10 | Plant and Equipment | Concrete equipment | Slip formers & concrete trains | Central road restraint slip former, including hopper etc. |  | wk
02.400.1000.20 | Plant and Equipment | Concrete equipment | Slip formers & concrete trains | Drainage channel slip former, including hopper etc. |  | wk
02.400.2000.10 | Plant and Equipment | Concrete equipment | Lorry mounted concrete pumps | Lorry mounted concrete pump up to 50 m3 / hour, boom up to 20m |  | hr
02.400.2000.20 | Plant and Equipment | Concrete equipment | Lorry mounted concrete pumps | Lorry mounted concrete pump 50.01 - 80 m3 / hour, boom 20.01- 40m |  | hr
02.400.2000.30 | Plant and Equipment | Concrete equipment | Lorry mounted concrete pumps | Lorry mounted concrete pump 80.01 m3 / hour and above, boom 40.01m and above |  | hr
02.400.2000.40 | Plant and Equipment | Concrete equipment | Lorry mounted concrete pumps | Skip for placing concrete |  | hr
02.400.2000.50 | Plant and Equipment | Concrete equipment | Lorry mounted concrete pumps | Concrete wash out plant / settlement tank |  | hr
02.400.3000.10 | Plant and Equipment | Concrete equipment | Vibrating pokers (self propelled) | Vibrator poker (self propelled) |  | hr
02.400.3000.20 | Plant and Equipment | Concrete equipment | Vibrating pokers (self propelled) | Vibrator poker (self propelled) poker head only |  | hr
02.400.4000.10 | Plant and Equipment | Concrete equipment | Vibrating Beams & Screeders | Vibrating rotary paddle screeder up to 1.80m |  | hr
02.400.4000.20 | Plant and Equipment | Concrete equipment | Vibrating Beams & Screeders | Vibrating beam screeds - Single | State width | hr
02.400.4000.30 | Plant and Equipment | Concrete equipment | Vibrating Beams & Screeders | Vibrating beam screeds - Double | State width | hr
02.400.5000.10 | Plant and Equipment | Concrete equipment | Concrete Saw | Hand held diesel concrete saw | i.e. Stihl saw or equivalent | hr
02.400.5000.20 | Plant and Equipment | Concrete equipment | Concrete Saw | Hand held petrol concrete saw | i.e. masonry / cut off | hr
02.400.5000.30 | Plant and Equipment | Concrete equipment | Concrete Saw | Pedestrian guided concrete saw | i.e. floor saw | hr
02.400.6000.10 | Plant and Equipment | Concrete equipment | Formwork | Formwork - beam | (e.g. Alform or similar) State size | wk
02.400.6000.20 | Plant and Equipment | Concrete equipment | Formwork | Formwork - brace or prop | (e.g. Rapidshore or similar) .State size.Where end link and tilt plate is an extra please show calculation of cost in rate column or state they are excluded | wk
02.400.6000.30 | Plant and Equipment | Concrete equipment | Formwork | Formwork - soldier | e.g. Super slim, Kwikform or similar) etc. State size | wk
02.400.6000.40 | Plant and Equipment | Concrete equipment | Formwork | Formwork - clamp assembly for timber waling | (includes hydraulic walers). State size | wk
02.400.6000.45 | Plant and Equipment | Concrete equipment | Formwork | Formwork - modular metal or fibreglass panels | State number and panel size or total area, nature and use (e.g. 60m2 formwork for vertical surfaces to barrier) | wk
02.400.6000.50 | Plant and Equipment | Concrete equipment | Formwork | Road form | State size | wk
02.400.6000.60 | Plant and Equipment | Concrete equipment | Formwork | Stake/road pin extractor for road form | State size | wk
02.400.6000.70 | Plant and Equipment | Concrete equipment | Formwork | Formwork - curved fibreglass (or other material) to concrete manhole surround | State chamber size (diameter) and height ( e.g. curved fibreglass fmwk to inspection chamber 1200mm diameter, 1500mm high) | wk
02.400.7000.10 | Plant and Equipment | Concrete equipment | Hire of scaffold | Erect scaffold | State type and size of temporary works structure (m3) | LS
02.400.7000.20 | Plant and Equipment | Concrete equipment | Hire of scaffold | Hire of scaffold - complete structure | (includes Acrow props). State individual components or type and size of temporary works structure (m3) | wk
02.400.7000.30 | Plant and Equipment | Concrete equipment | Hire of scaffold | Dismantle scaffold | State type and size of temporary works structure (m3) | LS
02.400.7000.40 | Plant and Equipment | Concrete equipment | Hire of scaffold | Scaffold tube | State length of individual tube and diameter | wk
02.400.7000.50 | Plant and Equipment | Concrete equipment | Hire of scaffold | Scaffold fittings | includes clips, joints, bends, universal joints, baseplates, castors, etc. State type and size | wk
02.400.7000.60 | Plant and Equipment | Concrete equipment | Hire of scaffold | Scaffold boards | State size | wk
02.400.8000.10 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Podium steps - complete | State height and width | wk
02.400.8000.20 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Proprietary scaffold tower system - complete | State height, plan area and manufacturer | wk
02.400.8000.25 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Podium step or proprietary scaffold tower system components | Where items charged separately. State type, dimensions, and manufacturer. | wk
02.400.8000.30 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Ladder | State type and length | wk
02.400.8000.70 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Crash deck or barrier landing | State type, size and height. | wk
02.400.8000.75 | Plant and Equipment | Concrete equipment | Ladders, Steps & Towers | Soft landing air bags | State type, size and number | wk
02.400.9000.10 | Plant and Equipment | Concrete equipment | Concrete & Grout Mixers | Concrete or mortar mixer - standalone | State size | hr
02.400.9000.20 | Plant and Equipment | Concrete equipment | Concrete & Grout Mixers | Concrete mixer - lorry mounted | State size | hr
02.400.9000.30 | Plant and Equipment | Concrete equipment | Concrete & Grout Mixers | Grout pan / mixer / pump | State size | hr
02.500.1000.10 | Plant and Equipment | Compressors | Compressors | Compressor up to 6.00 m3 / minute including hose | i.e. up to 212 cfm | hr
02.500.1000.20 | Plant and Equipment | Compressors | Compressors | Compressor 6.01 -12.0 m3 / minute including hose | i.e. 213 to 423 cfm | hr
02.500.1000.30 | Plant and Equipment | Compressors | Compressors | Compressor 12.01 -18.00 m3 / minute including hose | i.e. 424 to 635 cfm | hr
02.500.1000.40 | Plant and Equipment | Compressors | Compressors | Compressor 18.01 m3 / minute and above including hose | i.e. 636 cfm and above | hr
02.500.1000.50 | Plant and Equipment | Compressors | Compressors | Tractor mounted compressor including tools & hoses for 2 operatives use. |  | hr
02.500.1000.60 | Plant and Equipment | Compressors | Compressors | Tractors with front bucket and 2 tool compressor | i.e. Tractair | hr
02.500.2000.10 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Breaker or pick | (e.g. air, soil, tunnel, impact wrench, steel chisel, etc.). State type | hr
02.500.2000.20 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Scabbler or grinder - single headed |  | hr
02.500.2000.30 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Scabbler or grinder - multi-headed |  | hr
02.500.2000.40 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Sander |  | hr
02.500.2000.50 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Saw |  | hr
02.500.2000.60 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Poker |  | hr
02.500.2000.70 | Plant and Equipment | Compressors | Compressor Tools & Additional Hoses | Additional compressor hoses | State type, diameter and length | hr
02.600.1000.10 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Asphalting & Tarmacing Equipment | Pavers -mini up to 37kW |  | hr
02.600.1000.20 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Asphalting & Tarmacing Equipment | Pavers - tracked or wheeled 37.01 - 82 kW |  | hr
02.600.1000.30 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Asphalting & Tarmacing Equipment | Pavers - tracked or wheeled 82.01 kW and above |  | hr
02.600.2000.10 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Planers | Planer up to 0.35m wide |  | hr
02.600.2000.20 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Planers | Planer 0.36 - 1.00m wide |  | hr
02.600.2000.30 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Planers | Planer 1.01 - 2.00m wide |  | hr
02.600.2000.40 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Planers | Planer 2.01 - 3.00m wide |  | hr
02.600.2000.50 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Planers | Planer 3.01m wide and above |  | hr
02.600.3000.10 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Paving Slab Layer etc. | Paving slab layer | includes vacuum/suction lifter) | day
02.600.3000.20 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Paving Slab Layer etc. | Block grab |  | day
02.600.3000.30 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Paving Slab Layer etc. | Kerb layer |  | day
02.600.4000.10 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Establishment and removal of processing plant | State type of pant | LS
02.600.4000.20 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Material crushing plant |  | wk
02.600.4000.30 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Material screening or segregation plant |  | wk
02.600.4000.40 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Aggregate washing plant |  | wk
02.600.4000.50 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Concrete batcher |  | wk
02.600.4000.60 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Macadam batcher |  | wk
02.600.4000.70 | Plant and Equipment | Asphalting & Tarmacing Equipment, Paving Slab Layer etc. | Materials Processing | Weighbridge |  | wk
02.700.1000.05 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane up to 18 tonnes |  | hr
02.700.1000.10 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 18.01 - 28tonnes |  | hr
02.700.1000.15 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 28.01 - 48 tonnes |  | hr
02.700.1000.20 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 48.01 -68 tonnes |  | hr
02.700.1000.25 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 68.01 -108 tonnes |  | hr
02.700.1000.30 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 108.01 - 208 tonnes |  | hr
02.700.1000.35 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 208.01 -299 tonnes |  | hr
02.700.1000.40 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Wheeled crane 300 tonnes and above |  | hr
02.700.1000.45 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Crawler mounted cranes up to 40 tonnes |  | hr
02.700.1000.50 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Crawler mounted cranes 40.01 - 65 tonnes |  | hr
02.700.1000.55 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Crawler mounted cranes 65.01 tonnes and above |  | hr
02.700.1000.60 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Craneage ancillaries | Where slings, cradles, crane mats, etc. hired separately. State type | hr
02.700.1000.65 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Personnel Hoists | State type and maximum Safe Working Load | hr
02.700.1000.70 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Cranes | Material Hoists | State type and maximum Safe Working Load | hr
02.700.2000.10 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Access Platforms & Fork Lifts | Scissor Lift self propelled |  | hr
02.700.2000.20 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Access Platforms & Fork Lifts | Cherry Picker self propelled |  | hr
02.700.2000.30 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Access Platforms & Fork Lifts | Cherry Picker Lorry mounted |  | hr
02.700.2000.40 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Access Platforms & Fork Lifts | Tele handler with attachments or all terrain Forklift |  | hr
02.700.3000.10 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Hydraulic manhole cover lifter for covers up to 900 mm |  | day
02.700.3000.20 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Hydraulic manhole cover lifter 901 mm and above |  | day
02.700.3000.30 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | EDM Equipment |  | day
02.700.3000.35 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Levels |  | day
02.700.3000.40 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Laser level |  | day
02.700.3000.50 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Gas Detector |  | day
02.700.3000.55 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Cable Detector |  | day
02.700.3000.60 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | Noise Meter |  | day
02.700.3000.65 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | GPS |  | day
02.700.3000.70 | Plant and Equipment | Cranes, Mobile Access Platforms & Fork Lifts | Survey and Confined Spaces access equipment | HAV Monitoring equipment |  | day
02.800.1000.02 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Generators up to 16 kVA |  | hr
02.800.1000.04 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Generators 16.01 - 90 kVA |  | hr
02.800.1000.06 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Generators 90.01 -180 kVA |  | hr
02.800.1000.08 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Generators 180.01 kVA and above |  | hr
02.800.1000.10 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Transformer up to 16 KVA |  | hr
02.800.1000.12 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Transformer 16.01 - 90 KVA |  | hr
02.800.1000.14 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Transformer 90.01 -180 KVA |  | hr
02.800.1000.16 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Transformer 180.01 KVA and above |  | hr
02.800.1000.18 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Light tower 2 lights | State height | hr
02.800.1000.20 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Light tower 4 lights | State height | hr
02.800.1000.22 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Temporary traffic signals - 2 way control |  | hr
02.800.1000.24 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Temporary traffic signals - 3 way control |  | hr
02.800.1000.26 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Temporary traffic signals - 4 way control |  | hr
02.800.1000.28 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Electric powered drill or impact wrench | State type of drill or wrench | hr
02.800.1000.30 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Angle grinder |  | hr
02.800.1000.32 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Cut off / masonry saw |  | hr
02.800.1000.34 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Diamond drilling rig & water bottle |  | hr
02.800.1000.36 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Diamond drill rig water tank |  | hr
02.800.1000.38 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Diamond drill vacuum pump |  | hr
02.800.1000.40 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Pop rivet gun lazy tongs |  | hr
02.800.1000.42 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Hilti cartridge fixing gun |  | hr
02.800.1000.44 | Plant and Equipment | Miscellaneous Site Equipment | Electrical Equipment | Bench Saw |  | hr
02.800.2000.10 | Plant and Equipment | Miscellaneous Site Equipment | Pumps | Pump & hose up to 75mm diameter | includes single hose | hr
02.800.2000.20 | Plant and Equipment | Miscellaneous Site Equipment | Pumps | Pump & hose 76 - 115 mm diameter | includes single hose | hr
02.800.2000.30 | Plant and Equipment | Miscellaneous Site Equipment | Pumps | Pump & hose 115 mm diameter and above | includes single hose | hr
02.800.2000.40 | Plant and Equipment | Miscellaneous Site Equipment | Pumps | Additional hose | State diameter of hose and length | hr
02.800.3000.10 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Road sweeper with integral tank and gulley suction pump | State operating (day, out of hours) or travel time | hr
02.800.3000.20 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Towable Road Brush |  | hr
02.800.3000.30 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Waste Disposal fees |  | LS
02.800.3000.40 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Tractor with road brush(es) |  | hr
02.800.3000.50 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Establish and Remove wheel wash |  | LS
02.800.3000.60 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Wheel wash |  | hr
02.800.3000.70 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Drain Jetter or pressure washer | includes CCTV survey for pipe or duct | hr
02.800.3000.75 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Drain rods, reels, hoses, etc |  | hr
02.800.3000.80 | Plant and Equipment | Miscellaneous Site Equipment | Mechanical road sweepers, gritters etc. | Gritter with integral spreader (& snow blade if required) | State size of gritter lorry and snow blade (if provided) | hr
02.800.4000.10 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Mobile towable water bowsers up to 3,000 litres |  | hr
02.800.4000.20 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Mobile towable washer water bowsers up to 3,000 litres |  | hr
02.800.4000.30 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Mobile towable water bowsers 3,001 litres and above |  | hr
02.800.4000.40 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Lorry mounted water bowsers |  | hr
02.800.4000.50 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Mobile towable fuel bowsers up to 3,000 litres | State if includes bund or drip tray | hr
02.800.4000.60 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Mobile towable fuel bowsers 3,001 litres and above | State if includes bund or drip tray | hr
02.800.4000.70 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Bunded fuel tank up to 3,000 litres |  | hr
02.800.4000.80 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Bunded fuel tank up to 3,001 litres and above |  | hr
02.800.4000.90 | Plant and Equipment | Miscellaneous Site Equipment | Bowsers | Lorry mounted fuel bowsers (including drip trays & spillage kit) | State capacity of bowser | hr
02.800.5000.05 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Container with integral racking | e.g.ISO lockable 12m container or similar | wk
02.800.5000.10 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Container without racking for bulk materials | e.g. ISO lockable 12m container or similar | wk
02.800.5000.15 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Mobile Office - towable |  | wk
02.800.5000.20 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Main site offices including welfare facilities | State size of unit and type of facilities. | wk
02.800.5000.25 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Workforce welfare building | State size of unit and type of facilities. | wk
02.800.5000.30 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Establish temporary office(s), foundations & services connections, craneage & skirt | State size of unit and type of facilities. | LS
02.800.5000.35 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Hire of temporary Vehicle Recovery office, foundations & services connections, craneage & skirt | State size of unit | wk
02.800.5000.40 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Remove from site temporary office(s), foundations & services connections, craneage & skirt | State size of unit and type of facilities. | LS
02.800.5000.45 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Small temporary office | Includes Portakabin. State size of unit and whether supplied as shell or furnished | wk
02.800.5000.50 | Plant and Equipment | Miscellaneous Site Equipment | Stores & Offices | Single fibreglass toilet unit | Includes "tardis" | wk
02.800.6000.05 | Plant and Equipment | Miscellaneous Site Equipment | Skips | Skips - up to 4 m3 | State type of skip (i.e. wheelie bin) | day
02.800.6000.10 | Plant and Equipment | Miscellaneous Site Equipment | Skips | Skips - 4.01 m3 and above | State type of skip (i.e. wheelie bin) | day
02.800.6000.15 | Plant and Equipment | Miscellaneous Site Equipment | Skips | Skips - up to 16 m3 enclosed |  | day
02.800.6000.20 | Plant and Equipment | Miscellaneous Site Equipment | Skips | Skips - 16.01 m3 and above enclosed |  | day
02.800.6000.25 | Plant and Equipment | Miscellaneous Site Equipment | Skips | Skips - disposal of waste charge | includes charges for excess weight, comtaminated waste, etc. State type of material (inert, hazardous, etc) and type of charge | t
02.800.7000.10 | Plant and Equipment | Miscellaneous Site Equipment | Trench Supports | Trench supports | includes manhole or drag boxes. State type of support and size | wk
02.800.8000.10 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Tree stump grinder pedestrian operated |  | hr
02.800.8000.20 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Wood chipper | State duty | hr
02.800.8000.30 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Brush cutter or hedge trimmer |  | hr
02.800.8000.40 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Chain saw |  | hr
02.800.8000.50 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Mower | State type. Includes strimmer. | hr
02.800.8000.60 | Plant and Equipment | Miscellaneous Site Equipment | Miscellaneous Tools | Cutting, burning or welding kit |  | hr
02.800.9000.10 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Road cone | State colour, size, and number | day
02.800.9000.20 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Road plate | State size and depth (mm) | day
02.800.9000.30 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Vehicle barrier | e.g. Varioguard. State barrier type, size and overall length | day
02.800.9000.35 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Pedestrian barrier | e.g. Heras. State barrier type, size and overall length | day
02.800.9000.40 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Crash cushion | e.g. Varioguard. State barrier type, size and overall length | day
02.800.9000.50 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Temporary works and diversion signs | Includes pedestrian signage, metal A-frame. State type, size and number. | day
02.800.9000.60 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Electronic Fixed Text Message Sign (FTMS) |  | day
02.800.9000.70 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Electronic mobile text message sign | State power source | day
02.800.9000.90 | Plant and Equipment | Miscellaneous Site Equipment | Traffic Management Equipment | Miscellaneous traffic management equipment | Includes all other traffic management equipment ( e.g. traffic cone lights). State details and number. | day
02.900.1000.10 | Plant and Equipment | Fuel | Diesel & Petrol | Uls Gas Oil (unleaded red diesel) | Uls - Unleaded low sulphur, untaxed | l
02.900.1000.20 | Plant and Equipment | Fuel | Diesel & Petrol | Unleaded road diesel | (DERV) | l
02.900.1000.30 | Plant and Equipment | Fuel | Diesel & Petrol | Unleaded road petrol |  | l
02.900.2000.10 | Plant and Equipment | Fuel | Bottled gases | Gas for heating | (e.g. butane, propane,etc.). State type | kg
02.900.2000.20 | Plant and Equipment | Fuel | Bottled gases | Gas for cutting | (e.g. acetylene, oxygen, CO2, etc). State type | kg
02.950.1000.10 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Road plates | State dimensions | no
02.950.1000.15 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Road cones | State colour and size | no
02.950.1000.20 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Road cone lights | State colour and size | no
02.950.1000.25 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Overhead cable Guardian system components | State type and size | no
02.950.1000.30 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Temporary vehicle barrier | State type and size | m
02.950.1000.35 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Temporary pedestrian barrier | State type and size | m
02.950.1000.40 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Temporary barriers - ancillaries | includes fittings, clips, basplates etc. State type and size | no
02.950.1000.45 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Temporary vehicle access equipment | includes sleepers, alloy roadways, crane mats, proprietarysystems, etc. Excludes any permanent or temporary road building material. | no
02.950.1000.50 | Plant and Equipment | Purchase of non-mechanical equipment | Traffic management equipment purchased | Temporary signs | Includes all material types. Includes post or A-frame mounted | no
02.950.1500.10 | Plant and Equipment | Purchase of non-mechanical equipment | Setting Out equipment purchased | Timber pegs | State size | no
02.950.1500.15 | Plant and Equipment | Purchase of non-mechanical equipment | Setting Out equipment purchased | Steel pegs | State size | no
02.950.1500.20 | Plant and Equipment | Purchase of non-mechanical equipment | Setting Out equipment purchased | Setting out ancillaries | includes tapes, paint, clips, nails, etc. State type. | no
02.950.2000.10 | Plant and Equipment | Purchase of non-mechanical equipment | Concrete equipment purchased | Road forms | State size | m
02.950.2000.15 | Plant and Equipment | Purchase of non-mechanical equipment | Concrete equipment purchased | Road form pins | State size | no
02.950.3000.10 | Plant and Equipment | Purchase of non-mechanical equipment | Lifting equipment purchased | Slings and shackles | State size | no
02.950.3000.15 | Plant and Equipment | Purchase of non-mechanical equipment | Lifting equipment purchased | Chains and shackles | State size | no
02.950.4000.10 | Plant and Equipment | Purchase of non-mechanical equipment | Access equipment purchased | Podium step/landing components | State type of component and size | no
02.950.4000.15 | Plant and Equipment | Purchase of non-mechanical equipment | Access equipment purchased | Ladders | State size | no
02.950.4000.20 | Plant and Equipment | Purchase of non-mechanical equipment | Access equipment purchased | Scaffold tube | State length of individual tube and diameter | m
02.950.4000.25 | Plant and Equipment | Purchase of non-mechanical equipment | Access equipment purchased | Scaffold fittings | State type and size | no
02.950.4000.30 | Plant and Equipment | Purchase of non-mechanical equipment | Access equipment purchased | Scaffold boards | State size | no
02.950.5000.10 | Plant and Equipment | Purchase of non-mechanical equipment | Waste disposal equipment purchased | Pollution control consumables | includes oil spill kits, plant nappies, drip trays, etc. State type and size | no
02.950.5000.20 | Plant and Equipment | Purchase of non-mechanical equipment | Waste disposal equipment purchased | Skips | State size | no
02.990.1000.05 | Plant and Equipment | Other | Other - Equipment | Purchase of equipment (not hired) | Excludes equipment covered under 02.950 and consumables | LS
02.990.1000.07 | Plant and Equipment | Other | Other - Equipment | Purchase of plant consumables | includes blades, drill bits, lubricants, fuel additives etc. Excludes diesel, petrol and gases | LS
02.990.1000.10 | Plant and Equipment | Other | Other - Equipment | Unallocated Equipment | Include here new or otherwise non-standard items | LS
02.990.1000.15 | Plant and Equipment | Other | Other - Equipment | Equipment not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories | LS
03.100.1000.05 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Hardcore (or acceptable fill Class 1,2, or 3) |  | t
03.100.1000.10 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Filter Media (or Class 6A fill) | State type of fill | t
03.100.1000.15 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Fill for starter layer (or Class 6B, C, D or H fill) | State type of fill | t
03.100.1000.20 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Cement bound granular base (CBGB or Class 6E) | State type of fill | t
03.100.1000.25 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Capping material (class 6F fill) | State type of fill | t
03.100.1000.30 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Gabion Stone (Class 6G fill) | State size of stone | t
03.100.1000.35 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Fill for reinforced earth structures (or Class 6I or J fill) | State type of fill | t
03.100.1000.40 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Fill for Armco structures (or Class 6K, L or M fill) | State type of fill | t
03.100.1000.45 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Fill for around structures (or Class 6N or P fill) | State type of fill | t
03.100.1000.50 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Sub-base - Type 1 |  | t
03.100.1000.55 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Sub-base - Type 2 |  | t
03.100.1000.60 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Sub-base - Type 3 |  | t
03.100.1000.65 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Pipe bedding Type A (90% 10mm aggregate to dust) |  | t
03.100.1000.70 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Filter drain material Type B | e.g. (94% 10 - 40 Aggregate - 74% 20 - 40 Aggregate) | t
03.100.1000.75 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Sand including stone dust | State type | t
03.100.1000.78 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Rock salt & other de-icing aggregates |  | t
03.100.1000.80 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Part-load charge (aggregates) | includes additional charge for small quantities | t
03.100.1000.85 | Materials | Aggregates, Fill & Roadstone | Imported Aggregates &Fill | Waiting time (aggregates) |  | minute
03.100.2000.10 | Materials | Aggregates, Fill & Roadstone | Imported topsoil | Imported topsoil |  | t
03.100.3000.10 | Materials | Aggregates, Fill & Roadstone | Roadstone | Road Planings | includes asphalt arisings | t
03.100.3000.20 | Materials | Aggregates, Fill & Roadstone | Roadstone | Rolled asphalt binder course |  | t
03.100.3000.30 | Materials | Aggregates, Fill & Roadstone | Roadstone | Stone Mastic Asphalt (SMA) |  | t
03.100.3000.40 | Materials | Aggregates, Fill & Roadstone | Roadstone | Close graded macadam | State aggregate size and polished stone value (PSV) | t
03.100.3000.50 | Materials | Aggregates, Fill & Roadstone | Roadstone | Dense bitumen macadam (DBM50) |  | t
03.100.3000.60 | Materials | Aggregates, Fill & Roadstone | Roadstone | Heavy duty macadam (HDM50) |  | t
03.100.3000.70 | Materials | Aggregates, Fill & Roadstone | Roadstone | Open graded macadam |  | t
03.100.3000.80 | Materials | Aggregates, Fill & Roadstone | Roadstone | Part-load charge (roadstone) | includes additional charge for small quantities | t
03.100.3000.85 | Materials | Aggregates, Fill & Roadstone | Roadstone | Extra charge for night time / weekend delivery | i.e. working out of hours | LS
03.100.3000.90 | Materials | Aggregates, Fill & Roadstone | Roadstone | Waiting time (roadstone) |  | minute
03.100.4000.10 | Materials | Aggregates, Fill & Roadstone | Disposal of excavated material off site | Disposal of excavated material off site - acceptable | Use where service is provided by a Haulier and charged on Tonnage Basis. Includes inert/ non-hazardous material unless spcifically classed as unacceptable. | t
03.100.4000.20 | Materials | Aggregates, Fill & Roadstone | Disposal of excavated material off site | Disposal of excavated material off site - unacceptable | Use where service is provided by a Haulier and charged on Tonnage Basis. | t
03.100.4000.30 | Materials | Aggregates, Fill & Roadstone | Disposal of excavated material off site | Disposal of excavated concrete, tarmac and other hard material - off site | Use where service is provided by a Haulier and charged on Tonnage Basis | t
03.100.4000.40 | Materials | Aggregates, Fill & Roadstone | Disposal of excavated material off site | Disposal of excavated material - contaminated - off site | Use where service is provided by a Haulier and charged on Tonnage Basis | t
03.200.1000.05 | Materials | Concrete | Ready Mix Concrete | Blinding concrete up to Mix C12/15(BS/EN 206-1) |  | m3
03.200.1000.10 | Materials | Concrete | Ready Mix Concrete | Structural concrete - Mix C16/20 to C25/30 (BS/EN 206-1) |  | m3
03.200.1000.15 | Materials | Concrete | Ready Mix Concrete | Structural concrete - Mix C28/35 to C32/40 (BS/EN 206-1) |  | m3
03.200.1000.20 | Materials | Concrete | Ready Mix Concrete | Structural concrete -Mix C35/45(BS/EN 206-1) and stronger |  | m3
03.200.1000.25 | Materials | Concrete | Ready Mix Concrete | Structural concrete - Mix C16/20 to C25/30 (BS/EN 206-1) sulphate resisting |  | m3
03.200.1000.30 | Materials | Concrete | Ready Mix Concrete | Structural concrete - Mix C28/35 to C32/40 (BS/EN 206-1) sulphate resisting |  | m3
03.200.1000.35 | Materials | Concrete | Ready Mix Concrete | Structural concrete -Mix C35/45(BS/EN 206-1) and stronger sulphate resisting |  | m3
03.200.1000.38 | Materials | Concrete | Ready Mix Concrete | Structural concrete to stated design mix, strength not stated | Includes project specific design mixesST1 to ST6 where no design strength is specified. Where mix and design strength are stated, use items 03.200.1000.05-35 | m3
03.200.1000.40 | Materials | Concrete | Ready Mix Concrete | Specialist concrete | (e.g. lightweight foamed concrete, air entrained, etc). State type of concrete & strength | m3
03.200.1000.80 | Materials | Concrete | Ready Mix Concrete | Part load charge (concrete) | includes additional charge for small quantities | m3
03.200.1000.85 | Materials | Concrete | Ready Mix Concrete | Extra charge for night time / weekend delivery | i.e. working out of hours | LS
03.200.1000.90 | Materials | Concrete | Ready Mix Concrete | Waiting time (concrete) |  | minute
03.200.2000.10 | Materials | Concrete | Grout, cement, mortar additives and cement mortar | Ready-mix mortar | includes cement, granolithic, epoxy mortars, instant repair products, etc.. State type of mortar | m3
03.200.2000.20 | Materials | Concrete | Grout, cement, mortar additives and cement mortar | Cement | (e.g. OPC, SRC) State type of cement. | kg
03.200.2000.30 | Materials | Concrete | Grout, cement, mortar additives and cement mortar | Mortar & concrete additives | (e.g. plasticizer, lime). State type of additive | kg
03.200.2000.40 | Materials | Concrete | Grout, cement, mortar additives and cement mortar | Cement grout | includes cement / PFA. State type of grout | kg
03.200.2000.50 | Materials | Concrete | Grout, cement, mortar additives and cement mortar | Dry premixed bagged concrete | e.g. fence post foundation mixes. State type of concrete & use | kg
03.200.3000.05 | Materials | Concrete | Reinforcement | Mild steel bar (cut and bent) up to 16mm diameter | State diameter | t
03.200.3000.10 | Materials | Concrete | Reinforcement | Mild steel bar (cut and bent) 20mm diameter and above | State diameter | t
03.200.3000.15 | Materials | Concrete | Reinforcement | High yield steel bar (cut and bent) up to 16mm diameter | State diameter | t
03.200.3000.20 | Materials | Concrete | Reinforcement | High yield steel bar (cut and bent) 20mm diameter and over | State diameter | t
03.200.3000.25 | Materials | Concrete | Reinforcement | Stainless steel bar EN1.4462 bar cut | State diameter | t
03.200.3000.30 | Materials | Concrete | Reinforcement | High yield Prestress Strand | State diameter | t
03.200.3000.35 | Materials | Concrete | Reinforcement | Square Mesh Fabric reinforcement | State type | t
03.200.3000.40 | Materials | Concrete | Reinforcement | Helical steel reinforcement |  | t
03.200.3000.45 | Materials | Concrete | Reinforcement | Steel tie wire |  | kg
03.200.3000.50 | Materials | Concrete | Reinforcement | Stainless steel tie wire |  | kg
03.200.3000.55 | Materials | Concrete | Reinforcement | Reinforcement ancillaries | State type e.g. chairs, safety caps,etc. | LS
03.200.3000.60 | Materials | Concrete | Reinforcement | Reinforcing steel - spacers |  | per 1000
03.200.3000.65 | Materials | Concrete | Reinforcement | Mild steel dowel bar | State diameter and length | no
03.200.3000.70 | Materials | Concrete | Reinforcement | Stainless steel dowel bar | State diameter and length | no
03.200.3000.75 | Materials | Concrete | Reinforcement | Dowel bar ancillaries | (e.g. end caps, sleeves, etc). State type | no
03.200.4000.10 | Materials | Concrete | Formwork Materials | Plywood or other timber based sheet material | State type and thickness | m2
03.200.4000.20 | Materials | Concrete | Formwork Materials | Planed square edge carcassing timber | State size. Note that conversion to m3 units is needed | m3
03.200.4000.30 | Materials | Concrete | Formwork Materials | Sawn formwork carcassing timber | State size. Note that conversion to m3 units is needed | m3
03.200.4000.40 | Materials | Concrete | Formwork Materials | Formwork sundries | (e.g. mould oil, filer). State number and type of individual units (drum, bag, millilitre, etc.) | no
03.200.4000.50 | Materials | Concrete | Formwork Materials | Formwork - struts, props, plates and components | (e.g. Rapid bar) State type and dimensions. | no
03.200.4000.60 | Materials | Concrete | Formwork Materials | Formwork - curved fibreglass (or other material) to concrete manhole surround | State chamber size (diameter) and height | no
03.200.4000.70 | Materials | Concrete | Formwork Materials | Formwork - corrugated plastic sheet or other permanent forms | (e.g. Pecafil, Omnia) | m2
03.200.5000.10 | Materials | Concrete | Precast Concrete Components for Structures | PCC beam units | Statye type, dimensions, concrete class or strength | no
03.200.5000.20 | Materials | Concrete | Precast Concrete Components for Structures | PCC column units | Statye type, dimensions, concrete class or strength | no
03.200.5000.30 | Materials | Concrete | Precast Concrete Components for Structures | Other PCC units | Statye type, dimensions, concrete class or strength | no
03.300.1000.10 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe up to 300mm diameter | State pipe length, diameter, class or strength of concrete | m
03.300.1000.20 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe 301 - 900mm diameter | State pipe length, diameter, class or strength of concrete | m
03.300.1000.30 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe 901mm diameter and above | State pipe length, diameter, class or strength of concrete | m
03.300.1000.40 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe up to 300mm diameter - rocker | State pipe length, diameter, class or strength of concrete | m
03.300.1000.50 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe 301 - 900mm diameter - rocker | State pipe length, diameter, class or strength of concrete | m
03.300.1000.60 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe 901mm diameter and above - rocker | State pipe length, diameter, class or strength of concrete | m
03.300.1000.65 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Concrete pipe fittings | State type of fitting (e.g. bends), diameter, class or strength of concrete | no
03.300.1000.70 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Precast concrete culvert units | State section type, length, cross section size, concrete class or strength | m
03.300.1000.75 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Precast concrete culvert unit - ancillaries | (e.g. end walls, joint sets, access openings, etc.) State type, dimensions, concrete class or strength | no
03.300.1000.80 | Materials | Drainage, ducts, fittings, chambers | Precast Concrete Pipes & Culverts | Interceptors and separators | State type, dimensions, concrete class or strength or other material type where not concrete | no
03.300.2000.10 | Materials | Drainage, ducts, fittings, chambers | Clayware Pipes & Ducts | Clay pipe up to 300mm diameter | (e.g. Hepsleeve including collars). State pipe length and diameter | m
03.300.2000.20 | Materials | Drainage, ducts, fittings, chambers | Clayware Pipes & Ducts | Clay pipe 301 - 900mm diameter | (e.g. Hepsleeve including collars). State pipe length and diameter | m
03.300.2000.30 | Materials | Drainage, ducts, fittings, chambers | Clayware Pipes & Ducts | Clay pipe fittings | State type of fitting (e.g. bends, junctions, gullies, etc.) and diameter | no
03.300.3000.02 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic service pipe for gas & water; up to 100mm diameter | State diameter | m
03.300.3000.04 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic service pipe for gas & water; 101 - 300mm diameter | State diameter | m
03.300.3000.06 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic service pipe for gas & water; 301mm diameter and above | State diameter | m
03.300.3000.08 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic service pipe for gas & water; fittings | State type of fitting (e.g. bends, junctions, etc.) and diameter | no
03.300.3000.10 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe drain up to 300mm diameter | State whether single/twin wall and diameter | m
03.300.3000.12 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe drain 301 - 900mm diameter | State whether single/twin wall and diameter | m
03.300.3000.14 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe drain 901mm diameter and above | State whether single/twin wall and diameter | m
03.300.3000.16 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe drain coupler & sealing ring | Where supplied separately to pipe. State whether single/twin wall and diameter | no
03.300.3000.18 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe drain fittings | State type of fitting (e.g. bends, junctions, etc.), whether single/twin wall and diameter | no
03.300.3000.20 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic perforated pipe drain up to 300mm diameter | State whether single/twin wall and diameter | m
03.300.3000.22 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic perforated pipe drain 301 - 900mm diameter | State whether single/twin wall and diameter | m
03.300.3000.24 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic perforated pipe drain 901mm diameter and above | State whether single/twin wall and diameter | m
03.300.3000.26 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic perforated pipe drain coupler & sealing ring | Where supplied separately to pipe. State diameter | no
03.300.3000.28 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic perforated pipe drain fittings | State type of fitting (e.g. bends, junctions, etc.), whether single/twin wall and diameter | no
03.300.3000.30 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic pipe in gulley connection | i.e Ridgiflex or similar supplied in 25m coil. State diameter andjointing method | m
03.300.3000.32 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic twin-wall duct Black (power) | State diameter, jointing method and whether couplings are included | m
03.300.3000.34 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic twin-wall duct Purple (comms) | State diameter, jointing method and whether couplings are included | m
03.300.3000.36 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic twin-wall duct Orange (lighting) | State diameter, jointing method and whether couplings are included | m
03.300.3000.38 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic single-wall duct | State diameter, jointing method and whether couplings are included | m
03.300.3000.40 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic duct; coupler and sealing ring | Where supplied separately to pipe. State duct type, whether single/twin wall and diameter | no
03.300.3000.42 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Plastic duct: fittings | State type of fitting (e.g. bends, junctions, etc,), whether single/twin wall and diameter | no
03.300.3000.50 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Duct spacer | State diameter and number of ways | no
03.300.3000.52 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Duct end sealing bungs | State size of bung, cable size and type of service | no
03.300.3000.54 | Materials | Drainage, ducts, fittings, chambers | Plastic pipes and ducts | Draw cords & temporary bungs | State length and size | no
03.300.4000.10 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Plastic inspection chambers | State size of chamber and use | no
03.300.4000.40 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Plastic yard gulley | State size | no
03.300.4000.50 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Plastic yard gulley silt box | State size | no
03.300.4000.60 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Plastic yard gulley grating | State size | no
03.300.4000.70 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | 50mm diameter pipe for weep holes |  | no
03.300.4000.80 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Plastic Road Gulley | State size | no
03.300.4000.85 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Fin drain materials | State type and size. System used will vary - where geotextiles are not attached to drain pipes or cellar plastics use03.500.1000 | m
03.300.4000.90 | Materials | Drainage, ducts, fittings, chambers | Plastic fittings & Cellular drainage products | Cellular attenuation tank | State type and size | m3
03.300.5000.10 | Materials | Drainage, ducts, fittings, chambers | Ductile Iron Pipe / Fittings | Ductile iron pipe up to 300mm diameter | State pipe length and jointing method | m
03.300.5000.20 | Materials | Drainage, ducts, fittings, chambers | Ductile Iron Pipe / Fittings | Ductile iron pipe 301mm diamter and above | State pipe length and jointing method | m
03.300.5000.30 | Materials | Drainage, ducts, fittings, chambers | Ductile Iron Pipe / Fittings | Ductile iron pipe coupler & sealing ring | Where supplied separately to pipe. State diameter | no
03.300.5000.40 | Materials | Drainage, ducts, fittings, chambers | Ductile Iron Pipe / Fittings | Ductile iron pipe fittings | State type of fitting and diameter | no
03.300.5500.10 | Materials | Drainage, ducts, fittings, chambers | Valves & Penstocks | Penstocks | State type and diameter. Includes Hydrobrake | no
03.300.5500.20 | Materials | Drainage, ducts, fittings, chambers | Valves & Penstocks | Valves and spindles | State type and diameter | no
03.300.5500.30 | Materials | Drainage, ducts, fittings, chambers | Valves & Penstocks | Reducer plates and weirs for storm water storage | State type and diameter of pipe and outflow | no
03.300.6000.05 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete chamber rings internal diameter up to 1050mm | State diameter and height of unit | no
03.300.6000.10 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete chamber rings internal diameter 1051mm and above | State diameter and height of unit | no
03.300.6000.15 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete chamber cover slab internal diameter up to 1050mm | State diameter of unit | no
03.300.6000.20 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete chamber cover slab internal diameter 1051mm and above | State diameter of unit | no
03.300.6000.25 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete chamber reducer slab internal diameter 1051mm and above | State diameter of unit | no
03.300.6000.30 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Miscellaneous fittings or factory work to precast concrete chambers | State type of fitting or nature of work (e.g. ladder rungs, chains etc.) | no
03.300.6000.35 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete inspection chamber rectangular frames | State internal dimensions of chamber & height of unit | no
03.300.6000.40 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete inspection chamber rectangular cover slab | State internal dimensions of chamber & nature of opening | no
03.300.6000.45 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete gulley pot | State size | no
03.300.6000.50 | Materials | Drainage, ducts, fittings, chambers | Concrete Chamber Units | Precast concrete gulley cover | State size | no
03.300.7000.05 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Cover and frame | State material, size and grade | no
03.300.7000.10 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Gulley grating and frame | State material, size and grade | no
03.300.7000.15 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Hatch box cover | State material and size | no
03.300.7000.20 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Stop tap boxes covers | State material and size | no
03.300.7000.25 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Telecoms box cover | State size | no
03.300.7000.30 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Security cover & frame for modular security chamber boxes | State size and type | no
03.300.7000.35 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Security access modular chamber boxes | State size and type | no
03.300.7000.40 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Security access modular chamber box sump base | State size and type | no
03.300.7000.45 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Ductile iron channel & gratings combined |  | no
03.300.7000.50 | Materials | Drainage, ducts, fittings, chambers | Covers & Frames | Ductile iron channel & gratings combined - specials |  | no
03.400.1000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Precast concrete kerbs | State size and shape | m
03.400.1000.20 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Precast concrete kerbs curved 5.01 m radius and above | State size and shape | no
03.400.1000.30 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Precast concrete kerbs specials including curved up to 5m radius | State size and shape | no
03.400.1000.40 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Edging Kerb | State size and shape | m
03.400.1000.50 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Edging Kerb specials | State size and shape | no
03.400.1000.60 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | PC Dished channel |  | m
03.400.1000.70 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Drainage channel with grating | (e.g. Aco Drain) State materials, type and dimensions of channel and grating | m
03.400.1000.75 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Drainage channel with grating - specials | (e.g. end cpas, outfalls, etc.) State materials, type and dimensions of unit | no
03.400.1000.80 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Drainage block or kerb unit with integral slot drain | (e.g. Safeticurb) State materials, type and dimensions of unit | m
03.400.1000.90 | Materials | Kerbs, Paving, Bricks & Blocks | Kerbs, edgings and channels | Drainage unit with metallic slot drain | (e.g. Aco Q Max, Ultraslot). State materials, type and dimensions of unit | m
03.400.2000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 2-part combined secret channel and perforated kerb units | (e.g. Envirokerb or Beany kerb). State materials, type and dimension of unit | m
03.400.2000.20 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 2-part Combined secret channel and perforated kerb specials | (e.g. end caps, outfalls, etc). State materials, type and dimension of unit | no
03.400.2000.30 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 2-part combined secret channel and perforated kerb gulley units | State type and dimensions of unit | no
03.400.2000.40 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 2-part combined secret channel and perforated kerb mastic sealant |  | l
03.400.2000.50 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 2-part combined secret channel and perforated kerb bedding mortar |  | kg
03.400.2000.60 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 1-part secret channel and perforated kerb units | (e.g. Aco KerbDrain) State materials, type and dimensions of unit | m
03.400.2000.70 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 1-part secret channel and perforated kerb specials | (e.g. end caps, outfalls, etc.) State materials, type and dimensions of unit | no
03.400.2000.80 | Materials | Kerbs, Paving, Bricks & Blocks | Integrated channel and drainage blocks | 1-part secret channel and perforated kerb gulley units | State materials, type and dimensions of unit | no
03.400.3000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Block Paviors | Block Paviors | Standard brick or concrete. State type and size | m2
03.400.3000.20 | Materials | Kerbs, Paving, Bricks & Blocks | Block Paviors | Other paviours | (e.g. Charcon Grassgrid Paving, tactile, etc.) State type and size | m2
03.400.4000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Paving Slabs | Paving Slabs | State type and size | m2
03.400.5000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Bricks | Engineering bricks | State Class | per 1000
03.400.5000.20 | Materials | Kerbs, Paving, Bricks & Blocks | Bricks | Other bricks | State type (facing, common, etc.) | per 1000
03.400.6000.10 | Materials | Kerbs, Paving, Bricks & Blocks | Blocks | Concrete blocks | State type and size | no
03.500.1000.10 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Concrete waterproofing system | (e.g. Servipak, Bituthene, etc.) State type and gauge | m2
03.500.1000.20 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Concrete waterproofing system primer | (e.g.Mulseal, "blackjack", etc.) | m2
03.500.1000.30 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Damp proof membranes | (e.g. Visqueen) State type and gauge | m2
03.500.1000.40 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Geotextile | (e.g. Terram) State grade and use | m2
03.500.1000.50 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Warning barrier, duct or cable marker tape | (e.g. Nicoflex 600 etc.) | m
03.500.1000.55 | Materials | Membranes, Geotextiles, Jointing Materials | Membranes & Geotextiles | Tape ancillaries | includes fixing crimps, tools, etc. | no
03.500.2000.10 | Materials | Membranes, Geotextiles, Jointing Materials | Joint Fillers | Filler - fibre board | (e.g. Flexcell, etc) State type and thickness | m2
03.500.2000.20 | Materials | Membranes, Geotextiles, Jointing Materials | Joint Fillers | Filler - cellular plastic | (e.g. Expandafoam cord, etc.) State type and thickness | m2
03.500.2000.30 | Materials | Membranes, Geotextiles, Jointing Materials | Joint Fillers | Bitumen rubber sealing strip | State section size and length | m
03.500.3000.10 | Materials | Membranes, Geotextiles, Jointing Materials | Joint sealants & lubricants | Sealant | (e.g Thioflex, FOSROC, Lokfix etc.). State type | l
03.500.3000.20 | Materials | Membranes, Geotextiles, Jointing Materials | Joint sealants & lubricants | Pipe joint lubricant | State type of lubricant and pipe requiring lubrication. | l
03.500.4000.10 | Materials | Membranes, Geotextiles, Jointing Materials | Waterbars | PVC Water stop | State section size and length | m
03.600.1000.10 | Materials | Gabion Baskets, Reinforced Earth Components | Gabion Baskets | Galvanised Gabion Baskets | State size | no
03.600.1000.20 | Materials | Gabion Baskets, Reinforced Earth Components | Gabion Baskets | Galvanised Reno Mattress | State size | no
03.600.2000.10 | Materials | Gabion Baskets, Reinforced Earth Components | Reinforced Earth Components | Reinforced Earth Components | State type | no
03.700.1000.10 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Timber for Highway Boundary Fencing post & rails | State size. Note that conversion to m3 units is needed | m3
03.700.1000.12 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Timber panels for Highways Fencing & Noise Barriers | e.g. Timber panels made off site. State type and size of panels | m
03.700.1000.14 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Timber for Highways Fencing & Noise Barriers | e.g. feather edged boards for putting onto site assembled framework. State type and size | m
03.700.1000.20 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Plain or coated fencing wire |  | m
03.700.1000.22 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Barbed fencing wire |  | m
03.700.1000.30 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Galvanised mesh | (e.g. chain link) State height and coating (e.g. galvanised, plastic, etc) | m2
03.700.1000.32 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Galvanised wire mesh netting | (e.g. pig or sheep netting). State type and height | m2
03.700.1000.40 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Concrete fence posts | includes bracings and specials (e.g. anchor) State type and height | no
03.700.1000.50 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Metal palisade fencing posts | includes bracings and specials (e.g. acnhor). State type and height | no
03.700.1000.55 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Metal palisade fencing panels | State type and height | m
03.700.1000.60 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Pedestrian metal guard or handrail - tubes | i.e. "kee klamp" or similar. State diameter of tube | m
03.700.1000.65 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Pedestrian metal guard or handrail - fittings | includes fixings, connections, etc. State type & diameter | no
03.700.1000.70 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Pedestrian barrier posts | State type & height | no
03.700.1000.72 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Pedestrian barrier panels | State number & panel size or total area | m
03.700.1000.80 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Gates | State type, height and width | no
03.700.1000.85 | Materials | Fencing & Vehicle Restraint | Fencing & Gates | Fencing and gates - ancillaries | includes clips, nails, bolts, ironmongery, etc. State type | no
03.700.2000.10 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Corrugated Steel vehicle restraint - beams | State size of beam | m
03.700.2000.15 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Corrugated Steel vehicle restraint - posts | includes bracings and specials (e.g. acnhor). State type and height | no
03.700.2000.20 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Tensioned cable vehicle restraint - steel cable | State diameter | m
03.700.2000.25 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Tensioned cable vehicle restraint - posts | includes bracings and specials (e.g. acnhor). State type and height | no
03.700.2000.30 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Open box beam - beams | State size of beam | m
03.700.2000.35 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Open box beam - posts | includes bracings and specials (e.g. acnhor). State type and height | no
03.700.2000.40 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Rectangular hollow section - beams | State size of beam | m
03.700.2000.45 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Rectangular hollow section - posts | includes bracings and specials (e.g. acnhor). State type and height | no
03.700.2000.50 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Crash cushion | State type and height | no
03.700.2000.60 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Metal Parapet posts | State type and height | m
03.700.2000.65 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Metal Parapet panels | State number & panel size or total area | m
03.700.2000.70 | Materials | Fencing & Vehicle Restraint | Vehicle Restraint | Vehicle restraints - ancillaries | includes fixings, connections, etc. State type | no
03.720.1000.10 | Materials | Traffic Signs and Posts | Posts | Posts for fixed traffic non-illuminated signage | State type and height | no
03.720.1000.20 | Materials | Traffic Signs and Posts | Posts | Posts with light control box for fixed traffic illuminated signage | State type and height | no
03.720.1000.50 | Materials | Traffic Signs and Posts | Posts | Traffic sign ancillaries | e.g post extensions, clamps, caps, etc. State type | no
03.720.2000.10 | Materials | Traffic Signs and Posts | Signs | Traffic Signs; face up to 1m2 | State size of sign and type/legend | no
03.720.2000.20 | Materials | Traffic Signs and Posts | Signs | Traffic Signs; face 1.01 to 5m2 | State size of sign and type/legend | no
03.720.2000.30 | Materials | Traffic Signs and Posts | Signs | Traffic Signs; face 5.01 to 10m2 | State size of sign and type/legend | no
03.720.2000.40 | Materials | Traffic Signs and Posts | Signs | Traffic Signs; face 10.01m2 and above | State size of sign and type/legend | no
03.800.1000.10 | Materials | Piling Materials | Sheet Piles | Sheet Piles | State pile section size, length | m2
03.800.2000.10 | Materials | Piling Materials | Cast in-situ concrete piles | Cast in-situ concrete piles - reinforcement |  | t
03.800.3000.10 | Materials | Piling Materials | Precast concrete piles | Precast concrete piles | State pile type and size | m
03.800.4000.10 | Materials | Piling Materials | Steel H piles | Steel H piles | State pile section size. | m
03.800.5000.10 | Materials | Piling Materials | Spiral Steel piles | Spiral Steel piles | State pile section size. | m
03.800.6000.10 | Materials | Piling Materials | Plastic piles | Plastic piles | State pile section size. | m
03.850.1000.10 | Materials | Equipment Support Structures | Support Structures - Metal | Pole or post - straight | State height and section size | t
03.850.1000.15 | Materials | Equipment Support Structures | Support Structures - Metal | Pole or post - cantilevered | State height and section size | t
03.850.1000.25 | Materials | Equipment Support Structures | Support Structures - Metal | Mast | i.e fabricated. State height & cross-sectional dimensions | t
03.850.1000.30 | Materials | Equipment Support Structures | Support Structures - Metal | Portal Gantry | i.e fabricated. State height & cross-sectional dimensions | t
03.850.1000.35 | Materials | Equipment Support Structures | Support Structures - Metal | Brackets & Clamps | includes all types of fixtures and fixings to support equipment (e.g CCTV) | no
03.850.1000.40 | Materials | Equipment Support Structures | Support Structures - Metal | Isolated PCC plinth foundation | State dimensions and purpose (e.g. switchgear cabinet plinth) | no
03.900.1000.10 | Materials | Electrical Materials | Metal conductors | Metal electrical cable | State type of cable and size (mm2); type of sheathing andnumber of cores. | m
03.900.1000.20 | Materials | Electrical Materials | Metal conductors | Metal electrical cable - terminal | includes glands. State type of terminal, type and size of cable (mm2) | no
03.900.1000.30 | Materials | Electrical Materials | Metal conductors | Joint, splicing kit or tee | includes junction boxes. State type. | no
03.900.1000.40 | Materials | Electrical Materials | Metal conductors | Lightning Protection copper or aluminium tape |  | m
03.900.1000.50 | Materials | Electrical Materials | Metal conductors | Lightning Protection copper or aluminium tape joints, terminations or connections |  | no
03.900.1000.60 | Materials | Electrical Materials | Metal conductors | Lightning Protection - brass or aluminium fixing clips |  | no
03.900.1000.70 | Materials | Electrical Materials | Metal conductors | Earthing rods & clamps | State length and size | no
03.900.1000.80 | Materials | Electrical Materials | Metal conductors | Earthing rod - test point |  | no
03.900.2000.10 | Materials | Electrical Materials | Metal conductors - Equipment | Switchgear |  | no
03.900.2000.12 | Materials | Electrical Materials | Metal conductors - Equipment | Control equipment | State purpose & type | no
03.900.2000.14 | Materials | Electrical Materials | Metal conductors - Equipment | Heating equipment | State type (e.g. tubular heater, etc.) | no
03.900.2000.16 | Materials | Electrical Materials | Metal conductors - Equipment | Ventilating equipment | State type (e.g. exractor fan, etc.) | no
03.900.2000.18 | Materials | Electrical Materials | Metal conductors - Equipment | Switchgear cabinet shell only | State type (e.g. LeGrand GRP enclosure, etc.). Includes locking kit. | no
03.900.2000.20 | Materials | Electrical Materials | Metal conductors - Equipment | Off site assembled switchgear cabinet | i.e. prefitted. State purpose & contents | no
03.900.2000.25 | Materials | Electrical Materials | Metal conductors - Equipment | Feeder Pillars |  | no
03.900.2000.30 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting column with lighting head | State height and whether single or double head | no
03.900.2000.31 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting column only | State height and whether single or double head | no
03.900.2000.32 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting head only | State whether single or double head | no
03.900.2000.33 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting head, lantern & luminaire | State type and whether single or double head | no
03.900.2000.34 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting lantern & luminaire only | State type | no
03.900.2000.35 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting lantern only | State type | no
03.900.2000.36 | Materials | Electrical Materials | Metal conductors - Equipment | Lighting luminaire only | State type | no
03.900.2000.40 | Materials | Electrical Materials | Metal conductors - Equipment | Electronic traffic information signs - Advance Mortorway Indicator (AMI) |  | no
03.900.2000.42 | Materials | Electrical Materials | Metal conductors - Equipment | Electronic traffic information signs - Fixed Text Message Sign (FTMS) |  | no
03.900.2000.44 | Materials | Electrical Materials | Metal conductors - Equipment | Electronic traffic information signs - Variable Messaging Sign (VMS) |  | no
03.900.2000.50 | Materials | Electrical Materials | Metal conductors - Equipment | Electronic Variable speed limit signs |  | no
03.900.2000.60 | Materials | Electrical Materials | Metal conductors - Equipment | Electronic traffic information signs - other |  | no
03.900.2000.70 | Materials | Electrical Materials | Metal conductors - Equipment | Batteries for back up power supplies | State type & purpose | no
03.900.2000.75 | Materials | Electrical Materials | Metal conductors - Equipment | Battery charger | State type & purpose | no
03.900.2000.80 | Materials | Electrical Materials | Metal conductors - Equipment | Solar panels | State size, whether or not inclusive of supports and type of supports | no
03.900.2000.85 | Materials | Electrical Materials | Metal conductors - Equipment | Labels | State type and size | no
03.900.2000.90 | Materials | Electrical Materials | Metal conductors - Equipment | Miscellaneous metal conductor equipment | (e.g. transformers, etc). State type | no
03.900.3000.10 | Materials | Electrical Materials | Fibre Optic conductors | Fibre Optic cable | State type of cable and size (mm2) | m
03.900.3000.20 | Materials | Electrical Materials | Fibre Optic conductors | Fibre optic cable - terminal | includes glands. State type of terminal, type and size of cable (mm2) | no
03.900.3000.30 | Materials | Electrical Materials | Fibre Optic conductors | Joint, splicing kit or tee | State type | no
03.900.4000.10 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Signal booster / Antenna | (e.g. mini Hermes transponder) | no
03.900.4000.20 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | CCTV camera |  | no
03.900.4000.22 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Ambient Light Monitor (ALM) | i.e.photocell detector | no
03.900.4000.24 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Flash unit |  | no
03.900.4000.26 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Radar unit |  | no
03.900.4000.28 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Weather sensor | (e.g. wind, barometer, fog, frost, visibility precipitation sensor, etc.). State type | no
03.900.4000.30 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | ERT Emergency phone equipment and enclosure - composite item |  | no
03.900.4000.32 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | ERT Handset |  | no
03.900.4000.34 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | ERT Enclosure |  | no
03.900.4000.36 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | ERT miscellaneous components & fixings | e.g. responder | no
03.900.4000.40 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Interface Terminal / OCU with monitor screen | i.e. offence capture & recording unit equipment. State type & purpose | no
03.900.4000.42 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Interface Terminal / OCU - Monitor screen recorder and printer | State type & purpose (e.g. HADECS 3 local Maintenance Engineer terminal | no
03.900.4000.50 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | ANPR recordor / retrieval system | State type | no
03.900.4000.90 | Materials | Electrical Materials | Fibre Optic conductors - Equipment | Miscellaneous fibre optic conductor equipment | (e.g.tranformers) State type | no
03.900.5000.10 | Materials | Electrical Materials | Containment (ducts taken elsewhere) | Open cable tray | State type, size and use | m
03.900.5000.20 | Materials | Electrical Materials | Containment (ducts taken elsewhere) | Above ground conduit or ducting | State type, size and use | m
03.900.5000.30 | Materials | Electrical Materials | Containment (ducts taken elsewhere) | Separate GRP enclosures, cabinets, boxes and the like | State type, size and use | no
03.990.1000.10 | Materials | Other Materials | Other Materials | Unallocated materials | Include here new or otherwise non-standard items. State quantity and type of individual units (drum, bag, millilitre,etc). | LS
03.990.1000.15 | Materials | Other Materials | Other Materials | Materials not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories. | LS
03.990.1000.20 | Materials | Other Materials | Other Materials | Arithmetic errors |  | LS
03.990.1000.30 | Materials | Other Materials | Other Materials | Revenue from recycling materials |  | LS
04.100.1000.10 | Other | Provision of temporary services (non Mobile) | Provision of temporary water | Installation of temporary water service |  | LS
04.100.1000.20 | Other | Provision of temporary services (non Mobile) | Provision of temporary water | Charges for water consumption |  | LS
04.100.1000.30 | Other | Provision of temporary services (non Mobile) | Provision of temporary water | Remove temporary water service on completion of works |  | LS
04.100.2000.10 | Other | Provision of temporary services (non Mobile) | Provision of temporary gas | Installation of temporary gas service |  | LS
04.100.2000.20 | Other | Provision of temporary services (non Mobile) | Provision of temporary gas | Charges for gas consumption |  | LS
04.100.2000.30 | Other | Provision of temporary services (non Mobile) | Provision of temporary gas | Provision of temporary gas tank & base |  | LS
04.100.2000.40 | Other | Provision of temporary services (non Mobile) | Provision of temporary gas | Remove temporary gas on completion of works |  | LS
04.100.3000.10 | Other | Provision of temporary services (non Mobile) | Provision of temporary electricity | Installation of temporary electricity service |  | LS
04.100.3000.20 | Other | Provision of temporary services (non Mobile) | Provision of temporary electricity | Charges for electricity consumption |  | LS
04.100.3000.30 | Other | Provision of temporary services (non Mobile) | Provision of temporary electricity | Remove temporary electricity on completion of works |  | LS
04.200.1000.10 | Other | Payments to public authorities | Planning & building regulations fees associated with temporary offices | Planning fees associated with temporary offices |  | LS
04.200.1000.20 | Other | Payments to public authorities | Planning & building regulations fees associated with temporary offices | Building regulations fees associated with temporary offices |  | LS
04.200.1000.30 | Other | Payments to public authorities | Planning & building regulations fees associated with temporary offices | Scheme Registration Fees |  | LS
04.200.2000.10 | Other | Payments to public authorities | Orders, Licences & Fees | Environment Agency Licences |  | LS
04.200.2000.20 | Other | Payments to public authorities | Orders, Licences & Fees | Local Authority Licences / Orders |  | LS
04.200.2000.30 | Other | Payments to public authorities | Orders, Licences & Fees | Network Rail Costs |  | LS
04.200.2000.40 | Other | Payments to public authorities | Orders, Licences & Fees | Considerate contractor |  | LS
04.300.1000.10 | Other | Cancellation charges arising out from compensation event | Allowable cancellation charges | Restocking charges |  | LS
04.300.1000.20 | Other | Cancellation charges arising out from compensation event | Allowable cancellation charges | Abortive manufacturing costs |  | LS
04.300.1000.30 | Other | Cancellation charges arising out from compensation event | Allowable cancellation charges | Abortive delivery costs |  | LS
04.400.1000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Buying or leasing land | Land or building purchase costs |  | LS
04.400.1000.20 | Other | Payments associated with the temporary use of land and buildings etc. | Buying or leasing land | Land or building rent costs |  | LS
04.400.1000.30 | Other | Payments associated with the temporary use of land and buildings etc. | Buying or leasing land | Legal & other fees associated with buying, selling or renting land or buildings for temporary use |  | LS
04.400.1000.40 | Other | Payments associated with the temporary use of land and buildings etc. | Buying or leasing land | Building refurbishment costs associated with first occupying buildings & dilapidations |  | LS
04.400.2000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Compensation Payments to third parties | Compensation Payments to third parties e.g. for loss of crops |  | LS
04.400.3000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Royalties | Royalties |  | LS
04.400.4000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Inspection Certificates | Inspection Certificates | inc Fire | LS
04.400.5000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Charges for access to working areas | Charges for access to working areas |  | LS
04.400.6000.10 | Other | Payments associated with the temporary use of land and buildings etc. | Facilities for visits to the working areas by others | Facilities for visits to the working areas by others |  | LS
04.500.1000.10 | Other | Office supplies and services | Office supplies & services for the Contractor | Purchase of equipment and furniture (for Contractor) | Includes signage for compound & accomodation areas | LS
04.500.1000.20 | Other | Office supplies and services | Office supplies & services for the Contractor | Hire of equipment and furniture (for Contractor) |  | wk
04.500.1000.30 | Other | Office supplies and services | Office supplies & services for the Contractor | Communications/telephone systems (for Contractor) |  | LS
04.500.1000.40 | Other | Office supplies and services | Office supplies & services for the Contractor | IT (for Contractor) | (i.e. Computers/Servers/Video Conferencing etc) | LS
04.500.1000.50 | Other | Office supplies and services | Office supplies & services for the Contractor | Telephone charges (for Contractor) |  | LS
04.500.1000.60 | Other | Office supplies and services | Office supplies & services for the Contractor | Consumables (for Contractor) |  | LS
04.500.1000.70 | Other | Office supplies and services | Office supplies & services for the Contractor | Servicing of temporary toilets (for Contractor) | includes cleaning and effluent disposal service | LS
04.500.2000.10 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Purchase of equipment and furniture (for Client) | Includes signage for compound & accomodation areas | LS
04.500.2000.20 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Hire of equipment and furniture (for Client) |  | wk
04.500.2000.30 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Communications/telephone systems (for Client |  | LS
04.500.2000.40 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | IT (for Client) | (i.e. Computers/Servers/Video Conferencing etc) | LS
04.500.2000.50 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Telephone charges (for Client) |  | LS
04.500.2000.60 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Consumables (for Client) |  | LS
04.500.2000.70 | Other | Office supplies and services | Office supplies & services for the Client (Overseeing Organisation) | Servicing of temporary toilets (for Client) | includes cleaning and effluent disposal service | LS
04.500.3000.05 | Other | Office supplies and services | Safety Related Equipment | Personal Protective Equipment |  | LS
04.500.3000.10 | Other | Office supplies and services | Safety Related Equipment | First Aid Supplies |  | LS
04.500.3000.15 | Other | Office supplies and services | Safety Related Equipment | Safety Equipment | (i.e Rescue tripod, harness & stretcher, etc.) | LS
04.500.3000.20 | Other | Office supplies and services | Safety Related Equipment | Safety signs & literature | Site or personal safety specific | LS
04.500.3000.25 | Other | Office supplies and services | Safety Related Equipment | Vehicle equipment | (e.g. vehicle stickers, etc.) | LS
04.500.3000.30 | Other | Office supplies and services | Safety Related Equipment | Safety tests & checks |  | LS
04.500.3000.35 | Other | Office supplies and services | Safety Related Equipment | Health checks |  | LS
04.500.3000.40 | Other | Office supplies and services | Safety Related Equipment | Alcohol & drug tests |  | LS
04.990.1000.10 | Other | Other Charges | Other Charges | Unallocated charges | Include here new or otherwise non-standard items | LS
04.990.1000.15 | Other | Other Charges | Other Charges | Charges not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories | LS
04.990.1000.20 | Other | Other Charges | Other Charges | Arithmetic errors |  | LS
05.015.1040.10 | Other | Indirect Works Costs | Attendant Labour and Equipment-Small tools | Small tools for Contractor |  | LS
05.015.1040.20 | Other | Indirect Works Costs | Attendant Labour and Equipment-Small tools | Small tools for Client Overseeing |  | LS
05.015.3010.10 | Other | Indirect Works Costs | General Temporary Works-Site Infrastructure | Haulroads |  | m2
05.015.3010.20 | Other | Indirect Works Costs | General Temporary Works-Site Infrastructure | Hardstandings |  | m2
05.015.3010.30 | Other | Indirect Works Costs | General Temporary Works-Site Infrastructure | Temporary Structures |  | LS
05.015.3010.40 | Other | Indirect Works Costs | General Temporary Works-Site Infrastructure | Temporary Traffic Lights |  | LS
05.015.3010.50 | Other | Indirect Works Costs | General Temporary Works-Site Infrastructure | Protection of services |  | LS
05.015.3020.10 | Other | Indirect Works Costs | General Temporary Works-Waste Removal | General Waste Skips |  | wk
05.015.3020.20 | Other | Indirect Works Costs | General Temporary Works-Waste Removal | Recycables |  | wk
05.015.3020.30 | Other | Indirect Works Costs | General Temporary Works-Waste Removal | Builders Waste |  | wk
05.015.3020.40 | Other | Indirect Works Costs | General Temporary Works-Waste Removal | Revenue from recycling materials |  | LS
05.015.3030.10 | Other | Indirect Works Costs | General Temporary Works-Fencing (To Temporary Works and Structures) | Timber fences |  | m
05.015.3030.20 | Other | Indirect Works Costs | General Temporary Works-Fencing (To Temporary Works and Structures) | Temporary Security Type Panels |  | no
05.015.3030.30 | Other | Indirect Works Costs | General Temporary Works-Fencing (To Temporary Works and Structures) | Pedestrian Panels |  | no
05.015.3040.10 | Other | Indirect Works Costs | General Temporary Works -Scaffolding & Falsework | Scaffolding - Access Scaffolding |  | LS
05.015.3040.20 | Other | Indirect Works Costs | General Temporary Works -Scaffolding & Falsework | Falsework, Shuttering and the like |  | LS
05.015.3050.10 | Other | Indirect Works Costs | General Temporary Works-Temporary Piling & Cofferdams | Trenchsheets |  | m2
05.015.3050.20 | Other | Indirect Works Costs | General Temporary Works-Temporary Piling & Cofferdams | Piles |  | m2
05.015.3050.30 | Other | Indirect Works Costs | General Temporary Works-Temporary Piling & Cofferdams | Other Temporary systems |  | m2
05.015.3050.40 | Other | Indirect Works Costs | General Temporary Works-Temporary Piling & Cofferdams | General Temporary Works-Cofferdams |  | LS
05.015.3060.10 | Other | Indirect Works Costs | General Temporary Works-Miscellaneous Temporary Works | Miscellaneous Temporary Works |  | LS
05.015.4010.10 | Other | Indirect Works Costs | Traffic Management & Safety-Traffic Management | Establish TM |  | LS
05.015.4010.20 | Other | Indirect Works Costs | Traffic Management & Safety-Traffic Management | Maintain TM |  | LS
05.015.4010.30 | Other | Indirect Works Costs | Traffic Management & Safety-Traffic Management | Remove TM |  | LS
05.015.4010.40 | Other | Indirect Works Costs | Traffic Management & Safety-Traffic Management | TM (Establish, Maintain, Remove - All-in) |  | LS
05.015.4015.10 | Other | Indirect Works Costs | Traffic Management-Temporary Journey Time System - set-up, maintenance, monitoring and removal | Set-up temporary Journey Time System |  | LS
05.015.4015.20 | Other | Indirect Works Costs | Traffic Management-Temporary Journey Time System - set-up, maintenance, monitoring and removal | Maintain/monitor temporary Journey Time System |  | LS
05.015.4015.30 | Other | Indirect Works Costs | Traffic Management-Temporary Journey Time System - set-up, maintenance, monitoring and removal | Remove temporary Journey Time System |  | LS
05.015.4020.10 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary CCTV - set-up, maintenance, monitoring and removal | Set-up temporary CCTV |  | LS
05.015.4020.20 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary CCTV - set-up, maintenance, monitoring and removal | Maintain/monitor temporary CCTV |  | LS
05.015.4020.30 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary CCTV - set-up, maintenance, monitoring and removal | Remove temporary CCTV |  | LS
05.015.4030.10 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary Diversion of Traffic | Establish and Remove Traffic Diversions (public) |  | LS
05.015.4030.20 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary Diversion of Traffic | Maintain Traffic Diversions (public) |  | LS
05.015.4030.30 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary Diversion of Traffic | Construct Crossovers |  | LS
05.015.4030.40 | Other | Indirect Works Costs | Traffic Management & Safety-Temporary Diversion of Traffic | Remove Crossovers and Reinstate |  | LS
05.015.4040.10 | Other | Indirect Works Costs | Traffic Management & Safety-Recovery Vehicles | Establish & Remove Recovery Bases & Welfare Facilities |  | LS
05.015.4040.20 | Other | Indirect Works Costs | Traffic Management & Safety-Recovery Vehicles | Recovery Vehicle - Heavy |  | wk
05.015.4040.30 | Other | Indirect Works Costs | Traffic Management & Safety-Recovery Vehicles | Recovery Vehicle - Light |  | wk
05.015.4040.40 | Other | Indirect Works Costs | Traffic Management & Safety-Recovery Vehicles | Recovery Vehicle - Coaches/IPVs/Other |  | wk
05.015.4050.10 | Other | Indirect Works Costs | Winter Maintenance | Winter Maintenance - Gritting |  | LS
05.015.5010.10 | Other | Indirect Works Costs | Speed Enforcement-Temporary speed enforcement cameras | Set-up temporary speed enforcement cameras |  | LS
05.015.5010.20 | Other | Indirect Works Costs | Speed Enforcement-Temporary speed enforcement cameras | Maintain temporary speed enforcement cameras |  | LS
05.015.5010.30 | Other | Indirect Works Costs | Speed Enforcement-Temporary speed enforcement cameras | Remove temporary speed enforcement cameras |  | LS
05.015.5020.10 | Other | Indirect Works Costs | Speed Enforcement--ANPR | Set-up temporary ANPR |  | LS
05.015.5020.20 | Other | Indirect Works Costs | Speed Enforcement--ANPR | Maintain temporary ANPR |  | LS
05.015.5020.30 | Other | Indirect Works Costs | Speed Enforcement--ANPR | Remove temporary ANPR |  | LS
05.020.1010.10 | Other | Site Clearance | Site clearance | General site clearance |  | ha
05.020.1210.10 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Fences and barriers | Road Restraint - All Types (VCB measure in Demolitions) |  | m
05.020.1210.20 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Fences and barriers | Parapets |  | m
05.020.1210.30 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Fences and barriers | Pedestrian guardrails |  | m
05.020.1210.40 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Fences and barriers | Fencing |  | m
05.020.1210.50 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Fences and barriers | Environmental Barriers |  | m
05.020.1220.10 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Kerbs and channels | Kerbs, channels, edgings and the like |  | m
05.020.1220.20 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Kerbs and channels | Combined drainage & kerb blocks |  | m
05.020.1220.30 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Kerbs and channels | Linear drainage channel systems |  | m
05.020.1230.10 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Paving, brickwork etc | Blockwork & stonework |  | m3
05.020.1230.20 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Paving, brickwork etc | Paved Areas & the like |  | m2
05.020.1230.30 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Paving, brickwork etc | Brickwork |  | m2
05.020.1230.40 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Paving, brickwork etc | Copings, string courses and the like |  | m
05.020.1240.10 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Covers, gratings & frames |  | no
05.020.1240.20 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Traffic sign |  | no
05.020.1240.30 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Road stud |  | no
05.020.1240.40 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Marker post |  | no
05.020.1240.50 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Street furniture |  | no
05.020.1240.60 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Other roadworks | Take Up or Down and Set Aside for Re-use or Remove Off Site-Traffic signal |  | LS
05.020.1250.10 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | Cables |  | m
05.020.1250.20 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | Feeder pillars |  | no
05.020.1250.30 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | Lighting column including bracket arm & lantern etc |  | no
05.020.1250.40 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | Communications equipment (excl MS3 / MS4) |  | no
05.020.1250.50 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | MS3 Sign, post and arm |  | no
05.020.1250.60 | Other | Site Clearance | Take Up or Down and Set Aside for Re-use or Remove Off Site-Electrical and Communications | MS4 Sign, post and arm |  | no
05.020.5210.10 | Other | Site Clearance | Demolition | Demolition of individual or groups of buildings or structures |  | no
05.020.5210.20 | Other | Site Clearance | Demolition | Partial demolition of individual structures |  | LS
05.020.5210.30 | Other | Site Clearance | Demolition | Partial demolition of existing Gantries, CCTV Masts and Cantilever MSs including all attached equipment and all associated infrastructure |  | no
05.020.5210.40 | Other | Site Clearance | Demolition | Partial demolition of Drainage and Pipelines (all bores, buried and or above ground) with all associated equipment; penstocks, chambers, pumps, electrical assemblies and the like and all associated infrastructure |  | no
05.020.5210.50 | Other | Site Clearance | Demolition | Partial demolition and Removal of Vertical Concrete Barriers - All Types including all attached equipment and all associated infrastructure |  | m
05.020.5210.60 | Other | Site Clearance | Demolition | Removal of hazardous materials from existing structures, attached or associated equipment (asbestos and the like) |  | LS
05.030.1010.05 | Other | Fencing | Fencing | Concrete foundation to timber posts |  | no
05.030.1010.10 | Other | Fencing | Fencing | Wire to existing fence |  | m
05.030.1010.15 | Other | Fencing | Fencing | Wire mesh to existing fence |  | m
05.030.1010.20 | Other | Fencing | Fencing | Wire mesh fencing |  | m
05.030.1010.25 | Other | Fencing | Fencing | Timber post and rail fence |  | m
05.030.1010.30 | Other | Fencing | Fencing | Chain link fence - including foundations |  | m
05.030.1010.35 | Other | Fencing | Fencing | Close Boarded Fence |  | m
05.030.1010.40 | Other | Fencing | Fencing | Galvanized Steel Palisade fencing - unclimbable - including foundations |  | m
05.030.1010.45 | Other | Fencing | Fencing | Post and wire fencing |  | m
05.030.1020.10 | Other | Fencing | Gates and Stiles | Timber gate |  | no
05.030.1020.20 | Other | Fencing | Gates and Stiles | Steel gate |  | no
05.030.1020.30 | Other | Fencing | Gates and Stiles | Stile |  | no
05.030.1020.40 | Other | Fencing | Gates and Stiles | Fenced tree guards |  | no
05.030.1030.10 | Other | Fencing | Remove from store and re-erect fencing, gates and stiles | Remove from store and re-erect gate |  | no
05.030.1030.20 | Other | Fencing | Remove from store and re-erect fencing, gates and stiles | Remove from store and re-erect stile |  | no
05.030.1030.30 | Other | Fencing | Remove from store and re-erect fencing, gates and stiles | Remove from store and re-erect fence |  | m
05.030.1040.10 | Other | Fencing | Fencing, Gates & Stiles-Excavation in hard material | Extra over excavation for excavation in hard material in fencing works |  | m3
05.030.2001.05 | Other | Fencing | Environmental / Noise barriers; All Types | Environmental / Noise barriers; All Types - including foundations |  | m
05.030.2002.05 | Other | Fencing | Remove from store and re-erect Environmental / Noise barriers; All Types | Remove from store and re-erect Environmental / Noise barriers; All Types - including foundations |  | m
05.040.1010.10 | Other | Road Restraint Systems | H1 Safety Barriers - Containment Performance Class and working width class | H1 Safety Barrier |  | m
05.040.1010.20 | Other | Road Restraint Systems | H1 Safety Barriers - Containment Performance Class and working width class | H1 Terminals |  | no
05.040.1010.30 | Other | Road Restraint Systems | H1 Safety Barriers - Containment Performance Class and working width class | H1 Connections to existing systems |  | no
05.040.1010.40 | Other | Road Restraint Systems | H1 Safety Barriers - Containment Performance Class and working width class | H1 Transitions |  | no
05.040.1020.10 | Other | Road Restraint Systems | H2 Safety Barriers - Containment Performance Class and working width class | H2 Safety Barrier |  | m
05.040.1020.20 | Other | Road Restraint Systems | H2 Safety Barriers - Containment Performance Class and working width class | H2 Terminals |  | no
05.040.1020.30 | Other | Road Restraint Systems | H2 Safety Barriers - Containment Performance Class and working width class | H2 Connections to existing systems |  | no
05.040.1020.40 | Other | Road Restraint Systems | H2 Safety Barriers - Containment Performance Class and working width class | H2 Transitions |  | no
05.040.1030.10 | Other | Road Restraint Systems | H4a Safety Barriers - Containment Performance Class and working width class | H4 Safety Barrier |  | m
05.040.1030.20 | Other | Road Restraint Systems | H4a Safety Barriers - Containment Performance Class and working width class | H4 Terminals |  | no
05.040.1030.30 | Other | Road Restraint Systems | H4a Safety Barriers - Containment Performance Class and working width class | H4 Connections to existing systems |  | no
05.040.1030.40 | Other | Road Restraint Systems | H4a Safety Barriers - Containment Performance Class and working width class | H4 Transitions |  | no
05.040.1040.10 | Other | Road Restraint Systems | N2 Safety Barriers - Containment Performance Class and working width class | N2 Safety Barrier |  | m
05.040.1040.20 | Other | Road Restraint Systems | N2 Safety Barriers - Containment Performance Class and working width class | N2 Terminals |  | no
05.040.1040.30 | Other | Road Restraint Systems | N2 Safety Barriers - Containment Performance Class and working width class | N2 Connections to existing systems |  | no
05.040.1040.40 | Other | Road Restraint Systems | N2 Safety Barriers - Containment Performance Class and working width class | N2 Transitions |  | no
05.040.2010.10 | Other | Road Restraint Systems | Other Safety Barrier Work-Crossing Points | Emergency Access / Crossover Systems - (All Types and Classes) |  | no
05.040.2010.20 | Other | Road Restraint Systems | Other Safety Barrier Work-Crossing Points | Maintenance Crossing Points and Maintenance Access - (All Types and Classes) |  | no
05.040.2010.30 | Other | Road Restraint Systems | Other Safety Barrier Work-Crossing Points | Winter Maintenance Crossing Points - (All Types and Classes) |  | no
05.040.2020.10 | Other | Road Restraint Systems | Ancillary Items | Crash cushions |  | no
05.040.2020.20 | Other | Road Restraint Systems | Ancillary Items | Anti-glare screens |  | m
05.040.2510.10 | Other | Road Restraint Systems | Treatment of Existing/Re-use-Remove from store & re-erect safety barriers | Remove from store & re-erect safety barriers |  | m
05.040.2520.10 | Other | Road Restraint Systems | Treatment of Existing/Re-use-Raising/lowering barrier | Raising existing sockets |  | no
05.040.2520.20 | Other | Road Restraint Systems | Treatment of Existing/Re-use-Raising/lowering barrier | Post extension unit |  | no
05.040.3010.10 | Other | Road Restraint Systems | Pedestrian parapets & guardrails | Pedestrian guardrails |  | m
05.040.3010.20 | Other | Road Restraint Systems | Pedestrian parapets & guardrails | Pedestrian parapets |  | m
05.040.3020.10 | Other | Road Restraint Systems | Vehicle Parapets | Parapet |  | m
05.040.3020.20 | Other | Road Restraint Systems | Vehicle Parapets | Parapet Connections |  | no
05.040.4010.10 | Other | Road Restraint Systems | Concrete Barrier | Concrete Barrier |  | m
05.040.4010.20 | Other | Road Restraint Systems | Concrete Barrier | Concrete Barrier Transitions |  | no
05.040.4010.30 | Other | Road Restraint Systems | Concrete Barrier | Concrete Barrier Connections |  | no
05.040.4010.40 | Other | Road Restraint Systems | Concrete Barrier | Bifurcation |  | no
05.040.4010.50 | Other | Road Restraint Systems | Concrete Barrier | Sign Build outs |  | no
05.040.4010.60 | Other | Road Restraint Systems | Concrete Barrier | Other Items |  | LS
05.050.1001.02 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter <300mm in trench |  | m
05.050.1001.04 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=300mm but <600mm in trench |  | m
05.050.1001.06 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=600mm but <900mm in trench |  | m
05.050.1001.08 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=900mm but <1200mm in trench |  | m
05.050.1001.10 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1200mm but <1500mm in trench |  | m
05.050.1001.12 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1500mm but <1800mm in trench |  | m
05.050.1001.14 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1800mm but < 2100mm in trench |  | m
05.050.1001.16 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=2100mm but < 2400mm in trench |  | m
05.050.1001.18 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=2400mm in trench |  | m
05.050.1001.20 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter <300mm in heading |  | m
05.050.1001.22 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=300mm but <600mm in heading |  | m
05.050.1001.24 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=600mm but <900mm in heading |  | m
05.050.1001.26 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=900mm but <1200mm in heading |  | m
05.050.1001.28 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1200mm but <1500mm in heading |  | m
05.050.1001.30 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1500mm but <1800mm in heading |  | m
05.050.1001.32 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1800mm but < 2100mm in heading |  | m
05.050.1001.34 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=2100mm but < 2400mm in heading |  | m
05.050.1001.36 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter>=2400mm in heading |  | m
05.050.1001.38 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter <300mm by jacking or thrustboring |  | m
05.050.1001.40 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=300mm but <600mm by jacking or thrustboring |  | m
05.050.1001.42 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=600mm but <900mm by jacking or thrustboring |  | m
05.050.1001.44 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=900mm but <1200mm by jacking or thrustboring |  | m
05.050.1001.46 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1200mm but <1500mm by jacking or thrustboring |  | m
05.050.1001.48 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1500mm but <1800mm by jacking or thrustboring |  | m
05.050.1001.50 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=1800mm but < 2100mm by jacking or thrustboring |  | m
05.050.1001.55 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter >=2100mm but < 2400mm by jacking or thrustboring |  | m
05.050.1001.60 | Other | Drainage | Drains (excluding filter drains, narrow filter drains and fin drains) and circular piped culverts | Diameter>=2400mm by jacking or thrustboring |  | m
05.050.1002.05 | Other | Drainage | Filter drains in trench | Diameter <300mm |  | m
05.050.1002.10 | Other | Drainage | Filter drains in trench | Diameter >=300 but <450mm |  | m
05.050.1002.15 | Other | Drainage | Filter drains in trench | Diameter >=450mm |  | m
05.050.1002.25 | Other | Drainage | Filter drains in trench | Sub-base material |  | m3
05.050.1002.30 | Other | Drainage | Filter drains in trench | Lightweight aggregate infill |  | m3
05.050.1002.35 | Other | Drainage | Filter drains in trench | Not Used |  | m3
05.050.1002.40 | Other | Drainage | Filter drains in trench | Filter material contiguous with filter drain |  | m3
05.050.1003.05 | Other | Drainage | Fin drains and narrow filter drains | Fin drain specified design group - Stated Group (2 to 16) |  | m
05.050.1003.10 | Other | Drainage | Fin drains and narrow filter drains | Fin drain - Stated Type (5,6 ,7 etc) |  | m
05.050.1003.15 | Other | Drainage | Fin drains and narrow filter drains | Narrow filter drains specified design group - Stated Group (2 to 16) |  | m
05.050.1003.20 | Other | Drainage | Fin drains and narrow filter drains | Narrow filter drains - Stated Type (8,9 or other) |  | m
05.050.1004.05 | Other | Drainage | Connections | Connection of stated diameter pipe to existing drain or piped culvert |  | no
05.050.1004.10 | Other | Drainage | Connections | Connection of stated diameter pipe to existing chamber |  | no
05.050.1004.15 | Other | Drainage | Connections | Connection of stated diameter drain to permanently severed land or mole drain |  | no
05.050.1005.05 | Other | Drainage | Soft spots and other voids | Excavation of soft spots and other voids |  | m3
05.050.1005.10 | Other | Drainage | Soft spots and other voids | Filling of soft spots and other voids |  | m3
05.050.1006.05 | Other | Drainage | Supports left in excavation | Supports left in excavation |  | m2
05.050.1007.05 | Other | Drainage | Excavation in hard material | Excavation in hard material |  | m3
05.050.1008.05 | Other | Drainage | Sand, Band and Wick (Vertical Drain Types) Drains | Sand, Band and Wick (Vertical Drain Types) Drains |  | m
05.050.1801.05 | Other | Drainage | Chambers | Precast concrete chambers <=1050mm dia |  | no
05.050.1801.10 | Other | Drainage | Chambers | Precast concrete chambers >1050mm but <=1200mm dia |  | no
05.050.1801.15 | Other | Drainage | Chambers | Precast concrete chambers >1200mm but <=1500mm dia |  | no
05.050.1801.20 | Other | Drainage | Chambers | Precast concrete chambers >1500mm dia but <=1800mm dia |  | no
05.050.1801.25 | Other | Drainage | Chambers | Precast concrete chambers >1800mm dia but <=2100mm dia |  | no
05.050.1801.30 | Other | Drainage | Chambers | Precast concrete chambers >2100mm dia but <=2400mm dia |  | no
05.050.1801.35 | Other | Drainage | Chambers | Precast concrete chambers >2400mm dia |  | no
05.050.1801.40 | Other | Drainage | Chambers | Brick Chambers |  | no
05.050.1801.45 | Other | Drainage | Chambers | Chambers - Other materials |  | no
05.050.1802.05 | Other | Drainage | Polution control | Oil Interceptors - All types; in Carriageway areas only (not site compound) |  | no
05.050.1802.10 | Other | Drainage | Polution control | Pollution containment facility (complete) |  | LS
05.050.1803.05 | Other | Drainage | Gullies, Silt Traps & Soakaways | Gulley |  | no
05.050.1803.10 | Other | Drainage | Gullies, Silt Traps & Soakaways | Silt Trap |  | no
05.050.1803.15 | Other | Drainage | Gullies, Silt Traps & Soakaways | Soakaway |  | no
05.050.2001.05 | Other | Drainage | Headwalls | Pipe <300mm internal diameter |  | no
05.050.2001.10 | Other | Drainage | Headwalls | Pipe >=300mm < 600mm internal diameter |  | no
05.050.2001.15 | Other | Drainage | Headwalls | Pipe >=600mm < 900mm internal diameter |  | no
05.050.2001.20 | Other | Drainage | Headwalls | Pipe >=900mm internal diameter |  | no
05.050.2002.05 | Other | Drainage | Revetments | Pipe <300mm internal diameter |  | no
05.050.2002.10 | Other | Drainage | Revetments | Pipe >=300mm < 600mm internal diameter |  | no
05.050.2002.15 | Other | Drainage | Revetments | Pipe >=600mm < 900mm internal diameter |  | no
05.050.2002.20 | Other | Drainage | Revetments | Pipe >=900mm internal diameter |  | no
05.050.2003.05 | Other | Drainage | Concrete bagwork | In headwalls |  | no
05.050.2004.05 | Other | Drainage | Outfall | Outfall |  | no
05.050.5201.05 | Other | Drainage | Raising or lowering of covers and gratings on existing chambers and gullies | Cover & frame |  | no
05.050.5201.10 | Other | Drainage | Raising or lowering of covers and gratings on existing chambers and gullies | Grating & frame |  | no
05.050.5202.05 | Other | Drainage | Renewal of covers and gratings on existing chambers and gullies | Cover & frame |  | no
05.050.5202.10 | Other | Drainage | Renewal of covers and gratings on existing chambers and gullies | Grating & frame |  | no
05.050.5203.05 | Other | Drainage | Remove from store and reinstall chamber covers and frames, and gulley gratings and frames | Remove from store and reinstall cover & frame |  | no
05.050.5203.10 | Other | Drainage | Remove from store and reinstall chamber covers and frames, and gulley gratings and frames | Remove from store and reinstall grating & frame |  | no
05.050.5204.05 | Other | Drainage | Grouting up of existing drains and service ducts | Grouting up of existing drains and service ducts |  | LS
05.050.5205.05 | Other | Drainage | Cleaning existing drainage systems | Cleaning piped drainage system |  | m
05.050.5205.10 | Other | Drainage | Cleaning existing drainage systems | Cleaning drainage channels |  | m
05.050.5205.15 | Other | Drainage | Cleaning existing drainage systems | Cleaning linear drainage system |  | m
05.050.5205.20 | Other | Drainage | Cleaning existing drainage systems | Cleaning combined drainage & kerb system |  | m
05.050.5205.25 | Other | Drainage | Cleaning existing drainage systems | Cleaning of bridge drainage system |  | LS
05.050.5205.30 | Other | Drainage | Cleaning existing drainage systems | Cleaning of chambers |  | no
05.050.5205.35 | Other | Drainage | Cleaning existing drainage systems | Cleaning of gullies |  | no
05.050.5206.05 | Other | Drainage | Mechanical and Electrical Systems associated with Drainage systems | Mechanical and Electrical Systems associated with Drainage systems |  | LS
05.050.5207.05 | Other | Drainage | CCTV Survey of existing Drainage Systems | CCTV Survey of existing Drainage Systems |  | LS
05.050.5208.05 | Other | Drainage | Filter Drains - Excavate & replace filter material | Filter Drains - Excavate & replace filter material |  | m3
05.050.6001.05 | Other | Drainage | Drainage and Service Ducts in Structures | Substructure |  | no
05.050.6001.10 | Other | Drainage | Drainage and Service Ducts in Structures | Superstructure |  | no
05.050.6001.15 | Other | Drainage | Drainage and Service Ducts in Structures | Reinforced earth structure |  | no
05.050.6001.20 | Other | Drainage | Drainage and Service Ducts in Structures | Anchored earth structure |  | no
05.050.7001.05 | Other | Drainage | Filling to Pipe Bays and Verges on Bridges | Filling to Pipe Bays and Verges on Bridges |  | m3
05.060.0501.05 | Other | Earthworks | Topsoil Strip, Store, Dispose-Excavation | Excavation of acceptable material Class 5A |  | m3
05.060.0502.05 | Other | Earthworks | Topsoil - storage and disposal | Permanent storage of topsoil |  | m3
05.060.0502.10 | Other | Earthworks | Topsoil - storage and disposal | Disposal of acceptable material Class 5A (Topsoil) |  | m3
05.060.1001.05 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in cutting and other excavation |  | m3
05.060.1001.10 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in ditches and watercourses |  | m3
05.060.1001.15 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in structural foundations |  | m3
05.060.1001.20 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in gabion walling and mattresses |  | m3
05.060.1001.25 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in crib walling |  | m3
05.060.1001.30 | Other | Earthworks | Excavation of acceptable (excluding Class 5A) | Excavation of acceptable material excluding Class 5A in caps to mine working, well, swallow hole and the like |  | m3
05.060.1002.05 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in cutting and other excavation |  | m3
05.060.1002.10 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in ditches and watercourses |  | m3
05.060.1002.15 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in structural foundations |  | m3
05.060.1002.20 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in gabion walling and mattresses |  | m3
05.060.1002.25 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in crib walling |  | m3
05.060.1002.30 | Other | Earthworks | Excavation of unacceptable Class U1 | Excavation of unacceptable material Class U1 in caps to mine working, well, swallow hole and the like |  | m3
05.060.1003.05 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in cutting and other excavation |  | m3
05.060.1003.10 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in ditches and watercourses |  | m3
05.060.1003.15 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in structural foundations |  | m3
05.060.1003.20 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in gabion walling and mattresses |  | m3
05.060.1003.25 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in crib walling |  | m3
05.060.1003.30 | Other | Earthworks | Excavation of unacceptable Class U2 | Excavation of unacceptable material Class U2 in caps to mine working, well, swallow hole and the like |  | m3
05.060.1004.05 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in cutting and other excavation |  | m3
05.060.1004.10 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in ditches and watercourses |  | m3
05.060.1004.15 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in structural foundations |  | m3
05.060.1004.20 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in gabion walling and mattresses |  | m3
05.060.1004.25 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in crib walling |  | m3
05.060.1004.30 | Other | Earthworks | Excavation in hard material | Extra over excavation for excavation in Hard Material in caps to mine working, well, swallow hole and the like |  | m3
05.060.1005.05 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1005.10 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1006.05 | Other | Earthworks | Not Used | Not Used |  | m
05.060.1006.10 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1006.15 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1006.20 | Other | Earthworks | Not Used | Not Used |  | no
05.060.1007.05 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.1008.05 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1009.05 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.1009.10 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.1010.05 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.1010.10 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.1011.05 | Other | Earthworks | Excavation (By dredging); lakes, canals, rivers, Industrial lagoons and from silted locations in dock systems | Excavation (By dredging) |  | m3
05.060.1401.05 | Other | Earthworks | Processing of unacceptable material Classes U1A and U1B | Processing unacceptable material U1A into acceptable material |  | m3
05.060.1401.10 | Other | Earthworks | Processing of unacceptable material Classes U1A and U1B | Processing unacceptable material U1B into acceptable material |  | m3
05.060.1401.15 | Other | Earthworks | Processing of unacceptable material Classes U1A and U1B | Processing unacceptable material (rock) into 6N type material |  | m3
05.060.1402.05 | Other | Earthworks | Soil stabilisation | Soil stabilisation |  | m3
05.060.1402.10 | Other | Earthworks | Soil stabilisation | Soil stabilisation of capping |  | m3
05.060.1601.05 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in embankments and other areas of fill (excluding topsoil) |  | m3
05.060.1601.10 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in strengthened embankments (excluding topsoil) |  | m3
05.060.1601.15 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in earth structures (excluding topsoil) |  | m3
05.060.1601.20 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in landscape areas and environmental bunds (excluding topsoil) |  | m3
05.060.1601.25 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in fill on sub-base material, base and capping |  | m3
05.060.1601.30 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in fill in surcharge areas |  | m3
05.060.1601.35 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in fill to structures |  | m3
05.060.1601.40 | Other | Earthworks | Deposition of fill | Deposition of acceptable material in fill above structural concrete foundations |  | m3
05.060.1602.05 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1602.10 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.1801.05 | Other | Earthworks | Disposal of material | Disposal of acceptable material excluding Class 5A |  | m3
05.060.1801.10 | Other | Earthworks | Disposal of material | Not Used |  | m3
05.060.1801.15 | Other | Earthworks | Disposal of material | Disposal of unacceptable material Class U1 |  | m3
05.060.1801.20 | Other | Earthworks | Disposal of material | Disposal of unacceptable material Class U2 |  | m3
05.060.2001.05 | Other | Earthworks | Imported fill | Imported acceptable material other than class 6F |  | m3
05.060.2001.07 | Other | Earthworks | Imported fill | Imported acceptable material class 6F |  | m3
05.060.2001.10 | Other | Earthworks | Imported fill | Not Used |  | m3
05.060.2201.05 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in embankment and other areas of fill |  | m3
05.060.2201.10 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in strengthened embankments |  | m3
05.060.2201.15 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in earth structures |  | m3
05.060.2201.20 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in landscape areas and environmental bunds |  | m3
05.060.2201.25 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in fill on sub-base material, base and capping |  | m3
05.060.2201.30 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in fill in surcharge areas |  | m3
05.060.2201.35 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in fill to structures |  | m3
05.060.2201.40 | Other | Earthworks | Compaction of fill | Compaction of acceptable material in fill above structural concrete foundations |  | m3
05.060.2401.05 | Other | Earthworks | Topsoiling | Topsoiling <=100mm thick |  | m2
05.060.2401.10 | Other | Earthworks | Topsoiling | Topsoiling >100mm thick |  | m2
05.060.2401.15 | Other | Earthworks | Topsoiling | Imported topsoil Class 5B |  | m3
05.060.4501.05 | Other | Earthworks | Soil Preparation-Geotextiles | Geotextiles - Lightweight |  | m2
05.060.4501.10 | Other | Earthworks | Soil Preparation-Geotextiles | Geotextiles - Other |  | m2
05.060.4502.05 | Other | Earthworks | Soil Preparation-Completion of formation and sub-formation | Sub-formation |  | m2
05.060.4502.10 | Other | Earthworks | Soil Preparation-Completion of formation and sub-formation | Sub-formation on rock |  | m2
05.060.4502.15 | Other | Earthworks | Soil Preparation-Completion of formation and sub-formation | Formation |  | m2
05.060.4502.20 | Other | Earthworks | Soil Preparation-Completion of formation and sub-formation | Formation on rock |  | m2
05.060.4503.05 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.4503.10 | Other | Earthworks | Not Used | Not Used |  | m3
05.060.4504.05 | Other | Earthworks | Not Used | Not Used |  | m2
05.060.4505.05 | Other | Earthworks | Not Used | Not Used |  | m
05.060.5001.05 | Other | Earthworks | Ground Improvement-Precast Concrete Piling-Piling Plant | Establishment of pcc piling plant |  | LS
05.060.5001.10 | Other | Earthworks | Ground Improvement-Precast Concrete Piling-Piling Plant | Moving pcc piling plant |  | no
05.060.5002.05 | Other | Earthworks | Precast concrete piles: All Cross Sections | Supply piles |  | m
05.060.5002.10 | Other | Earthworks | Precast concrete piles: All Cross Sections | Stripping Vertical |  | no
05.060.5002.15 | Other | Earthworks | Precast concrete piles: All Cross Sections | Stripping Raking |  | no
05.060.5002.20 | Other | Earthworks | Precast concrete piles: All Cross Sections | Driving Vertical |  | m
05.060.5002.25 | Other | Earthworks | Precast concrete piles: All Cross Sections | Driving Raking |  | m
05.060.5002.30 | Other | Earthworks | Precast concrete piles: All Cross Sections | Lengthening Vertical |  | m
05.060.5002.35 | Other | Earthworks | Precast concrete piles: All Cross Sections | Lengthening Raking |  | m
05.060.5002.40 | Other | Earthworks | Precast concrete piles: All Cross Sections | Driving lengthened vertical piles - all lengths |  | m
05.060.5003.05 | Other | Earthworks | Ground Improvement - Precast Concrete Piling-Proof Loading of Piles | Establishment of PC concrete proof loading equipment |  | LS
05.060.5003.10 | Other | Earthworks | Ground Improvement - Precast Concrete Piling-Proof Loading of Piles | Proof loading of vertical piles |  | no
05.060.5003.15 | Other | Earthworks | Ground Improvement - Precast Concrete Piling-Proof Loading of Piles | Proof loading of raking piles |  | no
05.060.5204.05 | Other | Earthworks | Ground Improvement-Cast-in-Place Piling Plant | Establishment of cast-in-place piling plant |  | LS
05.060.5204.10 | Other | Earthworks | Ground Improvement-Cast-in-Place Piling Plant | Moving cast-in-place piling plant |  | no
05.060.5205.05 | Other | Earthworks | Cast-in-place piles | Cast-in-place piles <= 450mm dia |  | m
05.060.5205.07 | Other | Earthworks | Cast-in-place piles | Cast-in-place piles >450mm dia but <=600 mm dia |  | m
05.060.5205.10 | Other | Earthworks | Cast-in-place piles | Cast-in-place piles >600mm dia but <=900mm dia |  | m
05.060.5205.15 | Other | Earthworks | Cast-in-place piles | Cast-in-place piles >900mm dia |  | m
05.060.5205.20 | Other | Earthworks | Cast-in-place piles | Empty bores <=450mm dia |  | m
05.060.5205.25 | Other | Earthworks | Cast-in-place piles | Empty bores >450mm dia but <=600 mm dia |  | m
05.060.5205.30 | Other | Earthworks | Cast-in-place piles | Empty bores >600mm dia but <=900mm dia |  | m
05.060.5205.35 | Other | Earthworks | Cast-in-place piles | Empty bores >900mm dia |  | m
05.060.5205.40 | Other | Earthworks | Cast-in-place piles | Enlarged base |  | no
05.060.5206.05 | Other | Earthworks | Reinforcement for Cast-in-place piles | Steel bar reinforcement |  | t
05.060.5206.10 | Other | Earthworks | Reinforcement for Cast-in-place piles | Steel helical reinforcement |  | t
05.060.5207.05 | Other | Earthworks | Proof Loading of Cast-in-Place Piles | Establishment of cast-in-place proof loading equipment |  | LS
05.060.5207.07 | Other | Earthworks | Proof Loading of Cast-in-Place Piles | Proof loading of vertical piles |  | no
05.060.5207.10 | Other | Earthworks | Proof Loading of Cast-in-Place Piles | Proof loading of raking piles |  | no
05.060.5501.05 | Other | Earthworks | Ground improvement-stone columns-Establishment of plant | Establishment of dynamic compaction plant |  | LS
05.060.5501.10 | Other | Earthworks | Ground improvement-stone columns-Establishment of plant | Establishment of vibrated stone columns plant |  | LS
05.060.5502.05 | Other | Earthworks | Ground improvement - Dynamic compaction | Dynamic compaction in trial compaction |  | m
05.060.5502.10 | Other | Earthworks | Ground improvement - Dynamic compaction | Dynamic compaction in main compaction |  | m
05.060.5502.15 | Other | Earthworks | Ground improvement - Dynamic compaction | Dynamic compaction plant standing time |  | Hr
05.060.5502.20 | Other | Earthworks | Ground improvement - Dynamic compaction | Material in granular blanket |  | t
05.060.5503.05 | Other | Earthworks | Ground improvement - Vibrated stone columns | Vibrated stone columns of minimum diameter <= 600mm |  | m
05.060.5503.10 | Other | Earthworks | Ground improvement - Vibrated stone columns | Vibrated stone columns of minimum diameter > 600mm but <= 900mm |  | m
05.060.5503.15 | Other | Earthworks | Ground improvement - Vibrated stone columns | Vibrated stone columns of minimum diameter > 900mm but <= 1200mm |  | m
05.060.5503.20 | Other | Earthworks | Ground improvement - Vibrated stone columns | Vibrated stone columns of minimum diameter > 1200mm |  | m
05.060.5503.25 | Other | Earthworks | Ground improvement - Vibrated stone columns | Vibrated stone columns plant standing time |  | Hr
05.060.6001.05 | Other | Earthworks | Soil Nailing | Establishment of plant for soil nails |  | LS
05.060.6001.10 | Other | Earthworks | Soil Nailing | Moving plant for soil nails |  | no
05.060.6001.15 | Other | Earthworks | Soil Nailing | Permanent soil nails <=10m length to sloping areas |  | m
05.060.6001.20 | Other | Earthworks | Soil Nailing | Permanent soil nails > 10m length to sloping areas |  | m
05.060.6001.25 | Other | Earthworks | Soil Nailing | Permanent soil nails length <=10m length to other areas |  | m
05.060.6001.30 | Other | Earthworks | Soil Nailing | Permanent soil nails > 10m length to other areas |  | m
05.060.6001.35 | Other | Earthworks | Soil Nailing | Grouting Soil Nails |  | m
05.060.6002.05 | Other | Earthworks | Testing for Ground Investigation | Testing for Ground Investigation |  | LS
05.060.6501.05 | Other | Earthworks | Ground anchorages - anchorage plant | Establishment of ground anchorage plant |  | LS
05.060.6502.05 | Other | Earthworks | Ground anchorages | Ground anchorages in trial anchorages |  | m
05.060.6502.10 | Other | Earthworks | Ground anchorages | Ground anchorages in main anchorages |  | m
05.060.6503.05 | Other | Earthworks | Ground anchorages - waterproofing anchorage boreholes | Waterproofing boreholes |  | m
05.060.6504.05 | Other | Earthworks | Testing of Ground Anchors | Test equipment, testing and reporting |  | LS
05.060.7001.05 | Other | Earthworks | Gabion walling and mattresses | Gabion walling |  | m3
05.060.7001.10 | Other | Earthworks | Gabion walling and mattresses | Mattress |  | m3
05.060.7201.05 | Other | Earthworks | Crib walling | Crib walling |  | m2
05.060.7201.10 | Other | Earthworks | Crib walling | Crib walling - curved on plan |  | m2
05.060.7501.05 | Other | Earthworks | Instrumentation and monitoring - boring plant | Establishment of boring plant |  | LS
05.060.7502.05 | Other | Earthworks | Instrumentation and monitoring - boring holes | Boring vertical holes |  | m
05.060.7502.10 | Other | Earthworks | Instrumentation and monitoring - boring holes | Boring raking holes |  | m
05.060.7503.05 | Other | Earthworks | Instrumentation and monitoring - instrumentation | Installation of instrument |  | no
05.060.7503.10 | Other | Earthworks | Instrumentation and monitoring - instrumentation | Installation of tubing |  | m
05.060.7503.15 | Other | Earthworks | Instrumentation and monitoring - instrumentation | Installation of cabling |  | m
05.060.7503.20 | Other | Earthworks | Instrumentation and monitoring - instrumentation | Standard grouting |  | m
05.060.7503.25 | Other | Earthworks | Instrumentation and monitoring - instrumentation | Pressure grouting |  | m
05.060.7504.05 | Other | Earthworks | Instrumentation and monitoring - instrument hut or cabinet | Erection of instrument hut or cabinet |  | LS
05.060.7504.10 | Other | Earthworks | Instrumentation and monitoring - instrument hut or cabinet | Servicing of instrument hut or cabinet |  | LS
05.060.7504.15 | Other | Earthworks | Instrumentation and monitoring - instrument hut or cabinet | Dismantling of instrument hut or cabinet |  | LS
05.060.8001.05 | Other | Earthworks | Ground water lowering | Ground water lowering |  | LS
05.060.8002.05 | Other | Earthworks | Soft spots and other voids | Excavation of soft spots and other voids |  | m3
05.060.8002.10 | Other | Earthworks | Soft spots and other voids | Filling of soft spots and other voids |  | m3
05.060.8003.05 | Other | Earthworks | Disused sewers, Drains, Cables, Ducts, Pipelines and the like; occurring at formation level or sub-formation level; Disused basements, cellars and the like and gullies | Removal of disused services |  | m
05.060.8003.10 | Other | Earthworks | Disused sewers, Drains, Cables, Ducts, Pipelines and the like; occurring at formation level or sub-formation level; Disused basements, cellars and the like and gullies | Backfilling of disused services |  | m3
05.060.8003.15 | Other | Earthworks | Disused sewers, Drains, Cables, Ducts, Pipelines and the like; occurring at formation level or sub-formation level; Disused basements, cellars and the like and gullies | Backfilling of disused basements, cellars & the like |  | m3
05.060.8003.20 | Other | Earthworks | Disused sewers, Drains, Cables, Ducts, Pipelines and the like; occurring at formation level or sub-formation level; Disused basements, cellars and the like and gullies | Backfilling of disused gullies |  | no
05.060.8004.05 | Other | Earthworks | Supports left in excavation | Supports left in excavation |  | m2
05.060.8005.05 | Other | Earthworks | Trial pits | Trial pits |  | m3
05.060.8006.05 | Other | Earthworks | Breaking up and perforation of redundant pavements | Breaking up of redundant - unreinforced pavements |  | m2
05.060.8006.10 | Other | Earthworks | Breaking up and perforation of redundant pavements | Breaking up of redundant - reinforced pavements |  | m2
05.060.8007.05 | Other | Earthworks | Perforation of redundant slabs, basements and the like | Perforation of redundant - unreinforced pavements |  | m2
05.060.8007.10 | Other | Earthworks | Perforation of redundant slabs, basements and the like | Perforation of redundant - reinforced pavement |  | m2
05.060.8008.05 | Other | Earthworks | Filling and caps to mine working, well, swallow hole and the like | Filling to mine working, well, swallow hole and the like |  | m3
05.060.8008.10 | Other | Earthworks | Filling and caps to mine working, well, swallow hole and the like | Caps to mine working, well, swallow hole and the like |  | m3
05.060.8009.05 | Other | Earthworks | Lining of watercourses | Lining of watercourses |  | m2
05.060.8010.05 | Other | Earthworks | Clearing of existing ditches | Clearing of existing ditches |  | m
05.070.1001.10 | Other | Pavements | Sub-base | Type 1 unbound mixture |  | m3
05.070.1001.20 | Other | Pavements | Sub-base | Type 2 unbound mixture |  | m3
05.070.1001.30 | Other | Pavements | Sub-base | Type 3 (open grade) unbound mixture |  | m3
05.070.1001.40 | Other | Pavements | Sub-base | Category B (close graded) unbound mixture |  | m3
05.070.1001.50 | Other | Pavements | Sub-base | Type 4 (asphalt arisings) unbound mixture |  | m3
05.070.1001.60 | Other | Pavements | Sub-base | Cement bound granular mixture |  | m3
05.070.1001.70 | Other | Pavements | Sub-base | Wet lean concrete |  | m3
05.070.1001.75 | Other | Pavements | Sub-base | Sub-base - Foamed concrete |  | m3
05.070.1001.80 | Other | Pavements | Sub-base | Slag bound mixture |  | m3
05.070.1001.90 | Other | Pavements | Sub-base | Fly ash bound mixture |  | m3
05.070.1001.91 | Other | Pavements | Sub-base | Hydraulic road binder bound material |  | m3
05.070.1501.05 | Other | Pavements | Base | Cement Bound Granular Mixture (CBGM A) |  | m3
05.070.1501.10 | Other | Pavements | Base | Cement Bound Granular Mixture (CBGM B) |  | m3
05.070.1501.15 | Other | Pavements | Base | Cement Bound Granular Mixture (CBGM C) |  | m3
05.070.1501.20 | Other | Pavements | Base | Wet lean concrete |  | m3
05.070.1501.25 | Other | Pavements | Base | Hot rolled asphalt |  | m3
05.070.1501.30 | Other | Pavements | Base | Stone mastic asphalt |  | m3
05.070.1501.35 | Other | Pavements | Base | Slag Bound Mixture |  | m3
05.070.1501.40 | Other | Pavements | Base | Hydraulic bound mixture (HBM) |  | m3
05.070.1501.45 | Other | Pavements | Base | Dense asphalt concrete / Dense bitumen macadam (DBM50) |  | m3
05.070.1501.50 | Other | Pavements | Base | High Modular Base (HMB) |  | m3
05.070.1501.60 | Other | Pavements | Base | EME2 asphalt concrete |  | m3
05.070.1501.65 | Other | Pavements | Base | Slate macadam |  | m3
05.070.1501.67 | Other | Pavements | Base | Heavy duty macadam (HDM50) |  | m3
05.070.1501.70 | Other | Pavements | Base | Unreinforced concrete |  | m3
05.070.1501.75 | Other | Pavements | Base | Base - Foamed concrete |  | m3
05.070.1502.05 | Other | Pavements | Binder Course | Hot rolled asphalt |  | m3
05.070.1502.06 | Other | Pavements | Binder Course | High Modular Base (HMB) |  | m3
05.070.1502.07 | Other | Pavements | Binder Course | Stone mastic asphalt |  | m3
05.070.1502.10 | Other | Pavements | Binder Course | Dense asphalt concrete / Dense bitumen macadam (DBM50) |  | m3
05.070.1502.15 | Other | Pavements | Binder Course | EME2 asphalt concrete |  | m3
05.070.1502.17 | Other | Pavements | Binder Course | Heavy duty macadam (HDM50) |  | m3
05.070.1503.05 | Other | Pavements | Surface course | Hot rolled asphalt |  | m3
05.070.1503.10 | Other | Pavements | Surface course | Stone mastic asphalt |  | m3
05.070.1503.15 | Other | Pavements | Surface course | Dense bitumen macadam (DBM50) |  | m3
05.070.1503.20 | Other | Pavements | Surface course | Close graded asphalt concrete |  | m3
05.070.1503.25 | Other | Pavements | Surface course | Open graded asphalt concrete |  | m3
05.070.1503.30 | Other | Pavements | Surface course | Fine graded asphalt concrete |  | m3
05.070.1503.35 | Other | Pavements | Surface course | Dense asphalt concrete |  | m3
05.070.1503.40 | Other | Pavements | Surface course | Porous asphalt |  | m3
05.070.1503.45 | Other | Pavements | Surface course | Thin |  | m3
05.070.1504.05 | Other | Pavements | Concrete Pavement | Special permitted alternative design for concrete |  | m3
05.070.1504.10 | Other | Pavements | Concrete Pavement | Jointed reinforced concrete |  | m3
05.070.1504.15 | Other | Pavements | Concrete Pavement | Unreinforced concrete |  | m3
05.070.1504.20 | Other | Pavements | Concrete Pavement | Continuously reinforced concrete |  | m3
05.070.2001.05 | Other | Pavements | Regulating Course Bituminous | Stone mastic asphalt |  | m3
05.070.2001.10 | Other | Pavements | Regulating Course Bituminous | Dense bitumen macadam (DBM50) |  | m3
05.070.2001.15 | Other | Pavements | Regulating Course Bituminous | Dense macadam |  | m3
05.070.2001.20 | Other | Pavements | Regulating Course Bituminous | Close graded macadam |  | m3
05.070.2001.25 | Other | Pavements | Regulating Course Bituminous | Open graded macadam |  | m3
05.070.2001.30 | Other | Pavements | Regulating Course Bituminous | Fine graded macadam |  | m3
05.070.2001.35 | Other | Pavements | Regulating Course Bituminous | Heavy duty macadam (HDM50) |  | m3
05.070.2001.40 | Other | Pavements | Regulating Course Bituminous | Rolled asphalt (design mix) |  | m3
05.070.2001.45 | Other | Pavements | Regulating Course Bituminous | Rolled asphalt (design recipe mix) |  | m3
05.070.2001.50 | Other | Pavements | Regulating Course Bituminous | High Modulus base (HMB) |  | m3
05.070.2002.05 | Other | Pavements | Regulating Course Cement Bound | Cement Bound Granular Mixture (CBGM A) |  | m3
05.070.2002.07 | Other | Pavements | Regulating Course Cement Bound | Cement Bound Granular Mixture (CBGM B) |  | m3
05.070.2002.10 | Other | Pavements | Regulating Course Cement Bound | Cement Bound Granular Mixture (CBGM C) |  | m3
05.070.2002.15 | Other | Pavements | Regulating Course Cement Bound | Wet lean concrete |  | m3
05.070.2501.05 | Other | Pavements | Cold Milling | Cold Milling 100mm or less |  | m2
05.070.2501.10 | Other | Pavements | Cold Milling | Cold Milling over 100mm |  | m2
05.070.3001.05 | Other | Pavements | Surface Treatment | Slurry sealing |  | m2
05.070.3001.10 | Other | Pavements | Surface Treatment | Surface Dressing |  | m2
05.070.3001.15 | Other | Pavements | Surface Treatment | Bituminous Spray |  | m2
05.070.3001.20 | Other | Pavements | Surface Treatment | Resin based surface treatment |  | m2
05.070.3002.05 | Other | Pavements | Tack Coat | Tack Coat |  | m2
05.070.9001.05 | Other | Pavements | In situ recycling - The remix & repave processes | In situ recycling - The remix & repave processes: Repave |  | m2
05.070.9001.10 | Other | Pavements | In situ recycling - The remix & repave processes | In situ recycling - The remix & repave processes: Remix |  | m2
05.070.9001.15 | Other | Pavements | In situ recycling - The remix & repave processes | In situ recycling - The remix & repave processes: Remix / repave |  | m2
05.070.9002.05 | Other | Pavements | Reinstatement of paved areas | Reinstatement of paved areas |  | m2
05.070.9003.05 | Other | Pavements | Thin bonded repairs to existing concrete carriageway | Thin bonded repairs |  | m2
05.070.9004.05 | Other | Pavements | Full depth repairs & bay replacement repairs to existing concrete carriageway | Full depth repairs - unreinforced slab |  | m2
05.070.9004.07 | Other | Pavements | Full depth repairs & bay replacement repairs to existing concrete carriageway | Full depth repairs - reinforced slab |  | m2
05.070.9004.10 | Other | Pavements | Full depth repairs & bay replacement repairs to existing concrete carriageway | Bay replacement repairs - unreinforced slab |  | m2
05.070.9004.15 | Other | Pavements | Full depth repairs & bay replacement repairs to existing concrete carriageway | Bay replacement repairs - reinforced slab |  | m2
05.070.9004.20 | Other | Pavements | Full depth repairs & bay replacement repairs to existing concrete carriageway | Reinstatement of sub-base |  | m3
05.070.9005.05 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Removal of existing bituminous overlay |  | m2
05.070.9005.07 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Main trial |  | LS
05.070.9005.10 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Re-assessment trial |  | no
05.070.9005.15 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Saw-cutting existing pavement |  | m2
05.070.9005.20 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Cracking existing pavement |  | m2
05.070.9005.25 | Other | Pavements | Saw cutting, cracking & seating existing jointed reinforced concrete pavements | Seating existing pavement |  | m2
05.070.9006.05 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Removal of existing bituminous overlay |  | m2
05.070.9006.07 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Main trial |  | LS
05.070.9006.10 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Re-assessment trial |  | no
05.070.9006.15 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Cracking - Jointed unreinforced concrete pavements |  | m2
05.070.9006.20 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Cracking - CBM base |  | m2
05.070.9006.25 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Seating - Jointed unreinforced concrete pavements |  | m2
05.070.9006.30 | Other | Pavements | Cracking & seating of existing jointed unreinforced concrete pavements & CBM bases | Seating - CBM base |  | m2
05.070.9008.05 | Other | Pavements | Maintenance of arrester beds | Maintenance of arrester beds |  | LS
05.070.9009.05 | Other | Pavements | Repairs & patching | Repairs to potholes |  | kg
05.070.9009.07 | Other | Pavements | Repairs & patching | Repairs to depressions |  | kg
05.070.9009.10 | Other | Pavements | Repairs & patching | Patching in area <= 10m2 |  | m2
05.070.9009.15 | Other | Pavements | Repairs & patching | Patching in area 10m2 or more |  | m2
05.070.9510.10 | Other | Pavements | Joint repairs to existing concrete carriageway | Joint repairs |  | m
05.070.9510.15 | Other | Pavements | Joint repairs to existing concrete carriageway | Saw-cutting grooves |  | m
05.070.9510.20 | Other | Pavements | Joint repairs to existing concrete carriageway | Sealing grooves |  | m
05.070.9520.05 | Other | Pavements | Overbanding & inlaid crack sealing repair system | Simple overbanding repair system |  | m
05.070.9520.10 | Other | Pavements | Overbanding & inlaid crack sealing repair system | Fill & overbanding repair system |  | m
05.070.9520.15 | Other | Pavements | Overbanding & inlaid crack sealing repair system | Inlaid sealing repair system |  | m
05.110.1001.10 | Other | Kerbs, Footways And Paved Areas | Kerbs, Channels and Edgings | Kerbs |  | m
05.110.1001.20 | Other | Kerbs, Footways And Paved Areas | Kerbs, Channels and Edgings | Channels |  | m
05.110.1001.23 | Other | Kerbs, Footways And Paved Areas | Kerbs, Channels and Edgings | Channels - slip-formed or cast in-situ |  | m
05.110.1001.26 | Other | Kerbs, Footways And Paved Areas | Kerbs, Channels and Edgings | Channel outlets - slip formed or cast in-situ | including connections | no
05.110.1001.30 | Other | Kerbs, Footways And Paved Areas | Kerbs, Channels and Edgings | Edgings |  | m
05.110.1201.10 | Other | Kerbs, Footways And Paved Areas | Combined Drainage and Kerb Units | Combined Drainage and Kerb Units |  | m
05.110.1401.10 | Other | Kerbs, Footways And Paved Areas | Linear Drainage Channel Systems | Linear Drainage Channel Systems |  | m
05.110.1601.10 | Other | Kerbs, Footways And Paved Areas | Footways and paved areas | Slabs, setts or blocks |  | m2
05.110.1601.20 | Other | Kerbs, Footways And Paved Areas | Footways and paved areas | Concrete or Asphalt paving |  | m2
05.110.1601.30 | Other | Kerbs, Footways And Paved Areas | Footways and paved areas | Concrete cellular paving systems |  | m2
05.110.1601.40 | Other | Kerbs, Footways And Paved Areas | Footways and paved areas | Regulating course |  | m3
05.110.1602.10 | Other | Kerbs, Footways And Paved Areas | Steps | Steps |  | no
05.110.1602.20 | Other | Kerbs, Footways And Paved Areas | Steps | Modifications to existing steps |  | no
05.110.1603.10 | Other | Kerbs, Footways And Paved Areas | Slab-On-Edge | Paving slab-on-edge retaining wall |  | m
05.110.2001.10 | Other | Kerbs, Footways And Paved Areas | Additional concrete for kerbs, channels, edgings, combined drainage and kerb blocks and linear channel systems | Additional concrete for kerbs, channels, edgings, combined drainage and kerb blocks and linear channel systems |  | m3
05.110.2501.10 | Other | Kerbs, Footways And Paved Areas | Remove from store and relay kerbs, channels, edgings, combined drainage and kerb blocks and linear channel systems | Remove from store and relay kerbs, channels, edgings, combined drainage and kerb blocks and linear channel systems |  | m
05.110.3001.10 | Other | Kerbs, Footways And Paved Areas | Remove from store and relay paving flags, slabs and blocks | Remove from store and relay paving flags, slabs and blocks |  | m2
05.110.3501.10 | Other | Kerbs, Footways And Paved Areas | Remove from store and re-erect street furniture | Remove from store and re-erect street furniture |  | no
05.120.1010.10 | Other | Traffic Signs And Road Markings | Permanent illuminated traffic signs on posts | Illuminated traffic signs <=1.0m2 in area |  | no
05.120.1010.20 | Other | Traffic Signs And Road Markings | Permanent illuminated traffic signs on posts | Illuminated traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1010.30 | Other | Traffic Signs And Road Markings | Permanent illuminated traffic signs on posts | Illuminated traffic signs >5m2 but <=10m2 in area |  | no
05.120.1010.40 | Other | Traffic Signs And Road Markings | Permanent illuminated traffic signs on posts | Illuminated traffic signs >10m2 in area |  | no
05.120.1010.50 | Other | Traffic Signs And Road Markings | Permanent illuminated traffic signs on posts | Illuminated traffic signs including variable messaging |  | no
05.120.1020.10 | Other | Traffic Signs And Road Markings | Permanent non-illuminated traffic signs on posts | Non-illuminated traffic signs <=1.0m2 in area |  | no
05.120.1020.20 | Other | Traffic Signs And Road Markings | Permanent non-illuminated traffic signs on posts | Non-illuminated traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1020.30 | Other | Traffic Signs And Road Markings | Permanent non-illuminated traffic signs on posts | Non-illuminated traffic signs >5m2 but <=10m2 in area |  | no
05.120.1020.40 | Other | Traffic Signs And Road Markings | Permanent non-illuminated traffic signs on posts | Non-illuminated traffic signs >10m2 in area |  | no
05.120.1020.50 | Other | Traffic Signs And Road Markings | Permanent non-illuminated traffic signs on posts | Non-illuminated traffic signs including variable messaging |  | no
05.120.1030.10 | Other | Traffic Signs And Road Markings | Gantry mounted traffic signs | Gantry mounted traffic signs <=1.0m2 in area |  | no
05.120.1030.20 | Other | Traffic Signs And Road Markings | Gantry mounted traffic signs | Gantry mounted traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1030.30 | Other | Traffic Signs And Road Markings | Gantry mounted traffic signs | Gantry mounted traffic signs >5m2 but <=10m2 in area |  | no
05.120.1030.40 | Other | Traffic Signs And Road Markings | Gantry mounted traffic signs | Gantry mounted traffic signs >10m2 in area |  | no
05.120.1030.50 | Other | Traffic Signs And Road Markings | Gantry mounted traffic signs | Gantry mounted traffic signs including variable messaging |  | no
05.120.1040.10 | Other | Traffic Signs And Road Markings | Remove from store and re-erect illuminated Traffic Signs on posts | Remove from store and re-erect illuminated traffic signs <=1.0m2 in area |  | no
05.120.1040.20 | Other | Traffic Signs And Road Markings | Remove from store and re-erect illuminated Traffic Signs on posts | Remove from store and re-erect illuminated traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1040.30 | Other | Traffic Signs And Road Markings | Remove from store and re-erect illuminated Traffic Signs on posts | Remove from store and re-erect illuminated traffic signs >5m2 but <=10m2 in area |  | no
05.120.1040.40 | Other | Traffic Signs And Road Markings | Remove from store and re-erect illuminated Traffic Signs on posts | Remove from store and re-erect illuminated traffic signs >10m2 in area |  | no
05.120.1040.50 | Other | Traffic Signs And Road Markings | Remove from store and re-erect illuminated Traffic Signs on posts | Remove from store and re-erect illuminated traffic signs including variable messaging |  | no
05.120.1050.10 | Other | Traffic Signs And Road Markings | Remove from store and re-erect non-illuminated Traffic Signs on posts | Remove from store and re-erect non-illuminated traffic signs <=1.0m2 in area |  | no
05.120.1050.20 | Other | Traffic Signs And Road Markings | Remove from store and re-erect non-illuminated Traffic Signs on posts | Remove from store and re-erect non-illuminated traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1050.30 | Other | Traffic Signs And Road Markings | Remove from store and re-erect non-illuminated Traffic Signs on posts | Remove from store and re-erect non-illuminated traffic signs >5m2 but <=10m2 in area |  | no
05.120.1050.40 | Other | Traffic Signs And Road Markings | Remove from store and re-erect non-illuminated Traffic Signs on posts | Remove from store and re-erect non-illuminated traffic signs >10m2 in area |  | no
05.120.1050.50 | Other | Traffic Signs And Road Markings | Remove from store and re-erect non-illuminated Traffic Signs on posts | Remove from store and re-erect non-illuminated traffic signs including variable messaging |  | no
05.120.1060.10 | Other | Traffic Signs And Road Markings | Remove from store and re-erect Gantry Mounted Traffic Signs | Remove from store and re-erect gantry mounted traffic signs <=1.0m2 in area |  | no
05.120.1060.20 | Other | Traffic Signs And Road Markings | Remove from store and re-erect Gantry Mounted Traffic Signs | Remove from store and re-erect gantry mounted traffic signs >1.0m2 but <=5m2 in area |  | no
05.120.1060.30 | Other | Traffic Signs And Road Markings | Remove from store and re-erect Gantry Mounted Traffic Signs | Remove from store and re-erect gantry mounted traffic signs >5m2 but <=10m2 in area |  | no
05.120.1060.40 | Other | Traffic Signs And Road Markings | Remove from store and re-erect Gantry Mounted Traffic Signs | Remove from store and re-erect gantry mounted traffic signs >10m2 in area |  | no
05.120.1060.50 | Other | Traffic Signs And Road Markings | Remove from store and re-erect Gantry Mounted Traffic Signs | Remove from store and re-erect gantry mounted traffic signs including variable messaging |  | no
05.120.2010.10 | Other | Traffic Signs And Road Markings | Removal of Road Markings | Solid area removal |  | m2
05.120.2010.20 | Other | Traffic Signs And Road Markings | Removal of Road Markings | Raised rib lines removal |  | m
05.120.2010.30 | Other | Traffic Signs And Road Markings | Removal of Road Markings | Lines removal |  | m
05.120.2010.40 | Other | Traffic Signs And Road Markings | Removal of Road Markings | Arrows removal |  | no
05.120.2010.50 | Other | Traffic Signs And Road Markings | Removal of Road Markings | Letters, numbers, symbols, triangle & circles removal |  | no
05.120.2020.10 | Other | Traffic Signs And Road Markings | Road Markings | Solid area |  | m2
05.120.2020.20 | Other | Traffic Signs And Road Markings | Road Markings | Raised rib lines |  | m
05.120.2020.30 | Other | Traffic Signs And Road Markings | Road Markings | Lines |  | m
05.120.2020.40 | Other | Traffic Signs And Road Markings | Road Markings | Arrows |  | no
05.120.2020.50 | Other | Traffic Signs And Road Markings | Road Markings | Letters, numbers & symbols |  | no
05.120.2030.10 | Other | Traffic Signs And Road Markings | Road Studs | Road Studs |  | no
05.120.2040.10 | Other | Traffic Signs And Road Markings | Remove from store and Re-install road studs | Remove from store and Re-install road studs |  | no
05.120.3010.10 | Other | Traffic Signs And Road Markings | Temporary traffic signal installations | Temporary Traffic signal installation prescribed by the Engineer |  | LS
05.120.3020.10 | Other | Traffic Signs And Road Markings | Permanent traffic signal installation | Permanent traffic signal installation |  | LS
05.120.3030.10 | Other | Traffic Signs And Road Markings | Controlled & uncontrolled crossings | Prescribed temporary controlled crossing |  | LS
05.120.3030.20 | Other | Traffic Signs And Road Markings | Controlled & uncontrolled crossings | Permanent controlled crossing |  | LS
05.120.3030.30 | Other | Traffic Signs And Road Markings | Controlled & uncontrolled crossings | Prescribed temporary uncontrolled crossing |  | LS
05.120.3030.40 | Other | Traffic Signs And Road Markings | Controlled & uncontrolled crossings | Permanent uncontrolled crossing |  | LS
05.120.4010.10 | Other | Traffic Signs And Road Markings | Marker posts | Marker posts |  | no
05.120.4020.10 | Other | Traffic Signs And Road Markings | Permanent bollards | Internally illuminated permanent bollard |  | no
05.120.4020.20 | Other | Traffic Signs And Road Markings | Permanent bollards | Non-illuminated permanent bollard |  | no
05.120.4030.10 | Other | Traffic Signs And Road Markings | Node markers | Node markers |  | no
05.130.1010.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Fixed road lighting column <= 8m in height |  | no
05.130.1010.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Fixed road lighting column > 8m but <= 12m in height |  | no
05.130.1010.30 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Fixed road lighting column > 12m in height |  | no
05.130.1010.40 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Raise & lower road lighting column <= 8m in height |  | no
05.130.1010.50 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Raise & lower road lighting column > 8m but <= 12m in height |  | no
05.130.1010.60 | Other | Road Lighting Columns, Brackets & CCTV Masts | Road Lighting Columns | Raise & lower road lighting column > 12m in height |  | no
05.130.1020.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect Road Lighting Columns | Remove from store & re-erect fixed road lighting column |  | no
05.130.1020.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect Road Lighting Columns | Remove from store & re-erect raise & lower road lighting column |  | no
05.130.1030.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Replacement brackets and lantern units | Replace bracket and lantern to existing road lighting column |  | no
05.130.1030.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Replacement brackets and lantern units | Replace lantern unit to existing road lighting column |  | no
05.130.1030.30 | Other | Road Lighting Columns, Brackets & CCTV Masts | Replacement brackets and lantern units | Replace luminaire (bulb) to existing road lighting column |  | no
05.130.2010.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Wall Mountings | Surface mounted wall mounting |  | no
05.130.2010.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Wall Mountings | Recessed wall mounting |  | no
05.130.2020.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect Wall Mountings | Remove from store & re-erect surface mounted wall mounting |  | no
05.130.2020.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect Wall Mountings | Remove from store & re-erect recessed wall mounting |  | no
05.130.3010.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | CCTV and Cantilever Masts | CCTV mast |  | no
05.130.3010.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | CCTV and Cantilever Masts | Cantilever mast for traffic signals |  | no
05.130.3010.30 | Other | Road Lighting Columns, Brackets & CCTV Masts | CCTV and Cantilever Masts | Cantilever mast for speed cameras |  | no
05.130.3020.10 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect CCTV and Cantilever Masts | Remove from store & re-erect CCTV mast |  | no
05.130.3020.20 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect CCTV and Cantilever Masts | Remove from store & re-erect cantilever mast for traffic signals |  | no
05.130.3020.30 | Other | Road Lighting Columns, Brackets & CCTV Masts | Remove from store and re-erect CCTV and Cantilever Masts | Remove from store & re-erect cantilever mast for speed cameras |  | no
05.140.1010.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Surveys of existing network-Locating buried road lighting & traffic signs cable | Locating buried road lighting & traffic signs cable |  | m
05.140.1420.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Trench / Trenchless for cable or duct | Trench for cable or duct |  | m
05.140.1420.20 | Other | Electrical Work For Road Lighting And Traffic Signs | Trench / Trenchless for cable or duct | Trenchless for cable or duct |  | m
05.140.1440.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Duct | One way |  | m
05.140.1440.20 | Other | Electrical Work For Road Lighting And Traffic Signs | Duct | Two way | includes two single ducts installed together | m
05.140.1440.30 | Other | Electrical Work For Road Lighting And Traffic Signs | Duct | Three way | includes three single ducts installed together | m
05.140.1440.40 | Other | Electrical Work For Road Lighting And Traffic Signs | Duct | Four way or above | includes four or more single ducts installed together | m
05.140.1450.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Chambers | Chambers |  | no
05.140.1610.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 2 core <=16mm2 Cable |  | m
05.140.1610.20 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 2 core >16mm2 but <=70 mm2 |  | m
05.140.1610.30 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 2 core >70mm2 |  | m
05.140.1610.40 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 3 core <=16mm2 Cable |  | m
05.140.1610.50 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 3 core >16mm2 but <=70 mm2 |  | m
05.140.1610.60 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 3 core >70mm2 |  | m
05.140.1610.70 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 4 core <=16mm2 Cable |  | m
05.140.1610.80 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 4 core >16mm2 but <=70 mm2 |  | m
05.140.1610.90 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | 4 core >70mm2 |  | m
05.140.1610.95 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable & Duct | Cable - Other |  | m
05.140.1620.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable joints & terminations | Cable joints |  | no
05.140.1620.20 | Other | Electrical Work For Road Lighting And Traffic Signs | Cable joints & terminations | Cable terminations |  | no
05.140.1810.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Feeder pillars | Feeder pillars |  | no
05.140.1810.20 | Other | Electrical Work For Road Lighting And Traffic Signs | Feeder pillars | Modifications to Existing Feeder pillars |  | no
05.140.1820.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Remove from store & re-erect feeder pillars | Remove from store & re-erect feeder pillars |  | no
05.140.1830.10 | Other | Electrical Work For Road Lighting And Traffic Signs | Earth electrodes | Earth electrodes |  | no
05.150.1010.10 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Surveys | Locating buried communications cable |  | m
05.150.1010.15 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Surveys | Testing existing communications duct |  | m
05.150.1010.20 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Surveys | Testing existing communications cable |  | m
05.150.1010.30 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Surveys | Testing existing communications equipment |  | no
05.150.1020.10 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Temporary Communications Systems | Installation of Communications Interrupter System |  | LS
05.150.1020.20 | Other | Motorways Communications and Technology | Interface with Existing Communications Network-Temporary Communications Systems | Removal of Communications Interrupter System |  | LS
05.150.2010.10 | Other | Motorways Communications and Technology | Trench / Trenchless for cable or duct | Trench for cable |  | m
05.150.2010.20 | Other | Motorways Communications and Technology | Trench / Trenchless for cable or duct | Trench for duct |  | m
05.150.2010.30 | Other | Motorways Communications and Technology | Trench / Trenchless for cable or duct | Trenchless for cable or duct |  | m
05.150.2030.10 | Other | Motorways Communications and Technology | Duct | One way |  | m
05.150.2030.20 | Other | Motorways Communications and Technology | Duct | Two way | includes two single ducts installed together | m
05.150.2030.30 | Other | Motorways Communications and Technology | Duct | Three way | includes three single ducts installed together | m
05.150.2030.40 | Other | Motorways Communications and Technology | Duct | Four way | includes four single ducts installed together | m
05.150.2030.50 | Other | Motorways Communications and Technology | Duct | Multiple duct > 4-way | includes five or more single ducts installed together | m
05.150.2040.10 | Other | Motorways Communications and Technology | Chambers | Chambers |  | no
05.150.2040.20 | Other | Motorways Communications and Technology | Chambers | Modifications to existing chambers |  | no
05.150.3010.10 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | 25mm2 and below non armoured |  | m
05.150.3010.20 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | > 25mm2 but <= 70mm2 non armoured |  | m
05.150.3010.30 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | > 70mm2 non armoured |  | m
05.150.3010.40 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | 25mm2 and below armoured |  | m
05.150.3010.50 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | > 25mm2 but <= 70mm2 armoured |  | m
05.150.3010.60 | Other | Motorways Communications and Technology | Power Cables (supplied by the Contractor) | > 70mm2 armoured |  | m
05.150.3020.10 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | 25mm2 and below non armoured |  | m
05.150.3020.20 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | > 25mm2 but <= 70mm2 non armoured |  | m
05.150.3020.30 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | > 70mm2 non armoured |  | m
05.150.3020.40 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | 25mm2 and below armoured |  | m
05.150.3020.50 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | > 25mm2 but <= 70mm2 armoured |  | m
05.150.3020.60 | Other | Motorways Communications and Technology | Power Cables (supplied by the Overseeing Organisation) | > 70mm2 armoured |  | m
05.150.3030.10 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | 3 core non armoured |  | m
05.150.3030.20 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Quad non armoured |  | m
05.150.3030.30 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | 2-pair copper |  | m
05.150.3030.40 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Multi-pair copper |  | m
05.150.3030.50 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Fibre optic |  | m
05.150.3030.60 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Composite CCTV Cable |  | m
05.150.3030.70 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Loop Feeder Cable |  | m
05.150.3030.90 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Contractor) | Other communications cabling |  | m
05.150.3040.10 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | 3 core non armoured |  | m
05.150.3040.20 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Quad non armoured |  | m
05.150.3040.30 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | 2-pair copper |  | m
05.150.3040.40 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Multi-pair copper |  | m
05.150.3040.50 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Fibre optic |  | m
05.150.3040.60 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Composite CCTV Cable |  | m
05.150.3040.70 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Loop Feeder Cable |  | m
05.150.3040.90 | Other | Motorways Communications and Technology | Communications Cables (supplied by the Overseeing Organisation) | Other communications cabling |  | m
05.150.3050.10 | Other | Motorways Communications and Technology | Cable joints & terminations | Cable joints |  | no
05.150.3050.20 | Other | Motorways Communications and Technology | Cable joints & terminations | Cable terminations |  | no
05.150.4010.10 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Cameras |  | no
05.150.4010.20 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Cabinets (ground mounted) |  | no
05.150.4010.25 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Technology Equipment (supplied by the Overseeing Organisation ) - Cabinets (Combined Equipment Cabinet, CEC or similar) |  | no
05.150.4010.30 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Gantry Mounted Equipment |  | LS
05.150.4010.40 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Post Mounted Advanced Motorway Indicators (AMIs) |  | no
05.150.4010.50 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Emergency Telephones |  | no
05.150.4010.60 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Contractor) | Other equipment |  | LS
05.150.4020.10 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Cameras |  | no
05.150.4020.20 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Cabinets (ground mounted) |  | no
05.150.4020.25 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Technology Equipment (supplied by the Contractor) - Cabinets (Combined Equipment Cabinet, CEC or similar) |  | no
05.150.4020.30 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Gantry Mounted Equipment |  | LS
05.150.4020.40 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Post Mounted Advanced Motorway Indicators (AMIs) |  | no
05.150.4020.50 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Emergency Telephones |  | no
05.150.4020.60 | Other | Motorways Communications and Technology | Technology Equipment (supplied by the Overseeing Organisation) | Other equipment |  | LS
05.150.4030.10 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Cameras |  | no
05.150.4030.20 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Cabinets (ground mounted) |  | no
05.150.4030.25 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Remove from store & re-install communications cable & equipment - Cabinets (Combined Equipment Cabinet, CEC or similar) |  | no
05.150.4030.30 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Gantry Mounted Equipment |  | LS
05.150.4030.40 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Post Mounted Advanced Motorway Indicators (AMIs) |  | no
05.150.4030.50 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Emergency Telephones |  | no
05.150.4030.60 | Other | Motorways Communications and Technology | Remove from store & re-install communications cable & equipment | Other equipment |  | LS
05.150.4040.10 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Cameras |  | no
05.150.4040.20 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Cabinets (ground mounted) |  | no
05.150.4040.25 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Modifications to existing communications equipment - Cabinets (Combined Equipment Cabinet, CEC or similar) |  | no
05.150.4040.30 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Gantry Mounted Equipment |  | LS
05.150.4040.40 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Post Mounted Advanced Motorway Indicators (AMIs) |  | no
05.150.4040.50 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Emergency Telephones |  | no
05.150.4040.60 | Other | Motorways Communications and Technology | Modifications to existing communications equipment | Other equipment |  | LS
05.150.4510.10 | Other | Motorways Communications and Technology | Lightning Protection / Earthing | Lightning Protection |  | no
05.150.4510.20 | Other | Motorways Communications and Technology | Lightning Protection / Earthing | Equipotential Bonding |  | no
05.150.4510.30 | Other | Motorways Communications and Technology | Lightning Protection / Earthing | Earthing |  | no
05.150.4510.40 | Other | Motorways Communications and Technology | Lightning Protection / Earthing | Labelling |  | no
05.150.5010.10 | Other | Motorways Communications and Technology | Detector Installations | Loop Detector Installations |  | no
05.150.5010.20 | Other | Motorways Communications and Technology | Detector Installations | Radar Detector Installations |  | no
05.150.5010.30 | Other | Motorways Communications and Technology | Detector Installations | Ramp Metering Installations (including signal poles) |  | No
05.150.6010.10 | Other | Motorways Communications and Technology | Testing & Commissioning-Site Tests and Records | Site Records |  | LS
05.150.6010.20 | Other | Motorways Communications and Technology | Testing & Commissioning-Site Tests and Records | Site Acceptance Testing |  | LS
05.150.6010.30 | Other | Motorways Communications and Technology | Testing & Commissioning-Site Tests and Records | Soak Testing |  | LS
05.150.6010.40 | Other | Motorways Communications and Technology | Testing & Commissioning-Site Tests and Records | Other Testing |  | LS
05.150.6020.10 | Other | Motorways Communications and Technology | Testing & Commissioning-Commissioning | Stage 1 or up to Stage C commissioning |  | LS
05.150.6020.20 | Other | Motorways Communications and Technology | Testing & Commissioning-Commissioning | Stage 2 or Stage D to Stage G commissioning |  | LS
05.150.6020.30 | Other | Motorways Communications and Technology | Testing & Commissioning-Commissioning | Other Commissioning |  | LS
05.150.6020.40 | Other | Motorways Communications and Technology | Testing & Commissioning-Commissioning | Site Data Upload |  | LS
05.160.0501.10 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles-Piling Plant | Establishment of pcc piling plant |  | LS
05.160.0501.20 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles-Piling Plant | Moving pcc piling plant |  | no
05.160.0502.10 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Stripping Vertical |  | no
05.160.0502.12 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Stripping Raking |  | no
05.160.0502.15 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Vertical <= 10m in length |  | m
05.160.0502.20 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Vertical > 10m but <= 20m in length |  | m
05.160.0502.25 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Vertical > 20m in length |  | m
05.160.0502.30 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Raking <= 10m in length |  | m
05.160.0502.40 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Raking > 10m but <= 20m in length |  | m
05.160.0502.50 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Raking > 20m in length |  | m
05.160.0502.60 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Vertical <= 10m in length |  | m
05.160.0502.65 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Vertical > 10m but <= 20m in length |  | m
05.160.0502.70 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Vertical > 20m in length |  | m
05.160.0502.75 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Raking <= 10m in length |  | m
05.160.0502.80 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Raking > 10m but <= 20m in length |  | m
05.160.0502.82 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving Raking > 20m in length |  | m
05.160.0502.85 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Lengthening Vertical |  | m
05.160.0502.90 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Lengthening Raking |  | m
05.160.0502.91 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving lengthened vertical piles - all lengths |  | m
05.160.0502.92 | Other | Piling and Embedded Retaining Walls | Precast Concrete Piles: All Cross Sections | Driving lengthened raking piles - all lengths |  | m
05.160.0503.10 | Other | Piling and Embedded Retaining Walls | Proof Loading of Precast Concrete Piles | Establishment of pcc proof loading equipment |  | LS
05.160.0503.20 | Other | Piling and Embedded Retaining Walls | Proof Loading of Precast Concrete Piles | Proof loading of pcc vertical piles |  | no
05.160.0503.30 | Other | Piling and Embedded Retaining Walls | Proof Loading of Precast Concrete Piles | Proof loading of pcc raking piles |  | no
05.160.1001.10 | Other | Piling and Embedded Retaining Walls | Cast in Place Concrete Piles-Piling Plant | Establishment of concrete c-i-p piling plant |  | LS
05.160.1001.20 | Other | Piling and Embedded Retaining Walls | Cast in Place Concrete Piles-Piling Plant | Moving concrete c-i-p piling plant |  | no
05.160.1002.10 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Vertical <=450mm dia |  | m
05.160.1002.20 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Vertical >450mm dia but <=900 mm dia |  | m
05.160.1002.30 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Vertical >900mm dia |  | m
05.160.1002.40 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Raking <=450mm dia |  | m
05.160.1002.50 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Raking >450mm dia but <=900 mm dia |  | m
05.160.1002.60 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Cast-in-place concrete piles - Raking >900mm dia |  | m
05.160.1002.70 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Vertical <=450mm dia |  | m
05.160.1002.80 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Vertical >450mm dia but <=900 mm dia |  | m
05.160.1002.90 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Vertical>900mm dia |  | m
05.160.1002.91 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Raking <=450mm dia |  | m
05.160.1002.92 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Raking >450mm dia but <=900 mm dia |  | m
05.160.1002.93 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Empty bores - Raking >900mm dia |  | m
05.160.1002.94 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Steel bar reinforcement |  | t
05.160.1002.95 | Other | Piling and Embedded Retaining Walls | Cast-in-place Concrete Piles | Steel helical reinforcement |  | t
05.160.1004.10 | Other | Piling and Embedded Retaining Walls | Proof Loading of Cast in Place Concrete Piles | Establishment of c-i-p concrete proof loading equipment |  | LS
05.160.1004.20 | Other | Piling and Embedded Retaining Walls | Proof Loading of Cast in Place Concrete Piles | Proof loading of vertical c-i-p concrete piles |  | LS
05.160.1004.30 | Other | Piling and Embedded Retaining Walls | Proof Loading of Cast in Place Concrete Piles | Proof loading of raking c-i-p concrete piles |  | LS
05.160.1501.10 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles-Piling Plant | Establishment of steel bearing piling plant |  | LS
05.160.1501.20 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles-Piling Plant | Moving steel bearing piling plant |  | no
05.160.1502.10 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles <= 10m in length |  | m
05.160.1502.20 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles > 10m but <= 20m in length |  | m
05.160.1502.30 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles > 20m in length |  | m
05.160.1502.40 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles <= 10m in length |  | m
05.160.1502.50 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles > 10m but <= 20m in length |  | m
05.160.1502.60 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Steel bearing piles > 20m in length |  | m
05.160.1502.70 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving vertical steel bearing piles <= 10m in length |  | m
05.160.1502.80 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving vertical steel bearing piles > 10m but <= 20m in length |  | m
05.160.1502.90 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving vertical steel bearing piles > 20m in length |  | m
05.160.1502.91 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving raking steel bearing piles <= 10m in length |  | m
05.160.1502.92 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving raking steel bearing piles > 10m but <= 20m in length |  | m
05.160.1502.93 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving raking steel bearing piles > 20m in length |  | m
05.160.1502.94 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Lengthening pieces for Steel Bearing Piles |  | m
05.160.1502.95 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Driving vertical lengthened steel bearing piles |  | m
05.160.1502.96 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Welding on lengthening pieces to vertical steel bearing piles |  | no
05.160.1502.97 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Welding on lengthening pieces to raking steel bearing piles |  | no
05.160.1502.98 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Cutting or burning off surplus length of raking steel bearing piles |  | no
05.160.1502.99 | Other | Piling and Embedded Retaining Walls | Steel Bearing Piles - All Sections | Cutting or burning off surplus length of vertical steel bearing piles |  | no
05.160.1503.10 | Other | Piling and Embedded Retaining Walls | Proof Loading of Steel Bearing Piles | Establishment of steel bearing proof loading equipment |  | LS
05.160.1503.20 | Other | Piling and Embedded Retaining Walls | Proof Loading of Steel Bearing Piles | Proof loading of vertical steel bearing piles |  | no
05.160.1503.30 | Other | Piling and Embedded Retaining Walls | Proof Loading of Steel Bearing Piles | Proof loading of raking steel bearing piles |  | no
05.160.2001.10 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles-Piling Plant | Establishment of steel sheet piling plant |  | LS
05.160.2002.10 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Steel Sheet piles <=5m length in main construction |  | m2
05.160.2002.20 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Steel Sheet piles > 5 metres but <= 10m length in main construction |  | m2
05.160.2002.30 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Steel Sheet piles > 10m length in main construction |  | m2
05.160.2002.40 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Driving Steel Sheet piles <= 5m length in main construction |  | m2
05.160.2002.50 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Driving Steel Sheet piles > 5 metres but < = 10 m length in main construction |  | m2
05.160.2002.60 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Driving Steel Sheet piles > 10m length in main construction |  | m2
05.160.2002.70 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Cutting or burning off surplus length Steel Sheet Piles |  | m
05.160.2002.80 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Welding on lengthening pieces to Steel Sheet Piles |  | m
05.160.2002.90 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Extra over for supply of Steel Sheet Piles for corner pile |  | m
05.160.2002.91 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Extra over for supply of Steel Sheet Piles for junction pile |  | m
05.160.2002.92 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Extra over for driving Steel Sheet Piles for corner pile |  | m
05.160.2002.93 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Extra over for driving Steel Sheet Pilesfor junction pile |  | m
05.160.2002.94 | Other | Piling and Embedded Retaining Walls | Steel Sheet Piles | Capping Angle |  | m
05.160.2501.10 | Other | Piling and Embedded Retaining Walls | Diaphragm Walling Plant | Establishment of diaphragm walling plant |  | LS
05.160.2501.20 | Other | Piling and Embedded Retaining Walls | Diaphragm Walling Plant | Moving diaphragm walling plant |  | no
05.160.2502.10 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Diaphragm Walls <=450mm thick |  | m2
05.160.2502.20 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Diaphragm Walls >450mm thick but <=900mm thick |  | m2
05.160.2502.30 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Diaphragm Walls >900mm thick |  | m2
05.160.2502.40 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Empty excavation <=450mm thick |  | m2
05.160.2502.50 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Empty excavation >450mm thick but <=900mm thick |  | m2
05.160.2502.60 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Empty excavation >900mm thick |  | m2
05.160.2502.70 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Steel bar reinforcement |  | t
05.160.2502.80 | Other | Piling and Embedded Retaining Walls | Diaphragm Walls | Steel rolled sections as reinforcement |  | t
05.160.2801.10 | Other | Piling and Embedded Retaining Walls | Secant Pile Wall Plant | Establishment of hard/hard secant pile walling plant |  | LS
05.160.2801.20 | Other | Piling and Embedded Retaining Walls | Secant Pile Wall Plant | Establishment of hard/soft secant pile walling plant |  | LS
05.160.2802.10 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/hard Secant Pile Walls <=450mm dia |  | m2
05.160.2802.20 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/hard Secant Pile Walls >450mm dia but <=900 mm dia |  | m2
05.160.2802.30 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/hard Secant Pile Walls >900mm dia |  | m2
05.160.2802.40 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/soft Secant Pile Walls <=450mm dia |  | m2
05.160.2802.50 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/soft Secant Pile Walls >450mm dia but <=900 mm dia |  | m2
05.160.2802.60 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Hard/soft Secant Pile Walls >900mm dia |  | m2
05.160.2802.70 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Empty bore <=450mm dia |  | m2
05.160.2802.80 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Empty bore>450mm dia but <=900 mm dia |  | m2
05.160.2802.90 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Empty bore>900mm dia |  | m2
05.160.2802.92 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Steel bar reinforcement |  | t
05.160.2802.94 | Other | Piling and Embedded Retaining Walls | Secant Pile Walls | Steel rolled sections as reinforcement |  | t
05.160.3501.10 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Plant | Establishment of contiguous bored pile walling plant |  | LS
05.160.3501.20 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Plant | Contiguous Bored Pile Walls - Moving piling plant |  | no
05.160.3502.10 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Contiguous Bored Pile Walls <=450mm dia |  | m2
05.160.3502.20 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Contiguous Bored Pile Walls >450mm dia but <=900 mm dia |  | m2
05.160.3502.30 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Contiguous Bored Pile Walls >900mm dia |  | m2
05.160.3502.40 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Empty bores <=450mm dia |  | m2
05.160.3502.50 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Empty bores >450mm dia but <=900 mm dia |  | m2
05.160.3502.60 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Empty bores >900mm dia |  | m2
05.160.3502.70 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Steel bar reinforcement |  | t
05.160.3502.80 | Other | Piling and Embedded Retaining Walls | Contiguous Bored Pile Walls | Steel rolled sections as reinforcement |  | t
05.160.4001.10 | Other | Piling and Embedded Retaining Walls | King Post Wall Plant | Establishment of king post wall piling plant |  | LS
05.160.4001.20 | Other | Piling and Embedded Retaining Walls | King Post Wall Plant | Moving king post wall piling plant |  | no
05.160.4002.10 | Other | Piling and Embedded Retaining Walls | King Posts | Raking king post empty bores |  | m
05.160.4002.20 | Other | Piling and Embedded Retaining Walls | King Posts | Vertical cast-in-place king post piles |  | m
05.160.4002.30 | Other | Piling and Embedded Retaining Walls | King Posts | Raking cast-in-place king post piles |  | m
05.160.4002.40 | Other | Piling and Embedded Retaining Walls | King Posts | Vertical king post empty bores |  | m
05.160.4002.50 | Other | Piling and Embedded Retaining Walls | King Posts | Steel bar reinforcement |  | t
05.160.4002.60 | Other | Piling and Embedded Retaining Walls | King Posts | Steel rolled section members as reinforcement |  | t
05.160.4002.70 | Other | Piling and Embedded Retaining Walls | King Posts | Precast concrete members as reinforcement |  | m
05.160.4002.80 | Other | Piling and Embedded Retaining Walls | King Posts | King post walling |  | m2
05.160.4501.10 | Other | Piling and Embedded Retaining Walls | Screw Piles-Piling Plant | Establishment of screw piling plant |  | LS
05.160.4501.20 | Other | Piling and Embedded Retaining Walls | Screw Piles-Piling Plant | Moving screw piling plant |  | no
05.160.4502.10 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Lead sections <= 150mm diameter |  | m
05.160.4502.20 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Lead sections >150mm but <=300mm diameter |  | m
05.160.4502.30 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Lead sections >300mm diameter |  | m
05.160.4502.40 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Extension sections <= 150mm diameter |  | m
05.160.4502.45 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Extension sections >150mm but <=300mm diameter |  | m
05.160.4502.50 | Other | Piling and Embedded Retaining Walls | Screw Piles | Screw Piles - Extension sections >300mm diameter |  | m
05.160.4502.60 | Other | Piling and Embedded Retaining Walls | Screw Piles | Install Vertical |  | m
05.160.4503.10 | Other | Piling and Embedded Retaining Walls | Establishment of Screw Piles proof loading equipment | Proof loading of vertical piles |  | no
05.160.5001.10 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles-Piling Plant | Establishment of plastic sheet piling plant |  | LS
05.160.5001.20 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles-Piling Plant | Moving of plastic sheet piling plant |  | no
05.160.5002.10 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Supply Plastic Sheet piles |  | m2
05.160.5002.20 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Driving Plastic Sheet Piles |  | m2
05.160.5002.30 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Cutting or burning off surplus length Plastic Sheet Piles |  | m
05.160.5002.40 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Joining on lengthening pieces to Plastic Sheet Piles |  | m
05.160.5002.50 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Extra over for supply of Plastic Sheet Piles for corner pile |  | m
05.160.5002.60 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Extra over for supply of Plastic Sheet Piles for junction pile |  | m
05.160.5002.70 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Extra over for driving Plastic Sheet Piles for corner pile |  | m
05.160.5002.80 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Extra over for driving Plastic Sheet Piles for junction pile |  | m
05.160.5002.90 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Walings |  | t
05.160.5002.91 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Tie rods |  | t
05.160.5002.92 | Other | Piling and Embedded Retaining Walls | Plastic Sheet Piles | Capping Angle |  | m
05.160.5501.10 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame with platform - Super Span |  | no
05.160.5501.20 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame - Super Span |  | no
05.160.5501.30 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame with platform - Single Span/Cantilever |  | no
05.160.5501.40 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame - Single Span/Cantilever |  | no
05.160.5501.50 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame and platform - MS Cantilever |  | no
05.160.5501.60 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage frame and paved platform - MS Cantilever |  | no
05.160.5501.70 | Other | Piling and Embedded Retaining Walls | Composite Grillage Support Structures | Piled grillage platform - Comms |  | no
05.170.0210.02 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete in blinding 75mm or less in thickness |  | m3
05.170.0210.04 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete of nominal strength <=30N/mm2 | NOTE: Nominal strength = designed final (28 day) strength | m3
05.170.0210.06 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete of nominal strength >30N/mm2 but <= 40N/mm2 | NOTE: Nominal strength = designed final (28 day) strength | m3
05.170.0210.08 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete of nominal strength >40N/mm2 but <= 50N/mm2 | NOTE: Nominal strength = designed final (28 day) strength | m3
05.170.0210.10 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete of nominal strength >50N/mm2 | NOTE: Nominal strength = designed final (28 day) strength | m3
05.170.0210.12 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete ST 1 |  | m3
05.170.0210.14 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete ST 2 |  | m3
05.170.0210.16 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete ST 3 |  | m3
05.170.0210.18 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete ST 4 |  | m3
05.170.0210.20 | Other | Structural Concrete | In Situ Concrete | In Situ Concrete ST 5 |  | m3
05.170.0220.02 | Other | Structural Concrete | In Situ Post-Tensioned Prestressing for Structures | Tendon |  | m
05.170.0220.04 | Other | Structural Concrete | In Situ Post-Tensioned Prestressing for Structures | Stressing & grouting internal tendon |  | m
05.170.0220.06 | Other | Structural Concrete | In Situ Post-Tensioned Prestressing for Structures | Stressing external tendon |  | m
05.170.0220.08 | Other | Structural Concrete | In Situ Post-Tensioned Prestressing for Structures | Final stressing & grouting internal tendon |  | m
05.170.0220.10 | Other | Structural Concrete | In Situ Post-Tensioned Prestressing for Structures | Protective covering to external tendon |  | m
05.170.0230.02 | Other | Structural Concrete | Sprayed Concrete | Sprayed Concrete |  | m3
05.170.0810.02 | Other | Structural Concrete | Precast Concrete | Precast concrete member (beams) |  | no
05.170.0810.04 | Other | Structural Concrete | Precast Concrete | Precast concrete member (columns) |  | no
05.170.0810.06 | Other | Structural Concrete | Precast Concrete | Precast concrete slab |  | no
05.170.0810.08 | Other | Structural Concrete | Precast Concrete | Precast concrete segmental unit |  | no
05.170.0810.10 | Other | Structural Concrete | Precast Concrete | Precast concrete special units |  | no
05.170.0810.12 | Other | Structural Concrete | Precast Concrete | Precast concrete coping |  | m
05.170.0810.14 | Other | Structural Concrete | Precast Concrete | Precast concrete capping unit |  | m
05.170.0810.16 | Other | Structural Concrete | Precast Concrete | Precast concrete plinth |  | m
05.170.0810.18 | Other | Structural Concrete | Precast Concrete | Precast concrete box culvert <=1800mm in height |  | m
05.170.0810.20 | Other | Structural Concrete | Precast Concrete | Precast concrete box culvert >1800mm but <=2400mm in height |  | m
05.170.0810.22 | Other | Structural Concrete | Precast Concrete | Precast concrete box culvert >2400mm in height |  | m
05.170.0810.24 | Other | Structural Concrete | Precast Concrete | Precast concrete facing units |  | m2
05.170.0810.26 | Other | Structural Concrete | Precast Concrete | Precast concrete gantry |  | no
05.170.0820.02 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed member (beams) |  | no
05.170.0820.04 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed member (columns) |  | no
05.170.0820.06 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed slab |  | no
05.170.0820.08 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed segmental unit |  | no
05.170.0820.10 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed special units |  | no
05.170.0820.12 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed coping |  | m
05.170.0820.14 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed capping unit |  | m
05.170.0820.16 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed plinth |  | m
05.170.0820.18 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed box culvert <=1800mm in height |  | m
05.170.0820.20 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed box culvert >1800mm but <=2400mm in height |  | m
05.170.0820.22 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed >2400mm in height |  | m
05.170.0820.24 | Other | Structural Concrete | Precast Concrete Pretensioned Prestressed | Precast Concrete Pretensioned Prestressed facing units |  | m2
05.170.0830.02 | Other | Structural Concrete | Precast Concrete Post-tensioned Prestressed | Precast Concrete Post-tensioned Prestressed member (beams) |  | no
05.170.0830.04 | Other | Structural Concrete | Precast Concrete Post-tensioned Prestressed | Precast Concrete Post-tensioned Prestressed member (columns) |  | no
05.170.1010.02 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F1 horizontal >300mm |  | m2
05.170.1010.04 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F1 vertical/inclined >300mm |  | m2
05.170.1010.06 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F1 <= 300mm |  | m2
05.170.1010.10 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F2 horizontal >300mm |  | m2
05.170.1010.12 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F2 vertical/inclined >300mm |  | m2
05.170.1010.14 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F2 <= 300mm |  | m2
05.170.1010.18 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F3 horizontal >300mm |  | m2
05.170.1010.20 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F3 vertical/inclined >300mm |  | m2
05.170.1010.22 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F3<= 300mm |  | m2
05.170.1010.26 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F4 horizontal >300mm |  | m2
05.170.1010.28 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F4 vertical/inclined >300mm |  | m2
05.170.1010.30 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F4 <= 300mm |  | m2
05.170.1010.34 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F5 horizontal >300mm |  | m2
05.170.1010.36 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F5 vertical/inclined >300mm |  | m2
05.170.1010.38 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | FormworkClass F5 <= 300mm |  | m2
05.170.1010.42 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent formwork >300 |  | m2
05.170.1010.54 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent formwork <=300 |  | m2
05.170.1010.56 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Curved formwork >300 |  | m2
05.170.1010.58 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent curved formwork >300 |  | m2
05.170.1010.60 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Curved formwork <=300 |  | m2
05.170.1010.62 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent curved formwork <=300 |  | m2
05.170.1010.64 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Domed formwork |  | m2
05.170.1010.66 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent domed formwork |  | m2
05.170.1010.68 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Permanent structural formwork (Omnia planks) |  | m2
05.170.1010.70 | Other | Structural Concrete | Surface Finish of Concrete-Formwork | Void former |  | m
05.170.1020.02 | Other | Structural Concrete | Surface Finish of Concrete-Patterned Profile Formwork | Patterned Profile Formwork |  | m2
05.170.1020.04 | Other | Structural Concrete | Surface Finish of Concrete-Patterned Profile Formwork | Curved Patterned Profile Formwork |  | m2
05.170.1210.02 | Other | Structural Concrete | Reinforcement for Structures | Fabric reinforcement |  | m2
05.170.1210.04 | Other | Structural Concrete | Reinforcement for Structures | Steel bar reinforcement |  | t
05.170.1210.08 | Other | Structural Concrete | Reinforcement for Structures | Helical reinforcement |  | t
05.170.1210.10 | Other | Structural Concrete | Reinforcement for Structures | Dowel |  | m
05.170.1220.02 | Other | Structural Concrete | Reinforcement for Reinforced & Anchored Earth Structures | Vertical rods, strip & bar reinforcing elements |  | m
05.170.1220.04 | Other | Structural Concrete | Reinforcement for Reinforced & Anchored Earth Structures | Sheet, grid & mesh reinforcing elements |  | m2
05.170.1410.10 | Other | Structural Concrete | Concrete/Cement/Mortar Repairs | Repairs to structural concrete in supports, decks and gantries |  | LS
05.170.1410.20 | Other | Structural Concrete | Concrete/Cement/Mortar Repairs | Repairs to non-structural elements (plinths, joints, etc.) |  | LS
05.180.1010.10 | Other | Structural Steelwork | Fabrication of Steelwork | Fabrication of main members |  | t
05.180.1010.20 | Other | Structural Steelwork | Fabrication of Steelwork | Fabrication of deck panels |  | t
05.180.1010.30 | Other | Structural Steelwork | Fabrication of Steelwork | Fabrication of subsidiary steelwork |  | t
05.180.1020.10 | Other | Structural Steelwork | Erection of Steelwork | Trial erection at place of fabrication |  | LS
05.180.1020.20 | Other | Structural Steelwork | Erection of Steelwork | Permanent erection |  | t
05.180.3010.10 | Other | Structural Steelwork | Miscellaneous Metalwork | Miscellaneous Metalwork - Ladders |  | no
05.180.3010.20 | Other | Structural Steelwork | Miscellaneous Metalwork | Miscellaneous Metalwork - Handrails |  | no
05.180.3010.30 | Other | Structural Steelwork | Miscellaneous Metalwork | Miscellaneous Metalwork - Access covers and the like |  | no
05.180.3010.40 | Other | Structural Steelwork | Miscellaneous Metalwork | Miscellaneous Metalwork - Walkways, panels,screens and the like |  | no
05.180.3010.50 | Other | Structural Steelwork | Miscellaneous Metalwork | Miscellaneous Metalwork - Other |  | no
05.180.4010.10 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Galvanized steel facing units |  | m2
05.180.4010.20 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Stainless steel facing units |  | m2
05.180.4010.30 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Aluminium facing units |  | m2
05.180.4010.40 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Galvanized steel capping units |  | m
05.180.4010.50 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Stainless steel capping units |  | m
05.180.4010.60 | Other | Structural Steelwork | Metal Facing Units for Reinforced Earth Structures | Aluminium capping units |  | m
05.180.6010.10 | Other | Structural Steelwork | Fabrication of Portal Frame Gantries (measured from C/Line of legs ignoring intermediate supports) | Fabrication of Portal Frame Gantries<10m in length |  | no
05.180.6010.20 | Other | Structural Steelwork | Fabrication of Portal Frame Gantries (measured from C/Line of legs ignoring intermediate supports) | Fabrication of Portal Frame Gantries>=10m to < 20m in length |  | no
05.180.6010.30 | Other | Structural Steelwork | Fabrication of Portal Frame Gantries (measured from C/Line of legs ignoring intermediate supports) | Fabrication of Portal Frame Gantries >=20m to < 30m in length |  | no
05.180.6010.40 | Other | Structural Steelwork | Fabrication of Portal Frame Gantries (measured from C/Line of legs ignoring intermediate supports) | Fabrication of Portal Frame Gantries >=30m in length |  | no
05.180.6020.10 | Other | Structural Steelwork | Erection of Portal Gantries | Trial erection at place of fabrication |  | LS
05.180.6020.20 | Other | Structural Steelwork | Erection of Portal Gantries | Permanent erection |  | t
05.180.7010.10 | Other | Structural Steelwork | Fabrication of Cantilever Structures | Fabrication of Cantilever Structures - MS poles |  | no
05.180.7010.20 | Other | Structural Steelwork | Fabrication of Cantilever Structures | Fabrication of Cantilever Structures - Long Span |  | no
05.180.7020.10 | Other | Structural Steelwork | Erection of Cantilever Structures | Trial erection at place of fabrication |  | no
05.180.7020.20 | Other | Structural Steelwork | Erection of Cantilever Structures | Permanent erection |  | no
05.180.9010.10 | Other | Structural Steelwork | Collection, storage and erection of Structural Steelwork Structures - provided by the overseeing organisation | Collection, storage and erection of Structural Steelwork Structures - provided by the overseeing organisation |  | LS
05.180.9210.10 | Other | Structural Steelwork | Corrugated Steel buried Structures | Corrugated steel buried pipe |  | no
05.180.9210.20 | Other | Structural Steelwork | Corrugated Steel buried Structures | Corrugated steel buried arch |  | no
05.180.9210.30 | Other | Structural Steelwork | Corrugated Steel buried Structures | Corrugated steel buried pipe culvert |  | no
05.180.9210.40 | Other | Structural Steelwork | Corrugated Steel buried Structures | Corrugated steel buried arch culvert |  | no
05.180.9410.10 | Other | Structural Steelwork | Modification of existing gantries | Insitu fabrication of steelwork |  | t
05.180.9410.20 | Other | Structural Steelwork | Modification of existing gantries | Insitu erection of steelwork |  | t
05.180.9410.30 | Other | Structural Steelwork | Modification of existing gantries | Not Used |  | no
05.180.9410.40 | Other | Structural Steelwork | Modification of existing gantries | Not Used |  | no
05.180.9410.50 | Other | Structural Steelwork | Modification of existing gantries | Not Used |  | no
05.180.9420.10 | Other | Structural Steelwork | Refurbishment of existing gantries | Dismantle existing gantry |  | no
05.180.9420.20 | Other | Structural Steelwork | Refurbishment of existing gantries | Modification to existing gantry |  | no
05.180.9420.30 | Other | Structural Steelwork | Refurbishment of existing gantries | Re-erection of existing gantry |  | no
05.190.0210.10 | Other | Protection of Steelwork Against Corrosion | Organic Protective System | Organic Protective System |  | m2
05.190.0220.10 | Other | Protection of Steelwork Against Corrosion | Cathodic Protection | Cathodic Protection |  | LS
05.190.0230.10 | Other | Protection of Steelwork Against Corrosion | Concrete encasement | Concrete encasement |  | LS
05.200.0001.05 | Other | Waterproofing for concrete structures | Waterproofing, surface impregnation of concrete and removal of existing waterproofing | Waterproofing with mastic asphalt or proprietary waterproofing system |  | m2
05.200.0001.07 | Other | Waterproofing for concrete structures | Waterproofing, surface impregnation of concrete and removal of existing waterproofing | Waterproofing with 2 coats of tar |  | m2
05.200.0001.10 | Other | Waterproofing for concrete structures | Waterproofing, surface impregnation of concrete and removal of existing waterproofing | Waterproofing with 2 coats of bitumen |  | m2
05.200.0002.05 | Other | Waterproofing for concrete structures | Surface impregnation of concrete | Surface impregnation of concrete |  | m2
05.200.0003.05 | Other | Waterproofing for concrete structures | Removal of existing waterproofing | Removal of existing waterproofing |  | m2
05.200.0004.05 | Other | Waterproofing for concrete structures | Anti-graffiti Coating | Anti-graffiti Coating |  | m2
05.210.0001.05 | Other | Bridge Bearings | Bearings | Bearing |  | no
05.210.0001.10 | Other | Bridge Bearings | Bearings | Installation of bearing |  | no
05.230.1010.05 | Other | Bridge Expansion Joints and Sealing of Gaps | Bridge Deck Expansion Joints | Expansion joint |  | m
05.230.1010.10 | Other | Bridge Expansion Joints and Sealing of Gaps | Bridge Deck Expansion Joints | Fixed joint |  | m
05.230.1010.15 | Other | Bridge Expansion Joints and Sealing of Gaps | Bridge Deck Expansion Joints | Contraction joint |  | m
05.230.1015.05 | Other | Bridge Expansion Joints and Sealing of Gaps | Removal of Existing Expansion Joints | Removal of Existing Expansion Joints |  | m
05.230.1015.10 | Other | Bridge Expansion Joints and Sealing of Gaps | Removal of Existing Expansion Joints | Plate over existing expansion joints |  | m
05.230.2010.05 | Other | Bridge Expansion Joints and Sealing of Gaps | Sealing of gaps | Joint filler board |  | m2
05.230.2010.10 | Other | Bridge Expansion Joints and Sealing of Gaps | Sealing of gaps | Joint sealant |  | m
05.230.2010.15 | Other | Bridge Expansion Joints and Sealing of Gaps | Sealing of gaps | Water bar |  | m
05.230.2010.20 | Other | Bridge Expansion Joints and Sealing of Gaps | Sealing of gaps | Water stop |  | m
05.240.0210.10 | Other | Brickwork, Blockwork & Stonework | Brickwork, Blockwork & Stonework | Copings & string courses |  | m
05.240.0210.20 | Other | Brickwork, Blockwork & Stonework | Brickwork, Blockwork & Stonework | Walls |  | m2
05.240.0210.30 | Other | Brickwork, Blockwork & Stonework | Brickwork, Blockwork & Stonework | Facework to concrete |  | m2
05.240.0220.10 | Other | Brickwork, Blockwork & Stonework | Remove from store & relay Brickwork, Blockwork & Stonework | Copings & string courses |  | m
05.240.0220.20 | Other | Brickwork, Blockwork & Stonework | Remove from store & relay Brickwork, Blockwork & Stonework | Walls |  | m2
05.240.0220.30 | Other | Brickwork, Blockwork & Stonework | Remove from store & relay Brickwork, Blockwork & Stonework | Facework to concrete |  | m2
05.250.0210.02 | Other | Special Commissioned Structures | Special Commissioned Structures Designed by the Contractor or 3rd Parties | Special Commissioned Structure - DEFINITION REQUIRED (Only to be used with the approval of the HA Commercial Division / Estimating Team) |  | LS
05.270.0210.02 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Accommodation works | Accommodation works |  | LS
05.270.0410.02 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers: Power - Overhead |  | LS
05.270.0410.04 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers - Telecommunications |  | LS
05.270.0410.06 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers - Gas |  | LS
05.270.0410.08 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers - Potable Water |  | LS
05.270.0410.10 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers - Foul Water / Sewerage |  | LS
05.270.0410.12 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers: Other SU Costs - Nominate |  | LS
05.270.0410.14 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Contractor for Statutory Undertakers | Works by the Contractor for Statutory Undertakers - SU/Nominate |  | LS
05.270.0510.02 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers: Power - Underground |  | LS
05.270.0510.04 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers: Power - Overhead |  | LS
05.270.0510.06 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers - Telecommunications |  | LS
05.270.0510.08 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers - Gas |  | LS
05.270.0510.10 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers - Potable Water |  | LS
05.270.0510.12 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers - Foul Water / Sewerage |  | LS
05.270.0510.14 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Works by the Statutory Undertakers | Works by the Statutory Undertakers - SU/Nominate |  | LS
05.270.0620.02 | Other | Accommodation Works, Works for Statutory Undertakers, Provisional Sums and Prime Cost Items | Prime Cost Items | Prime Cost Items |  | LS
05.300.0510.10 | Other | Landscape & Ecology | Ground preparation and cultivation | Vegetation clearance |  | m2
05.300.0510.20 | Other | Landscape & Ecology | Ground preparation and cultivation | Subsoil treatment |  | m2
05.300.0510.30 | Other | Landscape & Ecology | Ground preparation and cultivation | Final preparation of soils |  | m2
05.300.0510.40 | Other | Landscape & Ecology | Ground preparation and cultivation | Final cultivations |  | m2
05.300.0520.10 | Other | Landscape & Ecology | Mulching | Mulching |  | m2
05.300.0520.20 | Other | Landscape & Ecology | Mulching | Mulch mats |  | m2
05.300.0520.30 | Other | Landscape & Ecology | Mulching | Sheet mulch |  | m2
05.300.0520.40 | Other | Landscape & Ecology | Mulching | Sheet mulch collars |  | no
05.300.1010.10 | Other | Landscape & Ecology | Seeding and turfing | Conventional Seeding |  | m2
05.300.1010.20 | Other | Landscape & Ecology | Seeding and turfing | Hydraulic Seeding |  | m2
05.300.1010.30 | Other | Landscape & Ecology | Seeding and turfing | Turfing |  | m2
05.300.1510.10 | Other | Landscape & Ecology | Planting | Trees |  | no
05.300.1510.20 | Other | Landscape & Ecology | Planting | Shrubs |  | no
05.300.1510.30 | Other | Landscape & Ecology | Planting | Wildflower plants |  | no
05.300.1510.40 | Other | Landscape & Ecology | Planting | Hedge plants |  | no
05.300.1510.50 | Other | Landscape & Ecology | Planting | Emergent, marginal and aquatic plants |  | no
05.300.1510.60 | Other | Landscape & Ecology | Planting | Bulbs |  | m2
05.300.2010.10 | Other | Landscape & Ecology | Maintenance-Weed control | Total weed control (generally) |  | m2
05.300.2010.20 | Other | Landscape & Ecology | Maintenance-Weed control | Total weed control to waterbodies |  | m2
05.300.2010.30 | Other | Landscape & Ecology | Maintenance-Weed control | Total weed control to individual trees/shrubs |  | no
05.300.2010.40 | Other | Landscape & Ecology | Maintenance-Weed control | Selective weed control (generally) |  | m2
05.300.2010.50 | Other | Landscape & Ecology | Maintenance-Weed control | Selective weed control to waterbodies |  | m2
05.300.2010.60 | Other | Landscape & Ecology | Maintenance-Weed control | Selective weed control to individual trees/shrubs |  | no
05.300.2010.65 | Other | Landscape & Ecology | Maintenance-Weed control | Weed control by spot application (generally) |  | m2
05.300.2010.70 | Other | Landscape & Ecology | Maintenance-Weed control | Weed control by spot application to waterbodies |  | m2
05.300.2010.80 | Other | Landscape & Ecology | Maintenance-Weed control | Weed control by spot application to trees/shrubs |  | no
05.300.2010.90 | Other | Landscape & Ecology | Maintenance-Weed control | Hand weeding |  | m2
05.300.2010.91 | Other | Landscape & Ecology | Maintenance-Weed control | Cutting weeds |  | m2
05.300.2010.92 | Other | Landscape & Ecology | Maintenance-Weed control | Cutting weeds to waterbodies |  | m2
05.300.2010.93 | Other | Landscape & Ecology | Maintenance-Weed control | Cutting weeds to trees/shrubs |  | no
05.300.2020.10 | Other | Landscape & Ecology | Maintenance of established trees and shrubs | Maintenance of established trees |  | no
05.300.2020.20 | Other | Landscape & Ecology | Maintenance of established trees and shrubs | Maintenance of established shrubs |  | m2
05.300.2030.10 | Other | Landscape & Ecology | Maintenance of established grassed area | Grass cutting |  | m2
05.300.2040.10 | Other | Landscape & Ecology | Maintenance of wildflower areas, areas of nature conservation value and ornamental planting areas | Maintenance of wildflower areas, areas of nature conservation value and ornamental planting areas |  | m2
05.300.2050.10 | Other | Landscape & Ecology | Control of rabbits and deer etc | Control within highway boundary |  | LS
05.300.2050.20 | Other | Landscape & Ecology | Control of rabbits and deer etc | Clearance in fenced areas of planting at location |  | LS
05.300.2810.10 | Other | Landscape & Ecology | Management of established waterbodies | Removal of rubbish & debris |  | LS
05.300.2810.15 | Other | Landscape & Ecology | Management of established waterbodies | Inspection of inlets & outlets |  | LS
05.300.2810.20 | Other | Landscape & Ecology | Management of established waterbodies | Silt inspection |  | LS
05.300.2810.30 | Other | Landscape & Ecology | Management of established waterbodies | Reed bed inspection |  | LS
05.300.2810.40 | Other | Landscape & Ecology | Management of established waterbodies | Silt removal |  | LS
05.300.3010.02 | Other | Landscape & Ecology | Special ecological measures | Installation of tunnels and underpasses | inlcudes bat bridges | LS
05.300.3010.04 | Other | Landscape & Ecology | Special ecological measures | Installation of habitat creation measures |  | LS
05.300.3010.06 | Other | Landscape & Ecology | Special ecological measures | Maintenance of tunnels and underpasses | inlcudes bat bridges | LS
05.300.3010.08 | Other | Landscape & Ecology | Special ecological measures | Maintenance of habitat creation measures |  | LS
05.300.3010.10 | Other | Landscape & Ecology | Special ecological measures | Ecological entrapment measures |  | LS
05.300.5010.10 | Other | Landscape & Ecology | Archaeology | Archaeology |  | LS
05.300.6010.10 | Other | Landscape & Ecology | Aftercare and Landscaping | Aftercare and Landscaping - to include all costs; supervision, management, general labour, plants and other materials, traffic management, equipment and removal and disposal of all arisings |  | LS
05.500.1010.10 | Other | Maintenance Painting Of Existing Steelwork | Maintenance painting | Surface preparation to general surfaces |  | m2
05.500.1010.20 | Other | Maintenance Painting Of Existing Steelwork | Maintenance painting | Protective system to general surfaces prepared |  | m2
05.990.1000.10 | Other | Other Manufacture & Fabrication | Other Manufacture & Fabrication | Unallocated Manufacture & Fabrication Charges | Include here new or otherwise non-standard items | LS
05.990.1000.15 | Other | Other Manufacture & Fabrication | Other Manufacture & Fabrication | Manufacture & fabrication charges not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories | LS
05.990.1000.20 | Other | Other Manufacture & Fabrication | Other Manufacture & Fabrication | Arithmetic errors |  | LS
05.990.1000.30 | Other | Other Manufacture & Fabrication | Other Manufacture & Fabrication | Unallocated Manufacture & Fabrication Charges - composite rates | Includes items that cover a number of CBS codes, such as multiple trades or multiple work series that were priced to suit the sub-contractor, not the HA requirements. | LS
06.100.1000.10 | Other | Civil Engineering Design | Civil Engineering Design | Design Manager |  | hr
06.100.1000.20 | Other | Civil Engineering Design | Civil Engineering Design | Engineer | State type of Engineer. Includes all specialisms and grades below Design Manager; includes technician grades | hr
06.100.1000.30 | Other | Civil Engineering Design | Civil Engineering Design | Material testing | State type of test. | LS
06.200.1000.10 | Other | Electrical Engineering Design | Electrical Engineering Design | Design Manager |  | hr
06.200.1000.20 | Other | Electrical Engineering Design | Electrical Engineering Design | Engineer | State type of Engineer. Includes all specialisms and grades below Design Manager; includes technician grades | hr
06.200.1000.30 | Other | Electrical Engineering Design | Electrical Engineering Design | Electrical assembly testing | State type of test. | LS
06.200.1000.40 | Other | Electrical Engineering Design | Electrical Engineering Design | Commissioning | State works being commissioned | LS
06.300.1000.10 | Other | Landscape & Environmental Design | Landscape & Environmental Design | Design Manager |  | hr
06.300.1000.20 | Other | Landscape & Environmental Design | Landscape & Environmental Design | Engineer | State type of Engineer. Includes all specialisms and grades below Design Manager; includes technician grades | hr
06.300.1000.30 | Other | Landscape & Environmental Design | Landscape & Environmental Design | Technician | State type of Technician Includes all specialisms and grades such as CAD, ICT, etc | hr
06.400.1000.10 | Other | Surveys | Surveys | Site photos and videos |  | LS
06.400.1000.20 | Other | Surveys | Surveys | CCTV Surveys |  | LS
06.400.1000.30 | Other | Surveys | Surveys | Condition Surveys |  | LS
06.700.1000.10 | Other | Overseeing Organisation Consultancy | Overseeing Organisation Consultancy | Design and Site Assurance (Lot 1) |  | LS
06.700.1000.20 | Other | Overseeing Organisation Consultancy | Overseeing Organisation Consultancy | Technology (Lot 2) |  | LS
06.700.1000.30 | Other | Overseeing Organisation Consultancy | Overseeing Organisation Consultancy | Commercial Assurance (Lot 3) |  | LS
06.700.1000.40 | Other | Overseeing Organisation Consultancy | Overseeing Organisation Consultancy | Traffic Modelling (Lot 5) |  | LS
06.800.1000.10 | Other | Specialist Services | Specialist services | Specialist services | includes doc shredding, Met Office reports, etc | LS
06.990.1000.10 | Other | Other Design | Other Design | Unallocated design costs | Include here new or otherwise non-standard items | LS
06.990.1000.15 | Other | Other Design | Other Design | Design costs not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories | LS
06.990.1000.20 | Other | Other Design | Other Design | Arithmetic errors |  | LS
07.100.1000.10 | Other | Insurance - included in delivery partner fee percentage | Insurance - included in delivery partner fee percentage | Insurance - included in delivery partner fee percentage |  | LS
07.200.1000.10 | Other | Insurance - excesses | Insurance - expenditure on items below minimum claim excess | Insurance excesses - damaged plant |  | LS
07.200.1000.20 | Other | Insurance - excesses | Insurance - expenditure on items below minimum claim excess | Insurance excesses - other than damaged plant |  | LS
07.990.1000.10 | Other | Other Insurance | Other Insurance | Unallocated insurance costs | Include here new or otherwise non-standard items | LS
07.990.1000.15 | Other | Other Insurance | Other Insurance | Insurance costs not described/quantified in accordance with CBS | Include here incorrect or incomplete standard items which prevent coding to relevant CBS categories | LS
07.990.1000.20 | Other | Other Insurance | Other Insurance | Arithmetic errors |  | LS
09.990.1000.10 | Other | Other | Other - recoverable cost | Unallocated recoverable costs | Include here new or otherwise non-standard items | LS
09.990.1000.20 | Other | Other | Other - recoverable cost | Arithmetic errors |  | LS
09.990.1000.30 | Other | Other | Other - recoverable cost | Working Area Overhead |  | LS
09.990.2000.10 | Other | Other | Other - non recoverable cost | Unallocated non-recoverable cost | Include here new or otherwise non-standard items | LS
09.990.2000.20 | Other | Other | Other - non recoverable cost | Arithmetic errors |  | LS

## CEs
Compensation Events | [7 empty] | Please indicate the percentage split of each agred CE against the Work Series by value. Eg. For TM CE only, please enter 100 under 0100-100A Traffic Safety and Management, For CE which half affects Filter Drains and Earthworks, enter 50 in 0500-200 Drainage - Filter Drains and 0600-100 Earthworks
[5 empty] | 0 | 0 | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CEMAR CE Ref | Status / Comments | Estimated | Contractors Quotation | SM Assessment | Implemented Value | Interim AFP Provision | Check | 0100-100 Preliminaries (Excluding TM) | 0100-100A Traffic Safety and Management | 0200-100 Site Clearance | 0300-100 Fencing, Gates and Stiles | 0400-100 Vehicle Restraint Systems (Rigid) | 0400-200 Vehicle Restraint Systems (Deformable) | 0400-300 Parapets and Guardrails | 0500-100 Drainage & Service Ducts | 0500-300 Drainage - Chambers and Gullies | 0500-400 Drainage - Headwalls and Outfall Works | 0500-200 Drainage - Filter Drains | 0600-100 Earthworks | 0700-100 Pavements - Sub Base | 0700-200 Pavements - Road Base | 0700-300 Binder Course | 0700-400 Surface (wearing) course | 0700-500 Planing | 0700-600 Rigid Pavement | 0700-700 Surface Treatment | 0700-800 Overbanding and Inlaid Crack Sealing Repair System | 1100-100 Kerbs and Channels | 1100-200 Footways and Paved Areas | 1200-200 Permanent Traffic Signal Installations | 1200-300 Road Markings | 1200-400 Road Studs | 1200-100 Traffic Signs and Bollards | 1300-100 Road Lighting Columns and Masts | 1400-100 Electrical work for road lighting, traffic signs - Cable and Duct | 1400-200 Electrical work for road lighting, traffic signs - Chambers | 1400-300 Electrical work for road lighting, traffic signs - Equipment | 1500-100 Motorway Communications equipment - Cable and Ducts | 1500-200 Motorway Communications equipment - Chambers | 1500-300 Motorway Communications equipment - Technology Equipment | 1500-400 Motorway Communications equipment - Looper Detector Installations | 1600-100 Piling and Embedded Retaining Walls | 1700-100 Structural Concrete (incl steel reinforcement) | 1800-100 Structural Steelwork | 1900/5000-100 Protective Systems (Incorporation Series 1900 & 5000) | 2000-100 Waterproofing | 2100-100 Bridge Bearings | 2300-100 Bridge Joints | 2400-100 Brickwork, Blockwork and Stonework | 2500-100 Special Structures (incl. acoustic fences) | 2700-100 Other Works (SUs, noise insulation, Acc works etc) | 3000-100 Landscape and Ecology

## PAF Calculation
Target Price Indices Uplift |  | (((L-B)/B)x((S+P)/S))
| Base date in contract data: | 2018-07-01
| Pricing Date |  | Date target price returned (amend for each return)
| Task Starting Date |  | Programmed scheme start date
B | the base date Task Index (B) is the value of the latest task index that had been released at the time of the base date | 113.4 | Base date index
L | the Task Index (L) is the value of the latest task index that had been released at the Pricing Date |  | BCIS index issued monthly by HE
P | the Pricing Period (P) is the period of time in weeks from the Pricing Date to the Task starting date | 0
S | the Index Period (S) is the period of time in weeks from the date of award of the Framework Contract to the Pricing Date | -6183.1429
| Indices Uplift | 0
| Tendered Items Target Price | 0
| Star Rates/Non Tendered Items Price - Base Rates | 0 | Provide total star rates using base rates
| Star Rates/Non Tendered Items Price - Current Rates | 0 | Provide total star rates using current rates
| Total Target Price (excl PAF) | 0
| HTMPAF Indices Uplift | 0
| Final Target Price Including PAF | 0
| LESS Original Target Cost | 0
| Final Price Adjustment for Inflation | 0

## PC Role
|  | PC - Final Target | 0 | To be completed by HE QS prior to final account
|  | Contractor 1 - Final Target | 0
|  | Contractor 2 - Final Target | 0
|  | Contractor 3 - Final Target | 0
|  | Contractor 4 - Final Target | 0
|  | Contractor 5 - Final Target | 0
|  | Contractor 6 - Final Target | 0
|  | Total Value of scheme | 0
FACTORS APPLICABLE WHEN APPOINTED PRINCIPLE CONTRACTOR
For Principle Contractor role and responsibilities in line with the requirements of CDM Regulations 2015
Value of Scheme | Band | Percentage (excluding fee)
upto £30k | Band A | 0% | 0
>£30k upto £250k | Band B | 0% | 0
>250k upto £1m | Band C | 0% | 0
>£1m upto £5m | Band D | 0% | 0
>£5m | Band E | 0% | 0
|  | Amend red text to your applicable uplift banding | 0
|  | Total Target PC Role uplift £ | 0 | Insert amount in original target for PC Role
|  | Amendments to Uplift for PC Role | 0

## Forecast
Spend Profile for -
Defined Cost Forecast
|  | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | check
| Staff | [13 empty] | 0
| Labour | [13 empty] | 0
| Plant | [13 empty] | 0
| Materials | [13 empty] | 0
| Charges | [13 empty] | 0
| Other & Sub Contractors | [13 empty] | 0
| Monthly Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scheme Total | 0
Previous month total
Total Increase in forecasted costs |  | 0
Contract Data - Option C & Clause Z57.2
[10 empty] | Share Ranges | Share %
[10 empty] | <85% | 0
[10 empty] | 85%-95% | 0.25
[10 empty] | 95%-105% | 0.5
[10 empty] | > 105% | 0.25
[10 empty] | Gain Share |  |  | Pain Share |  | Share Payment Due | Final Account Due
| Contractor | Original Target Cost | Agreed & Implemented CEs | Final Price Adjustment for Inflation | Amendments to Uplift for PC Role | Final Total of the Prices | Forecast PSPD | Variance | Share Range | <85% (Share: 0%) | 85%-95% (Share: 25%) | 95%-100% (Share: 50%) | 100%-105% (Share: 50%) | >105% (Share: 25%)
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
Note on F27: Logan, Ella: Amend to £0.00 if not PC on this scheme

## Data Dump
For Contractors Use

## Share Ranges
Final Account Calculations
Scheme Name: | 0
PIN: | 0
Contract Data - Option C & Clause Z57.2
Scheme Start Date: | 0 | [8 empty] | Share Ranges | Share %
[10 empty] | <85% | 0
Completion Date: | 0 | [8 empty] | 85%-95% | 0.25
[10 empty] | 95%-105% | 0.5
Application Stage : | Interim | [8 empty] | > 105% | 0.25
Procurement Method: | 0 | [8 empty] | Gain Share |  |  | Pain Share |  | Share Payment Due | Final Account Due
| Contractor | Original Target Cost | Agreed & Implemented CEs | Final Price Adjustment for Inflation | Amendments to Uplift for PC Role | Final Total of the Prices | Final PSPD | Variance | Share Range | <85% (Share: 0%) | 85%-95% (Share: 25%) | 95%-100% (Share: 50%) | 100%-105% (Share: 50%) | >105% (Share: 25%)
Applied | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
Assessed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0

## FA Statement
Area 10
Highways England
Atlantic House
Birchwood Point
Birchwood
Warrington
Area 10 Construction Works Framework |  |  |  | WA3 7WE
Final Account Statement for Scheme:
Contract: | 0
Scheme PIN No: | 0
Task Order No: | 0
Lot No: | 0
Contractor: | 0
Employer: | Highways England Company Limited
Financial Information:
| Original Target Costs: | 0
| Agreed and Implemented CEs: | 0
| PAF Adjustment: | 0
| PC Adjustment: | 0
| Final Total of the Prices: | 0
| Final Price for Services Provided to Date: | 0
| Pain / Gain Share: | 0
| Total Final Account: | 0
| Latest Cumulative Certified: | 0
| Final Account Due: | 0
We, 0 (0), accept the total amount of 0 excluding Value Added Tax, as the final account for scheme PIN 0.
We also retain our responsibilities for all defects, shrinkages and other faults arising in connection with our works in accordance with the terms of the Construction Works Framework contract and at common law. We further confirm that we have no outstanding claims against Highways England Company Ltd in respect of the above scheme.
Signed on behalf of | 0 |  | Signed on behalf of Highways England Company Ltd
Signed: |  |  | Signed:
Name: |  |  | Name:
Position: |  |  | Position:
Date: |  |  | Date:

## Apps Cert Calendar
Payment Schedule
| Period | Contractor Working Period End Date | Contractor AFP Due Date | SM Assessment Date | SM Certifcate Issue Date | Contractors Invoice Date | Final Payment Date
| 2020-01-01 | 2020-01-31 | 2020-02-05 | 2020-02-06 | 2020-02-13 | 2020-02-20 | 2020-03-20
| 2020-02-01 | 2020-02-29 | 2020-03-05 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-04-20
| 2020-03-01 | 2020-03-31 | 2020-04-05 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-05-20
| 2020-04-01 | 2020-04-30 | 2020-05-05 | 2020-05-06 | 2020-05-13 | 2020-05-20 | 2020-06-20
| 2020-05-01 | 2020-05-31 | 2020-06-05 | 2020-06-06 | 2020-06-13 | 2020-06-20 | 2020-07-20
| 2020-06-01 | 2020-06-30 | 2020-07-05 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-08-20
| 2020-07-01 | 2020-07-31 | 2020-08-05 | 2020-08-06 | 2020-08-13 | 2020-08-20 | 2020-09-20
| 2020-08-01 | 2020-08-31 | 2020-09-05 | 2020-09-06 | 2020-09-13 | 2020-09-20 | 2020-10-20
| 2020-09-01 | 2020-09-30 | 2020-10-05 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-11-20
| 2020-10-01 | 2020-10-31 | 2020-11-05 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-12-20
| 2020-11-01 | 2020-11-30 | 2020-12-05 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2021-01-20
| 2020-12-01 | 2020-12-31 | 2021-01-05 | 2021-01-06 | 2021-01-13 | 2021-01-20 | 2021-02-20
| 2021-01-01 | 2021-01-31 | 2021-02-05 | 2021-02-06 | 2021-02-13 | 2021-02-20 | 2021-03-20
| 2021-02-01 | 2021-02-28 | 2021-03-05 | 2021-03-06 | 2021-03-13 | 2021-03-20 | 2021-04-20
| 2021-03-01 | 2021-03-31 | 2021-04-05 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-05-20
| 2021-04-01 | 2021-04-30 | 2021-05-05 | 2021-05-06 | 2021-05-13 | 2021-05-20 | 2021-06-20
| 2021-05-01 | 2021-05-31 | 2021-06-05 | 2021-06-06 | 2021-06-13 | 2021-06-20 | 2021-07-20
| 2021-06-01 | 2021-06-30 | 2021-07-05 | 2021-07-06 | 2021-07-13 | 2021-07-20 | 2021-08-20
Formulas:
SM Assessment Date = [Contractor AFP Due Date]+1
Final Payment Date = EDATE([Contractors Invoice Date],1)

## ABS
HE ABS Analysis
|  | Input Agreed Target Price Split |  |  | Input Actual Quantities of Work |  | Defined Cost Components | [6 empty] | Cost Summary
[7 empty] | People |  | Equipment | [10 empty] | Variance
ACTIVITY DESCRIPTION | UoM | Initial Target Price Value | CE Price Value | Final Price Value | Actual Quantity |  | Staff | Labour | Plant | Other | Materials | Charges | Other/SC | People | Equipment | Materials | Charges | Other/SC | Grand Total | £ | %
0100-100 Preliminaries (Excluding TM) | days |  | 0 | 0 |  | 0100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0100-100A Traffic Safety and Management | days |  | 0 | 0 |  | 0100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0200-100 Site Clearance | item |  | 0 | 0 |  | 0200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0300-100 Fencing, Gates and Stiles | lin m |  | 0 | 0 |  | 0300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0400-100 Vehicle Restraint Systems (Rigid) | lin m |  | 0 | 0 |  | 0400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0400-200 Vehicle Restraint Systems (Deformable) | lin m |  | 0 | 0 |  | 0400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0400-300 Parapets and Guardrails | lin m |  | 0 | 0 |  | 0400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0500-100 Drainage & Service Ducts | lin m |  | 0 | 0 |  | 0500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0500-300 Drainage - Chambers and Gullies | no. |  | 0 | 0 |  | 0500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0500-400 Drainage - Headwalls and Outfall Works | no. |  | 0 | 0 |  | 0500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0500-200 Drainage - Filter Drains | cu m |  | 0 | 0 |  | 0500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0600-100 Earthworks | cu m |  | 0 | 0 |  | 0600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-100 Pavements - Sub Base | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-200 Pavements - Road Base | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-300 Binder Course | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-400 Surface (wearing) course | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-500 Planing | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-600 Rigid Pavement | cu m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-700 Surface Treatment | sq m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0700-800 Overbanding and Inlaid Crack Sealing Repair System | lin m |  | 0 | 0 |  | 0700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100-100 Kerbs and Channels | lin m |  | 0 | 0 |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100-200 Footways and Paved Areas | sq m |  | 0 | 0 |  | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200-200 Permanent Traffic Signal Installations | no. |  | 0 | 0 |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200-300 Road Markings | item |  | 0 | 0 |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200-400 Road Studs | lin m |  | 0 | 0 |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200-100 Traffic Signs and Bollards | no. |  | 0 | 0 |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1300-100 Road Lighting Columns and Masts | no. |  | 0 | 0 |  | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400-100 Electrical work for road lighting, traffic signs - Cable and Duct | lin m |  | 0 | 0 |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400-200 Electrical work for road lighting, traffic signs - Chambers | no. |  | 0 | 0 |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400-300 Electrical work for road lighting, traffic signs - Equipment | no. |  | 0 | 0 |  | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500-100 Motorway Communications equipment - Cable and Ducts | lin m |  | 0 | 0 |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500-200 Motorway Communications equipment - Chambers | no. |  | 0 | 0 |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500-300 Motorway Communications equipment - Technology Equipment | no. |  | 0 | 0 |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500-400 Motorway Communications equipment - Looper Detector Installations | no. |  | 0 | 0 |  | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1600-100 Piling and Embedded Retaining Walls | item |  | 0 | 0 |  | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1700-100 Structural Concrete (incl steel reinforcement) | cu m |  | 0 | 0 |  | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1800-100 Structural Steelwork | t |  | 0 | 0 |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1900/5000-100 Protective Systems (Incorporation Series 1900 & 5000) | sq m |  | 0 | 0 |  | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000-100 Waterproofing | sq m |  | 0 | 0 |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2100-100 Bridge Bearings | no. |  | 0 | 0 |  | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2300-100 Bridge Joints | lin m |  | 0 | 0 |  | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2400-100 Brickwork, Blockwork and Stonework | sq m |  | 0 | 0 |  | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2500-100 Special Structures (incl. acoustic fences) | item |  | 0 | 0 |  | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2700-100 Other Works (SUs, noise insulation, Acc works etc) | item |  | 0 | 0 |  | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000-100 Landscape and Ecology | sq m |  | 0 | 0 |  | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## List (hidden)
NEC Option | PC Role | Status
TSC Option C | Yes | Interim |  | Application for Payment
TSC Option E | No | Final |  | HE Assessment
AE Yates | ATM | Balvac | Carnell | Chevron | Colas | Concrete Repairs | Crown | Forkers | Ground Control | HW Martin | Interserve | J McCann | Joe Roocroft | L&R Roadlines | Route One | Volkerlaser | Wilson & Scott | WJ North
Lot 5 | Lot 7 | Lot 13 | Lot 4 | Lot 11 | Lot 9 | Lot 13 | Lot 4 | Lot 10 | Lot 7 | Lot 11 | Lot 5 | Lot 4 | Lot 9 | Lot 8 | Lot 14 | Lot 14 | Lot 8 | Lot 8
Lot 10 |  |  | Lot 5 |  | Lot 11 |  | Lot 6 |  |  |  |  | Lot 6
Lot 10