## Sch 3 Table 1
SPECTRA FIRST SCHEDULE 3 TABLE 1
Year 1: January - March 2018 £74,327.90
Activities - cross-referenced to DP | 2018-01-01 | 2018-02-01 | 2018-03-01
1.1. Attendance at Regional events, seminars, conferences and industry events |  | Attending 2 x SF organised events and/or third party events where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 3 x SF organised events and/or third party events where the opportunity to promote the Covenant to stakeholders has been approved with event organisers.
1.2. Briefing and publication contributions | Introductory briefings (customised) prepared and distributed to 5 targeted stakeholders. | Introductory briefings (customised) prepared and distributed to 5 targeted stakeholders.
2.1. Promotions to care leaving teams (11.02, 11.03 and 1.04) |  | 1 x briefing event delivered to 6 x local authority officers. | 1 x briefing event delivered to 6 x local authority officers.
|  | Promotions and engagement with transitions’ teams x 6. | Promotions and engagement with transitions’ teams x 6.
3.1. Regional awareness raising activities (10.01) |  |  | 2 x events organised to promote the Covenant to potential signatories.
3.2. Identifying ‘warm’ leads (10.02) | 20 x warm leads identified and approached for exploratory meetings.
3.3. Engaging businesses and organisations (10.03) |  | Follow-up meetings with 5 x warm leads to secure in-principle agreement to signing up to the Covenant. | Follow-up meetings with 5 x warm leads to secure in-principle agreement to signing up to the Covenant.
Costs | 11413.74 | 29365.05 | 33549.1
Year 2: April 2018 - March 2019 £565,350.52
Activities - cross-referenced to DP | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01
4.1 Attendance at Regional events, seminars, conferences and industry events | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders. | Attending and/or organising 1 x regional event/month at which the Covenant is promoted to key stakeholders.
4.2 Briefing and publication contributions | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders. | Two introductory briefings (customised) prepared and distributed to targeted stakeholders.
5.1 Promotions to care leaving teams (11.02, 11.03 and 1.04) | 2018-04-01: 6 x briefing events delivered to local authority officers (average 7 LAs/event); 2018-05-01: 7 x briefing events delivered to local authority officers (average 7 LAs/event); 2018-06-01: 7 x briefing events delivered to local authority officers (average 7 LAs/event); 2019-03-01: 6 x briefing events delivered to local authority officers (average 7 LAs/event)
| Promotions and engagement with 24 x transitions’ teams. | Promotions and engagement with 30 x transitions’ teams. | Promotions and engagement with 24 x transitions’ teams. | Promotions and engagement with 30 x transitions’ teams. | Promotions and engagement with 24 x transitions’ teams. | Promotions and engagement with 8 x transitions’ teams. |  |  |  | Promotions and engagement with 12 x transitions’ teams. |  | Promotions and engagement with 24 x transitions’ teams.
6.1 Regional awareness raising activities (10.01) | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories. | 2 x events organised to promote the Covenant to potential signatories.
6.2 Identifying ‘warm’ leads (10.02) | 12 x warm leads identified and approached for exploratory meetings. | 13 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings. | 13 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings. | 13 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings. | 13 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings. | 13 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings. | 12 x warm leads identified and approached for exploratory meetings.
6.3 Engaging businesses and organisations (10.03) | Follow-up meetings with 10 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 20 x organisations to negotiate Covenant offers | Follow-up meetings with 10 x organisations to negotiate Covenant offers
[8 empty] | Guest speaker at a third party event |  |  | Guest speaker at a third party event | Guest speaker at a third party event
[7 empty] | Promotional articles written targeting specifc sectors |  |  |  |  | Promotional articles written targeting specifc sectors
6.4 Promotions to care leaving teams (11.02, 11.03 and 1.04) | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams | 1 x weekly mailshots distributed to all care leaving teams
6.5 Promotions to care leavers | Processing applications for 50 x Privilege Cards | Processing applications for 200 x Privilege Cards | Processing applications for 250 x Privilege Cards | Processing applications for 250 x Privilege Cards | Processing applications for 250 x Privilege Cards | Processing applications for 250 x Privilege Cards | Processing applications for 500 x Privilege Cards | Processing applications for 500 x Privilege Cards | Processing applications for 500 x Privilege Cards | Processing applications for 750 x Privilege Cards | Processing applications for 750 x Privilege Cards | Processing applications for 750 x Privilege Cards
| Monthly mailshot (including social media postings) to care leavers with informatio about new offers and new Covenant signatories. | Monthly mailshot (including social media postings) to care leavers with informatio about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories. | Monthly mailshot to care leavers with information about new offers and new Covenant signatories.
|  |  | 1 x event organised to promote the Covenant and Covenant offers to care leavers |  |  |  | 2 x events organised to promote the Covenant and Covenant offers to care leavers |  | 1 x event organised to promote the Covenant and Covenant offers to care leavers |  | 1 x event organised to promote the Covenant and Covenant offers to care leavers | 1 x event organised to promote the Covenant and Covenant offers to care leavers
7.1 Promotions to care leaving teams (11.02, 11.03 and 1.04) | 2018-09-01: 1 x event organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats; 2018-10-01: 1 x event organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats; 2018-11-01: 2 x events organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats; 2019-01-01: 1 x event organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats; 2019-02-01: 1 x event organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats; 2019-03-01: 1 x event organised and delivered to promote early success to care leaving teams and enage them in dialoge about future opportunities and threats
7.2 Promotions through case studies (12.02) | 2018-10-01: 2 x case studies researched and prepared; 2018-11-01: 2 x case studies researched and prepared; 2018-12-01: 2 x case studies researched and prepared; 2019-01-01: 2 x case studies researched and prepared; 2019-02-01: 2 x case studies researched and prepared; 2019-03-01: 2 x case studies researched and prepared
7.3 Review performance management information and impact surveys |  |  | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers | Monthly 'customer feedback' survey with care leavers
7.4 Sharing information with the Department (11.05) |  |  | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department | Weekly information sharing with the Department
7.5 Dissemination to care leavers |  |  | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings | Sharing good news through social media postings
7.6 Annual celebration and Awards | 2019-02-01: Organisation and delivery of a national Celebration event
8.1 Monitor range and spread of Covenant signatories (12.01) |  |  | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics
8.2 Monitor take up and impact of Covenant offers (12.01, 12.03) |  |  | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics
8.3 Consultation with Care Leavers’ Forum | 2018-06-01: Two organised consultations with care leavers through regional care leavers' forums; 2018-09-01: Two organised consultations with care leavers through regional care leavers' forums; 2018-12-01: Two organised consultations with care leavers through regional care leavers' forums; 2019-03-01: Two organised consultations with care leavers through regional care leavers' forums
8.4 Identify and engage businesses to fill the gaps Covenant signatories (10.02, 10.03) | 2019-01-01: Two new businesses identified and engaged in development work to sign up to the Covenant; 2019-03-01: Three new businesses identified and engaged in development work to sign up to the Covenant
8.5 Negotiate new offers (10.03) | 2019-02-01: New offers being negotiated and confirmed with gap-filling Covenant signatories; 2019-03-01: New offers being negotiated and confirmed with gap-filling Covenant signatories
8.6 Promote new offers (11.02, 11.03, 11.04) | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots
9.1 Performance management information | 2019-03-01: Independent evaluation advertised and tenders invited.
Costs | 51559.54 | 56080.43 | 59710.23 | 48550.28 | 45349.71 | 42490.33 | 37254 | 32516.9 | 34547.27 | 40555.64 | 67191.39 | 49544.81
Year 3: April 2019 - December 2019 £297,682.56
Activities - cross-referenced to DP | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
10.1. Regional awareness raising activities (10.01) | Attending 2 x SF organised events and/or third party events where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 2 x SF organised events and/or third party events where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 2 x SF organised events and/or third party events where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 1 x SF organised event and/or third party event where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 1 x SF organised event and/or third party event where the opportunity to promote the Covenant to stakeholders has been approved with event organisers. | Attending 1 x SF organised event and/or third party event where the opportunity to promote the Covenant to stakeholders has been approved with event organisers.
10.1. Engaging businesses and organisations (10.03) | 3 x regional awareness-raising events organised to promote the Covenant to potential signatories. | 3 x regional awareness-raising events organised to promote the Covenant to potential signatories. | 3 x regional awareness-raising events organised to promote the Covenant to potential signatories. | 3 x regional awareness-raising events organised to promote the Covenant to potential signatories. |  | 3 x regional awareness-raising events organised to promote the Covenant to potential signatories. | 2 x regional awareness-raising events organised to promote the Covenant to potential signatories.
| 10 x warm leads identified and approached for exploratory meetings. | 10 x warm leads identified and approached for exploratory meetings. | 10 x warm leads identified and approached for exploratory meetings. | 10 x warm leads identified and approached for exploratory meetings. | 10 x warm leads identified and approached for exploratory meetings. | 5 x warm leads identified and approached for exploratory meetings.
| Development work with 15 businesses and organisations to sign the Covenant and introduce offers | Development work with 15 businesses and organisations to sign the Covenant and introduce offers | Development work with 15 businesses and organisations to sign the Covenant and introduce offers | Development work with 15 businesses and organisations to sign the Covenant and introduce offers | Development work with 10 businesses and organisations to sign the Covenant and introduce offers | Development work with 10 businesses and organisations to sign the Covenant and introduce offers | Development work with 10 businesses and organisations to sign the Covenant and introduce offers | Development work with 10 businesses and organisations to sign the Covenant and introduce offers
10.3. Promotions to care leaving teams (11.02, 11.03 and 1.04) | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email | Engagement with 19 x care leaving teams through outreach, telephone, and email
| Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots | Promotion to care leaving teams through weekly mailshots
| Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 600 x Privilege Cards | Processing applications for 200 x Privilege Cards
10.4. Review performance management for declining take up of offers and opportunities for a refresh | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal | Monthly monitoring of take up of offers with a view to refreshing, increasing promotion and/or withdrawal
10.5. Development work with signatories | Development work with 7 existing Covenant signatories to introduce new offers | Development work with 8 existing Covenant signatories to introduce new offers | Development work with 7 existing Covenant signatories to introduce new offers | Development work with 8 existing Covenant signatories to introduce new offers | Development work with 7 existing Covenant signatories to introduce new offers | Development work with 8 existing Covenant signatories to introduce new offers | Development work with 7 existing Covenant signatories to introduce new offers | Development work with 8 existing Covenant signatories to introduce new offers
11.1. Promotions to care leaving teams (11.02, 11.03 and 1.04) | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls | Promoting Covenant offers to all care leaving teams through e-mail and follow up calls
12.1. Monitor range and spread of Covenant signatories (12.01) | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics | Monthly monitoring of Covenant signatories by type, sector, geography, size and demographics
12.2. Monitor take up and impact of Covenant offers (12.01, 12.03) | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics | Monthly monitoring of take up of Covenant offers by type, sector, geography and care leaver demographics
12.3. Consultation with Care Leavers’ Forum | 2019-05-01: Two organised consultations with care leavers through regional care leavers' forums; 2019-07-01: Two organised consultations with care leavers through regional care leavers' forums; 2019-11-01: Two organised consultations with care leavers through regional care leavers' forums
12.5. Negotiate new offers (10.03) | 2019-09-01: Development work to negotiate 5 x new offers from existing Covenant signatories; 2019-10-01: Development work to negotiate 5 x new offers from existing Covenant signatories; 2019-11-01: Development work to negotiate 5 x new offers from existing Covenant signatories
13.1 Promote new offers (11.02, 11.03, 11.04) | 2019-09-01: 5 x new gap filling offers promoted to all care leaving teams through mailshots and telephone calls; 2019-10-01: 5 x new gap filling offers promoted to all care leaving teams through mailshots and telephone calls; 2019-11-01: 5 x new gap filling offers promoted to all care leaving teams through mailshots and telephone calls
[6 empty] | Promotional mailshots and social media postings to stimulate take up of new offers by 34 care leavers | Promotional mailshots and social media postings to stimulate take up of new offers by 34 care leavers | Promotional mailshots and social media postings to stimulate take up of new offers by 33 care leavers
13.2. Undertake final evaluation | 2019-05-01: Progres report of independent evaluation; 2019-07-01: Interim report of independent evaluation; 2019-09-01: Final report of independent evaluation
13.3. Prepare final reports (12.01, 12.03) | 2019-05-01: 4 x case studies researched and prepared; 2019-09-01: 4 x case studies researched and prepared; 2019-11-01: 2 x case studies researched and prepared
[7 empty] | Preparation of final reports and implementation of exit plan commences | Implementation of exit plan continuing | Implementation of exit plan concluded
Costs | 26622.99 | 45286.99 | 26622.99 | 42842.23 | 17960.51 | 44750.13 | 57257.14 | 29283.55 | 7056.03

## Jan - March 2018
Cost Matrix (additional lines can be added to the table below (ensuring that the Totals calculations remain accurate))
The Cost Matrix should:
· include the full costs (including day rates where appropriate) of delivering the requirement as detailed within the Specification;
· include costings which reflect the activities, products to be delivered and milestones as set out in your Delivery Plan, including the dates (or periods) of delivery;
· Provide details of the evidence of delivery you will provide to enable payment to be made which should be sufficient to demonstrate timely delivery to the appropriate standard; and
· Specify the linked Key Performance Indicator .
Name of organisation: | Spectra First
From January 2018 to March 2018
Objective, Activity, product to be delivered or milestone | Value | VAT | Total budget | Date (or period) of delivery | Evidence of delivery you will provide to enable payment to be made | Linked Key Performance Indicator to demonstrate your delivery is on track | Additional information you consider relevant
(ex VAT)
KPI - 5 x businesses and organisations engaged | 21559.1887 | 1647.7731 | 23206.9618 | Jan -March 2018 | Programmes, venue hire invoices, attendance sheets | Organisations signing the Covenant
Activity - Attendance at 5 regional events, seminars, conferences and industry events | 10479.5943 | 763.8866 | 11243.4809 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO @ 5 days, DSO @ 5 days, HMC@3 days, PRM @ 5 days | 4084.6154 |  | 4084.6154
Promotional and marketing activity venue hire |  | 0 | 0
Travel and subsistence | 600 | 120 | 720
Other categories of activity | 5794.979 | 643.8866 | 6438.8655
Activity - Briefings (x10) and publication contributions | 11079.5943 | 883.8866 | 11963.4809 | Jan -March 2018 | Monitoring reports to DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - CEO5 days, DSO@5 days, HMC@3days, PRM@5 days | 4084.6154 |  | 4084.6154
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence for briefings | 1200 | 240 | 1440
Other categories of activity | 5794.979 | 643.8866 | 6438.8655
0
0
KPI - Engagement with 12 local authorities | 7772.9316 | 606.3599 | 8379.2915 | Jan -March 2018
Activity - Promotions to care leaving teams (2 x briefing events) | 7772.9316 | 606.3599 | 8379.2915 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@2days, DSO@2days, HMC@2days, PRM@10days | 2907.6923 |  | 2907.6923
Promotional and marketing activity | 500 | 100 | 600
Travel and subsistence | 240 | 48 | 288
Other categories of activity | 4125.2393 | 458.3599 | 4583.5992
0
0
KPI - Engagement with 12 x transitions teams | 12236.4541 | 821.7599 | 13058.214
Activity - Promotions to care leaving teams (visits/follow up calls @ 1.5 days/LA) | 12236.4541 | 821.7599 | 13058.214 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@6, DSO@6 x 1.5 days/team | 4984.6154 |  | 4984.6154
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25%visits | 180 | 36 | 216 | Jan -March 2018
Other categories of activity | 7071.8387 | 785.7599 | 7857.5986
0
0
KPI - 5 organisations signing the Covenant | 27401.2744 | 2244.2442 | 29645.5185
Activity - Regional awareness raising activities (x2) | 7198.424 | 717.2266 | 7915.6507 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@2days, DSO@2days, HMC@2days, PRM@5days | 2215.3846 |  | 2215.3846
Promotional and marketing activity - advertising and venue hire | 1600 | 320 | 1920
Travel and subsistence | 240 | 48 | 288
Other categories of activity | 3143.0394 | 349.2266 | 3492.266
0
Activity - Identifying 20 ‘warm’ leads within existing networks with follow-up targeting and meetings) | 5048.621 | 377.5733 | 5426.1943 | Dec -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@3 days, DSOs@3 days, PRM@2days | 1938.4615 |  | 1938.4615
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 360 | 72 | 432
Other categories of activity | 2750.1595 | 305.5733 | 3055.7328
0
Activity - Engaging businesses and organisations (x10) | 15154.2293 | 1149.4443 | 16303.6736 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@8 days, DSO@8days, RBMs@4days, PRM@5days | 5769.2308 |  | 5769.2308
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 1200 | 240 | 1440
Other categories of activity | 8184.9985 | 909.4443 | 9094.4428
0
Activity - Promotions to care leaving teams (disseminating information about Covenant offers x 0) | 0 |  | 0 | Jan -March 2018 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing |  |  | 0
Promotional and marketing activity | 0 |  | 0
Travel and subsistence |  | 0 | 0
Other categories of activity | 0 |  | 0
Totals | 68969.8487 | 5320.137 | 74289.9858

## April 2018 - March 2019
Cost Matrix (additional lines can be added to the table below (ensuring that the Totals calculations remain accurate))
The Cost Matrix should:
· include the full costs (including day rates where appropriate) of delivering the requirement as detailed within the Specification;
· include costings which reflect the activities, products to be delivered and milestones as set out in your Delivery Plan, including the dates (or periods) of delivery;
· Provide details of the evidence of delivery you will provide to enable payment to be made which should be sufficient to demonstrate timely delivery to the appropriate standard; and
· Specify the linked Key Performance Indicator .
Name of organisation: | Spectra First
From April 2018 to March 2019
Objective, Activity, product to be delivered or milestone | Value | VAT | Total budget | Date (or period) of delivery | Evidence of delivery you will provide to enable payment to be made | Linked Key Performance Indicator to demonstrate your delivery is on track | Additional information you consider relevant
(ex VAT)
KPI - Engagement with 10 key stakeholders per month | 75237.7847 | 5302.2154 | 80540.0001 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Attendance at 12 regional events, seminars, conferences and industry events | 54082.8714 | 3843.0541 | 57925.9255 | April 2018 - March 2019 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - RMBs@1day/event, Admin @ 24 days | 25255.3846 |  | 25255.3846
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 7200 | 1440 | 8640
Other categories of activity | 21627.4868 | 2403.0541 | 24030.5409
Activity - Briefings (x24) and publication contributions | 21154.9133 | 1459.1613 | 22614.0746 | April 2018 - March 2019 | Monitoring reports to DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - HMC@5 days, RBMs@ 42 days, PRM@ 10 days, Admin @ 10 days | 10038.4615 |  | 10038.4615
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence for briefings | 2520 | 504 | 3024
Other categories of activity | 8596.4517 | 955.1613 | 9551.613
0
0
KPI - Engagement with 152 local authorities | 24064.3247 | 2334.1557 | 26398.4805 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions to care leaving teams (20 x briefing events for remaining 140 LAs) | 24064.3247 | 2334.1557 | 26398.4805 | April 2018 - March 2019 | Monitoring reports to DfE | Engagement with care leavers and their awareness of the Covenant
Staffing -HMC@5days, PRM@10days, RBMs@20 days, Admin@40days | 8976.9231 |  | 8976.9231
Promotional and marketing activity - venue hire @ £250 each | 5000 | 1000 | 6000
Travel and subsistence | 2400 | 480 | 2880
Other categories of activity | 7687.4017 | 854.1557 | 8541.5574
0
0
KPI - Engagement with 152 transitions teams - 6/week | 76825.203 | 4220.4072 | 81045.6101 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions to care leaving teams (visits/follow up calls/CRM @ 1.5 days/LA) | 76825.203 | 4220.4072 | 81045.6101 | April 2018 - March 2019 | Monitoring reports to DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - HMC@15days, RBMs@152 x 1.5 days, Admin @5days | 40361.5385 |  | 40361.5385
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25%visits | 1900 | 380 | 2280
Other categories of activity | 34563.6645 | 3840.4072 | 38404.0717
0
0
KPI - 150 organisations signing the Covenant | 180980.1753 | 14324.7716 | 195304.9469 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Regional awareness raising activities (x24) | 40689.2099 | 5369.8438 | 46059.0538 | April 2018 - March 2019 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - HMC@10days, PRM@15days, RBMs@24 days, Admin@24days | 10024.6154 |  | 10024.6154
Promotional and marketing activity - advertising and venue hire | 19200 | 3840 | 23040
Travel and subsistence | 2880 | 576 | 3456
Other categories of activity | 8584.5945 | 953.8438 | 9538.4384
Activity - Identifying 150 ‘warm’ leads within existing networks with follow-up targeting and meetings) | 10298.6204 | 581.4194 | 10880.0398 | April 2018 - March 2019 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@10 days, RBMs@12 days, Admin@5days | 5353.8462 |  | 5353.8462
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 360 | 72 | 432
Other categories of activity | 4584.7743 | 509.4194 | 5094.1936
Activity - Engaging businesses and organisations (x230) | 129992.345 | 8373.5084 | 138365.8534 | April 2018 - March 2019 | Monitoring reports to DfE | Organisations signing the Covenant
Staffing - CEO@6 days, DSO@15days, RBMs@1.5days, Admin@30days | 63830.7692 |  | 63830.7692
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 11500 | 2300 | 13800
Other categories of activity | 54661.5758 | 6073.5084 | 60735.0842
KPI - 5000 care leavers engaged | 4009.7193 | 205.5244 | 4215.2436 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Processing referrals from care leaving teams for Covenant Privilege Cards | 4009.7193 | 205.5244 | 4215.2436 | April 2018 - March 2019 | Monitoring reports to DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - Admin@0.5days/week | 2160 |  | 2160
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 1849.7193 | 205.5244 | 2055.2436
KPI - 165 care leavers taking up offers | 35111.0527 | 2903.3477 | 38014.4004 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions to care leaving teams (disseminating information about Covenant offers x 150) | 11084.6561 | 850.7738 | 11935.4299 | April 2018 - March 2019 | Monitoring reports to DfE | Increase take up of offers
Staffing - RBMs@0.1daysx152LAs, Admin@30days | 4947.6923 |  | 4947.6923
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25%visits | 1900 | 380 | 2280
Other categories of activity | 4236.9638 | 470.7738 | 4707.7375
Activity - Promotion to care leavers - mailshots | 6554.3488 | 335.9533 | 6890.3021 | April 2018 - March 2019 | Monitoring reports to DfE | Increase take up of offers
Staffing - HMC@5days, Admin@30days | 3530.7692 |  | 3530.7692
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25%visits | 0 | 0 | 0
Other categories of activity | 3023.5796 | 335.9533 | 3359.5329
Activity - Promotion to care leavers - promotional events (x6) | 17472.0478 | 1716.6207 | 19188.6685 | June 2018 - March 2019 | Monitoring reports to DfE | Increase take up of offers
Staffing - HMC@5days, RBMs@3days/event, Admin@30days | 6438.4615 |  | 6438.4615
Promotional and marketing activity advertising and venue hire | 4800 | 960 | 5760
Travel and subsistence | 720 | 144 | 864
Other categories of activity | 5513.5863 | 612.6207 | 6126.207
KPI - 12 case studies prepared | 15364.6817 | 1715.6997 | 17080.3813 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Research and prepare case studies (x12) | 15364.6817 | 1715.6997 | 17080.3813 | Oct 2018 - March 2019 | Monitoring reports to DfE | Care leavers aware and engaged in the Covenant
Staffing - HMC@5days, RBMs@2days research and writing up/case study | 4915.3846 |  | 4915.3846
Promotional and marketing activity | 4800 | 960 | 5760
Travel and subsistence | 1440 | 288 | 1728
Other categories of activity | 4209.297 | 467.6997 | 4676.9967
KPI - Good news stories in weekly mailshots of Covenant offers | 10024.2982 | 513.8109 | 10538.1091 | July 2018 - March 2019 | Monitoring reports to DfE
Activity - Review performance management information and impact surveys | 10024.2982 | 513.8109 | 10538.1091 | July 2018 - March 2019 | Monitoring reports to DfE | Care leavers aware and engaged in the Covenant
Staffing - PRM@1day/week | 5400 |  | 5400
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 4624.2982 | 513.8109 | 5138.1091
KPI - Guest speaker at 3 events | 1979.3097 | 155.0002 | 2134.3099 | Oct 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions through case studies | 1979.3097 | 155.0002 | 2134.3099 | Oct 2018 - March 2019 | Monitoring reports to DfE | Organisations signing up to the Covenant
Staffing - HMC@1day/event, Admin@1day/event | 872.3077 |  | 872.3077
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 360 | 72 | 432
Other categories of activity | 747.002 | 83.0002 | 830.0022
KPI - Contribution to two publicity activities (press releases, events, briefings) | 925.3198 | 47.4287 | 972.7485 | Oct 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions through case studies | 925.3198 | 47.4287 | 972.7485 | Oct 2018 - March 2019 | Monitoring reports to DfE | Organisations signing up to the Covenant
Staffing - HMC@2days, Admin@1day | 498.4615 |  | 498.4615
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 426.8583 | 47.4287 | 474.287
KPI - 7 x Regional promotional events for care leaving team managers | 12993.454 | 1311.5462 | 14305.0001 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Promotions to care leaving teams | 12993.454 | 1311.5462 | 14305.0001 | April 2018 - March 2019 | Monitoring reports to DfE | Care leavers aware and engaged in the Covenant
Staffing - HMC@3days, RBMs@1day/event, Admin@5days/event | 4661.5385 |  | 4661.5385
Promotional and marketing activity - venue hire | 3500 | 700 | 4200
Travel and subsistence | 840 | 168 | 1008
Other categories of activity | 3991.9155 | 443.5462 | 4435.4617
KPI - 5,000 care leavers notified of early successes | 29090.1303 | 3371.1769 | 32461.3072 | Oct 2018 - March 2019 | Monitoring reports to DfE
Activity - Dissemination to care leavers | 1156.6498 | 59.2859 | 1215.9357 | Oct 2018 - March 2019 | Monitoring reports to DfE | Care leavers aware and engaged in the Covenant
Staffing - HMC@1day, Admin@5days | 623.0769 |  | 623.0769
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 533.5729 | 59.2859 | 592.8587
Activity - Annual celebration and Awards | 27933.4805 | 3311.891 | 31245.3715 | 2019-02-01 | Monitoring reports to DfE | Care leavers aware and engaged in the Covenant
Staffing - CEO@2days, DSO@5days, HMC@10days, RBMs@3days, PRM@5, Admin@20days | 8238.4615 |  | 8238.4615
Promotional and marketing activity - venue hire, meals, entertainment and Awards (Awards sponsored ideally bur budgeted as a contingency) | 10000 | 2000 | 12000
Travel and subsistence - including regional delegations of care leavers (1/Englsh region) | 2640 | 528 | 3168
Other categories of activity | 7055.019 | 783.891 | 7838.91
KPI - Department informed of early successes (This KPI was not previously identified in its own right although the supporting activity has been identified and included) | 12312.0989 | 702.4725 | 13014.5715 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Sharing information with the Department | 12312.0989 | 702.4725 | 13014.5715 | April 2018 - March 2019 | Monitoring reports to DfE
Staffing - DSO@4 days, HMC@0.25days/week, PRM@1day/month, Admin@1day/month | 6373.8462 |  | 6373.8462
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - quarterly meetings | 480 | 96 | 576
Other categories of activity | 5458.2528 | 606.4725 | 6064.7253
KPI - 5 organisations signing the Covenant (filling gaps in provision) | 25335.6808 | 2064.6483 | 27400.329 | April 2018 - March 2019 | Monitoring reports to DfE
Activity - Monitor range and spread of Covenant signatories | 2313.2996 | 118.5717 | 2431.8713 | April 2018 - March 2019 | Monitoring reports to DfE | Diversity of organisations signing the Covenant
Staffing - PRM@1day/month | 1246.1538 |  | 1246.1538
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - quarterly meetings | 0 | 0 | 0
Other categories of activity | 1067.1457 | 118.5717 | 1185.7175
Activity - Monitor take up and impact of Covenant offers | 2313.2996 | 118.5717 | 2431.8713 | April 2018 - March 2019 | Monitoring reports to DfE | Increase take up of offers
Staffing - PRM@1day/month (cumulative analysis building on monthly analysis under KPI 'Good news stories in weekly mailshots of Covenant offers' | 1246.1538 |  | 1246.1538
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 1067.1457 | 118.5717 | 1185.7175
Activity - Consultations with Care Leavers Forums (2/region x4 regions) | 13190.5384 | 1330.5726 | 14521.111 | April 2018 - March 2019 | Monitoring reports to DfE | Increase care leavers' satisfaction
Staffing - PRM@5days, RBMs@3days/event, Admin@2days | 4735.3846 |  | 4735.3846
Promotional and marketing activity - venue hire | 2000 | 400 | 2400
Travel and subsistence - regional travel for RBMs and care leavers travel expenses to consultations | 2400 | 480 | 2880
Other categories of activity | 4055.1538 | 450.5726 | 4505.7264
Activity - Identify and engage businesses (x5) to fill the gaps Covenant signatories | 5769.1824 | 370.0801 | 6139.2625 | Jan 2019 - March 2019 | Monitoring reports to DfE | Diversity of organisations signing the Covenant
Staffing - PRM@3days, RBMs@3days/business | 2838.4615 |  | 2838.4615
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - RBMs to prospective gap filling signatories | 500 | 100 | 600
Other categories of activity | 2430.7208 | 270.0801 | 2700.8009
Activity - Negotiate new (gap filling) offers | 1749.3608 | 126.8521 | 1876.2129 | Jan 2019 - March 2019 | Monitoring reports to DfE | Diversity of offers available
Staffing - RBMs@1day/business | 807.6923 |  | 807.6923
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - RBMs to prospective gap filling signatories | 250 | 50 | 300
Other categories of activity | 691.6685 | 76.8521 | 768.5206
KPI - 300 x care leavers engaged | 2004.8596 | 102.7622 | 2107.6218 | Jan 2019 - March 2019 | Monitoring reports to DfE
Activity - Processing referrals from care leaving teams for Covenant Privilege Cards | 2004.8596 | 102.7622 | 2107.6218 | Jan 2019 - March 2019 | Monitoring reports to DfE | Care leavers aware of the Covenant
Staffing - Admin@0.25days/week | 1080 |  | 1080
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 924.8596 | 102.7622 | 1027.6218
KPI - 5 x organisations signing the Covenant (filling gaps in provision) | 1749.3608 | 126.8521 | 1876.2129 | Jan 2019 - March 2019 | Monitoring reports to DfE
Activity - Promote new offers | 1749.3608 | 126.8521 | 1876.2129 | Jan 2019 - March 2019 | Monitoring reports to DfE | Increase diversity of offers available
Staffing - RBMs@1day/business | 807.6923 |  | 807.6923
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - RBMs to prospective gap filling signatories | 250 | 50 | 300
Other categories of activity | 691.6685 | 76.8521 | 768.5206
KPI - 100 x care leavers taking up offers | 11084.6561 | 850.7738 | 11935.4299 | Jan 2019 - March 2019 | Monitoring reports to DfE
Activity - Promotions to care leaving teams (disseminating information about Covenant offers x 100) | 11084.6561 | 850.7738 | 11935.4299 | Jan 2019 - March 2019 | Monitoring reports to DfE | Care leavers taking up of Covenant offers
Staffing - RBMs@0.1daysx152LAs, Admin@30days | 4947.6923 |  | 4947.6923
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 1900 | 380 | 2280
Other categories of activity | 4236.9638 | 470.7738 | 4707.7375
KPI - Evaluation commisioned | 5517.6479 | 282.8156 | 5800.4635 | 2019-03-01 | Monitoring reports to DfE
Activity - Advertise ITT and select provider | 5517.6479 | 282.8156 | 5800.4635 | 2019-03-01 | Monitoring reports to DfE | Promoting good practice
Staffing - CEO@2days, DSO@3days, HMC@3days, RBM@2days, PRM@3days, Admin@3days | 2972.3077 |  | 2972.3077
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 2545.3402 | 282.8156 | 2828.1558
Totals | 524609.7575 | 40535.409 | 565145.1664

## April - December 2019
Cost Matrix (additional lines can be added to the table below (ensuring that the Totals calculations remain accurate))
The Cost Matrix should:
· include the full costs (including day rates where appropriate) of delivering the requirement as detailed within the Specification;
· include costings which reflect the activities, products to be delivered and milestones as set out in your Delivery Plan, including the dates (or periods) of delivery;
· Provide details of the evidence of delivery you will provide to enable payment to be made which should be sufficient to demonstrate timely delivery to the appropriate standard; and
· Specify the linked Key Performance Indicator .
Name of organisation: | Spectra First
From April 2019 to December 2019
Objective, Activity, product to be delivered or milestone | Value | VAT | Total budget | Date (or period) of delivery | Evidence of delivery you will provide to enable payment to be made | Linked Key Performance Indicator to demonstrate your delivery is on track | Additional information you consider relevant
(ex VAT)
KPI - Engagement with 10 key stakeholders per month (Q1) | 9723.2164 | 610.101 | 10333.3174 | April - December 2019 | Monitoring reports to the DfE
Activity - Attendance at 9 regional events, seminars, conferences and industry events | 9723.2164 | 610.101 | 10333.3174 | April - December 2019 | Monitoring reports to the DfE | Organisations signing the Covenant
Staffing - RMBs@1day/event, Admin @ 9 days | 5432.3077 |  | 5432.3077
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 1500 | 300 | 1800
Other categories of activity | 2790.9087 | 310.101 | 3101.0097
Activity - Briefings (x24) and publication contributions | 0 | 0 | 0 | April - December 2019 | Monitoring reports to the DfE | Engagement with care leavers and their awareness of the Covenant
Staffing
Promotional and marketing activity
Travel and subsistence for briefings
Other categories of activity | 0 | 0
0
KPI - 85 organisations signing the Covenant | 77388.768 | 6326.4443 | 83715.2123 | April - December 2019 | Monitoring reports to the DfE
Activity - Regional awareness raising activities (x17) | 25707.6762 | 3507.6563 | 29215.3325 | April - December 2019 | Monitoring reports to the DfE | Organisations signing the Covenant
Staffing - HMC@2days, PRM@15days, RBMs@17days, Admin@17days | 6650.7692 |  | 6650.7692
Promotional and marketing activity - advertising and venue hire | 13600 | 2720 | 16320
Travel and subsistence | 2040 | 408 | 2448
Other categories of activity | 3416.907 | 379.6563 | 3796.5633
Activity - Identifying 55 ‘warm’ leads within existing networks with follow-up targeting and meetings) | 6822.5958 | 315.7072 | 7138.303 | April - December 2019 | Monitoring reports to the DfE | Organisations signing the Covenant
Staffing - CEO@8 days, RBMs@9 days, Admin@5days | 4269.2308 |  | 4269.2308
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 360 | 72 | 432
Other categories of activity | 2193.365 | 243.7072 | 2437.0722
Activity - Engaging businesses and organisations (x100) | 44858.496 | 2503.0808 | 47361.5767 | April - December 2019 | Monitoring reports to the DfE | Organisations signing the Covenant
Staffing - DSO@5days, RBMs@1.5days, Admin@10days | 26330.7692 |  | 26330.7692
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 5000 | 1000 | 6000
Other categories of activity | 13527.7268 | 1503.0808 | 15030.8075
KPI - 130 new offers developed | 28836.0918 | 1209.1384 | 30045.2302 | April - December 2019 | Monitoring reports to the DfE
Activity - Review performance management for declining take up of offers and opportunities for a refresh | 5030.3448 | 189.6964 | 5220.0412 | April - December 2019 | Monitoring reports to the DfE | Increase take up of offers
Staffing - PRM@2days/month | 3323.0769 |  | 3323.0769
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 1707.2679 | 189.6964 | 1896.9643
Activity - Development work with 60 signatories (existing) | 23805.747 | 1019.442 | 24825.189 | April - December 2019 | Monitoring reports to the DfE | Diversity of Covenant offers
Staffing - PRM@5 days, RBMs@1.5days/signatory | 15230.7692 |  | 15230.7692
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25% visits | 750 | 150 | 900
Other categories of activity | 7824.9778 | 869.442 | 8694.4198
KPI - Engagement with 152 local authorities | 30405.2872 | 1454.9464 | 31860.2337 | April - December 2019 | Monitoring reports to the DfE
Activity - Promotions to care leaving teams (visits/follow up calls/CRM @ 1.5 days/LA) | 30405.2872 | 1454.9464 | 31860.2337 | April - December 2019 | Monitoring reports to the DfE | Care leavers and awareness of Covenant offers
Staffing - RBMs@0.75daysx152LAs, Admin @5days | 18830.7692 |  | 18830.7692
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - contingency for 25%visits | 1900 | 380 | 2280
Other categories of activity | 9674.518 | 1074.9464 | 10749.4644
KPI - 5000 care leavers engaged | 2452.2931 | 92.477 | 2544.7701 | April - December 2019 | Monitoring reports to the DfE
Activity - Processing referrals from care leaving teams for Covenant Privilege Cards | 2452.2931 | 92.477 | 2544.7701 | April - December 2019 | Monitoring reports to the DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - Admin@0.5days/week | 1620 |  | 1620
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 832.2931 | 92.477 | 924.7701
KPI - 300 care leavers taking up offers | 12338.318 | 465.2832 | 12803.6011 | April - December 2019 | Monitoring reports to the DfE
Activity - Promotions to care leaving teams (disseminating information about Covenant offers x 300) | 12338.318 | 465.2832 | 12803.6011 | April - December 2019 | Monitoring reports to the DfE | Increase take up of offers
Staffing - RBMs@0.2daysx152LAs, Admin@39days | 8150.7692 |  | 8150.7692
Promotional and marketing activity | 0 |  | 0
Travel and subsistence |  | 0 | 0
Other categories of activity | 4187.5487 | 465.2832 | 4652.8319
KPI - 10 organisations signing the Covenant (filling gaps in provision) | 2515.1724 | 94.8482 | 2610.0206 | April - December 2019 | Monitoring reports to the DfE
Activity - Monitor range and spread of Covenant signatories (12.01) | 2515.1724 | 94.8482 | 2610.0206 | April - December 2019 | Monitoring reports to the DfE | Diversity of organisations signing the Covenant
Staffing - PRM@1day/month | 1661.5385 |  | 1661.5385
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence - quarterly meetings | 0 | 0 | 0
Other categories of activity | 853.6339 | 94.8482 | 948.4822
KPI - 15 new offers developed | 24412.7959 | 1567.7466 | 25980.5424 | April - December 2019 | Monitoring reports to the DfE
Activity - Monitor take up and impact of Covenant offers | 8174.3103 | 308.2567 | 8482.567 | April - December 2019 | Monitoring reports to the DfE | Care leavers aware and engaged in the Covenant
Staffing - PRM@1day/week | 5400 |  | 5400
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 2774.3103 | 308.2567 | 3082.567
Activity - Consultations with Care Leavers Forums ( x6) | 9501.0574 | 974.9893 | 10476.0467 | April - December 2019 | Monitoring reports to the DfE | Increase care leavers' satisfaction
Staffing - PRM@5days, RBMs@3days/event, Admin@2days | 3766.1538 |  | 3766.1538
Promotional and marketing activity - venue hire | 1500 | 300 | 1800
Travel and subsistence - regional travel for RBMs and care leavers travel expenses to consultations | 2300 | 460 | 2760
Other categories of activity | 1934.9036 | 214.9893 | 2149.8929
Activity - Negotiate new offers x 15 | 6737.4281 | 284.5006 | 7021.9287 | July - December 2019 | Monitoring reports to the DfE | Diversity of Covenant offers
Staffing - PRM@5 days, RBMs@1.5days/offer | 4326.9231 |  | 4326.9231
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25% visits | 187.5 | 37.5 | 225
Other categories of activity | 2223.0051 | 247.0006 | 2470.0056
KPI - 300 care leavers engaged | 2452.2931 | 92.477 | 2544.7701 | April - December 2019 | Monitoring reports to the DfE
Activity - Processing referrals from care leaving teams for Covenant Privilege Cards | 2452.2931 | 92.477 | 2544.7701 | April - December 2019 | Monitoring reports to the DfE | Engagement with care leavers and their awareness of the Covenant
Staffing - Admin@0.5days/week | 1620 |  | 1620
Promotional and marketing activity | 0 |  | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 832.2931 | 92.477 | 924.7701
KPI - 100 care leavers taking up offers | 12079.8141 | 455.5349 | 12535.349 | April - December 2019 | Monitoring reports to the DfE
Activity - Promotions to care leaving teams (disseminating information about Covenant offers x 300) | 8621.4521 | 325.1186 | 8946.5707 | April - December 2019 | Monitoring reports to the DfE | Increase take up of offers
Staffing - RBMs@0.1daysx152LAs, Admin@39days | 5695.3846 |  | 5695.3846
Promotional and marketing activity | 0 |  | 0
Travel and subsistence |  | 0 | 0
Other categories of activity | 2926.0675 | 325.1186 | 3251.1861
Activity - Promotion to care leavers - mailshots | 3458.3621 | 130.4163 | 3588.7784 | April - December 2019 | Monitoring reports to the DfE | Increase take up of offers
Staffing - HMC@5days, Admin@15days | 2284.6154 |  | 2284.6154
Promotional and marketing activity | 0 |  | 0
Travel and subsistence - contingency for 25%visits | 0 | 0 | 0
Other categories of activity | 1173.7467 | 130.4163 | 1304.163
KPI - 10 case studies prepared | 5809.8084 | 300.2351 | 6110.0435 | April - December 2019 | Monitoring reports to the DfE
Activity - Research and prepare case studies (x10) | 5809.8084 | 300.2351 | 6110.0435 | April - December 2019 | Monitoring reports to the DfE | Care leavers aware and engaged in the Covenant
Staffing - PRM@2days, RBMs@2days research and writing up/case study | 3507.6923 |  | 3507.6923
Promotional and marketing activity |  |  | 0
Travel and subsistence | 500 | 100 | 600
Other categories of activity | 1802.1161 | 200.2351 | 2002.3512
KPI - National Conference | 68013.5439 | 8829.1972 | 76842.7411 | April - December 2019 | Monitoring reports to the DfE
Activity - Undertake final evaluation (contract letting, management, moitoring, reporting and report publication) | 32730.0057 | 5447.2998 | 38177.3055 | April - September 2019 | Monitoring reports to the DfE | Record/validate achievements, care leaver satisfaction and good practice
Staffing - CEO@1days, DSO@5days, HMC@3days, RBM@10days, PRM@3days, Admin@3days | 4472.3077 |  | 4472.3077
Promotional and marketing activity - evaluation and publication of evaluation report | 25000 | 5000 | 30000
Travel and subsistence - RBMs to feedback meetings | 960 | 192 | 1152
Other categories of activity | 2297.698 | 255.2998 | 2552.9978
Activity - Prepare final reports | 10172.4751 | 383.6083 | 10556.0834 | Oct - December 2019 | Monitoring reports to the DfE | Contract compliance
Staffing - CEO@1day, DSO@5days, HMC@2days, PRM@5days, RBMs@2days, Admin@2days | 6720 |  | 6720
Promotional and marketing activity | 0 | 0 | 0
Travel and subsistence | 0 | 0 | 0
Other categories of activity | 3452.4751 | 383.6083 | 3836.0834
Activity - To promote successes (National Conference, Annual Celebration and Awards) | 25111.0632 | 2998.2891 | 28109.3522 | Oct - December 2019 | Monitoring reports to the DfE | Good practice dissemination
Staffing - CEO@2days, DSO@5days, HMC@10days, RBMs@3days, PRM@5, Admin@20days | 8238.4615 |  | 8238.4615
Promotional and marketing activity - venue hire, meals, entertainment and Awards (Awards sponsored ideally) | 10000 | 2000 | 12000
Travel and subsistence - including regional delegations of care leavers (1/Englsh region) | 2640 | 528 | 3168
Other categories of activity | 4232.6016 | 470.2891 | 4702.8907
Totals | 276427.4023 | 21498.4293 | 297925.8317

## Total cost price
Period | Total Cost
January 2018 - March 2018 | 74289.9858
April 2018 - March 2019 | 565145.1664
April 2019 - December 2019 | 297925.8317
Total | 937360.9838