## References
Author | Source | Type | Dialogue area | Workstream | Status | Document amendment required
Tenderers | Dialogue | Conclusion | Outline Solution | Technical | Open | Yes
Highways England | e-Sourcing Portal | Action | Disseminate Traffic Data | Commercial | In Progress | No
| Kick Off Meeting | Clarification query | Disseminate Network and Asset Model | N/A | Closed
Disseminate Event Information
Disseminate Operational Intelligence
Transition and Transformation
Transition Services
Transformation Services
IT Service Management
Service Outcomes and Performance Measures
Service Continuity and Corporate Resolution Plan
Quality Plan
Feedback on Contract
Sub-Contractors
Software and Insurance
Transition and Transformation
Milestones and Testing
Financial model (inc. Risk Register, Service Charges and Milestones)
TUPE

## Log
Ref | Date submitted | Author | Source | Type | Workstream | Dialogue area | Document reference or theme | Description | Response | Owner | Status | Date response issued | Document amendment required? | Date amendment issued | Document amendment description
1 | 2020-07-27 | Tenderers | e-Sourcing Portal | Clarification query | N/A | Outline Solution | ITPD Appendix I | Please could Highways England confirm whether the 0900-1030 Outline Solution session, which is common to both the Technical and Commercial streams, will be a joint session with all attendees of both streams or if they will be separate sessions? | Yes, the first session of CD1 will be a joint session with both panels to review the Outline Solution (between 0900-1030). Once finished the panels will then split as per the individual agendas in the ITPD Appendix I. Note there are other areas where the panels will dial in together - The Kick Off Meeting Day 2 slide deck outlines these sessions. | Highways England | Closed | 2020-07-31 | No
2 | 2020-07-30 | Tenderers | Kick Off Meeting | Clarification query | N/A | Outline Solution | Outline Solution | Can you confirm the feedback on the outline solution will be written and provided through the Bravo Platform on Friday 14 August? | Yes, the intention is to provide written feedback and the formal route of doing so will be via Bravo. Feedback will only be on the outline solution and we shall not be providing feedback on the contract feedback template (ITPD Appendix G). | Highways England | Closed | 2020-07-31 | No
3 | 2020-07-30 | Tenderers | Kick Off Meeting | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | The financial model is due on 21 Aug - given the feedback on the solution is 1 week before (14 Aug) - and the CD1 sessions are 18-20 Aug (where we will gain further feedback), the financial model we discuss in CD2 (2-4Sept) will not be representative of the current solution thinking. With this in mind what is the intent for the CD2 session on the financial model? | There are sessions within CD2, CD3 and CD4 to discuss the financial model. The intention is that the model will develop across these sessions, but Highways England would appreciate an initial view on the contents of the model ahead of CD2. | Highways England | Closed | 2020-07-31 | No
4 | 2020-07-30 | Tenderers | Kick Off Meeting | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Relating to the above question (Ref 3), is this commentary on the content of the financial model or a population of the model based on the data the supply chain has at the moment ahead of the session. | Highways England are looking for an initial population of the model based on information available at that time. Highways England is aware that this will change as the dialogue progress as is the nature of the process. | Highways England | Closed | 2020-07-31 | No
5 | 2020-07-31 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Schedule 6.2 (Table 1), and Finance model (Tab “Pricing”) | In the finance model template provided, there are 3 Milestones listed after Milestone Ref 2.4 which do not appear in Table 1 of Schedule 6.2. Could you please confirm which Table is correct for Milestone Payment purposes? | Not all of the milestones are related to payments. The additional milestones are in relation to the potential extension periods. These have been deleted from the model. | Highways England | Closed | 2020-08-06 | No
6 | 2020-07-31 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | The example information provided in the Financial Model Template presents a potential discrepancy as the Prime Staff Rates do not flow to B4-Cost_Imp or B5-Cost_Service tabs unless the Skills Column contains the coded skills (e.g. A1 Advice and Guidance, A2 Technical Strategy and Planning, B1 Business Change Implementation, etc.) and also an associated SFIA level in the Responsibility Column. For example; in the Staff Rates, row 70, shows Finance Manager with an hourly rate calculated. However on the B4-Cost_Imp tab, row 25, the Finance Manager is shown with a zero cost rate. Is it Highway England’s intent to have the Prime Staff Rates entered as the Key Subcontractor 1, which shows every mix of the coded skills and SFIA Levels? | The model will be updated so the staff rates flow through to B4 and B5, and re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
7 | 2020-07-31 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | In the Financial Model Template on tab B6-Pricing, the costs and contingency are calculated totals from the cost input. The Milestone Payment is a formula which adds the columns for Costs + Forecast Contingency Costs. The Profit column is another formula which is the Milestone Payment – Costs – Contingency Costs. The column title is Milestone Payment but it is only adding the costs, hence subtracting the costs from the Milestone Payment will always show zero Profit. This error is easily corrected by changing the Milestone Payment to equal the sum of the Costs + Contingency Costs + Profit, where the Profit value is manually entered by the tenderer. However, Instruction 19 states “Do not delete formulae provided in the model.” Will Highways England be re-issuing the Financial Model Template ahead of the initial submission of the financial model on 21 Aug? | The model will be updated to allow for manual input of service provider profit, and re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
8 | 2020-07-31 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Schedule 7.1 - Section 9 (Gainshare) | Please can Highways England advise how the application of any Gainshare payments which may be payable to the Service Provider would operate with the Maximum Permitted Profit Margin? E.g. does any Gainshare paid sit outside of the Maximum Permitted Profit Margin | The Gain-Share Supplement falls within the scope of Charges (as defined in Schedule 1). It will be taken into account in any calculation of profit. | Highways England | Closed | 2020-08-06 | No
9 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 | We notice one of the staff in this file is enrolled on a DC pension scheme, please can Highways England confirm if this scheme is likely to be covered by the new fair deal scheme? | This scheme is not covered by the new fair deal scheme. Q 86 of NTIS PQQ Clarification Query log issue 7 refers. | Highways England | Closed | 2020-08-06 | No
10 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 | Please can Highways England confirm the working locations for the staff members on this sheet including if any are classified as Home Workers? | The working location for all NIS staff is the Highways England NTOC building at Quinton, Birmingham. None are classified as Home Workers | Highways England | Closed | 2020-08-06 | No
11 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 | We understand that this list refers to Sub-Contractor staff who are potentially in scope to transfer under TUPE, please can Highways England confirm that all of these staff are full time employees and that there are no part time or agency workers? | This information is in document "NTIS Subcontractor Staffing Information" in the Data room. This indicates there are no subcontractor part-time or agency workers in scope for TUPE. | Highways England | Closed | 2020-08-06 | No
12 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | Please can Highways England confirm the job titles for the 60 Employees in this list? | The job titles can be found in the Data Room within the Role Profiles folder and organogram (NIS F QUAL 026 Organogram (anonymous)) in the Registers folder | Highways England | Closed | 2020-08-06 | No
13 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | Please can Highways England confirm the contractual annual leave allowance? | Contractual annual leave allowances can be found in Data room documents: NIS Ltd Contract, NIS Ltd shift worker Contract, and NTIS Subcontractor Staff List. | Highways England | Closed | 2020-08-06 | No
14 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | Please can Highways England confirm the contractual working hours per week for all the staff listed? | This information can be found in Data Room documents as Q13 | Highways England | Closed | 2020-08-06 | No
15 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | For the avoidance doubt please can Highways England confirm the reference in Column B to "Per" indicates that all these staff are permanent? | PER means Permanent Member of Staff | Highways England | Closed | 2020-08-06 | No
16 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | Please can Highways England confirm that all staff listed in this sheet are full time employees and that there are no part time or agency workers? | Details of full and part-time employees can be found in "NIS Provisional Staff List "in the Data Room (column K). | Highways England | Closed | 2020-08-06 | No
17 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Provisional Staff List (Anonymous) | Please can Highways England confirm the pension data and scheme information for the staff in this list? | Pension information is included in Data Room documents "NTIS Subcontractor Staffing Information" , "NIS Ltd Contract", "NIS Ltd shift worker Contract". "Flexible Benefits", and "Simply Benefits". A further document "WSP Likemind Booklet" describing the NIS employee scheme will be added to the Data Room. | Highways England | Closed | 2020-08-06 | No
18 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 NIS Provisional Staff List (Anonymous) | Please can Highways England confirm if any of the NIS employees and sub-contractor staff have mobility clauses in their contract of employment? | Please see Data Room documents "NIS Ltd Contract " and "NIS Ltd shift worker Contract" under Flexibility for NIS employees. There is no mobility clause in place for subcontractor staff. | Highways England | Closed | 2020-08-06 | No
19 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 NIS Provisional Staff List (Anonymous) | Please can Highways England confirm which NIS employees and sub-contractor staff, if any, receive overtime payments and average amounts and values over 12 months. | All staff are eligible for overtime. The average monthly overtime payment for all staff over the last 12 months is £2,440. | Highways England | Closed | 2020-08-06 | No
20 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 NIS Provisional Staff List (Anonymous) | Please can Highways England confirm which NIS employees and sub-contractor staff, if any, have contractual shift patterns in their contracts and what they are? | NIS staff who are assigned to the Operational Information Centre work contractual shift patterns as set out in the "NIS Ltd Shiftworker Contract" in the Data Room. Early shifts 06:00 – 14:30, Late shift 13:30 – 23:00 & Night shift 21:00 – 06:30 Four NIS IT engineers are on a weekly rota (Mon-Mon) at an agreed standby rate, plus Overtime payment for time worked after call out at applicable OT rates | Highways England | Closed | 2020-08-06 | No
21 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3 NIS Provisional Staff List (Anonymous) | Please can Highways England confirm what the redundancy policy and terms are for all NIS employees and sub-contractor staff? | Redundancy terms for NIS employees are based on statutory guidelines. Subcontractor redundancy details can be found in the Data Room document "NTIS Subcontractor Staff Information) | Highways England | Closed | 2020-08-06 | No
22 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Schedule 2.1 (Service Description) (paragraph 4.1.1(T1-001)) | In the event that Highways England is unable to obtain all Existing Assets and Information from the Outgoing Service Provider, which is necessary for the Service Provider to provide the Operational Services post Transition, what process will be used to discuss and agree any impacts of such shortfalls? | Provision is made in the current agreement with the existing Service Provider (including in the Exit Plan) for the handover of Existing Assets and Information. It is envisaged that all parties will work together during the mobilisation period to prevent such shortfalls. | Highways England | Closed | 2020-08-06 | No
23 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Asset List June 2020 (in the Data Room) | The Asset List shows many assets that are End of Life/End of Support and no longer under mainstream vendor support / maintenance. Please can Highways England clarify if any support contracts are in place to support these assets and if so please provide details? | Support contracts are in place in accordance with current contractual requirements. Specific details will not be provided. | Highways England | Closed | 2020-08-06 | No
24 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | N/A | Please can Highways England clarify who will be responsible for the local area network in the Quinton office, where Highways England and the Supplier staff will cohabit? Is it a shared network or is it two discreet entities? | Highways England's corporate network and LAN is entirely separate from the LAN used by the supplier to deliver the NTIS services. The supplier is responsible for providing their own LAN and any LANs/WANs needed for delivery of NTIS services. | Highways England | Closed | 2020-08-06 | No
25 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | N/A | Please can Highways England clarify who will be responsible for providing internet connectivity in the Quinton office, where Highways England and the Supplier staff will cohabit? Is it a shared connectivity solution or is it two discreet connections? | The supplier will be responsible for providing their own internet connection and any internet connections required for NTIS solutions. | Highways England | Closed | 2020-08-06 | No
26 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | N/A | Please can Highways England clarify who will be responsible for the structured cabling to desks, patch panels, comms room(s) and patching in the Quinton office? | The structured cabling to desks and panels is provided by Highways England. The supplier should manage their own patching to that cabling | Highways England | Closed | 2020-08-06 | No
27 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | N/A | Please can Highways England clarify who will be responsible for power to the desks for such things as PCs and Laptops in the Quinton office? | Highways England will provide all power connections. | Highways England | Closed | 2020-08-06 | No
28 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Asset List May 2020 | There are no printers listed in the Asset List. How does Highways England envisage printing by the NTIS team to be handled? Is this a Highways England provided facility in the Quinton office? If not, then what print facilities are required for the current solution? | Print facilities are expected to be provided by the supplier. | Highways England | Closed | 2020-08-06 | No
29 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Asset List May 2020 | From the Asset List it is unclear which network devices form part of the data centre and can be decommissioned after migration to the cloud and which do not. Please can Highways England clarify this? | All network devices in the asset list are used for provision of the NTIS services. It will be dependent on solution design which items will be required post migration to the cloud. It is feasible that none will be required post migration. | Highways England | Closed | 2020-08-06 | No
30 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Asset List May 2020 | There are a small number of WiFi devices in the Asset List, please can Highways England clarify what these are used for? | These relate to the current supplier's internal Wifi | Highways England | Closed | 2020-08-06 | No
31 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Asset List May 2020 | The Asset List contains a number of PCs and Laptops. Please could Highways England detail how these are managed today? i.e. SCCM, WSUS, Intune. Also do Highways England and the NTIS team have separate end user device management platforms/services or do they use shared infrastructure? | The current supplier has their our own infrastructure and do not share with Highways England. NIS uses WSUS, PolicyPak & PDQ Deploy to manage PCs & Laptops | Highways England | Closed | 2020-08-06 | No
32 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query |  |  | N/A | How are the sites currently connected? Is this some form of WAN? If so please can Highways England specify the connectivity in place and who owns/manages this? | The NTOC site and Slough data centre are connected to a WAN which is provided and managed by the supplier using Virgin Media and BT for resilience. This is managed by NIS with support contracts with the supplier. NIS have their own internet connections in Quinton and Slough. NRTS is used if there is a TMU/ANPR/TAME outage that is not NTIS system related. NRTS liaise with EE to solve the problem. As part of the NRTS project, Telent provide and transport services between NTIS and the ROCs for access to the Highways England CCTV and Midas Systems, including resilient data links to the nominated Disaster Recovery Centre of Slough. | Highways England | Closed | 2020-08-06 | No
33 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Schedule 2.4 (Security Management) | Annex 3 of Schedule 2.4 is not available in the document repository. Please can Highways England provide a copy to enable us to understand your requirements in detail? | Annex 3 will be updated and provided in the near future. Once ready this answer will be updated and the document uploaded to Bravo. | Highways England | Closed | 2020-08-06 | No
34 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Schedule 2.4 (Security Management) | Please can Highways England confirm that the existing Core Information Management System (provided by the Outgoing Service Provider) has been Accredited and that there are no outstanding security issues or vulnerabilities? | The IMS is ISO accredited and there are not expected to be any security issues or vulnerabilities at service handover that require corrective action from the new supplier A signed Code of Connection is in place with Highways England. This was updated in July 2020. The current supplier is certified to ISO 27001:2013 and undertake annual PEN tests from an external company. | Highways England | Closed | 2020-08-06 | No
35 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Data Centre | Is it NTIS objective to get rid of the current Data Centre? Once the move to cloud is complete, is the cost of removing equipment from the existing Data Centre within scope for the supplier. | Highways England is looking for tenderers to determine what happens to existing assets and to establish the nature of future cloud service models. The supplier will be responsible for the disposal of all the exclusive assets within the service where the supplier determines that the assets are no longer required. | Highways England | Closed | 2020-08-06 | No
36 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Security | Does Highways England have any internal assessment as to the current cybersecurity risks associated with the system to be transitioned? | Yes we do have an internal assessment as to the current cybersecurity risks associated with the system to be transitioned and the level of risk is within Highways England's tolerance. |  | Closed | 2020-08-07 | No
37 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Data Centre | Does Highways England manage and operate all the data centres in scope of NTIS (Production and Non-Production) or is there dependency on outgoing supplier NIS who manage these data centres? Is it expected that the new supplier will have to take charge of all data centres and manage them going forward including eventually migrating to cloud. | The current service has infrastructure assets in the equipment rooms at the NTOC in Quinton, Birmingham (Highways England premises which are available for use by the new supplier in accordance with Schedule 13.1) and in leased space at Cyxtera, Slough Data Centre LRH1, 630 Ajax Avenue, Slough, England, SL1 4DG (a disaster recovery site). The assets used to deliver the service are included on the asset register and will be transferred to Highways England then to the new Service Provider if required. | Highways England | Closed | 2020-08-06 | No
38 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Service Desk Volumetrics | What do the group names mean – are these different IT support teams sitting in the Information Centre, Traffic engineers and Technology support team? | Yes, they are the internal groups within NIS covering IT, Traffic Engineering etc. and includes Thales. |  | Closed | 2020-08-07 | No
39 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Service Desk Volumetrics | Can you share the ticket dump including changes, incidents and requests with the description, resolution notes, time stamp, priority, Configuration item / application mapping, etc. | Please see document - service volumetrics additional data . Other items are seen as internal process elements and are therefore excluded. |  | Closed | 2020-08-07 | No
40 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | What is the ITSM tool used for capturing incidents, requests and changes? | CA service desk | Highways England | Closed | 2020-08-06 | No
41 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Service Desk Volumetrics | Groups like Thales, Service Desk, HATRIS service desk will continue to operate and support post vendor take over. Please confirm. | No. These services are provided by the current supplier, the new supplier will be fully responsible for implementing all of these functions in delivering NTIS | Highways England | Closed | 2020-08-06 | No
42 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Service Desk Volumetrics | June-Aug 2019 shows a spike in Severity Level 1 and 2 tickets – can you please let us know the reason for that? Is it seasonal – summertime peaks? Is that the trend seen every year? | This is not a seasonal or repeated trend. It was related to an unforeseen system issue, that required investigation and development to resolve. |  | Closed | 2020-08-07 | No
43 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Service Desk volumetrics | Please confirm that the SLAs for these tickets are measured on a 9x5 basis i.e. the clock stops at the end of the business day. If this is correct, can you let us know how that is managed during the summertime peaks as severity 1 / 2 tickets would need immediate attention and resolution? | They are measured on a 24/7 basis. Out of hours SL1 & SL2 incidents require an IT call out. |  | Closed | 2020-08-07 | No
44 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | Do the 7 IT specialists possess the necessary knowledge on IT architecture and code level knowledge for Transformation Planning or does the new provider need access to IT specialist from wider incumbent team to get knowledge transfer. Will Highways England facilitate access to IT specialists for purposes of knowledge transfer? | Highways England does not have information about the skills and experience of the individuals employed by the outgoing service provider. The outgoing service provider team based in Quinton has historically worked with the outgoing service provider's wider IT resources to complete service changes. We will facilitate access to the outgoing service provider during the mobilisation / transition phase. | Highways England | Closed | 2020-08-06 | No
45 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | Can Highways England confirm if the new supplier will have access to existing NTIS staff’s IT hardware and software for service delivery? If not, should we plan and budget the setup of IT systems for our delivery and transformation team? | The IT hardware and software used by the outgoing service provider's staff is listed in the asset register and will be transferred to Highways England and then to the new Service Provider if required. | Highways England | Closed | 2020-08-06 | No
46 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | How are user ids and accesses managed for NTIS service delivery team? Do they have Highways England ids or the ids/systems provided by their employer (NIS) that have requisite access to NTIS IT systems for service delivery? | All NIS staff have user IDs and access control issued and controlled by NIS that provide access to NTIS systems. | Highways England | Closed | 2020-08-07 | No
47 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | Is there a Highways England IT team that manages the onboarding, joiners and leavers process for team members? If yes, will the new supplier be able to continue to use that team’s services to enable their staff to deliver the services? If not, should the new supplier plan to set up an IT team to manage this service? | The new supplier will have to implement this service for their own staff delivering this service. | Highways England | Closed | 2020-08-06 | No
48 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | Please can Highways England specify which equipment (and associated licenses) will be novated to the new supplier at the start of service. | Please refer to the asset register in the dataroom. There are provisions in all the outgoing supplier's licences for novation to a new supplier | Highways England | Closed | 2020-08-06 | No
49 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | General IT | We understand that Highways England has begun a project on Information Vision and Strategy Implementation recently. Please can you confirm if that project is within the scope of work of NTIS | The Information Vision and Strategy [IVS] is not a project, rather a vision and strategy for how Highway' England can create customer value through data. The successful delivery of NTIS transition and transformation will contribute to the value propositions set out in the IVS. Appendix C of the NTIS Service Blueprint shows how NTIS relies upon and supports the delivery of various value propositions identified in the Highways England Information Vision & Strategy. | Highways England | Closed | 2020-08-06 | No
50 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | TUPE | Please provide a breakdown of costs (People, 3rd party services e.g. Inrix, Hardware and Software licensing) incurred in running NTIS services under the following categories for the last 5 years (2015-2019): a) ‘Run’ costs - for running NTIS operations (the contact centre and 6-7 member IT support team) b) ‘Change’ costs – for executing projects for transforming/upgrading IT systems/others | This information is commercially sensitive and will not be provided | Highways England | Closed | 2020-08-06 | No
51 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS provisional staff list | Please confirm if any employees have Fair Deal pension entitlement, and if so, please provide details | No Fair Deal pension entitlement - see Q9 and Q86 of NTIS PQQ Clarification Log Issue 7. | Highways England | Closed | 2020-08-06 | No
52 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS provisional staff list | Please confirm redundancy terms applicable for in scope employees | See Q21 | Highways England | Closed | 2020-08-06 | No
53 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS provisional staff list | Please confirm if there are any redundancy linked pension liabilities (Beckmann) for any employees arising out of current or previous defined benefit pension scheme entitlement | No Beckmann liabilities | Highways England | Closed | 2020-08-06 | No
54 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff information request | Please confirm if any employees have Fair Deal pension entitlement, and if so, please provide details | No Fair Deal pension entitlement - see Q9 and Q51 above and Q86 of NTIS PQQ Clarification Log Issue 7. | Highways England | Closed | 2020-08-06 | No
55 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff information request | Please confirm if there are any redundancy linked pension liabilities (Beckmann) for any employees arising out of current or previous defined benefit pension scheme entitlement | No Beckmann liabilities See Q53 | Highways England | Closed | 2020-08-06 | No
56 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transformation Services | Transformation | Please confirm if the Highways England mobile app is within the scope of transformation? If so can further details be provided and what are the current challenges with it? | The continued provision of an app is within the scope of the Operational Services post Transformation. For reference please see page 29 of the Service Blueprint in the data room. The App is classed as a DATEX II subscriber to present data via the app. | Highways England | Closed | 2020-08-06 | No
57 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B2 Staff Rates We have additional roles (“skills”) that we wish to price against the Implementation Phase and Baseline Service. Please can Highways England indicate where tenderers may enter the cost information for additional roles within the model? | Highways England can amend the model to suit. Please send the information through you wish to be added to the model. | Highways England | Closed | 2020-08-06 | No
58 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B6 Pricing The Financial Model does not pull through costs or risks against Milestone 2.3 Transformation Release or Milestone 2.4 Transformation Complete. However Tab A4 Highways England Inputs indicates that payments would be due against these milestones. Please can Highways England confirm whether tenderers should apportion costs to these milestones? | Model will be updated to allow for this milestone to be picked up on B6, and re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
59 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B4 Cost Imp Our solution may require us to cost operational resources against the Implementation Phase, and it appears as though the drop down selections in columns G to I do not currently permit this. Please can Highways England confirm how tenderers may include these costs on this tab? | Highways England have added an operational option to the drop down. The Model will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
60 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B4 Cost Imp Data input is permitted until December 2022, however the Tab B6 Pricing draws in costs incurred until the Initial Term End Date (January 2026). Please can Highways England confirm how tenderers may include costs up until this later date? | Columns were on hide mode. These have been unhidden. The Model will be re-issued tomorrow, | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
61 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B5 Cost Service Our solution may require us to cost operational resources against the Baseline Service, and it appears as though the drop down selections in columns G to I do not currently permit this. Please can Highways England confirm how tenderers may include these costs on this tab. | Highways England have added an operational option to the drop down. The Model will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
62 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B6 Pricing Row 26 pulls through costs and risks for Service Charge SC1 (as Annex 2 Table 2 of Schedule 7.1) from months 1 to 12 of the model timeline. However this does not correspond with Schedule 6.2 which proposes months 5 through to 29. Please can Highways England confirm which is to be priced? It is noted that for either case above, the range of dates falls outside the data input permitted on Tab B5 Cost Service. Please can Highways England confirm how tenderers may include costs for those periods? | Tab B5 gives the detail of the monthly service charge in columns FC - KP. The Model has been updated to pick this up in B6, and will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
63 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B6 Pricing Row 27 pulls through costs and risks for Service Charge SC2 (as Annex 2 Table 2 of Schedule 7.1) from months 13 to 24 of the model timeline. However this does not correspond with Schedule 6.2 which proposes months 30 through to 29. Please can Highways England confirm which is to be priced? | Tab B5 gives the detail of the monthly service charge in columns FC - KP. The Model has been updated to pick this up in B6, and will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
64 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B6 Pricing The formulas for the Service Charges Costs subtract the relevant contingency values. Can Highways England confirm that risk allowance should therefore be included within the constituent cost components in developing these costs? | The model has been updated to allow for manual input of service provider profit, and will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
65 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Various Tabs There are #REF errors in row 8 of Tab B3 Cost Risk register, row 11 of Tab B4 Cost Imp and row 11 of Tab B5 Cost Service. Please can Highways England confirm that these cells are not included in any calculation or analysis? | Model has been updated, and will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
66 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Tab B2 Staff Rates Cell H56 refers to Annex 5 of Schedule 7.1 which is “Not Used”. Please can Highways England confirm this should instead refer to Annex 6 of Schedule 7.1? | Model has been updated, and will be re-issued tomorrow. | Highways England | Closed | 2020-08-06 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
67 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Data Protection | Please can you clarify the level of Personal Data that is associated with the number plate information received and processed. | No personal information is collected, the number plate itself is not collected, only an irreversible hash value | Highways England | Closed | 2020-08-06 | No
68 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Data Protection | Is there any additional personal data received or stored as part of the system. | Customer facing website stores usernames, email addresses and passwords for public accounts | Highways England | Closed | 2020-08-06 | No
69 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Please can you confirm that approximate salary ranges are sufficient at this stage. | Approximate salaries ranges are ok at this stage. A fixed rate for the salary will be needed for the final submission. | Highways England | Closed | 2020-08-07 | No
70 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | It is unclear how to include costs for up front mobilisation or service operation in the first two years on the financial model, please can you clarify. | These costs should be allocated to the mobilisation milestone in B4. | Highways England | Closed | 2020-08-06 | No
71 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | It is unclear how to include margin in the transformation stage of the financial model, please can you clarify. | The margin should be added in column L in tab B6. The Model will be updated and published shortly. | Highways England | Closed | 2020-08-07 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
72 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | It is unclear how to include inflationary cost increase (i.e. salary rises) in the financial model, please can you clarify. | The Model will be updated with the addition of an "outputs" tab. This allows for indexation to be applied. The revised Model will be published shortly. | Highways England | Closed | 2020-08-07 | Yes | 2020-08-10 | ITPD - Appendix F - Financial Model template V2
73 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Please can you confirm that broad support from the Incumbent’s staff will be provided free of charge to the supplier during the transition period. | The scope of the termination services required to assist during the transition period will be agreed and funded by Highways England. The Incumbent will also have an agreed Exit Management Plan in place to support the transfer of the services to the new supplier. | Highways England | Closed | 2020-08-06 | No
74 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Staffing Information anonymous-2.xlsx | Please detail what level of life cover is in force for all employees on the NIS staffing list, and whether it is provided as a benefit of membership of a pension scheme or as a standalone employment benefit. This is usually expressed as a multiple of salary. | This information is included in Data Room documents "NTIS Subcontractor Staffing Information" , "NIS Ltd Contract", "NIS Ltd shift worker Contract". "Flexible Benefits", and "Simply Benefits". A further document "WSP Likemind Booklet" describing trhe NIS employee scheme will be added to the Data Room. | Highways England | Closed | 2020-08-06 | No
75 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Staffing Information anonymous-2.xlsx | Please provide the date the employees on the NIS staffing list commenced employment with the current employer | The Employee start date with NIS JV Ltd is the latest of 31 August 2011 or the date shown in Column D " Continuous Service Date". | Highways England | Closed | 2020-08-06 | No
76 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Staffing Information anonymous-2.xlsx | There is limited pension information available for the NIS TUPE employees. Please specify: •whether the available scheme is an occupational or personal pension scheme, •details of the range of employer contributions to which the individuals have a contractual right (e.g. matching percentage up to a cap, fixed rate linked to grade etc.). | Document "WSP Likemind Booklet" describing the NIS employee pension scheme will be added to the Data Room | Highways England | Closed | 2020-08-06 | No
77 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3.xlsx | Please provide a TUPE data extract for the Thales staff showing the following information: •Date of birth or age (with reference measurement date) •Employment start date •Continuous service date | The information regarding date of birth or age, and Employment start date is included in the Data Room " NIS subcontractor Staff Information". The Continuous service date information will be provided shortly. The information for date of birth or age is correct at 04/20. A revised spreadsheet has been added to the data room to include continuous service date. | Highways England | Closed | 2020-08-07 | No
78 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3.xlsx | One employee on the Thales TUPE list is noted as being a member of a DB scheme. Could you please confirm: •the name of this pension scheme •what date the member joined this Scheme, whether the member transferred benefits from previous pension schemes and what date is used for any continuous service date for scheme membership purposes •if the scheme is GAD-certified as Broadly Comparable to the any public sector pension schemes •if this employee is ex-public sector and if so, that they are still employed on the same services under which they were originally outsourced. | There are no Fair Deal or Beckmann/Martin liabilities applicable. From the questions, it appears that the supplier may believe there could be a connection to public-sector pension provision. There is not and we would therefore only confirm that the employee is not ex-public sector. | Highways England | Closed | 2020-08-14 | No
79 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NTIS Staff Information Request v0.3.xlsx | Please provide the following details for all employees in scope for TUPE: 1. Notice periods for all employees 2. Any employee allowances that are paid on a monthly or annual basis. 3. Call out/on call allowances. 4. Qualifying criteria and rates for any paid overtime. 5. Qualifying criteria, eligibility and payment criteria with reference to any bonus schemes and whether these are discretionary or contractual entitlements. 6. Contractual hours for each employee. 7. Working hours schedule for each employee. 8. Annual leave entitlements for each employee. 9. Collective bargaining agreements that apply to the transferring workforce. 10. Job titles for all employees. 11. Transferring liabilities e.g. such as ET claims or Personal injury claims, or long term sickness absence. 12. Current learning agreements. | The following information is in the Data Room under Staffing Information and Benefits or previous Query log Notice periods call out allowances overtime bonus schemes contractual hours working hours annual leave job profiles and organogram transferring liabilities There are no ET claims or Personal injury claims. There are no long term sick absences recorded in the last 2 years. The information below will be included in the Data Room shortly: collective bargaining agreements current learning agreements | Highways England | Closed | 2020-08-07 | No
80 | 2020-08-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | TUPE | Are there any sensitivities involved around offshoring some roles? | Highways England will reserve the right to individually approve or deny any request to send any data associated with the service for processing to other nations. NTIS PQQ Clarification Log Issue 7 Q23 & Q28 also covers further detail. | Highways England | Closed | 2020-08-06 | No
81 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Service Outcomes and Performance Measures | Schedule 2.2 (Performance Levels) (Paragraph 3) | Please can Highways England clarify the process to be followed in the event that changes to the business outcomes require revisions to the Performance Measures, i.e. change control procedure? | Please refer to clause 11 (Performance Indicators) of the main agreement. | Highways England | Closed | 2020-08-06 | No
82 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 8.6 (Service Continuity Plan & Corporate Resolution Planning) | Please can Highways England clarify the operation of paragraph 13 (Confidentiality and Usage of CRP Information) where the Relevant Customer is the Cabinet Office Markets and Service Providers Team, and the Service Provide has obtained a Valid Assurance from the Cabinet Office Markets and Service Providers Team and provided this to the Customer? | See Schedule 8.6 paragraph 11.6. | Highways England | Closed | 2020-08-07 | No
83 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Main Body Agreement (Clause 35) | Please can Highways England clarify the operation of this clause, as drafted it would appear that insured losses do not count towards the liability cap? | This is correct, liabilities which are, or would be if the insurance requested was in place, recoverable from the insurances are excluded from the liability cap. | Highways England | Closed | 2020-08-07 | No
84 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Schedule 8.4 (Reports & Records Provisions) | Paragraph 1.9.1 We would like to clarify that we are unable to share any information that is not in the public domain, as it is market sensitive for us as parted of a listed Group. We therefore are unable to provide anything for our company except for financial statements filed at Companies House. We can however provide the Group interim report as soon as it is published and this usually contains references to UK performance. Paragraph 1.9. We would like to clarify that we can only provide the financial statements once they have been filed with Companies House. We have recently agreed with another UK Government department that we would provide such data 285 days after year end, as this aligns with the 9 months we have to file our accounts after year-end. | This clause forms part of the GLS Model Services Contract which is mandatory for government via PPN 04/14. Therefore The Authority requires Schedule 8.4 to be complied with as drafted the requirement is included in the existing NTIS contract and supports financial distress and value for money reporting. Commercially sensitive information will be protected under the contract. | Highways England | Closed | 2020-08-28 | No
85 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Milestones and Testing | Schedule 6.3 (Testing Procedures) Annex 4 | Please can Highways England clarify the difference between the Risk Management Documentation to be provided under item 2.4 and the Risk Management Documentation to be provided under 6.14? Is the second plan just the current available Risk Management Document please? | The Risk Management Documentation required under item 2.4 relates to the service being transitioned; the documentation required under item 6.14 relates to the transformed service. | Highways England | Closed | 2020-08-06 | No
86 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Milestones and Testing | Schedule 6.3 (Testing Procedures) Annex 4 | Please can Highways England clarify the reference to Schedule 2.1 (Service Description) within Test Success Criteria item 2.6 Service Continuity? We assume the plan will be in accordance with Schedule 8.6? | Item 2.6 refers to both Schedule 2.1 and Schedule 8.6 because there are Service Continuity requirements in both schedules. Schedule 2.1 does not refer to Service Continuity explicitly. However, within Schedule 2.1 there are requirements to carry out Service Management in accordance with ITIL4 practices. ITIL4 contains Service Continuity Management. There are also disaster recovery requirements listed in Schedule 2.1 | Highways England | Closed | 2020-08-06 | No
87 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 7.4 | We need to ensure that Schedule 7.4 does not cause us to breach market regulations and/or local law, for example under paragraph 2.3.2, we can report information, but only where such information is in the public domain, i.e. our accounts have been filed and the information is publicly available. So for example we would ask that for clarity, certain paragraphs be subject to; “Service Provider’s compliance with market regulations and local law”. This concern has been discussed with another Government Department and such revisions agreed and made to ensure that suppliers are not being asked to breach law through updated drafting in this Schedule. | Schedule 7.4 requires reporting on the Financial Indicators within the set periods and is to ensure any Financial Distress Events are reported and managed in a timely manner. The Financial Indicators are calculated using Annex 4 and should not breach any local law but please advise of the relevant law if this is the case. | Highways England | Closed | 2020-08-06 | No
88 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | Schedule 4.2 Clause 3.3 | Please could Highways England confirm that they will pay all redundancy costs including NI? | No, Highways England will not be covering these costs | Highways England | Closed | 2020-08-06 | No
89 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 7.1 | Schedule 7.1 paragraph 2.3 states that Milestone Payments in respect of Interim Milestones shall contain only forecast Costs and Forecast Contingency Costs of the work required to achieve the Milestone and shall not include any Service Provider Profit nor any other form of margin.” And paragraph 2.4 states that “Where a Milestone Payment is due in accordance with this Agreement, the Customer shall pay the relevant Milestone Payment less: 2.4.1 any Milestone Retentions; and/or 2.4.2 if a Conditional Milestone Achievement Certificate is issued by the Customer Relationship Manager for any non-material Test Issues, any Service Provider Profit associated with the Milestone,” We acknowledge your response to CQ Ref 73, so is it therefore correct to assume that the profit on the ATP milestone is to be included in the invoice for the associated CPP milestone, but no further retention applies (e.g. essentially the CPP Milestone is Profit retention on ATP Milestones only)? | Profit can be included within the tendered value of an ATP milestone. Clause 2.4 advises that the profit element will not be paid where a Conditional Milestone Achievement Certificate has been issued instead of a Milestone Achievement Certificate. See also the provisions in Schedule 7.1 Part B paragraph 1.3 regarding payment of any withheld profit. | Highways England | Closed | 2020-08-07 | No
90 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Service Outcomes and Performance Measures | Schedule 2.2 para 10.3 | The text here states '…associated response times…' but the table below provides a fix time only. Is there an expectation for a separate measure to respond to incidents raised? If so what is the definition of a response and can we be provided with those target response times? | Clause 10.3 should read "associated fix times:" This will be amended alongside a reference in clause 10.1 which should refer to "the allocated Severity Levels (A-E) set out in paragraph 10.3, below." | Highways England | Closed | 2020-08-07 | No
91 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 12 para 2.2.2.2 | This paragraph requires the Key Subcontractors to have 3rd party certifications or be working towards them, but the specific certifications are not specified within the paragraph. Could Highways England please confirm which certifications the Key Subcontractors are required to hold, and if they are the same certifications that the Service Provider is also required to hold/maintain? | Quality management systems shall be accredited to ISO 9001. Clause 2.2.2.2 will be amended to clarify this point. | Highways England | Closed | 2020-08-07 | No
92 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Outline Solution | ITPD – Appendix I – Dialogue Prospectus – Table 2 and Day Two Kick-off Meeting slide pack | Table 2 in Appendix I – Dialogue Prospectus states that the 09:00 - 10:30 slot of CD1 is when the Tenderers must present the Operational Services aspect of their Outline Solution. However, slides 10, 30 and 31 of the Day Two Kick-off Meeting pack appear to suggest that Tenderers must present their entire Outline Solution. Please could Highways England confirm whether the entire Outline Solution needs to be presented at CD1 or just the Operational Services aspect? | Updated response (18 Aug 2020) The presentation for CD1 on the outline solution should focus on the operational services aspects only as per the ITPD Appendix I. Other elements will be covered in other sessions such as CD2, where transition and transformation of the outline solution will be discussed. Therefore we don't need you to go through the whole slide deck during session 1 of CD1. | Highways England | Closed | 2020-08-06 | No
93 | 2020-08-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Outline Solution | Outline Solution | Could Highways England please confirm whether title/separator slides contribute towards the 42-slide allowance for the Outline Solution? | The outline solutions should stick to 42 slides in total if possible. However should there be a need to include a title slide and 'separator' slides between sections to keep tidy then this is permitted (as long as no technical information is included on these slides i.e just a title). | Highways England | Closed | 2020-08-06 | No
94 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.1.1 T1-006 | Please can Highways England clarify when the missing Volumetric data (Volumetrics v2.xls) will be provided? Please can Highways England also clarify why some Volumetric data is classified as N/A? | "Volumetrics.xlsx" had two updates to the document, but the file name was not changed. A third version was uploaded with a different file name (Volumetrics V3.xlsx). Tenderers should use Volumetrics V3.xlsx. The previous version will be removed from the data room. In version 3 of the volumetrics document, the data storage requirements for the Video Information Highways are listed as N/A as there are streams and images are not stored by the current service provider. The storage requirements for the Customer Replacement Camera Stream System are N/A as this system is not currently being interfaced to, so storage requirements are unknown. | Highways England | Closed | 2020-08-07 | No
95 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.1.1 T1-007 | Please can Highways England confirm how the current incumbent provider performs these requirements? If this is being performed by the current incumbent, can we assume that we can utilise the same hardware and software to facilitate the service during transition and transformation, prior to the service being Transformed? | The outgoing service provider maintains Pre-Production Environments. Tenderers should not assume that all necessary hardware, software and know-how needed to maintain the Pre-Production Environments will be transferred to the new provider. | Highways England | Closed | 2020-08-07 | No
96 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.1.1 T1-011 | Please can Highways England provide a schematic of the ANPR interfaces to the rest of the system, including UI, communications with ROCs, underlying infrastructure (hardware and software supporting the service), etc.? | This information exists in separate documents listed in the data room. Please see: 1. WA119-08-007-002-03-02-05 R2.E05-ANPR Outstations EIDD v1.00.pdf 2. WA119-08-006-03-02-05 R2 E05 ANPROutstation EIRS V2.00.pdf 3. WA119-08-007-010-03 NTIS UI User Guide v2 00 Redacted.pdf 4. WA119-08-007-008-01 NTIS Base Infrastructure v9 0 (2) REDACTED v1.1.pdf 5. WA119-08-007-002-08-16 TDN - NTIS ANPR JTMS Design Note V2.00.pdf | Highways England | Closed | 2020-08-07 | No
97 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.2.1 T2-009 | Please can Highways England clarify what latency is required for users working from the Birmingham office? For Home workers, we will not be able to guarantee the same levels of latency. | Responsibility for the design of the Operational Services post Transformation so that they meet User needs rests with the new provider. Please refer to Schedule 2.1 paragraph 4.2.1 T2-004 to T2-007 (inclusive). | Highways England | Closed | 2020-08-07 | No
98 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.2.1 T2-013 | Please can Highways England clarify what is meant by this statement? | Requirement T2-013 refers to the design and implementation of changes in the organisation and management of the Service Provider Personnel when the transformed Service Provider System is deployed. The requirement is aligned to the ITSM practices of organizational change management and workforce and talent management. Requirement to be amended to include a reference to Service Provider Personnel. | Highways England | Closed | 2020-08-07 | No
99 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.2.1 T2-016 | Please can Highways England confirm whether the supplier will receive the solution (via NRTS), or does the supplier need to find a solution for this? Is there a Mobile Operator contract that will be novated to the new Supplier? | The Service Provider is responsible for designing the communications architecture, and they will need to work with NRTS to agree this design. The procurement of the mobile services to access the TMU, TAME and ANPR roadside equipment is provided by NRTS via contracts with BT/EE and Virgin Media. The Service Provider does not need to include this in their pricing, however the Service Provider is responsible for the technical management of these interfaces in terms of availability reporting. See response to Q32 | Highways England | Closed | 2020-08-14 | No
100 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.2.1 T2-019 | Please can Highways England confirm the users, and locations of these users, for the Operator Interface? | Our response to SQ Q119 remains valid: Confirmed details of Operational Users of the Operator Interface from the Customer Staff are not yet available although are likely to include all of Highways England's staff in the National Traffic Information Centre (NTIC) and nominated personnel in Highways England's Customer Contact Centre (both within the National Traffic Operations Centre (NTOC) at Quinton, Birmingham). Nominated personnel with Highways England's seven Regional Operations Centres (ROCs) may also be users of the operator interface. There is potential for over 100 geographically separated Customer users of the operator interface. We are looking for a scalable solution that can meet this and future needs. | Highways England | Closed | 2020-08-07 | No
101 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 4.2.1 T2-026 | Please can Highways England confirm if the supplier can use the Highways England Historical Data to perform event simulations against and building data algorithms, or will the Supplier need to keep its own Historical Data service. Please can Highways England also confirm when the new Historical Data Service will become available? | The supplier will need to store the historical data that it needs to deliver the service. We are currently unable to confirm when the Historical Data Service will become available or specifically what data it will contain, therefore it is important that the supplier does not create a dependency on access to the Historical Data Service. | Highways England | Closed | 2020-09-10
102 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5 | Please can Highways England confirm that all requirements under Operational Service Requirements, which are marked as ‘Operational Services post Transition’, are currently being delivered by the incumbent supplier and / or System and if so if they are meeting the current KPIs, PIs or SLAs? | The requirements for the Operational Services post Transition are currently being delivered by the existing Service Provider. The KPIs and PIs for the new service are different to those used for the existing service. Past performance has been considered in the identification of proposed service levels for the Operational Services post Transition. | Highways England | Closed | 2020-08-14 | No
103 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.2 C2-003 | The current requirement appears to be somewhat open-ended, please can Highways England be more specific as to what the estimates are of the ‘additional quantities of data’ they are referring to as this could have a potential cost implication? | The additional quantities of Traffic Data referred to in this requirement are related to the rollout of additional or upgraded traffic monitoring sensors as part of highway improvement schemes (for example, smart motorways). Typically this is dependent on the roads programme and equipment maintenance and support issues. We have updated the volumetrics spreadsheet in the data room to provide insights on the expected growth rates of this information. | Highways England | Closed | 2020-08-25 | No
104 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.4 C4-004 | Please can Highways England provide a copy of the document that details the ‘Signage Reference Data’? | Signage Reference Data is defined as "Customer defined VMS message legend Data and policies". The Highways England Visual Signs and Signals VSS policy defines what is acceptable. This is already in the data room. The current system uses dynamic placeholder messaging hence there is no explicitly defined list of messages that can be displayed. The documents titled "NTIS TDN 029 align tools" and "NTIS TP NTIS 003 Strategic responses" provides the most relevant information on the VMS message legends and routeset generaation. | Highways England | Closed | 2020-09-08
105 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.6 C6-018 | Please can Highways England explain how this will be defined or, if priority assignments already exist, would they need to be re-modelled and agreed with Highways England? Additionally, who is responsible for agreeing the priorities/rules? | There is an existing task based workflow system to help operators to undertake tasks associated with managing events. The Service Provider will need to Calculate and assign priorities to all Operational User tasks associated to delivering the outcomes of the NTIS service. This is a Service Provider responsibility. | Highways England | Closed | 2020-08-14 | No
106 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.7 C7-004 | Please can Highways England confirm who the ‘Trusted’ sources currently are and that we would be expected to continue to use? | A trusted source is an information source that can be relied upon to provide accurate information. The current service has the following list of trusted sources that support the 'One Team' approach to delivering the services: - ROC Traffic Officers - CCTV - Processed Traffic Data - NILO - National Network Managers (work with the NILO team) - Highways Inspectors Other sources can be used as trusted sources subject to review with Highways England. The Service Provider needs to provide a proposed list of Trusted Sources for their solution. Please see the definition of "Trusted Source" in Schedule 2.1A (Services Description Definitions). | Highways England | Closed | 2020-08-14 | No
107 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.10 C10-008 | Please can Highways England clarify if this should be updated per individual road user? | The current approach used is to determine the most appropriate response to Events occurring on the Strategic Road Network utilising known Events and VMS settings and Current and Historical traffic data. The response is for the benefit of the network not the individual road user as Highways England needs to balance the different needs of different users of the Strategic Road Network, hence we are looking to optimise the use of the network as a whole, not for individual users. However road users are looking for trusted, personalised information specific to their journey via a digital channel of their choice. Providing the right information in a timely manner related to their journey is most likely to result in the behavioural change required to deliver the service outcomes and balance the needs of different users of the road network. | Highways England | Closed | 2020-08-25 | No
108 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.10 C10-013 | Please can Highways England clarify what is meant by ‘Personalised VMS Responses’? | This is in reference to: (1) Providing information of relevance to road users on VMS, so that the majority of people travelling past the VMS find the information relevant to them. i.e. it is relevant to their journey they are current on. (2) Target information to specific sub users groups defined by the customer insights team. The current service uses a static set of routes and associated origin and destinations developed many years ago. We are looking for Service Providers to improve the current situation. | Highways England | Closed | 2020-08-14 | No
109 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.1 Clause 5.12 C12-009 | Please can Highways England confirm that these priority rules are already in place for Transition? In addition, please can Highways England provide the priority rules, or are these to be agreed with the new Supplier? | Existing rules are already in place in the outgoing service provider system. The Service Provider will need to identify priority rules logic for the transformed service in agreement with Highways England. | Highways England | Closed | 2020-08-14 | No
110 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.2 (Performance Levels) - PART II: Definitions KPI 1: VMS & information responses delivering positive impact | It is stated that KPI 1 is measured using the “Strategic Responses Delivering Benefit” approach then assessed against the “Analytical Assurance Framework”. Please can Highways England provide these documents? | The document "NIS TDN NTIS 048 TDN - Performance Measure 22 (WA119-08-007-002-08-55).pdf" describes how strategic responses delivering benefit is measured by the incumbent and is already in the data room. The Analytical Assurance Framework will be made available in the Data Room. We expect a similar approach as defined in WA119-08-007-002-08-55 to be used for the delivery of KPI1 for the operational services post transition. For the KPI1 operational services post transformation the Service Provider is required to suggest an approach and agree it with Highways England. | Highways England | Closed | 2020-08-14 | No
111 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.2 (Performance Levels) - PART II: Definitions KPI 2: Delivery Channel User Satisfaction Paragraph 2.1 | The KPI target is 80% (first period) and then 85% (second period) of respondents to complete the survey stating they are “highly satisfied”. Could you please advise what the other potential responses are? E.g. Highly satisfied, Satisfied, Dissatisfied… Customer Satisfaction will be reliant upon the efforts and performance of a range of resolver groups. Please can Highways England advise/describe any collaborative protocols across all resolver groups that are in place to improve customer satisfaction across the board? | We have placed the document titled "Customer Service Plan" in the data room. This describes the different customer groups to be engaged with for development of the survey. It is the Service Providers responsibility to propose, manage and agree the survey with Highways England. Note in the latest version of Schedule 2.2, 'KPI 2' has been changed to 'PI 8'. | Highways England | Closed | 2020-09-10
112 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.2 (Performance Levels) - PART II: Definitions KPI 2: Delivery Channel User Satisfaction Paragraph 2.1 | Can Highways England advise the number of users/parties who will receive the User Satisfaction surveys each quarter and also the user groups who will be surveyed? | This is for the Service Provider to propose, manage and agree with the customer relationship manager. | Highways England | Closed | 2020-08-14 | No
113 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.2 (Performance Levels) - PART II: Definitions KPI 9: Historical data service delivery channel availability Paragraph 9.1 | Please can Highways England advise if there are any likely to be any issues in accessing historical data currently managed by the incumbent? | No issues are expected in accessing historical data currently managed by the incumbent. | Highways England | Closed | 2020-08-14 | No
114 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.2 (Performance Levels) 4. Permitted maintenance 4.1 | Please could Highways England advise what level of downtime is agreed for the current service for maintenance? | Schedule 2.2., paragraph 4 sets out the Authority's expectations for the service. | Highways England | Closed | 2020-08-07 | No
115 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.2 (Performance Levels) - PART II: Definitions PI 4: Consistency of location translations Paragraph 15.1 | We would like to understand how the congruency of the relationship between the NTIS Network Model and the Customer System data model utilised to describe the location of Roadworks Events is determined. Please can Highways England explain how a judgement is made that 90% of an events length is correctly mapped against the sum of attributed linear referenced lengths? | One of the data sources utilised by NTIS is the location of roadworks. This is contained within the Network Occupancy Management System (NOMS) and routinely provided against the HAPMS Network Model with the linear reference of the start/end of the works in relation to the start of the link. Such, we know the works start 100m from the start and finish 568.4m from the start. This must be translated to the NTIS Network model which is currently done by a relationship model between the NTIS and HAPMS network. The records that the NTIS link is related to another HAPMS link and it starts 50m down the HAPMS link and ends 1257.5m down it. The works can therefore be transposed to the NTIS section with them starting 150m and ending at 618.4m. Schedule 2.2 Paragraph 15.2: An NTIS Link or Roadwork Event Link (as applicable) is to be considered congruent if it has at least 90% of its length correctly mapped against the sum of attributed linear referenced lengths from the Customer System linear reference data model. The first test is for congruency – here we look at the NTIS link, using the example above we could say the link is 1500m long, we have a HAPMS link mapped from 50-1257.5m covering 82% of the link. There should be at least two other HAPMS links that would be mapped to this location before and after. This isn’t always feasible and so the 90% threshold is a generous allowance for where these types of issues may occur. Schedule 2.2 Paragraph 15.2.1: Matched road sections must have a corresponding road name and type unless exceptions are agreed A key issue may be that we are modelling a parallel road or a slip road to the main carriageway. This can cause issues like closing the mainline rather the slip road due to poor mapping and translation. Schedule 2.2 Paragraph 15.2.2: the time parameter measures the amount of time the relationship between the NTIS Network and the Customer System linear reference data model is not congruent This alludes to the need to keep a temporal relationship and keep both models in sync. Schedule 2.2 Paragraph 15.2.3: Mapping will not considered to be correct where the start/end point of an NTIS Link or Roadwork Events model Link and the start/end point of the Customer System linear reference data model exceeds five (5) metres. To test that our 1500m NTIS section does not have 3 HAPMS links poorly mapped, the relationship of the start and ends is considered. It is possible to plot the coordinates of the start and end locations of each HAPMS section and compare this to the NTIS section and then deduct the linear reference. For a straight road these should be equal but the curvature/geometry of the road may mean these distances differ a little. | Highways England | Closed | 2020-09-08
116 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.3 (standards) APPENDIX 1 | We are unable to access all but 2 (Highways England Guidance for our contractors, National Roadside Telecommunications Services (NRTS) processes) of the links provided in Appendix 1 as most links take us to login pages. Please could Highways England provide copies of the relevant documents, policies etc? | All referenced documents in Appendix 1 except those available from TSS Plans Registry are available to view in the Data Room. You will need to register with the TSS Plans Registry to access to access documents not in the Data Room. | Highways England | Closed | 2020-08-07 | No
117 | 2020-08-06 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Schedule 2.3 (standards) 7.2 | Please can Highways England confirm that industry standard ITSM software such as Service Now and Cherwell that are ITIL aligned, have the specified capabilities (and are recognised in Gartner’s Magic Quadrant for IT Service Management tooling) are acceptable despite the fact that they do not appear on the AXELOS endorsed ITIL Software Scheme? | The Service Provider is responsible for selecting appropriate software to meet our requirements. We have not specified a particular tool to support ITSM, however we expect a tool to be used that can interface with the Service Now tool being developed by the TOC project. | Highways England | Closed | 2020-08-14 | No
118 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Outline Solution | 4.5 Layer 4 – Shared Services (WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6) | Is it correct to understand that shared services mentioned in Section 4.5 are supported by IT Team of Highway England? Can supplier Leverage these services in To be Future Architecture & Operating Model? | No, the shared services referred to here are the Service Providers responsibility to support and maintain as part of the operational services post transition. The term shared services in this context is referring to services shared for use across the NTIS application. It is responsibility of the Service Provider to determine how they will deliver To Be Future Architecture and Operating Model. | Highways England | Closed | 2020-08-14 | No
119 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Layer 5 - Physical Shared Services (WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6) | Is it correct to understand that physical shared services mentioned in Section 5 are supported by IT Team of Highway England? Can supplier Leverage these services in To be Future Architecture & Operating Model? | See Q118 | Highways England | Closed | 2020-08-14 | No
120 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | 4.6.1 (WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6) | Are there any other services than NTIS running on mentioned Blade servers and storage infrastructure? Is it correct to understand that Highway England IT Team supports the underlying Compute Hardware, Hypervisor & Storage Equipment & Services? | NTIS has dedicated blade servers for the production environment. The NTIS DR infrastructure is shared with the NTIS pre-production environments, however it is still dedicated to NTIS. The Service Provider supports and maintains the underlying Compute Hardware, Hypervisor & Storage Equipment & Services | Highways England | Closed | 2020-08-14 | No
121 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | 4.6.2 (WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6) | Is it correct to understand that Highway England IT Team supports the LAN & WAN? What is the expectation from Supplier? | No, the Service Provider is responsible for the connectivity for NTIS services. Section 3.7.5 of WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6 describes the four networks used by the outgoing service provider. Highways England provides access to roadside equipment via it's NRTS communication network contract and access to NTIS services for Highways England staff HE PSN network. The Highways England NRTS WAN provides access to MIDAS, Roadside VMS and CCTV streaming services. NRTS is also the procurement contract for TMU and ANPR and TAME roadside equipment connectivity, however these services go via third party Mobile Network Operator services. The Service Provider is responsible for engaging with the HE PSN and NRTS teams when undertaking network communications design and whilst supporting the service by reporting and helping to resolve issues with connectivity on these networks. See responses to Q32 and Q99. | Highways England | Closed | 2020-08-14 | No
122 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | General (tools) | Can supplier assume to leverage Highway England’s ITSM tool for its staff and for NTIS IT service management? Please share the ITSM tool version, where is it hosted and what all modules are configured? | The outgoing service provider maintains provides, hosts and supports CA Unicentre ITSM tool for the operation of the NTIS service. Highways England internally use ServiceNow to provide wider HE technology ITSM. The Service Provider is required to provide there own ITSM tools and interface with Highways England systems to communicate as a minimum incidents and problems and support root cause analysis and resolution. | Highways England | Closed | 2020-09-08
123 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Assets Register | We have noticed Laptop & Desktop hardware as part of NTIS assets list, who provides Enterprise End user services support on these devices (e.g. PC build, imaging & patching mgmt, PC data backups, Email & Collaboration services support? | These assets are used and supported by the outgoing Service Provider to operate the service and are available for the new Service Providers to use and support if required by their solution. | Highways England | Closed | 2020-08-14 | No
124 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | General (Monitoring) | Who does the NTIS IT infrastructure Monitoring? Can we assume that Highway England’s IT team Monitors (thru shared services e.g. Nimsoft) and triage it to NIS (WSP or Thales) for their Actions. Or the Monitoring consoles are extended to NIS staff to monitor and take subsequent actions? | The NTIS IT infrastructure Monitoring is a service provider responsibility. Highways England IT are not involved. | Highways England | Closed | 2020-08-14 | No
125 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | General (Monitoring) | Does Highway England’s Current Monitoring system has manager of manger capabilities to supress & co-relates the alerts from Compute, Network and applications? | As stated in the response to Q124 Highways England IT is not involved in monitoring the NTIS service. It is the service provider's responsibility to configure and support network monitoring tools as required to deliver the service. | Highways England | Closed | 2020-08-14 | No
126 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | General (tools) | What are the shared tools used for Hardware & Software Assets management? | There are no shared tools. The service provider is responsible for Hardware and Software Asset Management. | Highways England | Closed | 2020-08-14 | No
127 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | NIS F QUAL 026 Organogram anonymous / NIS PLN SERV 018 Resource capacity plan | We understand Thales separately provides 3rd line support on a 24x7 coverage. Please let us know the total number of resources that are currently part of this team (named as Thales Technical Authority) | Please see answer to Q158 | Highways England | Closed | 2020-09-08
128 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | MSA | As detailed discussed on services are yet to take place can Highways England confirm that terms of MSA can be discussed to ensure they are aligned to the agreed service and means of delivery including such key issues as liabilities, indemnities, licensing etc.? | The terms in the main agreement (Master Service(s) Agreement) are not subject to dialogue. Feedback submitted using the contract feedback template is being considered by Highways England. | Highways England | Closed | 2020-08-25 | No
129 | 07 August 2020 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.7 | Can HE please confirm as Data Controller what Personal Data will be processed by the Supplier? Schedule 2.7 lists specific Personal Data, but we also see mention of CCTV/camera feeds, in vehicle data gathering both of which raised concerns about IP, GPS or images and other Personal Data being gathered and processed. Contractual provisions in relation to Data Privacy can only be fully assessed once the extent and nature of the Personal Data to be processing is fully known. | Schedule 2.7 currently contains a draft list of personal data items that are likely to be subject to processing by the supplier. The final list of items will depend on the solution presented by the supplier. | Highways England | Closed | 2020-08-25 | No
130 | 2020-08-13 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Data Room Document | The role description for the Senior Data Maintenance Analyst states that he reports to the Data Maintenance Team Leader. The latter role description is missing from the roles folder in the data room. Please could this be provided? | The Data Maintenance Team Leader role profile has been added to the Data Room | Highways England | Closed | 2020-08-14 | No
131 | 2020-08-13 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Exit Management Plan | Please could Highways England provide a CMDB as the one in the Exit Management Plan is inaccessible and the asset list has no information on the number of licences that allows pricing etc. | Updated CMDB has been added to the Data Room. | Highways England | Closed | 2020-08-19 | No
132 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | WA119-08-007-002-07-02 V14.0 - DATABASE DESIGN DOCUMENT (RELEASE 3.9) | We are unable to locate the following documents that are referenced by WA119-08-007-002-07-02 V14.0 - DATABASE DESIGN DOCUMENT (RELEASE 3.9): - NIS - TN 014 Data Retention and Disposal Policy v0.4 - Thales - WA119-08-007-002-07-02-23 OBI Reporting Design Document - Thales - WA119-08-014-009 NTIS DB Operational Procedures document - Thales - WA119-40-13 Environments - Thales - WA119-08-007-002-07-02-04-16 NTIS Schema Report Please could they be shared? | Database design document V15 has been added to the data room with additional detail on the database design. The referenced documents refer to internal processes not deemed relevant to the service being procured. | Highways England | Closed | 2020-09-23
133 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 3 para 4.1 | We would like to request the following modification to para 4.1 as follows: “The Customer will use reasonable endeavours ensure that the Outgoing Service Provider performs its exit obligations under the Existing Contract, including, to the extent such obligations exist in the Existing Contract assisting with an orderly Transition; knowledge transfer; access to premises; transfer of Assets, Sub-contracts and Software; and providing reasonable access to the Transferring Former Service Provider Employees, or as further set out in Schedule 3 (Customer Responsibilities)” Rationale: It is of key importance that to ensure a successful transition that the incumbent meets their exit obligations and that any further Customer Responsibilities’ (related to the incumbents) are met. As set out in the ITPD, we recognise that as the Service Provider solution matures, Section 3 of Schedule 3 will be adapted and as such, we include reference to this, within the clause. | No. The current wording, together with the existing and any agreed additional provisions in Schedule 3, is appropriate for meeting the objectives stated in the rationale. | Highways England | Closed | 2020-08-27 | No
134 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 6.3 | We would like to request a modification as follows: “For each Test, the Service Provider shall consult with the Customer Relationship Manager to establish what Test Stages are required, which are reasonable and appropriate. The Customer reserves the right to require any combination, or all, of the following Test Stages to be undertaken, and the Service Provider shall incorporate the Customer’s requirements in this respect into the relevant Test Plan and will discuss and agree any consequential impact on resources and other Test Plans” Rationale: This minor modification is requested so that any Test stages that are agreed are reasonable and appropriate. This will avoid any additional risk being factored in to account for ambiguity and unnecessary Testing stages which may be disproportionate or excessive. | We will amend this paragraph (Annex 5 paragraph 1) to read, "For each Test, the Service Provider shall consult with the Customer Relationship Manager to establish what Test Stages are required. The Customer Relationship Manager, acting reasonably, reserves the right to require any combination, or all, of the following Test Stages to be undertaken, and the Service Provider shall incorporate the Customer Relationship Manager’s requirements in this respect into the relevant Test Plan and will discuss and agree any consequential impact on resources and other Test Plans." | Highways England | Closed | 2020-08-27 | Yes |  | Amended text in Schedule 6.3 as per cell J135.
135 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 7.1 (Part F) | We request removal of Part F of Schedule 7.1 and the associated Appendix 1. Rationale: We have other contracts in place with Highways England and other large UK government customers, and in our experience, the use of a Project Bank Account is not necessary. The mechanics of the Project Bank account would lead to additional administration The removal of this section of 7.1 will support efficiency in the payment of invoices between Highways England and the Service Provider and the Service Provider and its Sub-contractors. This also avoids the Service Provider in having to include cost for a separate bank account and the additional administration effort that would be needed to administer, and is better value for money. | Highways England included the Project Bank Account clause on all contracts as is policy. The wording will not be removed from the contract, however exemptions can be made to not set one up should certain criteria be satisfied (for example but not limited to having no supply chain). The wording must remain. | Highways England | Closed | 2020-08-28
136 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Main body Agreement, clause 7.12 (Software Warranty) | Due to the definition of Software, including Specially Written Software, Service Provider Software and Third Party Software, the Warranty as written presents a large risk to the Service Providers. A large proportion of the Third Party Software will be inherited/novated over to the Service Provider, to which the Service Provider will have little control over the terms and conditions to which it inherits and potentially an inability to include a Warranty provision of a similar nature. As such we request that the Software Warranty is limited to Specially Written Software and Service Provider Software only. | No. An exclusion of Third Party Software from the provisions in clause 7.12 is not permissible. | Highways England | Closed | 2020-08-27 | No
137 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Digital Delivery Channels Currently the (desktop) website is branded as Traffic England, whilst the mobile web site and iOS, Windows and Android are all branded as Highways England and/or sit under the Highways England domain. Can Highways England confirm what the intention is for the Traffic England brand and where they expect transformed digital channels such as the web site to reside? For instance, whether the intention is a for a standalone digital service (Traffic England) or for mobile/web/app to be fully integrated in the Highways England domain and brand. | No specific plans to re-brand either digital customer delivery channel. However, HE are constantly seeking feedback from customers as to the value provided by the HE website and traffic information app and may therefore wish to direct changes in future. | Highways England | Closed | 2020-08-27 | No
138 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Financial Model | There is no area in the Finance Model to include Pricing Assumptions. Where should the potential Service Providers include their pricing assumptions that they have made? | The Financial Model has been updated so tenderers can include assumptions/comments within. | Highways England | Closed | 2020-08-28 | Yes |  | NTIS Financial Model V.6
139 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 3 (Customer Responsibilities) | Please could Highways England advise on the process for adding additional dependencies to Schedule 3 which the potential Service Provider identifies through the dialogue process? | Please raise any proposed amendments to Schedule 3 during dialogue on the Service Provider Solution. The intention is that any amendments to Schedule 3 are agreed through the commercial workstream before dialogue closes. | Highways England | Closed | 2020-08-27 | No
140 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Are there any known performance issues with the current solution and in particular with: • Oracle database performance • Application stack performance • Analytics • Networking/Infrastructure | The NTIS provider recently undertook a performance review of the existing solution to ensure it continues to operate within its original design tolerances. This report cannot be shared but the key findings and action from that report are: • There are no concerns with utlisation of network infrastructure and it remains well within it's design capacity. • There is sufficient storage at the primary NTOC datacentre to last several years. The storage capacity at the DR site has been increased, it will likely have to be reassessed before May 2022 whether to further increase storage at the DR site. • Changes were made to bring database performance back within design tolerances. These include: • moved heavily utilised DB tables to newly introduced SSD storage in the storage array. • optimised stored procedures to ensure efficient queries across partitioned data • CPU and RAM usage across all VMs remains well witin design tolerances. Some virtual machine configurations were optimised to increase efficiency of available resource use e.g. - 8vcpu reconfigured to 2x 4vcpu sockets for optimal NUMA cpu/RAM config. The actions taken are expected to keep the NTIS service operating within it's design constraints throughout the transition period. This will not preclude the need for regular monitoring by the new provider and any developing performance issues to be identified and addressed with the cooperation of the customer in those activities. | Highways England | Closed | 2020-09-23
141 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 | We note that there are many software products which are licensed and are listed in the asset register. Please could the following information be provided for each licensed software product used in the active operation of the system, and for the development and testing capabilities : Product Name, Licensor of Product, License type (floating, hard coded, dongle etc) , Number of licenses, License type (perpetual or termed) Licensing metric (unit of measure) Incept Date, Expiry Date, Novation details, Contact details, Limitations of use (development only, operations, open source, GNU etc) and any details of a Support and Maintenance that may be in place and any other information that can be shared around existing costs. | The available information has been provided in the data room. The licence type, contact details and costs (commercially confidential) will need to be obtained and validated by the Service Provider. Novation Details have been provided where known, however note that the vast majority of licences expire on the 26th May 2021 . Further, Oracle have indicated that the new supplier will need to enage with at least 3 months before the start of operational services to obtain a licence and support. | Highways England | Closed | 2020-08-28
142 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | NIS Staffing Information anonymous-2 | NTIS Staff In file: “NIS Staffing Information anonymous-2”, there is a list of 60 staff. However, in the: “NTIS Market Engagement Event Slides” on slide 23, this details 62 staff. Could Highways England please confirm the correct list please? | Please raise any proposed amendments to Schedule 3 during before dialogue closes. | Highways England | Closed | 2020-08-27 | No
143 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 | File: “Asset List June 2020” provides a list of all the assets that would be transferred to the new Service Provider. In file: “NTOC Site Information”, this shows a number of UPS in the equipment rooms and there is also an external generator, none of which are listed in the Asset List. Who would take responsibility for the maintenance and support of the power subsystems? | Power supply at the NTOC site, including UPS and generator, is the responsibility of Highways England. | Highways England | Closed | 2020-08-27 | No
144 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.4 (Security management) Para 5.9 | This paragraph states that If the Customer Relationship Manager determines that the Service Provider's actions taken pursuant to the Risk Management Rejection Notice have not reduced the residual risks to the Core Information Management System to an acceptable level and issues a further Risk Management Rejection Notice, the failure to receive a Risk Management Approval Statement shall constitute a material Default and the Customer may by terminate this Agreement with immediate effect by issuing a Termination Notice to the Service Provider in accordance with Clause 41.1.2 (Termination by the Customer). Is the only option within this contract to reduce the risk, what happens to risks that can be transferred or accepted etc. | Risk transfer and risk acceptance are options available to risk managers as part of risk management practice. The provisions in paragraph 5.9 can be used as a last resort where effective risk management has not been carried out. | Highways England | Closed | 2020-08-27 | No
145 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.4 (Security management) para 7.12 | This paragraph states that If any repeat Security Test carried out pursuant to Paragraph ‎7.9 reveals an actual or potential Breach of Security or weakness exploiting the same root cause failure, such circumstance shall constitute a material Default and the Customer may by terminate this Agreement with immediate effect by issuing a Termination Notice to the Service Provider in accordance with Clause 41.1.2 (Termination by the Customer). This needs clarification for the word “repeat” - does this reflect to repeat as in remediation scan or annual retest? | Paragraph 7.9 should refer to "this Paragraph 7" instead of "this Paragraph 8". This typographical error will be corrected. Notwithstanding this error, the Security Tests referred to in paragraph 7.9 are defined in paragraph 7.1.4. Paragraph 7.12 refers to a repeat of the tests defined in paragraph 7.1.4. | Highways England | Closed | 2020-08-27 | Yes |  | Correction of typo.
146 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.4 (Security management) para 8.1 | This paragraph states that the Customer and the Service Provider acknowledge that from time to time vulnerabilities in the Information System will be discovered which unless mitigated will present an unacceptable risk to the Customer Please could you clarify is this is meant for all vulnerabilities, What about low risk vulnerabilities or vulnerabilities without known exploits? | This paragraph should be construed as worded - i.e. vulnerabilities "which unless mitigated will present an unacceptable risk to the Customer Data." | Highways England | Closed | 2020-08-27 | No
147 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 2.4 (Security management) para 1.2 | Regarding the wording regarding SECRET or TOP SECRET, the Service Provider shall only do so where it has notified the Customer prior to receipt of such Customer Data and the Service Provider shall implement additional measures as agreed with the Customer from time to time in order to ensure that such information is safeguarded in accordance with the applicable Standards. This could have significant cost implications and other requirements such as clearances. We are assuming there is no requirement for S or TS data on NTIS, please could you confirm? | There is currently no S or TS data present within NTIS and there is no expectation of a requirements for S or TS data at present | Highways England | Closed | 2020-08-27 | No
148 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 | There are many hardware items that are listed in the asset register. Please could the following information be provided for each piece of hardware used in the active operation of the system and for the development and testing capabilities: Product Name, OEM of Product, Serial Numbers, OEM Part Number, Support Asset Tag, Incept and Expiry date or any warranties or support/maintenance contracts, Novation details of any support/maintenance contracts, Contact details and any other information that may be helpful in determining running costs. | This information has been added to the data room (Asset List). | Highways England | Closed | 2020-08-28
149 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please can you clarify the scope of any contracts that are expected to Novate to the new supplier. Specifically it is important to understand the current cost of these contracts and on ongoing conditions, such as termination clauses, that may apply once they are novated. | Contracts will be novated to the new supplier at the discretion of the new supplier. Any novated contracts will require renewal immediately following transition and the new supplier will have the option to extend existing contracts, or negotiate new contracts and licenses. | Highways England | Closed | 2020-09-08
150 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please can you clarify whether it is acceptable to include more than 10 people in the dialogue sessions | No - the dialogue sessions will remain 10 per supplier (5 for each session in total). However should you need to swap out members between sessions you can, but Highways England will need to know who the 5 are in each session in advance (via Appendix A on Bravo). | Highways England | Closed | 2020-08-25 | No
151 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | TUPE |  | Please can you clarify whether the 7 people on the list from Thales are within the scope of TUPE (in addition to the 62 people from NIS) | Can confirm the 7 people on the list from Thales and the 60 staff detailed in the NIS staff list are within scope of TUPE | Highways England | Closed | 2020-08-27 | No
152 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | TUPE |  | Please can you confirm that age of the assets in the list already provided | This information has been added to the data room (Asset List). | Highways England | Closed | 2020-08-28
153 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | TUPE |  | Please can you clarify whether the quality manager is in the scope of the TUPE | Can confirm they are within scope of TUPE | Highways England | Closed | 2020-08-27 | No
154 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please can you clarify the level of permitted maintenance that was included as part of the incumbent’s contract | There is no permitted maintenance in the NTIS 2021-2026 contract however, KPI8 and KPI9 have had service levels set to allow for maintenance. This is a change in approach from the incumbent contract. | Highways England | Closed | 2020-08-27 | Yes |  | Change as shown
155 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please can you clarify the status of the backup site in Slough and any aspects of this that will be novated to the new supplier | The backup site in Slough is leased rack space in a shared service hosting centre. The contract with Cyxtera shared hosting centre wiis available for novation to the new provider. | Highways England | Closed | 2020-09-23
156 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please can you clarify the expectation that all Software that is used should be licensed to Highways England | Please refer to paragraphs 22, 23 and 24 of the draft main body agreement for details of licensing provisions. Software that needs to be licenced for the Service Provider Solution should be licenced to the Service Provider. If the Service Provider and or Highways England believe a more efficient and economical approach is available if Highways England licence the products/services rather than the Service Provider then this can be discussed during Transition. | Highways England | Closed | 2020-09-10
157 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | We recognise that the KPI’s are new and would like to take the opportunity run these against live data to understand the level of risk that we need to be modelling. | The KPIs and their associated service levels have been calculated based on the incumbent KPIs and service levels. Highways England expects these to be achievable and would not expect risk to be allocated to these. If during Transition the Service Provider demonstrates these as not being achievable then Highways England will consider the service levels associated with these KPIs. | Highways England | Closed | 2020-09-08
158 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | NIS F QUAL 026 Organogram anonymous NIS PLN SERV 018 Resource Capacity Plan[1.0] | There is a mention of Level 3 support being provided by Thales on a 24x7 basis. In “NIS F QUAL 026 Organogram anonymous” file we observed that Thales provides L3 support. Please confirm if this support is provided as part of the 62 resources which are under TUPE . If not, is it correct to assume that it is delivered by separate pool of resources from Thales(NIS) and the new supplier is expected to provide this as part of the new proposal | There are seven application support staff from Thales on the TUPE list. The 24x7 Thales support utilises a shared service facility within Thales and therefore utilises resources outside of the 61 NTIS resources. The new supplier will be expected to provide adequate 24/7 cover. | Highways England | Closed | 2020-09-08
159 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Is it correct to assume that the support for Highways England’s office equipment(CCTV cameras, wallboards, content management systems, meeting room equipment etc.) are out of scope for the RFP. Please confirm | Highways England's office equipment is provided and maintained by Highways England, this includes wallboards, meeting room equipment on site CCTV etc | Highways England | Closed | 2020-08-27 | No
160 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | • Please confirm if the IT specialists under TUPE are currently doing hands and feet support for the DC in Quinton. Please confirm Please clarify on who is doing the hands and feet support for BCP/DR DC in Slough and other RCCs | The IT specialists in the NISJV and Thales staffing lists are providing the hands and feet support for the NTOC and DR data centres | Highways England | Closed | 2020-08-27 | No
161 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | We have assumed that the service desk is only for NTIS IT related service matters and IT issues of Highways England’s users are out of scope. Please confirm | This is correct. A small group of named Highways England analysts are approved to contact the NTIS service desk to raise identified data quality issues. | Highways England | Closed | 2020-08-27 | No
162 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Please share the contract details which NIS has with BT and Virgin for providing Internet and WAN services. Please confirm these contracts can be novated to supplier so that we can include the price as part of our next submission | The contracts with BT and Virgin are for provision of connectivity as detiailed in the "NTIS Base infrastructure" document in the data room. These contracts can be novated to the new supplier subject to approval by the provider. | Highways England | Closed | 2020-09-23
163 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 Net Book value June 2020 | • Please share the age of the assets which are under scope for Hardware asset takeover in “asset list June 2020” file Please let us know the difference between Exclusive and non-exclusive hardware devices in the “asset list June 2020” file. | Asset age is now included in the asset register in the data room. Exclusive assets are those Assets which are used exclusively in the provision of the Services; Both exclusive and non-exclusive software are in the scope of asset takeover | Highways England | Closed | 2020-09-08
164 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 Net Book value June 2020 | • Please let us know the difference between Exclusive and non-exclusive softwares in the “asset list June 2020” file. We see that Highways England has shared the net book values of both types of softwares(Exclusive and non-Exclusive) in “Net Book Value June 2020” file. Please confirm if both the types of softwares are under the scope of asset takeover | Exclusive assets are those Assets which are used exclusively in the provision of the Services; Both exclusive and non-exclusive software are in the scope of asset takeover | Highways England | Closed | 2020-08-27 | No
165 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  |  | Supplier understands that current ITSM tool is CA service desk. Supplier is proposing to bring the new ITSM tool before service commencement. Please confirm if supplier can continue to access a read only copy of existing IT service management tool for historical information. | CA Service Desk licence will be available for novation/transfer, the details of the license are in the Asset Register in the data room The historical data in the CA Service Desk Tool will also be made available for the new supplier to review. | Highways England | Closed | 2020-09-11
166 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Asset List June 2020 | Supplier assumes that all as-is hardware & software assets of both types (exclusive and non-exclusive) are available to leverage during the contract period | This is correct | Highways England | Closed | 2020-09-08
167 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution |  | Currently Supplier has considered cloud hoisting location as 'Azure UK South Region' (which has multiple Availability Zone which means more than One Azure DC for High availability). Since few services are not available in UK west Region, Supplier has not accounted for any regional failures (which are very rare). Please confirm if you are fine with this approach or please suggest if we can host in other regions outside of UK(e.g. in EEA) | This is detail that will need to be agreed during service design. Decisions like these are reviewed on a case by case. The Service Provider should put forward its current solution. | Highways England | Closed | 2020-09-08
168 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | TUPE | NIS Staffing Information anonymous-2.xlsx | Please can Highways England confirm the number of the vacancies the existing provider currently has with relation to the service, and if any of those vacancies are included on the list of staff information provided. | There are currently three vacancies. Two are open. The third is currently filled by a fixed term contract expiring when the current provider contract ends. An updated staffing list has been added to the Data Room | Highways England | Closed | 2020-09-08
169 | 2020-08-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Milestones and Testing |  | Can Highways England provide additional detail on the areas to be covered within the CD 2, Commercial Workstream, session 2 – ‘Transition and Transformation Milestones and Testing - Tenderers may be asked to present on specific aspects of their approach to Transformation’ | Agendas are currently being drafted and will be circulated in due course. In respect of the commercial workstream for CD2 session 2 it is envisaged that tenderers will concentrate on Transition and Transformation in respect of Schedules 6.1A and 6.1B as well as covering commercial areas in more detail post session 1. Highways England will also be interested on the approach transformation has or may have on milestones and testing (Schedules 6.2 and 6.3).Confirmation will follow once agendas are published to Bravo. | Highways England | Closed | 2020-08-27 | No
170 | 2020-08-25 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Appendix F | The following changes are required to Appendix F. • Worksheet: “C1-Outputs” cells F17:G21 – in order to properly align the ‘Contract Month Starting’ and ‘Contract Month Ending’ • Worksheet: “B6-Pricing” cells L13 and L15 – in order to accommodate the profit on Transformation • Worksheet: “B6-Pricing” cells I13 and I15 – in order to accommodate the profit to be added to come up with the ‘Milestone Payment’ • Worksheet: “B6-Pricing” cells N32:N33 – in order to adjust the timeline to desired level. | The Financial Model has been updated and the errors highligted have been corrected. | Highways England | Closed | 2020-08-28 | Yes |  | NTIS Financial Model V.6
171 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Schedule 2.2, section 10.2.3.1 | Schedule 2.2, section 10.2.3.1 states: ‘corrective action has been successfully completed and the root cause of the Service Incident removed’ Please could Highways England confirm that the focus of activity during the fix time period is to restore the service to full operation (Incident Management) and that the fix time stops once the service is restored? The identification and removal of root cause of a service incident (Problem Management) may require detailed analysis and, for example, a code release which in turn requires a full test cycle to be carried out. Can Highways England please confirm that it is acceptable to carry out this work outside the fix time, once the service has been restored? | Highways Engand will review and potentially update the definition of fix time to limit it to restoration of service. | Highways England | Closed | 2020-09-08 | Yes
172 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Traffic Data | Technical Dialogue Session 1 | Please could Highways England confirm the current use of the Align Toolset and how they intend to make the toolset available in future? | The Align toolset are used to maintain the majority of the configuration data in the current service. The Align toolset is available for use by the new Service Provider (on the Software Asset List). Highways England do not have the rights to modify this tool. Thales own the IPR for this tool. The tool is used to support delivery of the Static Network Data Maintnenace Business Processes. These are available in the data room. | Highways England | Closed | 2020-09-23
173 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Network and Asset Model | Technical Dialogue Session 1 | Please could Highways England confirm the plans for the introduction of a revised Network Model including if possible the anticipated delivery dates? | See highways england - Network Model Overview doc uploaded to the data room. | Highways England | Closed | 2020-09-21
174 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Traffic Data | Technical Dialogue Session 1 | Please can Highways England provide further detail on the plans for the Historical Data Service, including: Definition of the HDS interface? In the post Transition service will a bulk upload of data from NTIS be required? Is it assumed that the new HDS will be in place for the Transformed NTIS service? Will the HDS provide the DATD function? | Please refer to answer to question 101. In addition - the HDS interface will be Azure based ETL and/or messaging for ingest of data into HDS Bulk loads are required as per NTIS requirements C11-007. Projected go-live coincides with transformation in May 2023 HDS will not provide the DATD function. This DATD service is not required to be delivered by NTIS post transformation, it is not currently used. | Highways England | Closed | 2020-09-23
175 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Traffic Data | Technical Dialogue Session 1 | Please can Highways England provide more information on the CHARM adaptor and how it is anticipated to be used in both post Transition and post Transformation services? | The CHARM Adapter is used by the incubment to interface with CHARM Interchange Interface and the legacy HETMS Message Sign Syubsystem NMCS interface. It allow setting of signs and reciept of Sign and Signal settings from both the legacy HETMS and CHARM systems. It is up to the supplier to decide whether to continue to use the CHARM adapter for the Transformed Service. "NIS-NCA-002-NTISCharmAdapter-FunctionalSpecification-V4.1" has been placed in the data room. | Highways England | Closed | 2020-09-10
176 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Event Information | Technical Dialogue Session 1 | Please can Highways England clarify if NTIS is expected to publish un-validated Event data? | Yes both Validated and Unvalidated Events - See requirement C12-014 in Schedule 2.1. | Highways England | Closed | 2020-09-08
177 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Operational Intelligence | Technical Dialogue Session 1 | Please can Highways England clarify the analytics tools that NTIS is current utilising? | Oracle Business Intelligence | Highways England | Closed | 2020-09-08
178 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Operational Intelligence | Technical Dialogue Session 1 | Please can Highways England clarify the requirement for origin and destination of the route? | Personalised VMS responses are related to the journey that a user is taking or planning to take and hence the routes they will take. If the information provided is not relevant to their route they are unlikely to trust the information Highways Engand provides and as a result will not adjust there behaviour when an Event impacting their route does occur. There are three key types of route that the current NTIS uses: 1. VMS responses use known origin and destination routesets related to providing the most useful information on VMS that impacts the majority of user journeys passing the VMS at that time. 2. Travel Time routes for displaying predicted Journey Times on VMS. 3. User generated routes on the Highways England website and App | Highways England | Closed | 2020-09-21
179 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Event Information | Technical Dialogue Session 1 | Please can Highways England clarify the services provided by Saturn Eclipse in respect to the website or mobile app? | Saturn Eclipse provide the website at m.highwaysengland.co.uk. Saturn Eclipse provide "mobile data services", this service consumes NTIS Datex 2 and translates the data to a lightweight json format, the lightweight data is presented via an api which is consumed by the mobile applications and the mobile website | Highways England | Closed | 2020-09-08
180 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Operational Intelligence | Technical Dialogue Session 1 | Please can Highways England confirm when their Historical Data Service will be deployed? | Please refer to the answer to Q101 & Q174 | Highways England | Closed | 2020-09-21
181 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Operational Intelligence |  | What contracts do HE see as being novated, assigned etc. to the successful bidder? | Current contracts will be listed in the Data Room, the successful bidder can decide which contracts they need to novate to continue to deliver the service. | Highways England | Closed | 2020-09-10
182 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Service Continuity and Corporate Resolution Plan |  | Given the ongoing Covid-19 pandemic can HE confirm that provisions regarding working from home can be discussed during dialogue and appropriate amendments made to the Agreement? | The National Traffic Operations Centre (NTOC) in Quinton and other Highways England premises are currently subject to reduced occupancy and social distancing as a result of the ongoing COVID-19 pandemic. These precautions may extend into 2021. We intend to include this constraint within the draft contract (schedule 13.1 and/or schedule 13.2). No other COVID-19-related amendments to the draft contract are currently envisaged. Please raise any further, specific COVID-19-related concern for transition or transformation as a question. There are further dialogue sessions on transition and transformation which may be used to discuss this matter if necessary. | Highways England | Closed | 2020-09-10 | Yes | TBC | As per the response to the question.
183 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract |  | Where provision of the MSA are not relevant to the solution being delivered can HE please confirm that these will be deleted before contract finalisation? | Where areas are open for dialogue and Highways England agree an amendment is required, the final contract will be amended. For the most part, we do not anticipate deleting provisions in the main service agreement as this was not subject to dialogue. | Highways England | Closed | 2020-09-08
184 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract |  | There are a number of provisions in the MSA which are not aligned to an agile delivery model including acceptance of deliverables for example once a Deliverable is Approved then it is deemed accepted and our delivery obligation in respect thereto is complete. Can HE confirm that appropriate amendments will be made to the agreement? | We are aware that the milestones in draft Schedule 6.2 and the associated testing arrangements in draft Schedule 6.3 may not be best suited to an agile approach. These schedules are subject to dialogue for that reason. Please refer to the answer to Q208 for details of how amendments to draft schedules 6.2 and 6.3 will be progressed through the dialogue process. Highways England is looking to satisfy itself during dialogue that any alternative milestones and testing regimes will deliver value-for-money and product assurance. Amendments to other parts of the draft agreement are not anticipated. | Highways England | Closed | 2020-09-10
185 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Feedback on Contract |  | Can HE confirm if bidders will have access to any Government Data classified as ‘Official’ or higher? | We do not expect the supplier to have access to government data classified as 'Official' or higher. | Highways England | Closed | 2020-08-28
186 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract |  | Given TUPE is in scope our expectation would be that any outgoing service provide would provide the incoming and HE with any indemnity in relation to any claims that would arise prior to transfer date. A mutual indemnity could also be provided in relation to the new supplier. Can HE confirm this is agreeable? This ultimately protects HE in both scenarios. | An indemnity is provided in Schedule 9.1 Staff Transfer from the Former Service Provider to the Customer and the Service Provider. | Highways England | Closed | 2020-09-21
187 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Quality Plan |  | There appears to be a discrepancy between the information in the kick off deck and that in the ITPD information regarding the submission of the draft Schedule 12 (Quality Plan). We have assumed that this would be submitted on the 18th as specified in the ITPD (and in line with the discussion for CD4) – please confirm. | The ITPD is correct. The Quality Plan is to be submitted as part of Dialogue Document Drop D ahead of CD4 (18th Sep). | Highways England | Closed | 2020-08-27 | No
188 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Financial model (inc. Risk Register, Service Charges and Milestones) |  | Please can you provide the annual costs for running the Data Centre to support NTIS services (Maintenance contracts, warranty, 3rd party services, Efforts (which are over & above IT support personnel under Tupe) – currently we see Thales provides 3rd level support but we do not see the effort (FTE count)? | Highways England are unable to share the current breakdown of prices as these are commercially sensitive. However some information is already availiable in the public domain such as the OJEU value, award value and company accounts. The Thales staff providing 3rd line support are detailed in the Thales TUPE transfer list. | Highways England | Closed | 2020-09-10
189 | 2020-08-26 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition and Transformation |  | Please can you provide the estimated costs for the planned refresh of the end of life components in the estate. If this is not available please could you provide the average historical refresh costs. | All components and their purchase date are provided in the asset register, Highways England is not expecting a change on this position during the life of the current contract. Highways England expects the bidder to manage IT assets to deliver the service. | Highways England | Closed | 2020-09-10
190 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | NIS F Qual organogram anonymous document NTIS Sub-Contractor Staff Information NTIS Staff Information Request | We are trying to align the organogram (indicating 62 roles) to the NTIS Sub-Contractor Staff Information and the NTIS Staff Information Request date (indicating 67 roles when combined). Please can Highways England confirm that all of the roles shown in the organogram are in scope for TUPE? Also please can Highways England confirm that the Service Delivery Manger role in the organogram is the same as the Service Delivery Manager Role in the NTIS Sub-Contractor Staff Information file? Please can Highways England confirm if the remaining 6 roles in the NTIS Sub-Contractor Staff file are covered in the Thales Technical Authority box in the Organogram? | From the NIS organogram 61 roles are included in the NIS Staffing list. (The Service Delivery Director is not included as within scope for TUPE) The Service Delivery Manager in the NTIS subcontractor Staff Information List is the subcontractor Service Delivery Manager and not the same role as the NIS Service Delivery Manager indicated on the NIS organogram. The 7 roles in the the NTIS Subcontractor staff list are covered in the Thales Technical Authority box. An updated NIS staffing List will be added to the Data Room to reflect 61 roles. Please note Q12 and Q151 incorrectly stated 60 roles. (omitting a role currently filled by a an individual on a fixed term contract) | Highways England | Closed | 2020-08-28
191 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Technical | IT Service Management | Schedule 2.1 (Services Description) | Please can Highways England clarify our understanding relating to the intended operation of the Highways England contact/service desk. C15-011 states that External Users as well as Interfacing Third Parties for all IT Service Management queries relating to 1st, 2nd and 3rd line support will contact us directly. We had assumed that the Highways England contact/service desk would be the first point of contact for External Users etc. to perform triage, prior to contacting us, where the call/incident relates to our solution/scope of services? | There is a list of 10 specific named users from HE Contracts team, HE PAU, Leidos and DfT who have permission to raise an incident directly with the NTIS service desk. These users are trusted with the requisite knowledge to raise requests appropriately. | Highways England | Closed | 2020-09-10
192 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model (amended) | Can HE confirm that the milestone payment calculation in the ‘B6 – Pricing’ tab should sum J12 to L12 and not J12 to K12? | The Financial Model has been updated and the errors highligted have been corrected. | Highways England | Closed | 2020-08-28 | Yes |  | NTIS Financial Model V.7
193 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model (amended) | Can HE confirm that the service charge payment calculation in the ‘B6 – Pricing’ tab should for L28-L32 should align to the format in L26 and L27? | The Financial Model has been updated and the errors highligted have been corrected. | Highways England | Closed | 2020-08-28 | Yes |  | NTIS Financial Model V.7
194 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: Number of Events that NTIS handled (planned and unplanned, regardless of whether action was taken) (per month / per week). | Raw Event Data relating to 2019 and up to August 2020 can be found in the spreadsheet "Volumetrics Event Data" which has been placed in the Data Room\Post Publication Folder | Highways England | Closed | 2020-09-08
195 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: % Number of Events in each category of Datex2 event types (per month / per week). | See Q194 Event categories: Congestion High sided Vehicle Closure Obstruction Police Incident RTC Roadworks Spillage Other Road Management Other | Highways England | Closed | 2020-09-08
196 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: % Number of Events with Duration greater than 1 hour (per month / per week). | See Q194 | Highways England | Closed | 2020-09-08
197 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: % Number of Events with Duration greater than 2 hours (per month / per week). | See Q194 | Highways England | Closed | 2020-09-08
198 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: % Number of Events with Duration greater than 4 hours (per month / per week). | See Q194 | Highways England | Closed | 2020-09-08
199 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: % Number of Events with Duration greater than 8 hours (per month / per week). | See Q194 | Highways England | Closed | 2020-09-08
200 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: For one calendar year, all Events by Motorway Type (Rural M-Way / Urban M-Way / Smart M-Way / Smart ALR / A-Road). | See Q194 NIS do not categorise roads in the way requested. (these road categorisations are used by ROCs to determine the required patrol coverage, and police response.) However we have included the Link Name that the event occurred on so analysis can be performed on road name. | Highways England | Closed | 2020-09-08
201 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: Number of Events where a diversion route is used (as opposed to simple information messages) | The Volumetrics Spreadsheet has been updated (V5) with this information. | Highways England | Closed | 2020-09-14 | Yes | 2020-09-10 | Volumetrics V5
202 | 2020-08-27 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Disseminate Event Information | Event Volumetrics | Please could Highways England provide volumetrics relating to the following: Number of Events where VMS are set by NTIS (out of total) | The Volumetrics Spreadsheet has been updated (V5) with this information. | Highways England | Closed | 2020-09-14 | Yes | 2020-09-10 | Volumetrics V5
203 | 2020-09-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) |  | The potential Service Provider will be building their price on information provided in the Data Room. After contract award there may be deltas in information which are identified by the Service Provider (i.e. deltas from the bid baseline Data Room). To prevent unnecessary risk allocation, we propose that an annex is added to Schedule 2.1 prior to contract award which reflects the “as-is” Data Room prior to contract award, to which the Service Provider based their price. In the event that any deltas are identified post Contract award from the Data Room baseline, then this would be dealt with as a Change. Can Highways England please confirm that this is acceptable and that language can be incorporated in the contract to reflect this? | We do not currently intend to amend the provisions currently in paragraph 2 of the draft main body agreement (Due Diligence) or to make the proposed amendment to Schedule 2.1. We are continuing to update the data room in response to previous questions. Please highlight any identified omissions or inaccuracies in the updated data room, and any associated risk allocations, for discussion during the forthcoming dialogue sessions. | Highways England | Closed | 2020-09-08
204 | 2020-09-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Milestones and Testing | Schedule 2.2 KPI1 | This KPI seems to suggest that measurement at the individual vehicle level is required. Could Highways England please confirm whether our interpretation is correct? | The measurement should derive from the measured count of vehicles affected by an event and the measured travel time/delay data available which will provide an average travel time/delay time per vehicle. | Highways England | Closed | 2020-09-08
205 | 2020-09-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Milestones and Testing | Schedule 2.2 KPI7 | Our reading is that the "k" value excludes the free flow journey times so it is about the accuracy of the predictions when flows start to increase. Is this interpretation correct? Unplanned events will impact the accuracy of journey times – could Highways England please confirm if they should be excluded? | Schedule 2.2 states "this calculation will only apply to Predicted Journey Times that exceed the Free-Flow Journey Time". Journey time predictions are crucial during unplanned events and should not be excluded. The service provider is already required to measure the delay impact of an unplanned event (requirements C6-005, C6-006) which by itself mitigates the problem of predicting journey times for an unplanned event. | Highways England | Closed | 2020-09-21
206 | 2020-09-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Milestones and Testing | Schedule 2.2 KPI8 | We are not clear what "expected" means in the calculation. Could Highways England please clarify? | The expected outputs are measured as what we expect to see from what has been collected. So if the system is expected to collect traffic data items every 1 minute then we would expect 1440 mins of traffic traffic items to be published every day e.g one item every minute. In this case the service reporting period measurement would be 1440 mins per day * No. days in service period of expected outputs. | Highways England | Closed | 2020-09-21
207 | 2020-09-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Milestones and Testing | Schedule 2.2 KPI9 | We are not clear what "expected" means in the calculation. Could Highways England please clarify? | See Q206 | Highways England | Closed | 2020-09-21
208 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  |  | Please can Highways England confirm what the process and next step is for the potential service providers to suggest additional Milestone Payments and their associated Deliverables? | Please propose any changes to the milestones (Schedule 6.2) and testing (Schedule 6.3) for discussion during the forthcoming dialogue sessions (CD3 and CD4). This matter is relevant to both the commercial and technical workstreams. The financial model template is being updated to enable additional milestones to be included in the model. | Highways England | Closed | 2020-09-08
209 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) |  | Thank you for your response to CQ 138 (Assumptions), and we will add our Assumptions to the finance model as suggested. However as discussed in CD 2 we propose that some language is needed in the contract to provide clarity and context to the purpose of the assumptions contained within the Finance Model (to which we would have relied upon to build the Charges). Our suggestion as discussed at the CD session is to include language around Assumptions and how these would be dealt with commercially (for clarity). An illustration of the proposed language (or similar) is as follows “The Service Provider has based the Charges on a number of Assumptions (as specified in the Finance Model). In the event that an Assumption is not accurate, then the Parties shall agree in good faith a Change to address any inaccuracies with the related Assumption” Language to this effect could be included in Schedule 7.1 or the Main terms. A definition would also need to link this clause for “Assumptions” which could cross refer to those Assumptions in the Finance Model. | Further to Q138, assumptions should be identified in the financial model in the form of priced risks that can be discussed during the forthcoming dialogue sessions and, where possible, mitigated. We do not currently intend to make the proposed amendment in Schedule 7.1 or the main agreement. | Highways England | Closed | 2020-09-21
210 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Please could Highways England provide direction on the expected use of Column 13, Service Provider Profit, on Tab B2, Staff Rates, as the entries into this column do not link to any other calculation in the model. | This column has been deleted. The rates for staff should be a all inclusive. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
211 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | In Tab B-3 Cost Risk Register, the drop down for Milestones excludes Services. Can Highways England either confirm that risks are not allowed during the Service period, or that Services will be added to the drop down in the model? | has been added to the model. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
212 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | In tab B4-Cost_Imp, calculations show False in Column L when costs are entered each month including the Milestone date month. For example, Milestone 1.2, date is 27 May 2021. If costs are entered in Jan through May of 2021, Column L shows “FALSE”. Can this be corrected in the financial model, or to allow submissions with False representations when the data spread is correct? | This problem should be resolved. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
213 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Tab B4 Allows cost entries through Dec 2022. The “Transformation Complete” Milestone is Aug 2023. Hence, the Financial Model would be missing costs for Labour and Travel for 8 months. Please provide direction on how these costs are to be included? | The model has been updated to include the extension period to Jan 28. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
214 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Tab B5-Cost_Service tab input section allows hours/quantities through Dec 2032. The corresponding calculations only calculates cost through Jan 2026.Can Highways England provide clear direction on the total Period of Performance to be included in the cost submission? | The model has been updated to run to Jan 28 to include the extension period. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
215 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | In Tab B5, there are– 160 hours entered in cell M13, for Jan 21. This is a protected cell so input cannot be deleted. Can Highways England provide an unprotected file to allow this change or provide a revised model which removes these hours? | The model has been updated to not include any example data. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
216 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Tab B5-Cost_Service, Column K formula assumes entry of labour in the order listed on the B2-Staff_Rates tab as opposed to a lookup of the Skills and Responsibility entered in columns H and I, respectively. Can Highways England confirm that it is the intent that the model be populated in this defined labour listing? | The staff rate is produced by the supplier populating columns G,H & I from the given drop down list. There is no defined listing. | Highways England | Closed | 2020-10-02
217 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Tab B6, the Service Period 4 is shown as months 38-48 (11 months). Service period 5 Shown as months 51-60 (10 months). The Cost and Contingency average is based on these month numbers so will incorrectly reflect the annual average unless every month is exactly the same cost. Can Highways England provide a revised model to correct the month numbers on this tab? | The model has been updated to allow manual input of the service period dates. Revised version of the Financial Model has been uploaded to Bravo | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
218 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Cost input allows entry of extension years for a full 7 year’s costs. The summary only includes through year 5. Can Highways England confirm that this was intentional? | The model has been updated to allow for the full 7 years. The model has been updated to allow for the full 7 years | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
219 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | NTIS Financial Model V.7 | Tab C1-Outputs Row 16 does not include the pricing in row 15; cell BR15 did not have formula to total the monthly costs for row 15; cells BU15:CF15 are missing the formula; Cells BU16:CF16, does not include the values in row 15. Will Highways England provide a corrected Financial Model to correct these issues? | The model has been updated to pick up these errors. The cell references do not align anymore as more columsn have been added to allow for the extension period. The model has been updated to allow for the full 7 years. | Highways England | Closed | 2020-09-11 | Yes | 2020-09-11 | Financial Model V.8
220 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition Services |  | Please advise all supporting contracts, their novatability at the point of Transition along with outstanding terms (including renewal date) | Please refer to 'NTIS Suppliers V2' spreadsheet in the data room. | Highways England | Closed | 2020-09-21 | Yes | 2020-09-14 | NTIS Suppliers V2
221 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition Services |  | Please advise all supporting software licences and their novatability at the point of Transition along with outstanding terms (inc. renewal date) and warranty status of each | The licenses and expiry dates are listed in the Asset Register in the data room. All licenses have novation options but in many cases we cannot establish actual terms with the license holder until the novating party is appointed. | Highways England | Closed | 2020-09-21
222 | 2020-09-04 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Software and Insurance |  | Please provide any identifying codes that allow software licences to be purchased on your behalf and access discounts | The bidder should assume in their bid that they will responsible for purchsing all licenses without assitance from Highways England. | Highways England | Closed | 2020-09-11
223 | 2020-09-08 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Service Outcomes and Performance Measures | Schedule 2.1 (Services Description), Section 5.14, ID C14-015 | Please can Highways England clarify what it is seeking from this requirement and the meaning of ‘In-vehicle on-network Traffic Sensors Data values’? | "In-vehicle On-network Traffic Sensors Data" is defined in draft Schedule 2.1A. The requirement refers to the monthly reporting of the number of identical values in the In-vehicle On-network Traffic Sensors Data dataset. This is intended to be an indicator of the amount of in-fill / extrapolated data included from in-vehicle sources and to provide a view when significant changes occur to the in-vehicle data sources/quantities. | Highways England | Closed | 2020-09-14
224 | 2020-09-08 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Service Outcomes and Performance Measures | Schedule 2.2 (Performance Levels) Annex 1 – PART 2, 12 - PI1 | The definition for calculation of the accuracy of unplanned event durations is based on the variation of the nearest Predicted Event Duration halfway through the Unplanned Event Duration. Given that the forecast durations for significant unplanned events may be provided by third parties and subject to change during the event, please could Highways England explain why all validated events are included and the rationale for just selecting the accuracy based on the prediction at the halfway point? | The ROC's do not always provide estimated incident durations/end times. The current service receives incident information from ROCs which is then entered into NTIS Events and used by NTIS alogirthms to generate estimated values for Time to Clear and Return to Normal traffic conditions. We considered measuring the accuracy of all predictions made, however this would require us to define when predictions are made, therefore we believe measuring the accuracy at the halfway point is the best compromise. We are not minded to change PI1 at this stage. | Highways England | Closed | 2020-09-23
225 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model (Outputs) | The apportionment of costs in this sheet does not appear to be doing what we expected and understand that this may be due to a formula error. Please can Highways England confirm that this has been fixed in the next version of the model? | Please can you provide further clarity on the error so we can rectify | Highways England | Closed | 2020-09-11
226 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | CHARM Adapter | From the discussion we understand that Highways England have a licence to use the CHARM adapter but please can you confirm if this right is able to passed on to us and also what the arrangements there are around hosting of the adapter and any ongoing support service arrangements that Highways England have / will have with Saturn Eclipse? Please can Highways England also confirm that if changes to CHARM are required for Transformed Services that we will have the rights to freely modify the exiting code? | The CHARM Adapter code will be added to the Software register as Specially Written Software. This means Highways England has a perpetual licence to 'use' this software. 'Use' includes the right to load, execute, store, transmit, display, copy (for the purposes of loading, execution, storage, transmission or display), modify, adapt, enhance, reverse compile, decode, translate, or otherwise utilise that Software. The current hosting of this application is in the Saturn Eclipse AWS tenancy and support is provided by Saturn Eclipse. | Highways England | Closed | 2020-09-14
227 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | Sch 2.3 Standards and Transitioned Service | It originally appeared as if the requirements of Sch 2.3 were applicable from the outset but following CD2 discussion, Nick confirmed the intent was for these to apply to the transformed service as the current service and system cannot be guaranteed to be compliant upon hand over. Please can Highways England include words to reflect that compliance is only required for the transformed Services and that the transitioned service will not need to comply with any standards it does not already comply with? Please can Highways England also confirm which of the Schedule 2.3 standards the current Services currently comply with or align to? | We will clarify the extent to which the standards identified in draft Schedule 2.3 apply to the current service provider's system in an update to either Schedule 2.1 or Schedule 2.3. Highways England does not expect technical standards to be applied retrospectively to the system being transferred from the outgoing service provider. | Highways England | Closed | 2020-09-23 | Yes
228 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | Remote apps support VPN | We understand that the current application is supported remotely by Thales using a VPN which is all part of their provision and we should assume that it will not be available post transition. Please can Highways England confirm that this is the case? | The current 2nd line application support is predominently undertaken by Thales using VPN access via their support subcontract agreement with NIS. The NIS contract with HE ends on May 26th 2021. The Service Provider will need to ensure an adequate solution is in place to support the service post transition. | Highways England | Closed | 2020-09-14
229 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model (Key Subcontractor Mark Up) | As discussed we were concerned that it appeared from the model that we were not allowed to add any margin to Key Subcontractors. During discussion it was explained that this was not the original intention. Please can Highways England therefore confirm that we can add margin to Key Subcontracts (and other suppliers) and include it elsewhere in the pricing model? | Service provided profit is input on the pricing sheet, this covers all profit for that given milestone of service charge. | Highways England | Closed | 2020-10-02
230 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | NTIS Database Design Document Ref WA119-08-007-002-07-02 v13 | Please could Highways England provide the following document: NTIS Database Design Document Ref WA119-08-007-002-07-02 v13 | This was added to the data room 4 September 2020 | Highways England | Closed | 2020-09-11
231 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Network and Asset Model | NTIS Schedule 2 (Services Description) T2-026: The Service Provider shall support the Customer’s development of a new Historical Data Service by providing bulk Data transfers when requested by the Customer Relationship Manager. | Please can Highways England confirm whether we would need to create the API/integration or data mapping, or do we only assist in loading the bulk data in the format it has been stored, i.e. CSV, etc. with no reliance on data mapping, ETL or otherwise? | The Service Provider is responsible for extracting the historical data from the legacy R2.5 NTIS databases using open standards and supporting the Historical Data Service Supplier in loading this data into historical data service. It is the Service Providers responsibility to define the solution to do this. | Highways England | Closed | 2020-09-14
232 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Network and Asset Model | NTIS Schedule 2 (Services Description) 5.12.1 These are the requirements to Publish Personalised Traffic Data, Event Data, Asset Data and Operational Intelligence to Users in accordance with their needs using open standards, defined formats and APIs, to Subscribing Third Parties as well as to CHARM, to set messages on VMS. | Please can Highways England be more specific regarding 'User needs', as this is not well defined? Or, should we assume that '5.13 C13: Present Data and Operational Intelligence', addresses the User needs? | 5.13 C13: Present Data and Operational Intelligence is the current minimum requirement. However it is up to the Service Provider to identify and verify the user needs as per requirements T2-004, T2-005 and T2-006. | Highways England | Closed | 2020-09-21
233 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition and Transformation | T1-007: The Service Provider shall provide Pre-Production Environments so that, if required, the Service Provider can alter or rebuild the parts of the Service Provider System that have been transferred from the Outgoing Service Provider. | Please can Highways England confirm how the current incumbent performs this requirement, and confirm that all infrastructure/assets/software etc. necessary to perform this shall be transferred to the Service Provider? | The development environments are supported and maintained by Thales and Saturn Eclipse independently. The staging environments are hosted in the Disaster Recovery Site in Slough on the Disaster Recovery Infrastructure. The staging environment will be transfered to the new Service Provider. The development environment will not be transferred to the new Service Provider. It is up to the new Service Provider to ensure change is developed, adequately tested and deployed to the production environment in a managed way that minimises Risk in accordance with the schedule 2.1 C16: Technology Management requirements. | Highways England | Closed | 2020-09-23
234 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transformation Services | T2-009: The Service Provider shall design the Service Provider System to comply with the following Customer core non-functional requirements: (a) accelerated delivery components and any subsequent changes to components; (b) the volume of Data without degradation of the Services during peaks; (c) all concurrent Users without obvious degradation of the Services during peaks; (d) enhancement of components without disproportionate effort; (e) re-usability of components; (f) interoperability of components; (g) latency that is acceptable to Users; (h) maintainability of components without a disproportionate impact on other components; (i) monitoring and understanding of the status of the Service Provider System; (j) portability to alternative architectures or platforms; (k) recoverability in the event of Service Incidents and Problems; (l) resilience in the event of peaks in demand; (m) scalability without disproportionate effort to meet changing Customer requirements; (n) survivability in the event of disaster; (o) consistency of outputs; and (p) volumetrics specified in Annex | Please can Highways England define 'Time to Recover', as well as 'Acceptable Data Loss'. Please can Highways England confirm that latency requirements will be discussed and agreed with Users during Transition, and that these requirements will form part of the Transformed service. | These core non-functional reqirements are to be considered and discussed as part of the system design activities in transformation. Highways England has defined Availability and IT Fix time KPIs that relate to 'Time to Recover'. The availability KPIs in schedule 2.2 KPI8 and KPI9, as well as the IT fix time KPI10 are the most relevant. Highways England has specified a Recovery Point Objective or 1 hour in requirement C15-031. This relates to the Acceptable Data Loss non-functional requirement. | Highways England | Closed | 2020-09-21
235 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Disseminate Traffic Data | Severity 1 issues | Please can Highways England confirm how often Severity 1 issues are experienced and how Thales is involved in resolving these? | We refer you to the Service Desk Volumetrics document in the data room "Service Desk volumetrics additional request 05-Aug-2020 v1" which shows the current service severity/priority levels (1,2 and 3). The new contract defines IT fix times in KPI10 which include 5 levels of severity with associated fix times. Thales provide third line application support when required. | Highways England | Closed | 2020-09-23
236 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition and Transformation | Exit Management Plan 14.5 u) Exit Management Plan 20 Appendix D Exit Milestones Exit Management Plan Appendix E Timeline | We note that the Exit Management Plan includes, in Termination Services, reference to "ceasing all non-critical Software changes..", please can Highways England confirm if provisional dates have been agreed for this. If not please can Highways England confirm when the target date is for confirmation of the detailed exit plan schedule? We note that this may be included in the embedded file "Draft Exit Programme" and / or "Exit Timeline" but we are unable to open these from the plan document, please can Highways England provide separate copies of these documents as well? | The timeline for ceasing non-critical software changes is 6 months prior to expiry of the contract which will be 26 November 2020. Please also refer to the 'Exit Timeline' in the data room. | Highways England | Closed | 2020-10-01
237 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | WIP projects | Please can Highways England provide us with a list of all current WIP projects that are currently in progress and expected to still be running on the Effective Data (27th Jan 2021) and also any that are anticipated as be still running on the Full Service Start Date (27th May 2021), and confirm that we are not expected to allow for any costs to support such WIP projects? We assume that any support to such WIP projects would be managed through change requests, please can Highways England confirm that this is correct? | We do not expect to have any WIP projects to hand over at Full Service Start Date. If there are any remaining WIP that should be handed over at service start we would expect those to be dealt with through formal change control. | Highways England | Closed | 2020-09-23
238 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Tooling implementation | Please can Highways England confirm that the Service Provider will be able to implement their own Tooling, e.g. Monitoring, during Transition? If so when is the earliest date that this will be possible and what process will we need to go through? | The Service Provider will be able to change the tooling at Operational Services Start Date. We expect monitoring of the service from the new Service Provider from this date. Note the incumbent provides a fully managed service without HE interference. The new Service Provider will have access to the outputs of te existing tools and monitoring provisions until Operational Services Start date. | Highways England | Closed | 2020-10-01
239 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | CHARM functionality | Please can Highways England confirm the expected functionality from CHARM, and what functionality will still be coming in from COBS, etc. as well as the effective replacement period of the existing data feeds with CHARM? | The Interchange Interface Specification in the data room provides the details of the exposed functionality of the CHARM Service. The https://tssplansregistry.highwaysengland.co.uk/ register documentation defined in Schedule 2.3 describes the functionality of the COBS service (MCH1748G, TR2070I, TR2132G, TR2133J, TR2139G, TR2142F). | Highways England | Closed | 2020-09-21
240 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Sub-Contractors | NTIS Sub-Contractor Staff Information | Please can Highways England provide Role Profiles for all Thales staff? In addition, please also provide the expanded roles/profiles for the NIS team providing Support services? | Documents "NIS IT Skillset" and "Thales roles and skillset" have been added to the Post Publication folder in the Data Room | Highways England | Closed | 2020-09-23
241 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Historical Database | Please can Highways England confirm when the Historical Database is planned to become available for us to interface with? | Please refer to the answer to Q101. | Highways England | Closed | 2020-09-10
242 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | CHARM Adaptor | Please can Highways England confirm that the current CHARM adapter will be able to set the VMS messages via CHARM without changes to the NTIS systems/services or the CHARM adaptor? | The CHARM Adapter is used by the incubment to interface with CHARM Interchange Interface and the legacy HETMS Message Sign Syubsystem NMCS interface. It allow setting of signs and reciept of Sign and Signal settings from both the legacy HETMS and CHARM. It is not expected that software changes will be required when each CHARM ROCs go live. | Highways England | Closed | 2020-09-10
243 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | CHARM Adaptor | We assume that we will only be required to integrate with the CHARM adapter as part of the ongoing programme of roll outs to the RCCs but that any other CHARM related development, maintenance or integration is out of scope of the NTIS 21+ contract? Please can Highways England confirm that this is correct? | The CHARM adapter is within the NTIS contract scope. The NTIS service at Transition is expected to interface with HETMS and CHARM. After Transformation the NTIS system is expected to interface with CHARM via the Interchange Interface. It is up to the Service Provider to determine how best to deliver this interface. | Highways England | Closed | 2020-09-10
244 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | Camera and video feeds | Please can Highways England confirm that the Service Provider of the NTIS services will have access to camera and video feeds via VIH post-transition? | This is correct as per schedule 2.1 annex 2 tables 1 and 2 references 11a and 11b. | Highways England | Closed
245 | 2020-09-09 | Tenderers | e-Sourcing Portal | Clarification query |  | Financial model (inc. Risk Register, Service Charges and Milestones) | Financial Model | Please can you provide the information on the salary versus roles so that we can work on the risk budget for this. | See Q12 | Highways England | Closed | 2020-09-23
246 | 2020-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | NIS Staffing Information anonymous-2.xlsx | The documents referenced in the response to Q74 detail the life cover levels that are available for Thales staff but not for the NIS staff. Please could you confirm what level of life cover is in force for the 60 employees on the NIS staffing list? This is usually expressed as a multiple of salary. | The level of life cover is 3x salary for all employees on the NIS provisional staffing list. | Highways England | Closed | 2020-09-25
247 | 2020-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | IT Service Management |  | Will Highways England own and fund the procurement of the dedicated connection route between On-prem data centre(s) and the cloud infrastructure to be established for hosting NTIS applications? | No, the new NTIS provider will own and fund. | Highways England | Closed | 2020-09-21
248 | 2020-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Sub-Contractors |  | We understand that all the hardware and software assets would be loaned/leased to the supplier through a nominal contract. Please let us know the details of the nominal contract. Also, we assume that all the maintenance & support contracts for these assets would be funded by Highways England | The new NTIS provider will be responsible for the maintenance and support contracts of the NTIS assets. These will be assigned in accordance with Clause 13.1 of the main agreement. | Highways England | Closed | 2020-09-21
249 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Outline Solution | NTIS v2.0 – Schedule 2.1, Data Collection Requirement 11c | This specifies that the interface to Customer replacement camera system is via the CHARM Interface Exchange, yet neither the CHARM Adapter Functional Spec nor the CHARM Interchange Interface Spec contain any references to Video. Can Highways England please elaborate on how NTIS will interface to the DVNP cameras? |  | Highways England | Open
250 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution |  | Please can Highways England share any detailed design documentation for the Saturn Eclipse mobile data services and specifically any specifications and scope of the lightweight JSON format that presented as an API to mobile website and app? | Please see document added to the data room: NIS EIDD NTIS 011 - Mobile Data Server Interface | Highways England | Closed | 2020-09-23
251 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6, page 14, item 11 | Could Highways England please provide the Concept of Operations Document as referenced in “WA119-08-007-002-02-03-02 R3.9 System Subsystem Design Description v6” on page 14, item 11? | This document will not be shared as it has not been updated for a number of years to reflect the latest operating model. | Highways England | Closed | 2020-09-23
252 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Software and Insurance | Net Book Value June 2020.xlsx | In the file: “Net Book Value June 2020”, it lists 5 rows for Oracle, only one of which has a Cost. Could Highways England please provide Costs for the other rows and in particular the Oracle Database Enterprise Edition? |  | Highways England | Open
253 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | Net Book Value June 2020.xlsx | Please can Highways England define any tooling integrations (API, Rest, Email) with the NIS CA ITSM tool that are currently within scope of the existing NTIS solution? | CA ITSM provides both the system /application monitoring and service desk functions (Nimsoft for monitoring and CA Service Desk for raising Incidents, problems and changes). The service desk uses email integration to notify service users of service impacting incidents. | Highways England | Closed | 2020-09-23
254 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract |  | If Highways England were to include a 3-month bedding-in period against KPI service credits, would other remedies available to Highways England (as set out in clause 11.3 of the main terms - performance failures) also be subject to the waiver during this 3-month period? | We do not intend to waive the requirements of paragraph 11.3 during the proposed three-month bedding in period. | Highways England | Closed | 2020-10-02
255 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transformation Services | NTIS v2.0 – Schedule 2.1, Data Collection Requirement 11c | Can Highways England please elaborate on the customer replacement camera system roll-out timescales and volumes? |  | Highways England | Open
256 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution |  | In the interim period between the NTIS transformed service being available and the Highways England Historic Data Service becoming available, what is the requirement for Highways England data analysts and scientists to have continued access to the data, and specifically: - What toolsets do you currently use? Do you require to continue to use these tools or are you open to using alternatives from the service provider? - If using the existing toolset, what datasets do you require access to, and in which formats? - Do you require local access to the data or are you open to using an environment provided by the service provider? |  | Highways England | Open
257 | 2019-09-17 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution |  | Please can Highways England provide a list of database objects (including tables, views, procedures, packages, functions) that are relevant for the NTIS application with a brief description for each object? | Please see "NTIS Schema report" document now added to data room. | Highways England | Closed | 2020-10-06
258 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | CD3 - Commercial | Please can Highways England confirm that Schedule 3 (Customer Responsibilities) will be a deliverable (specific Customer Responsibilities to be inserted by us) as part of our tender submission? | The contents of Schedule 3 are not a deliverable for the tender. Additional customer responsibilities are subject to dialogue and agreement in the remaining dialogue sesssions. The acceptance of additional customer responsibilities is at the discretion of Highways England. | Highways England | Closed | 2020-10-02
259 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | CD3 - Technical | During the CD3 Technical Stream discussion we covered the current service accreditation. We assume that some security risks exist today that have been deemed acceptable to pass accreditation. Please can Highways England confirm that all accepted security risks that exist at the time of service commencement continue to be acceptable until the end of transformation? | There are outstanding risks where the mitigations in place are considered appropriate to bring the overall risk within tolerable levels. All risks will be subject to ongoing review during the provision of the services and could require further mitigation if circumstances change. Mitigatiions can follow the change control process where required. | Highways England | Closed | 2020-09-23
260 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | CD3 - Technical (existing NTIS Supplier list V2) | Please can Highways England explain what the Virgin VPN is used for? Is this a divergent link to give High Availability internet connectivity capability into the Quinton office or something else? | The use of the Virgin connectivity is explained in document WA119-08-007-008-01 in the data room | Highways England | Closed | 2020-09-23
261 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | CD3 - Technical (existing NTIS Supplier list V2) | In the list of the Outgoing Service provider’s contracts there is a voice recording contract with Weston Digital. Please can the Customer confirm if voice recording is a requirement for the Transitioned service and if so: * What needs to be recorded? * Who needs access to the recordings? * How long do the recordings need to be stored for? * Please also confirm that this is not a requirement for the Transformed service? | Voice recording is the current Service Providers method of recording telephone notifications from ROC's and other sources. The recordings are also used to support the training and monitoring of the Information Centre staff. If the new supplier wishes to continue to monitor activity in this was then they will be required to implement a similar process. It is not required for any Highways England activities. | Highways England | Closed | 2020-09-21
262 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | CD3 - Technical | We understand that the network model to be used during transition and post-transition is the one that has already been provided as part of the data room documentation. Can Highways England please confirm when the new network model, that was discussed during CD3, will be available for use? We are assuming the new network model will only be required as part of the post transformation service. | Alignment with the Highways England Definitive Network Model is in scope for transformation (ref: C4-007). Forecast delivery dates are described in the data room document (Highways England - Network Model Overview) | Highways England | Closed | 2020-09-21
263 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | CD3 - Technical | We notice that KPI5 (formerly KPI1.1) has been increased to 99.5% but from the historic data it has only achieved this level twice in 12 mths. Please can Highways England explain the rationale behind this increase given past performance and provide any recent performance data that indicates that the increase is achievable? |  | Highways England | Open
264 | 2020-09-21 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Outline Solution | Azure update received 18th September | Please can Highways England explain if the NTIS AD accounts are held in a dedicated NTIS AD infrastructure or if they are entwined with the the Outgoing Service Providers AD platform. If they are entwined please can Highways England state how this will be made available to the Service Provider for continuity of the NTIS service? | The NTIS infrastructure has dedicated AD provision | Highways England | Closed | 2020-09-23
265 | 2020-09-23 | Tenderers | e-Sourcing Portal | Clarification query | Technical |  | NTIS Requirements Changes_14092020 | In the recently released file: “NTIS Requirements Changes_14092020”, could Highways England please clarify for the following requirements, whether the original wording should be retained and augmented or replaced by the new wording? C4-007; C15-002; C15-018. Furthermore, should C15-002 apply to C15-012? |  | Highways England | Open
266 | 2020-09-23 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition and Transformation | Net Book Value June 2020.xlsx | In the Net Book Value June 2020.xslx document there seem to be four lines relating to ITSM tools. Line 5 is for Nimsoft and has a cost associated, lines 26, 27 and 29 (CA ITSM tool modules) have no cost associated but we assume are related. Is this the case? If so, is the cost shown at line 5 (circa £106k) the total cost for all CA ITSM modules or just for the Nimsoft piece? |  | Highways England | Open
267 | 2020-09-25 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition and Transformation | WA119-08-007-002-07-02 V15.0 | Section 7.1 of the Database Design Document (Release 3.13) references another document (WA119-08-007-002-07-02-04-16 NTIS Schema Report) for information on physical layout and entity relationship diagrams. Can this document or information (in particular Entity Relationship Diagrams / Physical Data Model) please be provided? | Please see "NTIS Schema report" document now added to data room. | Highways England | Closed | 2020-10-06
268 | 2020-09-25 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition and Transformation | Asset List August 2020 | The Asset List Aug 2020 has a tab named 'Software' and a tab named 'Licences'. Please could Highways England explain the difference between the software tab and the licences tab as they do not appear to directly relate to one another? If items within the software tab are required to run the existing estate then further information is required to enable pricing. We need full details of this software including the exact product names and versions along with the quantity and license type / unit purchased. Where available, existing product identification or deal registration numbers will enable us to get the best priced continued support. |  | Highways England | Open
269 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Software and Insurance |  | Please share the details of the license version, full product names and the total number of licenses for each software present in the asset register. we would need this for the maintenance contracts of the software assets |  | Highways England | Open
270 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Software and Insurance |  | For Redhat Oracle and Vmware softwares, please share the license account number. We need this to get the maintenance quotes from the OEMs |  | Highways England | Open
271 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Software and Insurance |  | Request you to share the details of the existing maintenance contracts for both hardware and software assets |  | Highways England | Open
272 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Software and Insurance |  | Please let us know who owns the software licenses which are there in the asset register. Would it be the incumbent or Highways England? | The incumbent owns the licenses in the asset register. | Highways England | Closed | 2020-10-02
273 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Technical | TUPE |  | During the Transition phase our team will require the outgoing supplier’s support for: getting access to the team for application and process knowledge transfer sessions and meetings, setting up user ids to access NTIS systems / application components and documentation, review performance/KPI reporting processes and to onboard a small number of tools and accelerators to aid the analysis of code base. This is required to ensure our team gathers the requisite knowledge of overall NTIS service delivery ecosystem including applications and processes and to comply with our service continuity plans and mitigate any TUPE transfer risk and aid the development of our Transformation Plan. We will define the associated details for this clearly in the detailed Transition Plan, and will take care to not adversely impact the production systems and delivery of live services by the outgoing supplier’s delivery team. Please can Highways England confirm that the outgoing supplier will be able to provide us this support | Highways England has a right to request termination services from the incumbent and could include these requirements in the scope of the requested services. | Highways England | Closed | 2020-10-01
274 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 8.3 (Dispute resolution) | Can Highways England confirm that the adjudication provisions as set out in Schedule 8.3 shall be replaced with an alternative dispute resolution process? Current drafting is referring provisions more usual in a construction contract and not an IT services agreement. |  | Highways England | Open
275 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Feedback on Contract | Schedule 2.4 (Security) | Paragraph 7.13 talks of confirmation being provided by CEO or equivalent officer. Can Highways England confirm that the Chief Information Security Officer would be a suitable alternative? |  | Highways England | Open
276 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Software and Insurance |  | Please can you provide the role description for “Engineering Manager” role listed in the “Subcontractor staff” list. | Please refer to the latest Thales Roles and Skillset spreadsheet. The Engineering Manager role has been added. | Highways England | Closed | 2020-10-02 | Yes | 2020-09-30 | Thales Roles and Skillset
277 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Schedule 7.1, Annex 6 | This states “The Staff Rates used to determine any change to the Charges to this Agreement shall be calculated in accordance with this Annex to Schedule 7.1.” Does this imply that Annex 6 applies only to additional work? Currently, Corporate Overheads are included in Miscellaneous. However, we have to include the Corporate Overhead % on page 41 in section 21 Service Provider Profit. We are assuming this is only for calculating charges for any change/additional work according to section 6 Annex 6 provides charging methodology relating to staff. What is the charging methodology for non-people related costs? |  | Highways England | Open
278 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Financial model (inc. Risk Register, Service Charges and Milestones) | Worksheet: B6 – Pricing (Financial Model) | Column J “Cost” within Service Charge includes Forecast Contingency Cost. This needs to be removed as it is resulting in an incorrect column L. |  | Highways England | Open
279 | 2020-09-29 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Bravo | I received a notification this morning from Bravo saying that the NTIS closing date was the 2nd October. I assume this is a leftover from the original end of Dialogue. Can you confirm that the portal will remain open until the actual closing of 28th Oct. | This was the original closure date of the dialogue phase which has now been moved to the 7th October to accomodate CD5. A new bravo area will be set up for the ISFT stage. | Highways England | Closed | 2020-10-01
280 | 2020-09-30 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  | Oracle install base information | Does the Oracle Licensing information stated in the “Oracle install base information” document in the Data Room cover all NTIS environments including DR site? | Yes, these licenses cover all environments, including those hosted at the DR site. | Highways England | Closed | 2020-10-02
281 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Milestones and Testing |  | Please can Highways England share some more information around the level of testing performed on changes that are released into the current operation? Any approved test plans/test reports that may highlight the level of testing throughout the test process lifecycle for the different types of change (such as minor patch updates through to more major changes). |  | Highways England | Open
282 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Sub-Contractors | NTIS Suppliers V2 | Please can Highways England provide Account manager/contact details and Contract numbers, reference numbers and/or circuit details for all of the suppliers listed in NTIS Supplier V2 to allow us to ensure that we have the correct scope for the existing estate when requesting our own pricing for Novation / Take on and continuation of the services supplied? |  | Highways England | Open
283 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Sub-Contractors | Asset List September 2020 | Please can Highways England provide Account manager/contact details and Contract numbers, reference numbers and/or circuit details for all of the suppliers listed in Asset List September 2020-Hardware Tab - Columns E and M to allow us to ensure that we have the correct scope for the existing estate when requesting our own pricing for Novation / Take on and continuation of the services supplied? |  | Highways England | Open
284 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | NTIS Sub Contractor Staff Information | For the 7 in scope subcontractor (Thales) employees can you please confirm their contractual / office location? | The Thales employees are based in Cheadle in Greater Manchester | Highways England | Closed | 2020-10-02
285 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | NTIS Sub Contractor Staff Information NIS Staffing Information | In light of Covid 19 please can the Authority confirm for both the incumbent and subcontractor current arrangements for in scope employees i.e. are people working from home, equipment that has been issued, have working from home allowances been issued etc? |  | Highways England | Open
286 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | NIS Staffing Information (anonymous) V4 | We note that on the revised list Employee ID 60 is now a vacancy. Please can Highways England provide: o Role description and related salary and benefits data for the role? o Is the role actively being recruited for? | See Q287 | Highways England | Closed | 2020-10-02
287 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | NIS Staffing Information (anonymous) V4 | We noted that on the revised list Employee 60 is a “WSP” Consultant. Please can Highways England provide a description of this role and confirm that it is in scope for TUPE transfer? Please also provide associated salary / pay data? | This role is the NIS Service Delivery Manager (role profile is included in the Data Room) which is currently vacant. The previous incumbent has taken a position within WSP and so is no longer on the NIS payroll. They are covering the NIS role on a part-time basis not currently recruiting. The 2019 salary rate for this role was £77000 per annum with pension contribution of 5%, death benefit 3 times salary and medical insurance of £503. | Highways England | Closed | 2020-10-02
288 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Technical | Transition Services | NIS Staffing Information (anonymous) V4 | Please can Highways England exaplin what the “Rate Medi” in column N refers to. There are four employees with a cost of £503.94 and one employee with £1209.46. Please can Highways England confirm that the “Simply Flexible” Benefits sheet applies to all roles on the NIS Staffing (anonymous) V4 sheet as well as the NITS subcontractor information? | Column N relates to employer funded medical insurance The Simply Flexible Benefits applies only to NTIS subcontractor staff (Thales) | Highways England | Closed | 2020-10-02
289 | 2020-10-01 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition Services | Exit Timeline | It is noted that the Outgoing Service Provider is required to submit the “final staff list” 14 days before the transfer. Under the TUPE Regulations 2014 final staff data must be submitted 28 days before transfer. Please can the Exit timeline be updated to reflect this timeline? | The Exit timeline has been corrected to reflect 28 days. | Highways England | Closed | 2020-10-02 | Yes | 2020-10-02 | Exit Timeline V2
290 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Draft ISFT - Page 14 - Paragraph 3.1.6 | This paragraph states that the 'digital page limits apply to the entirety of the relevant sections including paper covers, title pages and annexes'. Would Highways England please consider excluding document title/cover pages, version control pages and contents pages from the page limit? These pages will not include any core content of the document, but will aid the presentation, version history record and ability to navigate the document. If the decision is for them to be included in the page limit, it is likely that we will remove them from our documents for the final tender submission. | As per the ISFT it is clear what is included in page limits and this will not be changed on this procurement. If tenderers however believe this has a knock on effect to thier responses and require additional pages then please raise this at the ISFT stage with valid reasoning as to why more pages are required. Highways England with then review and either accept/request the request. Note any changes will be applied to all tenderers. | Highways England | Closed | 2020-10-02
291 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Schedule 2.4 | Schedule 2.4 references the Cyber essentials Plus and ISO 27001 in several places throughout. For clarification, does Highways England require NTIS to be formally Certified and accredited to 27001 and Cyber Essentials Plus, or only demonstrate compliance through an internal audit? |  | Highways England | Open
292 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | High Level Business Process Hierarchy.pdf | Document “High Level Business Process Hierarchy.pdf” shows the various process documents, many of which were provided on the 16th September in the folder: “NIS Business Processes”. Could Highways England please provide the following additional documents: Information Centre: NIS P IC 020 –Operations; NIS P IC 030 –Event Management; NIS P IC 040 –Planning; NIS P IC 050 –Strategic Responses; NIS P IC 060 –Shift Management. |  | Highways England | Open
293 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  |  | Can Highways England please confirm that non-exclusive assets are not used outside of the NTIS user base in scope for transition and transformation, and that all back end systems supporting these non-exclusive assets are for the sole use of the NTIS users? | Yes, these assets are only used by the users in scope for transfer and are for the sole use of these users. | Highways England | Closed | 2020-10-02
294 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | WA119-08-007-008-01 NTIS Base Infrastructure v9 0 (2) REDACTED v1.1 | In document: “WA119-08-007-008-01 NTIS Base Infrastructure v9 0 (2) REDACTED v1.1”, some of the images are corrupted – for example page 13. Is it possible to have an updated version of the document? | "Document base infrastructure figure 2-1" added to data room. | Highways England | Closed | 2020-10-06
295 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  |  | As Oracle 11g is the current NTIS database and there are licenses for Oracle Diagnostics & Tuning packs are you able to provide up-to-date performance reports such as Automatic Workload Repository (AWR), Active Session History (ASH), the Automatic Database Diagnostic Monitor (ADDM). This will allow us to understand the various workload (Operational, Reporting) profiles that will help us understand associated costs relating to the proposed solution. |  | Highways England | Open
296 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Schedule 2.6 section 5.1 | This section defines a minimum level of efficiency savings of 5% per year from Year 2. Please can Highways England confirm that this is an average efficiency per year over the period of the contract and that the supplier would not be penalised for making larger savings earlier on in the contract. For example if the saving in year 2 is 10% then the year 3 figure should not need a further 5% on top of the year 2 figure. |  | Highways England | Open
297 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query |  |  | Process Mapping | We have identified the following NTIS processes which do not have process map documentation. The following processes do not appear in the data room a. Planning - NIS P IC 04 b. Shift Management - NIS P IC 06 Please can Highways England provide these documents |  | Highways England | Open
298 | 2020-10-02 | Highways England | e-Sourcing Portal | Clarification query | Commercial |  | All bidders | We are seeking reassurance that NTIS Cloud service offering will be affordable for the duration of the service. Please advise your approach to protecting Highways England from adverse commercial and service impact from predicted and unpredicted peaks and troughs in cloud utilisation including but not limited to deployment, storage, processing, use of functions. |  | Tenderers | Open
299 | 2020-10-02 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  |  | Could Highways England please provide annual costs for software license and software support costs for the current NTIS service please? | The annual cost of software licences and service support contracts for the current NTIS service (excluding Thales and WSP support contracts) is £2,699, 682. This annual cost of software licences and service support contracts for the current NTIS service from INRIX, Oracle and RedHat is £2,114,758. This figure is a subset of the £2,699,682 figure above. | Highways England | Closed | 2020-10-02
300 | 2020-10-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition and Transformation |  | Are you able to provide any clarification on the level of "innovation spend" that is expected as a part of the overall 7 year spend envelope approved for the NTIS project?’ |  | Highways England | Open
301 | 2020-10-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial |  |  | Could you please confirm whether or not Highways England would be agreeable to contracting directly with suppliers of data for use in future NTIS services? | We would like to point suppliers to the requirements C3-001, C3-003, C8-004 that relate to the collection and use of In-vehicle On-Network Sensors Event Data. Highways England have no current plans to sign up to commercial terms with any data provider for the delivery of this data and we expect suppliers to price to deliver these requirements. | Highways England | Closed | 2020-10-06
302 | 2020-10-05 | Tenderers | e-Sourcing Portal | Clarification query | Commercial | Transition and Transformation |  | We would like to request Highways England consider increasing the allowed page count for the ISFT response on the Quality Plan from 15 pages. | We can confirm that we agree to increasing the allowable number of pages for your Quality Plan in the Final Tender from 15 to a maximum of 25 pages. | Highways England | Closed | 2020-10-06
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
1087
1088
1089
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
1118
1119
1120
1121
1122
1123
1124
1125
1126
1127
1128
1129
1130
1131
1132
1133
1134
1135
1136
1137
1138
1139
1140
1141
1142
1143
1144
1145
1146
1147
1148
1149
1150
1151
1152
1153
1154
1155
1156
1157
1158
1159
1160
1161
1162
1163
1164
1165
1166
1167
1168
1169
1170
1171
1172
1173
1174
1175
1176
1177
1178
1179
1180
1181
1182
1183
1184
1185
1186
1187
1188
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206
1207
1208
1209
1210
1211
1212
1213
1214
1215
1216
1217
1218
1219
1220
1221
1222
1223
1224
1225
1226
1227
1228
1229
1230
1231
1232
1233
1234
1235
1236
1237
1238
1239
1240
1241
1242
1243
1244
1245
1246
1247
1248
1249
1250
1251
1252
1253
1254
1255
1256
1257
1258
1259
1260
1261
1262
1263
1264
1265
1266
1267
1268
1269
1270
1271
1272
1273
1274
1275
1276
1277
1278
1279
1280
1281
1282
1283
1284
1285
1286
1287
1288
1289
1290
1291
1292
1293
1294
1295
1296
1297
1298
1299
1300
1301
1302
1303
1304
1305
1306
1307
1308
1309
1310
1311
1312
1313
1314
1315
1316
1317
1318
1319
1320
1321
1322
1323
1324
1325
1326
1327
1328
1329
1330
1331
1332
1333
1334
1335
1336
1337
1338
1339
1340
1341
1342
1343
1344
1345
1346
1347
1348
1349
1350
1351
1352
1353
1354
1355
1356
1357
1358
1359
1360
1361
1362
1363
1364
1365
1366
1367
1368
1369
1370
1371
1372
1373
1374
1375
1376
1377
1378
1379
1380
1381
1382
1383
1384
1385
1386
1387
1388
1389
1390
1391
1392
1393
1394
1395
1396
1397
1398
1399
1400
1401
1402
1403
1404
1405
1406
1407
1408
1409
1410
1411
1412
1413
1414
1415
1416
1417
1418
1419
1420
1421
1422
1423
1424
1425
1426
1427
1428
1429
1430
1431
1432
1433
1434
1435
1436
1437
1438
1439
1440
1441
1442
1443
1444
1445
1446
1447
1448
1449
1450
1451
1452
1453
1454
1455
1456
1457
1458
1459
1460
1461
1462
1463
1464
1465
1466
1467
1468
1469
1470
1471
1472
1473
1474
1475
1476
1477
1478
1479
1480
1481
1482
1483
1484
1485
1486
1487
1488
1489
1490
1491
1492
1493
1494
1495
1496
1497
1498
1499
1500
1501
1502
1503
1504
1505
1506
1507
1508
1509
1510
1511
1512
1513
1514
1515
1516
1517
1518
1519
1520
1521
1522
1523
1524
1525
1526
1527
1528
1529
1530
1531
1532
1533
1534
1535
1536
1537
1538
1539
1540
1541
1542
1543
1544
1545
1546
1547
1548
1549
1550
1551
1552
1553
1554
1555
1556
1557
1558
1559
1560
1561
1562
1563
1564
1565
1566
1567
1568
1569
1570
1571
1572
1573
1574
1575
1576
1577
1578
1579
1580
1581
1582
1583
1584
1585
1586
1587
1588
1589
1590
1591
1592
1593
1594
1595
1596
1597
1598
1599
1600
1601
1602
1603
1604
1605
1606
1607
1608
1609
1610
1611
1612
1613
1614
1615
1616
1617
1618
1619
1620
1621
1622
1623
1624
1625
1626
1627
1628
1629
1630
1631
1632
1633
1634
1635
1636
1637
1638
1639
1640
1641
1642
1643
1644
1645
1646
1647
1648
1649
1650
1651
1652
1653
1654
1655
1656
1657
1658
1659
1660
1661
1662
1663
1664
1665
1666
1667
1668
1669
1670
1671
1672
1673
1674
1675
1676
1677
1678
1679
1680
1681
1682
1683
1684
1685
1686
1687
1688
1689
1690
1691
1692
1693
1694
1695
1696
1697
1698
1699
1700
1701
1702
1703
1704
1705
1706
1707
1708
1709
1710
1711
1712
1713
1714
1715
1716
1717
1718
1719
1720
1721
1722
1723
1724
1725
1726
1727
1728
1729
1730
1731
1732
1733
1734
1735
1736
1737
1738
1739
1740
1741
1742
1743
1744
1745
1746
1747
1748
1749
1750
1751
1752
1753
1754
1755
1756
1757
1758
1759
1760
1761
1762
1763
1764
1765
1766
1767
1768
1769
1770
1771
1772
1773
1774
1775
1776
1777
1778
1779
1780
1781
1782
1783
1784
1785
1786
1787
1788
1789
1790
1791
1792
1793
1794
1795
1796
1797
1798
1799
1800
1801
1802
1803
1804
1805
1806
1807
1808
1809
1810
1811
1812
1813
1814
1815
1816
1817
1818
1819
1820
1821
1822
1823
1824
1825
1826
1827
1828
1829
1830
1831
1832
1833
1834
1835
1836
1837
1838
1839
1840
1841
1842
1843
1844
1845
1846
1847
1848
1849
1850
1851
1852
1853
1854
1855
1856
1857
1858
1859
1860
1861
1862
1863
1864
1865
1866
1867
1868
1869
1870
1871
1872
1873
1874
1875
1876
1877
1878
1879
1880
1881
1882
1883
1884
1885
1886
1887
1888
1889
1890
1891
1892
1893
1894
1895
1896
1897
1898
1899
1900
1901
1902
1903
1904
1905
1906
1907
1908
1909
1910
1911
1912
1913
1914
1915
1916
1917
1918
1919
1920
1921
1922
1923
1924
1925
1926
1927
1928
1929
1930
1931
1932
1933
1934
1935
1936
1937
1938
1939
1940
1941
1942
1943
1944
1945
1946
1947
1948
1949
1950
1951
1952
1953
1954
1955
1956
1957
1958
1959
1960
1961
1962
1963
1964
1965
1966
1967
1968
1969
1970
1971
1972
1973
1974
1975
1976
1977
1978
1979
1980
1981
1982
1983
1984
1985
1986
1987
1988
1989
1990
1991
1992
1993
1994
1995
1996
1997
1998
1999
2000
2001
2002
2003
2004
2005
2006
2007
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038
2039
2040
2041
2042
2043
2044
2045
2046
2047
2048
2049
2050
2051
2052
2053
2054
2055
2056
2057
2058
2059
2060
2061
2062
2063
2064
2065
2066
2067
2068
2069
2070
2071
2072
2073
2074
2075
2076
2077
2078
2079
2080
2081
2082
2083
2084
2085
2086
2087
2088
2089
2090
2091
2092
2093
2094
2095
2096
2097
2098
2099
2100
2101
2102
2103
2104
2105
2106
2107
2108
2109
2110
2111
2112
2113
2114
2115
2116
2117
2118
2119
2120
2121
2122
2123
2124
2125
2126
2127
2128
2129
2130
2131
2132
2133
2134
2135
2136
2137
2138
2139
2140
2141
2142
2143
2144
2145
2146
2147
2148
2149
2150
2151
2152
2153
2154
2155
2156
2157
2158
2159
2160
2161
2162
2163
2164
2165
2166
2167
2168
2169
2170
2171
2172
2173
2174
2175
2176
2177
2178
2179
2180
2181
2182
2183
2184
2185
2186
2187
2188
2189
2190
2191
2192
2193
2194
2195
2196
2197
2198
2199
2200
2201
2202
2203
2204
2205
2206
2207
2208
2209
2210
2211
2212
2213
2214
2215
2216
2217
2218
2219
2220
2221
2222
2223
2224
2225
2226
2227
2228
2229
2230
2231
2232
2233
2234
2235
2236
2237
2238
2239
2240
2241
2242
2243
2244
2245
2246
2247
2248
2249
2250
2251
2252
2253
2254
2255
2256
2257
2258
2259
2260
2261
2262
2263
2264
2265
2266
2267
2268
2269
2270
2271
2272
2273
2274
2275
2276
2277
2278
2279
2280
2281
2282
2283
2284
2285
2286
2287
2288
2289
2290
2291
2292
2293
2294
2295
2296
2297
2298
2299
2300
2301
2302
2303
2304
2305
2306
2307
2308
2309
2310
2311
2312
2313
2314
2315
2316
2317
2318
2319
2320
2321
2322
2323
2324
2325
2326
2327
2328
2329
2330
2331
2332
2333
2334
2335
2336
2337
2338
2339
2340
2341
2342
2343
2344
2345
2346
2347
2348
2349
2350
2351
2352
2353
2354
2355
2356
2357
2358
2359
2360
2361
2362
2363
2364
2365
2366
2367
2368
2369
2370
2371
2372
2373
2374
2375
2376
2377
2378
2379
2380
2381
2382
2383
2384
2385
2386
2387
2388
2389
2390
2391
2392
2393
2394
2395
2396
2397
2398
2399
2400
2401
2402
2403
2404
2405
2406
2407
2408
2409
2410
2411
2412
2413
2414
2415
2416
2417
2418
2419
2420
2421
2422
2423
2424
2425
2426
2427
2428
2429
2430
2431
2432
2433
2434
2435
2436
2437
2438
2439
2440
2441
2442
2443
2444
2445
2446
2447
2448
2449
2450
2451
2452
2453
2454
2455
2456
2457
2458
2459
2460
2461
2462
2463
2464
2465
2466
2467
2468
2469
2470
2471
2472
2473
2474
2475
2476
2477
2478
2479
2480
2481
2482
2483
2484
2485
2486
2487
2488
2489
2490
2491
2492
2493
2494
2495
2496
2497
2498
2499
2500
2501
2502
2503
2504
2505
2506
2507
2508
2509
2510
2511
2512
2513
2514
2515
2516
2517
2518
2519
2520
2521
2522
2523
2524
2525
2526
2527
2528
2529
2530
2531
2532
2533
2534
2535
2536
2537
2538
2539
2540
2541
2542
2543
2544
2545
2546
2547
2548
2549
2550
2551
2552
2553
2554
2555
2556
2557
2558
2559
2560
2561
2562
2563
2564
2565
2566
2567
2568
2569
2570
2571
2572
2573
2574
2575
2576
2577
2578
2579
2580
2581
2582
2583
2584
2585
2586
2587
2588
2589
2590
2591
2592
2593
2594
2595
2596
2597
2598
2599
2600
2601
2602
2603
2604
2605
2606
2607
2608
2609
2610
2611
2612
2613
2614
2615
2616
2617
2618
2619
2620
2621
2622
2623
2624
2625
2626
2627
2628
2629
2630
2631
2632
2633
2634
2635
2636
2637
2638
2639
2640
2641
2642
2643
2644
2645
2646
2647
2648
2649
2650
2651
2652
2653
2654
2655
2656
2657
2658
2659
2660
2661
2662
2663
2664
2665
2666
2667
2668
2669
2670
2671
2672
2673
2674
2675
2676
2677
2678
2679
2680
2681
2682
2683
2684
2685
2686
2687
2688
2689
2690
2691
2692
2693
2694
2695
2696
2697
2698
2699
2700
2701
2702
2703
2704
2705
2706
2707
2708
2709
2710
2711
2712
2713
2714
2715
2716
2717
2718
2719
2720
2721
2722
2723
2724
2725
2726
2727
2728
2729
2730
2731
2732
2733
2734
2735
2736
2737
2738
2739
2740
2741
2742
2743
2744
2745
2746
2747
2748
2749
2750
2751
2752
2753
2754
2755
2756
2757
2758
2759
2760
2761
2762
2763
2764
2765
2766
2767
2768
2769
2770
2771
2772
2773
2774
2775
2776
2777
2778
2779
2780
2781
2782
2783
2784
2785
2786
2787
2788
2789
2790
2791
2792
2793
2794
2795
2796
2797
2798
2799
2800
2801
2802
2803
2804
2805
2806
2807
2808
2809
2810
2811
2812
2813
2814
2815
2816
2817
2818
2819
2820
2821
2822
2823
2824
2825
2826
2827
2828
2829
2830
2831
2832
2833
2834
2835
2836
2837
2838
2839
2840
2841
2842
2843
2844
2845
2846
2847
2848
2849
2850
2851
2852
2853
2854
2855
2856
2857
2858
2859
2860
2861
2862
2863
2864
2865
2866
2867
2868
2869
2870
2871
2872
2873
2874
2875
2876
2877
2878
2879
2880
2881
2882
2883
2884
2885
2886
2887
2888
2889
2890
2891
2892
2893
2894
2895
2896
2897
2898
2899
2900
2901
2902
2903
2904
2905
2906
2907
2908
2909
2910
2911
2912
2913
2914
2915
2916
2917
2918
2919
2920
2921
2922
2923
2924
2925
2926
2927
2928
2929
2930
2931
2932
2933
2934
2935
2936
2937
2938
2939
2940
2941
2942
2943
2944
2945
2946
2947
2948
2949
2950
2951
2952
2953
2954
2955
2956
2957
2958
2959
2960
2961
2962
2963
2964
2965
2966
2967
2968
2969
2970
2971
2972
2973
2974
2975
2976
2977
2978
2979
2980
2981
2982
2983
2984
2985
2986
2987
2988
2989
2990
2991
2992
2993
2994
2995
2996
2997
2998
2999
3000