NEW ENGINEERING CONTRACT (NEC) /

ENGINEERING & CONSTRUCTION

CONTRACT (ECC)

ANNEX E TO SCHEDULE 10

WORKS INFORMATION

&

SITE INFORMATION

APPLICABLE TO

WORKS CONTRACTS UNDER  THE OVERSEAS CAPITAL FRAMEWORK USING THE NEC FORM OF CONTRACT

Date: 15 Feb 21					Version: 1.0

CONTENTS

PART 1 – WORKS INFORMATION	4

INTRODUCTION	4

BACKGROUND TO THE PROJECT	4

PROJECT AIM & OBJECTIVES	4

PROJECT SITE/LOCATION	4

SCOPE OF THE PROJECT	4

DESIGN & CONSTRUCTION COMPLIANCE CERTIFICATION	5

BUILDING INFORMATION MODELLING (INCL COMMON DATA ENVIRONMENT	6

TESTING AND INSPECTION……………………………………………………………………………….....7

CONTRACTOR PERFORMANCE	7

TOWN AND COUNTRY PLANNING………………………………………………………………………   ..8

PROJECT PROGRAMME…………………………………………………………………………   …………8

TECHNICAL STANDARDS	9

TRAINING	11

CONSTRAINTS	11

QUALITY MANAGEMENT	12

SITE ACCESS AND SECURITY	12

SITE SAFETY AND PROTECTION	13

APPLICATION OF CONSTRUCTION, DESIGN & MANAGEMENT REGULATIONS	14

SURVEYS	14

THROUGH LIFE COST MANAGEMENT	15

CONTRACT RECORDS	16

SUSTAINABLE DEVELOPMENT AND THE ENVIRONMENT	16

ISSUED PROPERTY	18

MATERIALS ARISING FROM THE CONTRACT	18

TAKEOVER PROCESS	18

GOVERNMENT SOFT LANDINGS                                                                                                      19

PROJECT INTERFACES	19

PART 2 – SITE INFORMATION	22

SITE LOCATION	22

SITE INVESTIGATION	22

REPORTS AND SURVEYS & OTHER LOCALLY HELD DATA	22

PUBLIC INFORMATION	22

BURIED PLANT	23

BURIED PIPE & CABLE SERVICES	23

ADJACENT BUILDINGS, STRUCTURES OR PLANT	23

NON MOD OWNED BUILDINGS & ESTATE	24

COMPLIANCE PERIOD SPECIFIC INFORMATION	24

OTHER SITE SPECIFIC INFORMATION	24

AVAILABILITY & ACCESS TO SITE INFORMATION	25

TABLES

Table 1  Key Project interfaces	20

APPENDICES

Appendix  1 Contents List of a Typical Works Contract Project Specification

Appendix  2

Appendix  3 Timber and Timber Containing Products

Appendix  4

Appendix  5 etc

REFERENCES

| A | Board of Officers – Siting Board Report - reference and date |
| --- | --- |
| B | Sustainability Assessment Matrix Version xxx dated xxx |
| C | G2 Security Recommendations of Threat Assessment of Siting Board Options – reference and date |
| D | Project Specification Version xxx – reference and date |
| E | Stage 1 DEEP Review – reference and date |
| F | Survey stage DREAM/BREEAM/CEEQUAL Assessment – reference and date |
| G | Development Control Planning Approval – reference and date |
| H | MOD Fire Officers Design Review & /Issue of Certificate A – reference and date |
| I | Schedule 1 – Scope of Framework Agreement Version xxx dated xxx |
| J | Annex I to Schedule 11 – Works & Site Information – Version xxx dated xxx |
| K | Government Buying Standards - Construction Products/Sustainable Procurement see DEFRA Website |

PART 1 – WORKS INFORMATION

INTRODUCTION

- The purpose of the Works Information & Site Information is to provide technical details about the nature of the works in output terms and any operational requirements and constraints that will apply. This and the associated documentation is to be read in conjunction with the requirements detailed in :the overarching Framework Agreement which details the general requirements and aspects of service delivery applicable to all Framework Projects.

BACKGROUND TO THE PROJECT

- The project was initially conceived…

Insert relevant extracts from URD, ROEI and Assessment Study as applicable to provide a short summary statement.

PROJECT AIM & OBJECTIVES

- The aim of the project is to:

Insert from URD e.g. ‘Single Statement of Need’ and should include minimum design life

- The objectives of the project are to:

Insert objectives from the URD e.g. bullet point format

PROJECT SITE/LOCATION

- Identify the location for the new project/works by reference to the recommendations of the Establishments Board of Officers convened to determine the preferred location agreed at the Siting Board.

Provide details of the Siting Board and any agreed associated site working areas for use by the Framework contractor.

SCOPE OF THE PROJECT

- The scope of the project will be developed from the Assessment Study preferred option/recommendation and defined by the Employer’s designer through sketch drawings and a fully developed Project Specification. The Contractor shall then complete and fully own the design and deliver construction in accordance with project requirements and criteria.

- The Sketch Design comprises of General Arrangement and Location drawings and specification criteria, upon which full development control approval has been secured and are referenced as follows:

List here the drawings, specifications and other related design documentation comprising the Sketch Design.

- During the design a Design Review Process shall provide assurance to the Project Manager as to the progress of the design by the Contractor to the required time and quality.

List here the design review process requirements such as meetings, design documents certification etc.

- To satisfy the requirement, the implementation and delivery of the works in entirety (inclusive of all component parts) and subsequent operation, maintenance, repair and/or replacement is to be fit for intended purpose and to provide a demonstrable through life, best value and sustainable solution to the Employer.

- The Design Excellence Evaluation Process (DEEP) is the MOD design quality assessment tool and the Contractor shall (where appropriate), with the Project Manager and appropriate stakeholders, carry out DEEP assessments at the relevant and respective stages.

- The Key User Requirements of the Works Project are: The Project Manager is to:

  - List KURs, URD/Assessment Study/DIO decisions as appropriate.

    - Function:  Specify as appropriate intended function of the building/facility and the DIO project requirements and relationships, operational requirements and efficiency. Refer to DEEP handbook for guidance.

    - Impact:  Include statements as appropriate to define design context, form and internal considerations. Refer to DEEP handbook for guidance.

    - Build:  Include statements as appropriate to define building/facility performance (including minimum design life), engineering and fabric. Refer to DEEP handbook for guidance.

    - Additional Output Requirements:  List any specific additional output requirements, if appropriate and not covered elsewhere e.g. power distribution, IT/Data cabling and connection to site infrastructure, server rooms, secure storage, 3rdparty interface specifications etc.

- Compliance Period:  If on project completion, operation and maintenance is to be undertaken by the Contractor,  the compliance period duration and maintenance regime are to be delivered as specified

- The Project Manager should consult with the Service Manager and/or Prime Contractor’s local maintenance organisation to develop this requirement.

DESIGN & CONSTRUCTION COMPLIANCE CERTIFICATION

- The Contractor shall in developing the detailed design comply with procedures stated by the Project Manager in the Project Specification for coordination, checking and approval of successive design stages up to and including final submission for acceptance by the Project Manager, which may include:

- a.	Building control;

  - Fire;

  - CTM / Security

  - Communication Information Systems;

  - Explosive Storage/Environments

- Building Control. The procedures to be followed by the Authority’s designer are contained in MOD Building Regulations Compliance System PI 02/10.

  - The compliance procedure mandates the issue of certification at specified points in the projects to the Project Manager. Certification is provided by the Compliance Certifier (in this case the Employer’s designer) for the project.  The certificates provide the declaration that the works comply with the design solution contained within the Approved Documents or equivalent which support the Building Regulations.

  - Separate certification is required for both design and structural design.

- Fire Officer. Compliance with Building Regulations is intrinsically linked with Crown Fire Standards in particular Parts B – Fire Safety and Part M – Access to and Use of Buildings.  It is anticipated that throughout the compliance process there will be consultation with the DFRMO Project Fire Officer where appropriate.  MOD Certificate ‘A’ (Restriction of Works Certificate) will be required.  A list of drawings required for fire approval and certification prior to issue of MOD Certificate ‘A’ is detailed in the Fire Safety Technical Specification.

- Amendment or revision of the arrangements proposed or required may have a significant effect on the fire safety measures necessary. It is a mandatory requirement that advice/approval be sought from the Project Fire Officer prior to implementation.

- CIS Installation. Installation design drawings are to be approved by the Project Manager prior to building construction and installation work.

- The following CIS documentation in support of the installation shall be provided to the Project Manager prior to the takeover of the building. As a guide the documentation pack shall include as a minimum the following:

  - One hard copy and one soft copy (pdf and CAD) of the as-fitted drawings that detailed the installed position of the CIS infrastructure (cables, cable containment, LAN, equipment and Ups);

  - Comprehensive test results for CAT5e and Fibre Optic installations in accordance with the requirements of JSP 480

  - Certificate of Electrical Conformance indicating that the installation has been completed in accordance with this requirement;

  - Detailed rack layouts showing installed equipment positions and wall elevations for mounted CIS furniture.

- The issue of an Installation Conformance Certificate is dependant upon the above documentation being provided.

Project Manager to list here the procedures to be followed in development and signing off the design, who will be responsible on behalf of the employer and any necessary 3rd party certification prior to submission for acceptance.

BUILDING INFORMATION MODELLING (INCL COMMON DATA ENVIRONMENT)

- The Works Contractor shall adopt the use of Building Information Modelling (BIM) process and appropriate technologies, in accordance with the British Standard 1192 suite of documents, including BS1192-4:2014 (COBie – Code of practice); in line with UK Government’s Construction Strategy (GCS) 2011–15 and the GCS 2016-20.

- The Works Contractor shall fully participate in Government Soft Landings (GSL) processes, as, in part, defined by BS 8536 Parts 1 and 2 (Briefing for design and construction – Part 1: Code of practice for facilities infrastructure and Part 2: Code of practice for asset management (Linear and geographical infrastructure)).

- The Works Contractor shall liaise with the appropriate DIO Regional Delivery Region / Site Liaison representatives to align the interest of those who design and construct an Asset with those who subsequently use it.

- The Works Contractor shall use processes, technologies and systems that meet the UK Government’s BIM requirements in accordance with the DIO’s Exchange Information Requirements (EIR) and ensure that all information and data in these systems is maintained in accordance with security classification of the Level 2 Asset and in accordance with any asset specific Built Asset Security Information Requirements (BASIR).

- The Works Contractor warrants and undertakes that it shall comply with the Employer supplied documents and shall act as the BIM Information Manager on this Contract.

- The Works Contractor shall act as the BIM Information Manager on this Contract, as more fully set out in the Employer supplied documents

- The Works Contractor shall work with the DIO PM, Technical Support Provider (TSP) and project Stakeholders to review and validate the Project IDP

- The Works Contractor shall produce the Master Information Delivery Plan to meet the requirements of the Project Information Delivery Plan developed by the Employers TSP in liaison with the Employers Project Manager. In collaboration with the Employers TSP the Contractor shall update the MIDP throughout the project and ensure that information is published throughout each stage in accordance with the Project IDP and MIDP.

- The Works Contractor shall undertake a collaborative approach and facilitate workshops to promote BIM process and appropriate technologies and Government Soft Landing (GSL) with both the Projects Technical Support Provider, Employer staff and/or the Employers representatives.

- The Works Contractor shall throughout the course of the contract, as a result of their work development activities, update the COBie Demand Matrix (CDMx) in accordance with the DIO EIR, Project IDP and Asset Information Requirements (AIR), appropriate to those work development activities to ensure COBie data is delivered at the appropriate stage LOD & LOI.

- The Project Manager shall provide the Employers Information Requirement (EIR), Project Information Delivery Plan (IDP), BEP Evaluation Assessment Criteria, BIM Information Manager Roles & Responsibilities and DIO Project BMAT

- The Works Contractor will provide a BEP for the project.

TESTING AND INSPECTION

- The contractor shall carryout the following tests and inspections, all to be witnessed by the Project Manager:

- The Project Manager to list here the tests and inspections required including the materials, facilities, and samples required for such tests.

- The Project Manager to list here the materials, facilities and samples that will be provided by the Employer

- Sufficient notice shall be given to the Project manager to enable witnessing of the tests and inspections.

- PM to insert minimum notice required.

CONTRACTOR PERFORMANCE

- The Contractor’s performance will be measured on the Works Contract in accordance with the Success Measures and Targets and the Call Off KPIs.

- The Design will be formally reviewed by the Project Manager.  There will be a two –stage Inspection:

              - One –off interim measurement at design mid-point which will occur at  PM to insert;

              - One-off final measurement at design completion which will occur at PM to insert.  This will include all information provided by the Contractor and specialists.

- For the purposes of this project the following will be considered to be major or minor non-compliances.

- Project Manager to list here what would be considered a minor non-compliance.  For example:

- Not submitting requested information in timely manner

- Monthly reports missing detail on some minor issues

- Failing to have a specific test witnessed

- Project Manager to list here what would be considered a major non-compliance.  For example:

- Non-compliance with key technical standard

- Non –compliance with planning condition

- Non-compliance with Fire Officer Requirement

- Breach of security requirement

- Breach of any health and safety requirement including contravention of appointed CDM appointed duties

- Missing agreed completion date by more than a minor degree

- Failure to meet the required technical standard

- Failure to carryout a specific test

- Over – running agreed contract programme.

TOWN & COUNTRY PLANNING

- The Project Manager will secure full development control approval for projects to be tendered under the Frameworks unless identified in the project scope as a requirement of the Contractor.

- Were applicable the Project will be undertaken in compliance of Host Nation Legislation.

- The Works Contractor is to discharge all the Planning Conditions notified.

- The Project Manager is to list here all Planning Conditions

- The Project Manager is to list here all relevant Host Nation Legislation.

PROJECT PROGRAMME

- The project is to be delivered in accordance with the agreed programme at contract award and works are to be completed and handed over to the Project Manager no later than insert date.

If applicable notify Tenderers of any customer critical dates to be factored into the programme with reasons and impacts of not achieving them.

Where there is no critical in service date then the Contractor’s best proposal may be inserted.

The Contractor’s project programme will be reviewed by the Project Manager at regular progress meetings to validate actual project progress against the tendered project plan.

The Project Manager is to specifically state what meetings the Contractor is to attend which should include Design review, construction progress, takeover and compliance and any other relevant meetings indicating frequency and/ or number of where appropriate e.g monthly, quarterly annually 2 per year etc

TECHNICAL STANDARDS

- The works are to be designed, constructed and maintained, inclusive of compliance period if applicable, in accordance with the Sketch Design, Project Specification and relevant Mandatory Technical Standards identified below:

- Mandatory

- a.	JSP 375 – MOD Health and Safety Handbook (Unrestricted)

- b.	JSP 440 – Defence Manual of Security (Restricted)

- Note: To ensure compliance with JSP 440 in the first instance contractors should refer to HMG Security Policy Framework (unrestricted) which is available at the following link;

- http://www.cabinetoffice.gov.uk/resource-library/security-policy-framework

  - JSP 480 – Defence Co-ordinating Installation Design Authority Manual of Regulations for Installation of Communications and Information Systems (Unrestricted).

  - Generic CIS Design Specification for the Provision of Communications and Information Systems (CIS) and Communications Electronic (CE) Equipment Infrastructure.

  - Defence Infrastructure Fire Standards (DFIS). Published 2017.

  - Standard Fire Precautions for Contractors Engaged on the Crown Estate ISBN 0117530948 (Unrestricted)

  - Defence Works Functional Standard – Counter Terrorist Measures (CTM) – Construction Standards for MOD Buildings Subject to Terrorist Threat (Restricted). Note: The threat level applicable to an establishment and appropriate CTM measures will be notified by the Project Manager.

  - DEO Design and Maintenance Guide DMG 08 – Space requirements for plant access, operation and maintenance.

  - MOD Building Regulations Compliance System – DIO PI 02/10

Project Manager to list here any other Mandatory Standards specifically relevant to the project not identified in above and cross reference to the Project Specification for any other technical standards.

- It is MOD Policy that facilities are to be provided to meet no more than Minimum Military Requirement, to standards that ensure the Minimum Through Life Cost.

- MOD standards (e.g. Joint Services Publications) represent standards the Employer generally adopts and to which it is accustomed. Deviation from these standards must be approved by the Project Manager and are to be clearly identified and supported by valid justifications that provide demonstrable additional benefits.

- The Contractor shall adopt best current practice and standards applied within the UK Construction Industry in delivery of Framework projects which are to comply with all current Legislation, Regulations and relevant MOD policy, including Building Construction, Sustainability, Health and Safety, Environmental and Fire.

- The MOD considers the following publications will be relevant to most UK MOD Establishment projects.

The Project Manager is to list all list all relevant MOD Standards

  - JSP 315 – Building Performance Standards (Unrestricted)

b.	JSP 362 – Defence Lands Handbook (Unrestricted)

c	JSP 392 – Management of Radiation Protection in Defence (Unrestricted)

  - JSP 418 – Management of Environmental Protection in Defence (Unrestricted)

  - JSP 434 – Defence Construction in the Built Environment (Unrestricted)

  - JSP 850 – Infrastructure and Estate Policy (Unrestricted)

  - DSA 01.1	Defence policy for health, safety, and environmental protection

  - MOD Policy Infrastructure 01/20 Infrastructure Function Estate Policy in support of Net Zero Transition.

  - DIO Policy Products:

    - DIO Policy Instructions;

      - PI 06/11 on Environmental Performance Assessment’s (Built Environment) (including BREEAM, Code for Sustainable Homes, CEEQUAL and other tools)

      - PI 03/08 on site waste management plans, and the Greening Government commitment to divert between 80-100% of construction waste from landfill.

      - PI 08/09 on energy Performance of Buildings (and a potential requirement to display Energy Certificates)

      - DSA01.1 – Defence Policy for Health, Safety and Environmental Protection (Unrestricted)

    - Information Notices;

    - Safety Alert notices;

    - Practitioners Guides;

    - Design and Maintenance Guides;

    - Functional Standards;

    - Health & Safety Warning & Alert Notices;

    - Specifications;

    - Technical Bulletins;

    - Warning Notice;

    - Approved Codes of Practice;

- Although JSP 315 Scales of Accommodation are not mandatory or an automatic entitlement they are a proven method of ensuring compliance with functionality/operability and they will be used by the Project Manager for benchmarking purposes. Proposals that deviate from these scales must be clearly identified and supported by valid justifications that provide demonstrable additional benefits to functionality/operability/cost.

- Contractor design development for United States Visiting Forces (USVF) projects located on UK MOD sites shall comply with specific USVF design requirements to include but not limited to:

              - Unified Facility Criteria (UFCs)

              - American Disability Act (ADA)

              - US Department of Defence Standards

              - Base Architectural and Compatibility Standards

              - Engineering Technical Letters (ETLs)

              - Construction Technical Letters (CTLs)

              - Force Protection

              - USVF Security Standards

  - Airfield Ground Lighting (AGL)

  - NATO Standards

  - Lightning Protection

  - Department of Defence Dependants Schools (DoDDS)

  - Asbestos Hazard Emergency Response Act (AHERA)

  - National Fire Protection Association (NFPA)

- The Contractor shall confirm with the Project Manager the standards that shall be applied to this project. Omissions or irregularities identified shall be brought to the Project Managers attention as soon as the Contractor becomes aware.

- The Project Manager will, upon a formal request, and subject to appropriate security clearance of the recipient, facilitate the provision of any document which is not publicly available on the relevant websites and has not otherwise been issued to the Contractor.

TRAINING

- The Contractor is to provide an outline training schedule for agreement with the Project Manager.  The Establishment APs will undertake that training prior to the pre-takeover date. The Contractor is to nominate a person to familiarise the Authorised Persons with the equipment, systems or locations having significant risk in order for the adoption of JSP 375 Volume 3 Safety Rules and Procedures. The Contractor is to allow sufficient time and resources before acceptance of the works by MOD to allow the APs to become familiar with the new facility and associated hazards.

- PM is to insert the time to be allowed for training APs

- PM to list the systems and or equipment that require specific training.

CONSTRAINTS

- The Contractor shall note the following constraints:

              - The normal working hours for                  are                   Mon to Fri.  Access to undertake works outside these times will require prior approval from the Project Manager.

              - Any proposed shut down period of services within the establishment is to be notified at least five (5)  working days in advance to the Project Manager for approval by the Employer or if for justifiable reasons this is not acceptable to the Employer an alternative shutdown period shall be agreed.

    - The Project Manager is to:

    - List any funding constraints (if applicable)

    - List any constraints in respect of occupied or part occupied buildings.

    - List any constraints in respect to sequence for phasing or delivery timing of the works which shall include specified date for possession of site by the Contractor.

    - List any restrictions to height of temporary structures.

    - List any other specific planning issues known to exist. e.g. Listed Buildings, Section 106 Contributions known/anticipated planning requirements or conditions etc Refer to Town & Country Planning para 21.

    - List any other site specific constraints e.g. special licences to permit contractors to work in certain areas (high explosives): CRB checks for schools: special driver training for airfields or off-road: FOD fences for airfield s etc

    - List any Environmental, Ecological, Archaeological constraints that may exist on or adjacent to the project area including any restrictions in respect of noise or vibration.

    - List any exceptional conditions that may apply e.g. exceptionally high security restrictions which require the contractor to undergo increased security clearance, known site closures/VIP visits. Airfield operations etc

    - List any restrictions that apply to deliveries, parking or the establishment internal traffic routing.

QUALITY MANAGEMENT

- The Contractor will provide as part of his works project tender submission an outline Project Quality Plan which will subsequently be developed in detail post contract award.  The Project Quality Plan shall be submitted to the Project Manager within four (4) working weeks of contract award.  The Project Manager may amend the period to suit the complexity of the project.

SITE ACCESS AND SECURITY

- Access to the establishment/site is strictly controlled and all personnel are required to hold appropriate MOD security passes. The Contractor’s personnel, including sub-contractors are to have undergone MOD security vetting to BPSS/SC/DV.  It should be noted that obtaining appropriate security clearance usually takes between six (6) and ten (10) working weeks.  The Contractor shall be responsible for obtaining security clearance for all his personnel and those in his supply chain. Security clearance is not guaranteed.  All personnel will be required to comply with local Security Standing Orders.

If the establishment has higher than normal MOD security requirements or the project is classified above ‘Official Sensitive’ this should be stated.

List any special/additional security requirements together with a statement of likely impact to the contractor’s delivery of the project.

- The Contractors personnel will be restricted to designated working areas and access routes and will not have access to other parts of the Establishment without express permission of the Employer.

List any local access restrictions that may apply e.g. vehicle weight limits, vehicle width or height restrictions, prohibited roads etc.

List any special/additional acess arrangements that may, or need to be, made e.g. discrete or temporary contractor/goods delivery site entrance, outside perimeter security fence, consents or easements etc.

- The Contractor shall notify in advance details of deliveries/subcontractors visiting the site to the Establishment Security Access Point and should allow for security escorts at appropriate security clearance as required to enable personnel and goods to gain access to the site.

- The use of cameras on the site is prohibited without the approval from the Project Manager or the Employer. Permitted photographs must not contain any images of personnel or military/sensitive equipment

- The Project Manager shall advise on the use of mobile telephones, notifying the Contractor of any specific restrictions in use.

SITE SAFETY AND PROTECTION

- The Contractor shall liaise with the Project Manager and establishment 4C representative in respect to compliance with H & S duties, roles and responsibilities and coordination of such throughout the life of the project.  The Project Manager is to:

List details of relevant points of contact, hierarchies and lines of communication.

List items the contractor will need to be familiar with or undertake such as site Fire Safety Plan, local emergency response procedures etc.

List and reference any specific items under the above requiring protective measures.

List any procedure necessary for reporting and repair of any damage arising under the above.

- The Contractor shall liaise with the Project Manager in regard to preparation and agreement of the following Schedules of Dilapidations: the Project Manager is to list the schedules required for:

- Roads, pavements and street furniture

- Car parking and hardstanding

- Landscaped areas

- Existing buildings and facilities

- Government Furnished Equipment

- Utilities and their infrastructure

- PA and sound systems

- Fixed equipment

- List any Schedules of Dilapidations required

- Trees

- And anything else that may be affected by the Works

- The Project Manager will provide the Contractor or Supervisor a Schedule for Maintaining Cleanliness of Road and Traffic Routes within the establishment utilised by vehicles transiting to and from the site.  The Schedule is at Annex  XXX

- The Contractor shall liaise with the Project Manager in respect to establishing a ‘good neighbour’ policy and how he will demonstrate this.  The policy the that the Contractor must allow for the following as a minimum:

The Project Manager is to list any specific requirements with regard to reducing nuisance or inconvenience factors arising from works activities such as close proximity to a school, hospital or critical operations facility etc. and responsibilities for resident/occupant liaison.

- The site boundaries and suitably fenced compound to the construction site(s) will be identified and agreed with the Project Manager or Supervisor prior to commencement of works.

- The Contractor shall identify with the Project Manager or Supervisor where a requirement to arrange for attendance of Authorised Persons or issue of Permits to Work in respect to the project.

APPLICATION OF CONSTRUCTION, DESIGN & MANAGEMENT REGULATIONS

- For the purpose of these regulations the Health and Safety Executive (HSE) is the enforcing authority on the MOD Estate.

- The Construction (Design and Management) (CDM) Regulations 2015 lay down the legal principles for the management of health, safety and welfare on all construction work, in particular these establish legal duties for:

  - The Client

  - The Principal Designer (including projects involving more than one designer or contractor).

  - The Principal Contractor (including projects involving more than one contractor)

  - Designers

  - Contractors

- The following appointments shall be made:

  - Client.  Within the various forms of contract managed by DIO, it is possible for Front Line Commands, DIO and DIO Contractors all to be considered as being a ‘Client’ as defined under the Regulations. In these circumstances, provision is made for one or more parties to agree to be treated as ‘the Client’ for the purposes of CDM 2015.  The Contract Form for the Project eg Contract Data Part 1 will identify who will be fulfilling the Client duty.

  - Principal Designer.  The Client must formally appoint a competent Designer to be the Principal Designer for the project. The Principal Designer is to be appointed as early as possible in the design process, if practicable at the concept stage (DPoW Stage 2) and to remain in place so long as there is a need for their role to be performed.

  - Principal Contractor is The Works Contractor in overall charge of the construction phase. They are appointed by the client and there should only be one Principal Contractor for a project at any one time.

SURVEYS

- Surveys undertaken relevant to this project include:

- The PM is to delete/add as appropriate and include survey reports as Appendices and to note whether or not the surveys come with collateral warranties or not:

Topographical

Geo-Technical

Building Condition

Building Services

Ground Investigation

Land Quality Assessment

Environmental Impact Assessment

Flood Risk Assessment

Structural

Dimensional

Condition

Asbestos

Hazardous Substances

Unexploded Ordnance

Drains (incl CCTV)

Archaeological

Habitat

Meteorological

Noise/Acoustic

- The Contractor is responsible for locating all services relating to, or affected by, the project, determining capacity and condition and for liaison with the relevant suppliers, including Aquatrine for water & waste water services, for connection, alterations to, or diversions of, any pipe or cable service.

THROUGH LIFE COST MANAGEMENT

- Where requested in the mini-ITT, the format and presentation of through life cost data shall be as the format supplied to meet specific MGBC criteria.  The information to be provided at tender will include:  the Project Manager to list here the key headings and the time period for review:

Works Cost

Professional Fees

Project Risk (50%)

Commercial Risk (50%)

Client Risk (50%)

Non-Recoverable VAT

Cost of Capital

Depreciation

Rates Rents

Training

MOD Staff Costs

Maintenance

Running Costs

Planned Maintenance Costs

Assumptions

Any other criterion depending on total estimated WLC value

- The cost data and approach to meet the Employer business case criteria shall be notified by the Project Manager.  This will form part of the completed design submission and will be updated as the project progresses to capture realised design changes and risks.  The completed document shall be submitted at completion of the work.  The following information shall be included:  the Project Manager to list here the key headings and the time period for review:

Actual Works Cost

Realised Project Risks

Realised Commercial Risks

Non-Recoverable VAT

Depreciation

Rates Rents

Training

MOD Staff Costs

Agreed Maintenance Regime

Running Costs

Maintenance Costs

Confirmed Assumptions

Other

CONTRACT RECORDS

- The Contract Records shall be retained for a period of Project Manager to insert number of years years after the expiry of the contract period.

- The Project Manager is to consider the appropriate length of the retention period and insert the required number of years.  The minimum requirement is 6 years for those projects without a compliance period and 7 years for those projects with a compliance period.

SUSTAINABLE DEVELOPMENT AND THE ENVIRONMENT

- The Contractor is to build upon and expand earlier Sustainability Appraisals undertaken and deliver appropriate detailed assessments. Ensure that appraisals and assessments reflect climate change predictions and likely risks, and that building designs allow for adaptation to potential impacts.

- The Contractor is to provide information and attend workshops for implementing insert assessment methodology at the detailed design and construction stage.  The Contractor will be responsible for achieving at least the following scores for these two separate stages.  These will be assessed at the end of Phase 2 (Design) and Phase 4 (Takeover) as more particularly set out in the Framework Performance Management Plan at Schedule 3 to the Framework Agreement.

The Project Manager is to refer to Stage 1 DREAM/BREEAM/CEEQAL assessment from Assessment Study and its outcomes.

The Project Manager is to refer to survey stage of the relevant assessment methodology selected for the project, continuing with the design, construction and operational stages as the project progresses.

Delete below as applicable, and insert at paragraph 56  the relevant or alternative assessment methodology appropriate to the project.

- Defence Related Environment Assessment Methodology 4 Construction (DREAM)

- Building Research Establishment Environment Assessment Methodology (BREEAM)

- Civil Engineering Environmental Quality Assessment and Award Scheme (CEEQUAL)

- The project manager is to specify the % scores the Contractor is required to achieve for this project at the Design and Takeover Stages recognising that the two scores may not be the same.

- The following ecological actions need to be undertaken by the Contractor.

The Project Manager is to identify other potential heritage or ecological requirements the Contractor may be required to undertake which could include:

- Gaining Scheduled Monument Clearance, Listed Building Consents or Conservation Area Consents or other consents on behalf of MOD, if required.

- Reporting finds of Treasure (gold or silver objects and coins) and other historic artefacts to the DIO Historic Environment Team.

- Ensuring any work is not detrimental to the heritage value of the asset or wider environment. The Contractor should look for opportunities to enhance heritage value.

- The Contractor is to use qualified, specialist staff when assessing or altering MOD heritage assets (i.e. accredited with the Institute for Archaeologists (IFA) and/or Institute of Historic Building Conservation (IHBC))

- When undertaking any archaeological excavation as part of Planning or temporary, enabling works activity etc, the Contractor (or sub-contractors) shall produce a project design for both excavation and post excavation work, including the publication and archiving of a report.

- Carrying out a Habitats Regulations Assessment (if the development is likely to affect a European designated site or species)

- Carrying out ecological survey work, to identify risks to designated sites or protected species prior to commencing works (if ecological issues are not known in the site information pack).

- Applying for SSSI assents / consents on behalf of MOD or protected species licenses as appropriate.

- Implement control or eradication measures for pests and invasive species.

- Preparation of tree surveys, including tree constraints plans. arboricultural implications plan and arboricultural method statements.

The Project Manager is to list any requirements for the protection of flora, fauna and trees including details of species habitat locations, breeding periods etc and requirements for relocating, re-establishing or compensating etc.

- The Contractor is to provide a suitable Site Management Plan, to demonstrate how environmental risks have been identified and will be managed, including method statements for handling specific risks involving e.g. heritage assets, protected habitats and species or hazardous materials. The Site Management Plan shall allocate adequate space and access for the safe movement, appropriate storage and segregation of construction plant, materials, components, site fabrication or production activities and removal of site waste.  See paragraph 60 for recycling material arising from the works.

- The Project Manager is to list any requirements or details to comply with Site Waste Management Plan Regulations 2008 and/or any other relevant legislation and requirements for recycling, re-use or salvage etc.

- The Contractor is to ensure that environmental incidents and near misses on MOD sites are reported to the Project Manager and that there is collaboration with the Employer to support investigations and identify remedial actions or improvements to working practices

- the Contractor is to ensure that designs for new buildings and major refurbishments go beyond Building Regulations compliance and meet industry benchmarks and good practice in water efficiency (e.g. WRAP Code of Practice for water efficiency):

  - Install water meters in new buildings to enable consumption to be monitored.

  - Report data to the Authority on water and energy used during the construction phase.

  - Install electricity and gas meters in new buildings so that consumption can be monitored. Meters to be compatible with MOD’s wider automated meter readings (AMR) and data reporting systems.

- The Project Manager is to provide details of the AMR and data reporting systems.

- The Contractor to ensure and demonstrate compliance with Government Buying Standards for relevant materials, products and components.

- The Contractor to ensure and demonstrate that all timber and timber-containing products are from sustainable sources and legally harvested / traded, and that custody / audit trail documentation is retained for audit purposes in accordance with Appendix 3 to Annex I (Timber and Timber Containing Products).

- The Climate Change Act sets a legally binding requirement for the UK to achieve “net zero” greenhouse gas emissions by 2050.  “MOD Policy Infrastructure 01/20 - Infrastructure Function Estate Policy” sets out how MoD will support of a Net Zero Transition. MOD policies must be applied through the lens of transitioning to 'net zero' through minimising energy consumption and greenhouse gas emissions.

- JSP 850 sets out Sustainability in Infrastructure Management and Design Development through; Sustainability Appraisal, Environmental Performance Assessment, Climate resilience, Through Life Costs, Cost of Carbon, Construction Pipeline and Data, Energy Management Plan, Site Waste Management Plans, Life Water Costs and Government Soft Landings.

ISSUED PROPERTY

- The Contractor shall be responsible for calibration and maintenance of the Issued Property as listed below:

- The Project Manager is to list here all the Government Furnished Equipment that will be provided for use by the Contractor and/or inclusions in the Works.

- Issued Property will not normally be replaced and the cost of providing alternative equipment shall be included in the Contract.  However, exceptionally if Issued Property is deemed necessary by the Project Manager and needs to be replaced during the course of the Contract, the cost of replacement will be funded by the Employer.

MATERIALS ARISING FROM THE CONTRACT

- Materials arising from excavation and demolition will become the responsibility of the Contractor and are to be removed from site.  Unless stated otherwise the following arisings may be stored on a suitable location within the Establishment for use for in other Works:

- PM to list here the materials and volumes that may be retained by the Employer for incorporation into other Contracts:

- Crushed brick rubble

- Crushed road planings

- Crushed concrete

- etc

- The PM will list here the locations for storage:

- Location A

- Location B

- Location C

- And any special storage requirements (bunding, containment etc)

TAKEOVER PROCESS

- A formal structured Takeover of the Project shall be provided by the Contractor to fully comply with the following takeover process.

  - The PM will specify the takeover process as either that set out in Schedule 7 of the Framework Agreement or a different process if the project is on an  OGD or USVF establishment.  In this case a copy of that process will be supplied.

  - For MOD as detailed in the Schedule 7 of the Framework Agreement.  For USVF and OGD establishments other such mandated processes, and agreed by the Project Manager the relevant takeover process for each project will be specifically identified in Works Information & Site Information.

- Dependent upon the project contractual arrangements this may need to take account of 2 distinct and separate Takeover processes occurring at:

  - The end of construction for occupation.

  - The end of the compliance period for transfer to the Regional Prime Contractor who then assumes responsibility for future operation and maintenance.

  - Prior to Takeover under each process a Schedule of Defects shall be agreed with the Project Manager. For each scenario the Contractor retains his obligation to rectify any defects or omissions occurring under a 12 calendar months Defects Correction Period.

GOVERNMENT SOFT LANDINGS

- Whilst overall responsibility for the delivery of the project shall remain with the DIO PM and/or the Employers representatives, the Works Contractors, as part of the design function along with the appropriate project stakeholders, shall provide support in delivery of GSL in accordance to the GSL Guidance.

- The Works Contractors, shall provide a GSL Point of Contact (PoC) for each call off issued under the Framework.  This individual will liaise with the Authorities GSL Champion and GSL Focal Point.

- GSL Reviews are required to be completed by the Works Contractor and the DIO Project Manager at the end of each DPoW Stage.

- The PM is to provide the schedule of reviews

- The PM shall provide the MOD Government Soft Landings Guidance

- The Works Contractor is to provide evidence that the policy and guidance is being incorporated.

PROJECT INTERFACES

- The key project interfaces and main Points of Contact are at detailed at Table 1 including Utility suppliers.

- The PM is to insert relevant details at Table 1

- Other projects/programmes or major infrastructure works that may impact upon the project, or that the project may impact upon, such as SLAM, Aquatrine etc on the MOD estate, that are in progress or planned during the course of the project.

- The PM is to list any of the aforementioned where an impact on or by the project may arise.

- Liaison with external stakeholders, including Local Planning Authority should only be conducted after prior consultation with the Project Manager.

Table 1  Key Project interfaces

| NEC ROLE INTERFACES |  |  |  |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Employer |  |  |  |
| Supervisor |  |  |  |
| MOD/DIO ROLE INTERFACES |  |  |  |
| Senior Site /End User Reps e.g. QM/RQMS |  |  |  |
| Site/Establishment Reps e.g Comdt/CO |  |  |  |
| DIO Service Manager |  |  |  |
| Prime Contractor Senior Delivery Manager |  |  |  |
| Defence LMS Rep |  |  |  |
| DIO Construction Economy Team Quantity Surveyor |  |  |  |
| DIO Risk Manager |  |  |  |
| DIO H & S Advisor |  |  |  |
| Establishment 4C’s Representative |  |  |  |
| Establishment Environmental Focal Point |  |  |  |
| Establishment Security Officer |  |  |  |
| MOD Fire Officer |  |  |  |
| SCIDA |  |  |  |
| ESTABLISHMENT UTILITY PROVIDERS |  |  |  |
| Water and Sewerage- | Aquatrine Package No. |  |  |
| Electricity |  |  |  |
| Gas |  |  |  |
| Telephone |  |  |  |

PART 2 – SITE INFORMATION

SITE LOCATION

- Insert details of the Site Location identifying general features, Establishment name address etc including post code and OS grid reference. Identify on Location Plans project site boundaries, areas excluded to the contractor for operational or other reasons etc.

Information is at Appendix… to Annex …. (Site Location).

The Project Manager to list appendix included

SITE INVESTIGATION

- Insert details on any sub soil investigation, land quality assessments, borehole or trial pit records and location plans, including water table levels or any other relevant records/ reports relating to site investigation.   Insert details of Establishment Pollution Risk.

Information is at Appendix… to Annex …(Site Investigation)

The Project Manager to list appendix included

REPORTS AND SURVEYS & OTHER LOCALLY HELD DATA

- Insert details of any reports, surveys and other site data undertaken/commissioned or collated by the Employer in respect to the physical characteristics of the Site and its surroundings and date undertaken or published.

The Project Manager is to list any relevant reports, surveys and locally held data which may include:

- Topographic surveys

- Previous Construction H&S files or ‘as built’ information

- Contamination surveys

- Arboricultural reports

- Archaeological reports and management plans

- Hydrological/Hydrographic data

- Asbestos/hazardous materials register

- Party wall & rights of light details

- Building condition surveys/dilapidations

- Site plans or mapping – including footpaths and rights of way.

- SSSI or other habitat and protected species surveys and management plans

- Site Climate Risk Assessments (CIRAM) or climate adaptation plans if completed

The Project Manager is state whether or not these surveys come with collateral warranties or not.

Information is at Appendix…to Annex…. (Reports and Surveys)

The Project Manager to list appendix included

PUBLIC INFORMATION

- Insert details of any known publicly available information in regard to the site and its surroundings to assist the Contractor to undertake further research or make his own interpretation of the data available.

The Project Manager is to list any publicly available information relating to the establishment, site and surroundings which may include:

- Historic uses of the site

- Geological information

- Academic research/study papers

- Local development plans

- Previous planning applications submitted

- Meteorological information/data (including future climate predictions e.g. UK Climate Impact Prediction data e.g. UKCIP 2009)

Information is at Appendix…to Annex …(Public Information)

The Project Manager is to list appendix included

BURIED PLANT

- Insert details of known or suspected buried plant.

The Project Manager is to Insert details of known (or suspected) buried plant or service ducts which may include:

- Buried tanks

- Capped wells

- Service ducts for steam heating

Information is at Appendix… to Annex (Buried Plant)

The Project Manager is to list appendix included

BURIED PIPE & CABLE SERVICES

- Insert details of buried pipe and cable services.

The Project Manager is to insert details of known (or suspected) buried plant or service ducts which may include which may include:

- Foul and/or surface water drainage

- Gas mains

- Water mains

- Telecommunications

- Fibre optic cables

- Fuel lines

- Electricity mains indicating voltage classification

Information is at Appendix…to Annex (Buried Pipe and Cable Services)

The Project Manager is to list appendix included

ADJACENT BUILDINGS, STRUCTURES OR PLANT

- Insert details of adjacent buildings, structures or plant (including the heritage value or any protected species / habitat interest)

The Project manager is to insert details about buildings, structures and/or plant adjacent to, or situated on, the actual site which may include:

- Electricity substation

- Gas pumping stations

- Boundary fences/walls etc

- Bridges

- Buildings & basements

- Towers and masts

Information is at Appendix… to Annex … (Adjacent Buildings, Structures or Plant)

The Project Manager is to list appendix included

NON MOD OWNED BUILDINGS AND ESTATE

- Insert details of non MOD owned property or estate.

The Project Manager is to insert any details of non MOD property or estate in respect to Title or any other such relevant information which may include, but not necessarily restricted to;

- Hirings

- Lettings

- Wayleaves & Easements

- Casual use

- Public rights of way / permissive access

- Any known unauthorised occupations / boundary disputes

- Statutory designations (archaeology and wildlife)

- Planning status – LDF & any extant / lapsed planning permissions

- Strategic docs/plans & management plans affecting the site (should include forestry and woodland)

- Byelaws

- Neighbouring issues

- Key stakeholders & issues

- Misc local info e.g. contamination, flooding, local ‘projects’ e.g. community etc.

- Energy Performance Certificates

Information is at Appendix…to Annex …..(Non MOD Owned Buildings and Estate)

The Project Manager is to list appendix included

COMPLIANCE PERIOD SPECIFIC INFORMATION

- Insert details of compliance period specific information

- Operational Need of Asset

- Establishment Specific Task Schedule

- Establishment Specific Preventative Maintenance Tasks

- List of Reports for Compliance Regime

- Site Inclusive Repair Limit

- Helpdesk Standing Instructions

OTHER SITE SPECIFIC INFORMATION

- Other relevant site specific information.

The Project manager is to include here any relevant site information not deemed to sit under previous headings

AVAILABILITY & ACCESS TO SITE INFORMATION

- In addition to any information provided the Framework Contractor, can by arrangement with the Project Manager, access all relevant site information through the offices of the establishment Prime Contractor. Details are as follows:

- Company

- Office Address

- Named POC

- Tel No

- APPENDIX 1 to Annex I Contents of a Typical Works Contract Project Specification

1. Architectural Requirements

1.1 General

1.2 External Architecture

1.3 Interior Finishes

1.3.1 General

1.3.2 Walls

1.3.3 Floors

1.3.4 Ceilings

1.3.5 Fixtures and Fittings

1.4 Sound Insulation

1.5 Signage

1.6 Hard and Soft Landscape and External Lighting

2. Structural Engineering Requirements

2.1 General

2.2 Structural Form

2.3 Counter Terrorist Measures (CTM

3. Civil Engineering Requirements

3.1 General

3.2 Foul Drainage

3.3 Hydrogeology

3.4 Surface Water Drainage

3.5 External Works

3.5.1 Roads and Footways

3.5.2 Demolition

3.5.3 Service Diversions

3.6 Contractors compound

3.7 Landscaping works

4. Building Services Requirements

4.1 General

4.1.1 Standards

4.1.1.1 Environmental Design Standards

4.1.2 Scope of Works

4.1.3 Sequence of Works

4.1.4 Works to existing Facilities

4.1.5 Electrical Design Calculations

4.1.5.1 Maximum Demand calculations

4.1.5.2 Cable calculations

4.1.5.3 Lighting calculations

4.1.5.4 Cable Containment

4.1.6 Sub Contractor’s Design Compliance

4.1.7 Co-ordination

4.1.8 Fire-Stopping, Noise Transmission and Weatherproofing

4.1.9 Fire Strategy

4.1.10 Loads, Diversities and Spare Capacities

4.1.11 Services Installation Life

4.1.12 Full Life Cycle Costing

4.1.13 Asset Register

4.1.14 Handover Requirements

4.1.15 DREAM Assessment

4.1.16 Spares and Tools

4.1.17 Contractor’s Drawings

4.1.18 Design Reviews

4.1.19 Services Support

4.1.20 Maintenance Access

4.1.21 Earthing Down

4.1.22 Applicable regulations

4.1.23 Insurance Inspections

4.1.24 The Provision and Use of Work Equipment Regulations 1998 (PUWER)

4.1.25 Mounting Heights

4.1.26 Existing Infrastructure, Permit to Dig, Permit to Work

4.2 Site Infrastructure Alterations

4.2.1 Location of Existing Services

4.2.2 High Voltage Cabling

4.2.2.1 General

4.2.2.2 HV Ring Main

4.2.3 Low Voltage cabling

4.2.3.1 General

4.2.3.2 Unknown services

4.2.3.3 Supply to Building

4.2.4 British Telecom

4.2.5 Closed Circuit Television

4.2.6 Comms. Connectivity

4.2.7 Fire Alarm Remote Transmission

4.2.8 Building Management System (BMS) Remote Transmission

4.2.9 Remote Metering System

4.3 Infrastructure Connections

4.3.1 Potable Water Supplies

4.3.2 Electrical Supply

4.3.2.1 General

4.3.2.2 Main Cable

4.3.2.3 Grading

4.3.2.4 Distribution Sub Station Log Books

4.3.3 New Communications Infrastructure Connections and Cabling

4.3.3.1 General

4.3.3.2 Internal Backbone Cabling

4.3.4 Building Management Systems Infrastructure Connections

4.3.5 Metering System

4.3.5.1 General

4.3.5.2 Commissioning

4.3.6 Fire Alarm Infrastructure Connections

4.3.7 Mass Notification / Public Address (PA) Infrastructure Connections

4.4 Internal Mechanical Installations

4.4.1 Ventilation

4.4.1.1 General

4.4.1.2 Toilets

4.4.2 Heating

4.4.2.1 General

4.4.2.2 Pipework and Fittings

4.4.3 Domestic Water Services

4.4.3.1 General

4.4.3.2 Cold Water Distribution

4.4.3.3 Hot Water Systems

4.4.4 Above Ground Foul Drainage

4.5 Internal Electrical Installations

4.5.1 Mains Distribution

4.5.1.1 General

4.5.1.2 Main Switchboard

4.5.1.3 Metering

4.5.1.4 Labelling

4.5.1.5 Power Factor Correction (PFC

4.5.1.6 Transient Voltage Surge Suppression

4.5.1.7 Fireman’s Switch

4.5.1.8 Signage

4.5.2 Sub Mains Distribution

4.5.2.1 General

4.5.2.2 Sub Main Cables General

4.5.2.3 Sub Main Cable Containment

4.5.2.4 Cable Containment Support Work

4.5.3 Sub Circuit Management

4.5.3.1 Distribution Boards

4.5.3.2 Sub Circuit Cabling

4.5.3.3 Labelling

4.5.3.4 Trunking

4.5.3.5 Conduits

4.5.3.6 Dado Trunking

4.5.3.7 External Cabling

4.5.4 Lighting

4.5.4.1 General

4.5.4.2 Lighting Design Parameters & Calculations

4.5.4.3 Lighting Design Requirements to Specific Areas

4.5.4.4 Luminaires

4.5.5 Lighting Control

4.5.5.1 General

7.5.5.2 Lighting Control Requirements to Specific Areas

4.5.6 Emergency Lighting

4.5.6.1 General

4.5.6.2 Testing System

4.5.6.3 Commissioning

4.5.7 External Lighting

4.5.7.1 General

4.5.7.2 Footpath Lighting

4.5.7.3 External Plant Compounds

4.5.8 General (Utility) Power

4.5.8.1 General

4.5.8.2 BS 1363 Socket Outlets

4.5.8.3 Plant Rooms

4.5.9 Building Fittings

4.5.9.1 General

4.5.9.2 Window Actuators

4.5.9.3 Local Mechanical Services Plant

4.5.9.4 Rainwater Harvesting

4.5.9.5 Trace Heating

4.5.9.6 Hand Dryers

4.5.9.7 Taps

4.5.10 Communications

4.5.10.1 Structured Cabling – General

4.5.10.2 Equipment Installation

4.5.10.3 Structured Cabling Containment - General

4.5.10.4 Active Equipment

4.5.11 Mass Notification and Public Address (PA) System

4.5.11.1 General

4.5.11.2 Control Equipment Main System

4.5.11.3 Speakers

7.5.11.4 Cabling

4.5.12 Bomb Alert System

4.5.13 Security Systems

4.5.14 Ventilation Shutdown

4.5.15 Lightning Protection System (LPS)

4.5.15.1 General

4.5.15.2 Air termination

4.5.15.3 Down conductors

4.5.15.4 Earth electrodes

4.5.15.5 Existing Building

5.5.15.6 Transient Voltage Surge Suppression (TVSS)

4.5.16 Earthing (Grounding)

4.5.16.1 General

4.5.16.2 Building Service Plant Rooms

4.5.16.3 Bonding Conductors

4.5.16.4 Supplementary Bonding

4.5.17 Disabled Alarms

4.5.18 Leak detection

4.6 Fire Detection, Alarm and Suppression

4.6.1 Fire Detection and Alarm

4.6.1.1 General

4.6.1.2 Mimic Diagram

4.6.1.3 Auxiliaries

4.6.1.4 Fire Doors

4.6.1.5 Initiation Points

4.6.1.6 Fire Alarm Sounders/Beacons

4.6.1.7 Cabling

4.6.2 Fire Suppression Systems

4.6.3 Commissioning and Soak Test

4.7 Building Management System

4.7.1 General

4.7.2 Points

4.7.3 Connection to Head End

4.7.4 Local Control Panel

4.7.5 Meters

5. General Requirements

5.1 Design Requirements

5.2 Use of Hardwood

5.3 Robustness

5.4 Kitemarked Products

5.5 Architectural Compatibility

6. Project Constraints

6.1 Adjacent Building Use

6.2 Site Constraints

6.3 Carrying Out the Works

6.4 Work Clearance Requests

6.5 Topography and Land Use

6.6 Ground Conditions

6.7 Contamination

6.8 Archaeological Interest

6.9 Ecology

7. Town Planning

7.1 Support for Archaeological Investigations

7.1.1 General Items

7.1.2 Method of Excavation

7.1.3 Subsequent Delays

8. Design Life

9. Liaison with Agencies acting for the Authority

10. Health and Safety Requirements

11. Sustainability and Environment

11.1 DREAM Ratings

11.2 Policy

11.2.1 General Waste Requirements

11.2.2 Site Environmental Requirements

11.2.2.1 Solid Waste

11.2.2.2 Hazardous Materials

11.2.2.3 Hazardous Waste

12. Defects Liability

13. Compliance Period (Where Required)

DEEP information can be found at http://www.mod.uk/DefenceInternet/MicroSite/DIO/OurPublications/EstateAndSustainableDevelopment/DesignExcellenceEvaluationProcessdeep.htm

Due to be subsumed into JSP 850 sometime during 2021.

Although JSP 315 Scales of Accommodation are not mandatory or an automatic entitlement they are a proven method of ensuring compliance with functionality/operability and they will be used by the DIO Project Manager for benchmarking purposes. Proposals that deviate from these scales must be clearly identified and supported by valid justifications that provide demonstrable additional benefits to functionality/operability/cost.

https://www.dreamassess.com/