Invitation to Quote (NFNPA – 0044)

Demand for recreation in the New Forest

Summary

During the summer of 2018, the New Forest Recreation Management Strategy Steering Group (RMS Steering Group) intends to consult the public on draft proposed actions for an update to the New Forest National Park Recreation Management Strategy 2010-2030.

To help ensure that draft actions are appropriate the RMS Steering Group is commissioning a consultant to provide updated information on the numbers of people coming to the New Forest National Park to engage in recreation, and the degree to which this has changed and is likely to change in the future. This will help inform draft actions as partner organisations seek to achieve a net gain for the working and natural landscape and for the recreational experience.

Background

The 2004-5 Tourism South East survey calculated that the New Forest received a total of 13.5m day visits, of which 60% were day visitors (many very local in origin) and 40% were staying visitors (from further afield). Many people now believe that visitor numbers have increased significantly since that time.

In 2008 Sharpe et al assessed the impacts of new development on visitor numbers to the New Forest and predicted an additional 1.05 million person visits per annum in the period 2006-2026. Similar work has been done on the joint mitigation strategy being adopted by the 15 local planning authorities along the Solent Coast.

This contract seeks to identify and quantify ‘indicators of change’ that can be used alongside the data about new development. Together, the data can be applied to the results of the 2004-5 survey to produce updated estimates of the number of visits to the New Forest National Park now, and the changes that can be expected in the future.

Recent changes also need to be set in the context of changes that have been happening for many years (e.g. since the 1970s when car parks were first created in the New Forest) and compared with national trends.

The demand for recreation report will also help inform a review of the ways in which information is provided to visitors to help them enjoy their time in sustainable ways because it will help put into context the different challenges associated with engaging with different audiences.

For reference, information about the 2017 Recreation Management Strategy ‘Future Forest’ consultation and the two reports about this consultation (Findings Report and Next Steps Report) are available on the NPA website www.newforestnpa.gov.uk/futureforest.

RMS Steering and Advisory Groups

This brief was drawn up by the RMS Steering Group, which comprises representatives from the Forestry Commission, Verderers, Natural England, New Forest District Council, Hampshire County Council and New Forest National Park Authority (NPA). The contract is being commissioned by the NPA and is jointly funded with other members of the RMS Steering Group.

There is a wider RMS Advisory Group which has representatives from an additional 10 organisations and forums. The consultant should be independent of the organisations on the RMS Steering and Advisory Groups and provide an objective assessment. The RMS Advisory Group is made up of the steering group members plus the Commoners Defence Association, Equine Forum, Hampshire & Isle of Wight Wildlife Trust, National Trust, New Forest Association, New Forest Dog Owners Group, New Forest Access Forum, Go New Forest CIC, Ringwood & Fordingbridge Footpath Society, RSPB and the Cycle Working Group

The work will largely be a desk based assessment of sources of existing information, but will require some direct contact with organisations on the RMS Steering and Advisory Groups in order to acquire and/or verify data and evidence that they hold.

Budget and Timescale

There is a budget of up to £8k (exc. VAT) for this contract.

The public consultation will take place in June, July and August 2018, but the recreation demand report will be needed in advance of this to aid the formulation of the draft actions and to ensure all the consultation documentation is assembled in time.

The proposed timescale is therefore as follows:

- 18 May Successful contractor notified

- w/c 28 May Initial meeting with contractor to confirm scope and nature of the work

- 14 June Initial draft report completed and provided to the NPA

- 21 June Steering Group comments on draft report provided by NPA

- 28 June Amended report completed and provided to the NPA

- 5 July Steering Group comments on amended report provided by NPA

- 12 July Final report completed and provided to the NPA

Style and content of the report

The report may be published as a background paper to support the public consultation on recreation management and its headline conclusions will be of significant public interest. The report must therefore be both ‘accessible’ (e.g. through the use of tables, graphs and diagrams) and provide sufficient detail to satisfy those who wish to read more or scrutinise the data and evidence used.

The report should include:

- an updated estimate of the current number of day visits to the New Forest National Park, including a breakdown of its component elements (e.g. day versus staying visitors)

- estimates of the number of people where possible

- predictions for changes that should be expected over the next 20 years

- basic analyses of the relationships between these ‘day visits’ and numbers of people visiting at different frequencies, at different times of year and for different purposes – and from this the types of recreational impacts that may be helped or exacerbated

- the methodology by which the above estimates were calculated (i.e. the ‘indicators of change’ used)

- a commentary that puts the estimates in a historical setting (since the 1970s) and explains the key drivers for any changes (e.g. national trends, local house building)

Because the report is for use online, the use of hyperlinks to other reports and sources of information will avoid unnecessary duplication and help keep the report concise.

Sources of data and evidence

The report should draw together and analyse relevant existing data and evidence. Much of this has already been analysed and made available to the public, for example to support the development of Local Plans and mitigation strategies. However, other relevant information will need to be collated from various organisations and analysed to extract useful information.

The table below lists possible sources of data and evidence that could be considered in the production of the report. It is not meant to be exclusive, and the contractor should use their own knowledge to revise and supplement this list.

| Data / evidence topic | Options / sources | Comments |
| --- | --- | --- |
| Number of people visiting the New Forest for different reasons | - TSE 2004/5 Visitor Survey - STEAM reports for ‘leisure visits’ (via NPA) - Cambridge model tourism reports (via NPA) - Camp site occupancy (Camping in the Forest, via FC) - VisitEngland Great British Tourism Survey (VisitEngland) - Regional accommodation occupancy model - Key attractions visitor data (inputs to STEAM) via NPA and via VisitBritain here - Visitor and residents surveys (via NPA) - Audience Development Plan: Our Past, Our Future Partnership | - See notes on differences between STEAM and Cambridge models |
| Road traffic / use of cars since 1970s when current network of car parks was established | - National data from DfT and Office of Rail and Road - Local car parking data (NFDC) - Traffic counts on local network (HCC) - Traffic counts for A31 and A36 (Highways England, online) | - Some NFDC car parks are less popular with local people and used more by visitors (without parking clocks) than others - NPA has some traffic count data from HCC - Data on use of FC car parks are not currently available |
| Use of public transport | - Railway station entries/exits (Office for Rail and Road, online) - NF Tour passenger journeys (Go South Coast, via NPA) - Beach Bus passenger journeys (Go South Coast, via NPA) | - See NPA visitor and residents surveys for evidence of modal shift away from cars |
| Number of local people / dogs walking in heathland areas during the winter | - Winter Bird Survey data – NPA partial analysis of HOS data |  |
| Cycling | - Cycle hire data (cycle hire shops – via NPA) - Visitor surveys in other National Parks (via NPA) - Cycling UK, Sustrans and British Cycling data - On road and off road cycle counter data | - FC data include permitted and non-permitted routes |
| Number of residents living within reach of sensitive / designated sites | - Local Plan housing allocations - Population census data |  |
| National trends | - National economy? - Lifestyle changes? - Modal shifts? - MENE |  |
| State of the Park Report | - NPA website | - Various data and trends |

Skills and experience required

The consultant will need to demonstrate the following blend of skills and experience:

    - ability to calculate and forecast visitor numbers in a robust way from a variety of secondary sources

    - ability to summarise complex information in clear and accessible ways

    - understanding of the New Forest’s visitor economy and the ways in which different datasets are used to calculate visitor numbers

    - understanding of the ways in which local people enjoy recreation across the New Forest and how this can cause impacts on the environment, local people and the ‘working Forest’

    - experience of undertaking similar projects in rural destinations / protected landscapes without clear pay barriers

    - ability to complete the brief within the allocated time and agreed budget

Submission

Prospective suppliers should:

- Outline your approach to delivering this brief, in consideration of the skills and experience for the requirements listed above, demonstrating how you can add value to the tasks listed

- Outline your experience of delivering briefs of a similar nature, if possible  through examples of prior similar work

- Present your proposed timeline for completing this project

The Authority proposes to pay 25% of the budget upon commencement of the project, with further equal stage payments being made at suitable agreed points in the delivery of the project. Tenderers should outline if they wish to propose a different payment schedule to this, noting that any proposed amendments will be subject to the evaluation process.

A copy of the Authority’s Standard Conditions of Contract for Services can be found below:

Please note that the Authority will not be liable for any costs incurred in the preparation of proposals or any associated work effort.

All submissions can be made via our e-Procurement portal In-tend and must be submitted by 12noon on Friday 11 May.

Any queries must be made via the In-tend portal and any subsequent clarifications will be notified likewise (you will receive email notification from the In-tend system should this be the case).

For queries relating to the procurement process, please contact:

Chris Pathmadeva

Finance and Procurement Officer

New Forest National Park Authority

chris.pathmadeva@newforestnpa.gov.uk

Direct Line: 01590 646678