## DEFFORM 10B

(Edn 05/23)

|  |  | Name REDACTED |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Commercial Manager St George’s House DMS Whittington Lichfield Staffordshire WS14 3PY |  |  |  |
| IBM United Kingdom Limited PO Box 41 North Harbour Portsmouth Hampshire PO6 3AU |  |  |  |  | Your Reference:. Our Reference: 707960451. Date: 27 October 2023. |
| For the attention of: REDACTED Senior Managing Consultant |  |  |  |  |  |

Dear REDACTED

## Contract 707960451 for the Provision of Tririga Cloud Migration POC from IBM United Kingdom Limited (“Contract”) Amendment Number One

Reference’s:

- IBM G Cloud 13 CCN Outstanding Changes CR4 250923 Dated 25 September 2023.

Background

- With reference to and in accordance with the abovenamed Contract, the Authority has agreed to amend the Contract in order to undertake:

•	Amendments to the scope of the CP&F Integration

•	Removal of the CAFM Integration from delivery scope with design updates to reflect the preferred position of CAFM-ACE on MODCloud to be provided

•	Changes to timescales of the Build & Test Phases due to DIO delays in completing environment set-up.

- The amendment will in accordance with the enclosed Contract Change Notice as prepared by IBM,

- Unless otherwise defined in this contract amendment letter, terms defined in the Contract shall have the same meaning when used in this contract amendment letter.

Amendments to Contract

- The Contract shall be amended as follows:

  - As per the enclosed Contract Change Notice as prepared by IBM.

  - Milestone Payment Schedule amended as follow:

| ID | Milestone | Date | Value |
| --- | --- | --- | --- |
| 1b | Design Document Updates – CP&F and CAFM | 29th September 2023 | REDACTED |
| 2a | Completion of TRIRIGA Migration to TAS | 6th October 2023 | REDACTED |
| 2b | Build Phase Completion | 24th October 2023 | REDACTED |

- The total value of this contract amendment is £14,220.00 ex VAT.

- The current overall contract value for the Contract will be amended to £604,427.50 ex VAT.

Effective Date

- The Contract shall be amended on the terms set out in paragraph 3 above with effect on and from the date on which this contract amendment letter is countersigned by the Contractor (the Effective Date).

Continuity

- All other terms and conditions of the Contract remain unchanged and the Contract shall, save as amended by this contract amendment letter, continue in full force and effect.

- With effect on and from the Effective Date, the Contract and the amendment set out at paragraph 3 above shall be read and construed as one document.

- Save for the amendments set out in paragraph 3 above, nothing in this contract amendment letter shall be deemed to be an amendment to the terms of the Contract or a waiver or consent by the Authority to any breach or potential breach (present or future) of any provision of the Contract or any waiver of any default which arises on or after the date of this contract amendment letter. Nothing in this contract amendment letter shall prejudice the Authority’s rights under the Contract.

Governing Law and Jurisdiction

- Clause 11.9 (Law and Justification) of Framework RM1557, English Law applies.

- Please sign and return the enclosed copy of this contract amendment letter within ten (10) Business Days of the date of this letter to confirm your acceptance of and agreement to the amendments to the terms and conditions of the Contract.

Yours sincerely

| Signature |  |
| --- | --- |
| For and on behalf of the Secretary of State for Defence |  |
| Name and Title | REDACTED |
| Date | 27 October 2023 |
| We acknowledge and confirm our agreement to the terms of this letter of which this is a copy. For and on behalf of the Company Name [insert company name in full] |  |
| Name, Title and Company Position |  |
| Signature |  |
| Date |  |