## Sheet1
Nepacs Circles of Accountability and Support
Mobilisation and Year One Delivery Plan - NORTH EAST REGION
|  |  | Award | Mobilisation |  |  |  | Year One
| Activity | Person(s) Responsible | Nov |  | Dec | Jan | Feb | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Governance
1 | Award | Commissioners
2 | Standstill | Commissioners
3 | Call-off contract signed | CEO/ Commissioners
4 | Inform key staff and stakeholders | CEO
5 | Confirmation of project mobilisation manager - | CEO
6 | Agree small mobilisation working group to include , DSLs and, Family Worker Lead | CEO
7 | Nomination of Board sponsor - nominated Trustee to take lead at Board level | Chair
8 | Nominate members of Board Sub-Committee membership | Chair
9 | Kick-start meeting with mobilisation team | Project Lead
10 | Review of detailed project plan with update of any changes | Project Lead
11 | Finalise project plan with SLT and Board Sub-Committee | CEO/ Project Lead
12 | Review and update RAID log | CEO/ Project Lead
13 | Weekly updates to project plan/ RAID log | Project Lead
14 | Provide weekly written updates to Probation Director and other key stakeholders | Project Lead
15 | Establish internal team meetings schedule | Project Lead
16 | Agree SLT/Board reporting arrangements for forthcoming year | CEO | bar: Year One Jan
17 | Develop and agree Critical Function List to minimise disruption of a COSA in the event of staff shortgages and sickness | Project Lead | bar: Year One Jan
18 | Update business continuity plan to include Circles service | CEO/ Project Lead | bar: Year One Dec to Year One Jan
Probation and Commissioner engagement
1 | Kick-start meeting between CEO/Project Lead and Commissioners | CEO/ Commissioners
2 | Kick-start meeting with Regional Probation representatives | CEO/ Project Lead
3 | Commissioners/Probation representatives meet key staff to be involved in mobilisation and delivery | Project Lead
4 | Joint review of any imminent issues/challenges and discussion surrounding mitigations | Project Lead
5 | Joint review of detailed project plan and identification of any changes required | Project Lead
6 | Finalise project plan with commissioners | Project Lead
7 | Joint review and update of RAID log | Project Lead
8 | Establish weekly review meeting schedule with commissioners | Project Lead
9 | Agree communication and reporting arrangements | Project Lead
10 | Agree SLA with Probation | Project Lead
11 | Agree ISA with Probation | Project Lead
12 | Agree and confirm referral processes including referral criteria and accompanying documentation | Project Lead
13 | Confirm risk management processes and safeguarding escalation procedures | Project Lead
14 | Reconfirm Probation Service's cyber, information assurance and data processing requirements | Project Lead
15 | Create and agree Information Security Management Plan | Project Lead
16 | Confirm Probation vetting requirements for staff and Volunteers and reporting/ recording arrangements | Project Lead
17 | Agree KPI Performance Reporting systems | Project Lead | bar: Year One Jan
Stakeholder engagement
1 | Initial contract award/ introductory communications sent to stakeholders by commissioners/ Nepacs communications team as agreed | CEO
2 | Circles UK introduce CEO, Project Lead and other staff to key stakeholders across Region, where not yet known to Nepacs as already agreed | CEO/Circles
3 | Make informal contact with Safeguarding Leads, Social Services, Prisons, Police, PCCs and other key contacts across Region | CEO
4 | Visits to key contacts by Dawn Simpson, Service Lead | Project Lead
5 | Agree with Probation and Circles UK the 'core' organisational membership of any Outer Circles | Project Lead
6 | Ensure all stakeholders are aware of the agreed referral processes via Probation | Project Lead
7 | Nepacs staff to provide stakeholders with briefing son the Circles programme | Project Lead | bar: Year One Feb to Year One Mar
8 | Invite stakeholders to attend Circles training sessions to provide further knowledge of the programme | Coordinator/ Training Lead | bar: Year One Feb to Year One Mar
Membership/ Accreditation finalisation
1 | Review checklist of outstanding actions (Sept-October) including updated Volunteer Policy and Handbook | Coordinator
2 | Joint review of paperwork with fellow providers, especially HumberCare to ensure sharing of best practice | Coordinator
2 | Submit final policies and documents to Circles UK for sign-off | CEO
3 | Create easy read versions of Core Member paperwork | Coordinator
4 | Submit easy read versions for sign off | Coordinator
5 | All documents and policies signed off | Coordinator
6 | Circles UK attend meeting of Board to review working relationship going forward | Chair/ Circles | bar: Year One Jan
Staff recruitment
1 | Launch internal recruitment for Coordinator position(s) | HR
2 | Interview internal applicants | HR/ Project Lead
3 | Appoint internal applicants | HR/ Project Lead
4 | Ensure staff are vetted in accordance with agreed Probation vetting requirements | HR/ Project Lead
5 | Service-specific training for internal applicants | Training Lead
6 | If no internal applicant, launch external advert | HR
7 | Shortlist | HR/ Project Lead
8 | Interview | HR/ Project Lead
9 | Appoint | HR/ Project Lead
10 | Conduct all Probation vetting in accordance with vetting arrangements | HR
11 | Induction and training for new staff | Training Team | bar: Year One Feb
Volunteer Recruitment
1 | Continue internal recruitment/training amongst our existing pool of Volunteers (already underway) | Volunteer Coord
2 | Meet with Volunteer Coordinator to plan social media recruitment campaigns | Comms Team
3 | Meet with partner organisations, including CAB, local charities representing people with protected characteristics to plan recruitment campaigns | Project Lead/ Volunteer Coord
4 | Meet with University partners to plan recruitment from related courses, e.g. criminology, sociology | Project Lead/ Volunteer Coord
5 | Ensure all Volunteers are vetted in accordance with agreed Probation vetting requirements | Volunteer Coord
6 | Meet with Volunteers 1-2-1 to explain programme | Coordinator
7 | Undertake full assessment of Volunteer suitability mapped against Circles UK approved job descriptions | Coordinator
8 | Review all training records | Coordinator
9 | Check all existing Volunteers recruited have Enhanced DBS clearance | Coordinator
10 | Targeted recruitment campaigns throughout the year on social media | Comms Team | bar: Year One Feb; Year One Apr; Year One Jun; Year One Aug; Year One Oct; Year One Dec
11 | Targeted recruitment campaigns in local employers, organisations - 'Volunteer Recruitment Roadshows' | Comms Team | bar: Year One Mar; Year One May; Year One Jul; Year One Sep; Year One Nov; Year One Jan
12 | On-going programme of Volunteer interviews/inductions | Coordinator
Staff and Volunteer Training
1 | Complete development of internal Circles UK-approved training programme for volunteers (already underway) | Training Coord
2 | Training Needs review with in-coming staff/volunteers based on Circles UK requirements | Training Coord
3 | Establish organisational plan to assess staff training needs | Training Coord
4 | Project Leadership, DSLs, FSWs and others complete internal Circles UK training | Training Coord
5 | Establish formal training record to audit all staff and Volunteer Circles training | Training Coord
6 | Arrange time with newly recruited staff/volunteers to receive induction training prior to transfer | Training Coord
7 | Complete training to meet immediate needs | Training Coord
8 | Establish programme for on-going CPD | Training Coord
9 | Annual review of training programme | Training Coord | bar: Year One Jan
10 | Complete awareness raising training sessions for partner/ potential partners | Training Coord | bar: Year One Mar; Year One Jun; Year One Sep; Year One Jan
Premises
1 | Identify with Probation and other stakeholders existing sites for initial Circles meetings | Project Lead
2 | Agree with selective Nepacs' current community delivery sites access for Circles meetings where appropriate | Project Lead
3 | Agree with partners (e.g. Humankind, Ingeus) use of their appropriate locations | CEO/ Project Lead
4 | Undertake Site Suitability checks for all chosen locations | Project Lead
5 | On-going liaison with charity partners, stakeholders and community venues to identify potential delivery sites | Project Lead | bar: Year One Feb to Year One Mar
6 | Quarterly review of each delivery site used | Project Lead | bar: Year One Apr; Year One Jul; Year One Oct; Year One Jan
Technology
1 | Review all cyber, information assurance and data processing systems to reconfirm alignment with Circles UK and Probation requirements | Office Manager/ Project Lead/ IT Team
2 | Agree and establish systems for transferring referral and reporting data securely between Probation and Coordinators | Project Lead
3 | Agree and establish systems for recording Action Plans | Project Lead/ Coordinator
4 | Undertake audit with IT provider to ensure access to secure systems for staff in readiness for 2 weeks before go-live | Project Lead/ IT Team
5 | Provide relevant IT training to staff and Volunteers | Training Coordinator
6 | Acquire SafeShores software and ensure staff and Volunteers are trained in its use | Project Lead/ Training Coordinator
7 | Meet with Probation Data Security representatives for final check to ensure storage of data is compliant with Probation requirements/ GDPR/ Data Protection Act | Project Lead/ IT Team
8 | Confirm compliance with NCSC Cloud Security Principles | Project Lead/ IT Team
9 | Information Management Security Plan agreed with Probation and any other appropriate stakeholders | Project Lead/ IT Team
10 | Establish protocols for use of digital technologies with Core Members | Project Lead
11 | Share protocols with Volunteers and staff prior to commencement of all Circles | Project Lead | bar: Year One Feb to Year One Jun
Processes including safeguarding
1 | Review and update all existing Circles recording and referral forms to ensure alignment with requirements of the contract | DSL/ Project Lead
2 | Review and update all 'journey travelled', outcome star and other progress monitoring documentation to ensure evaluation systems are in place | DSL/ Project Lead
3 | Review safeguarding escalation flowcharts/guidance | DSL/ Project Lead
4 | Share process for conducting risk assessments with Probation and MAPPA colleagues | DSL/ Project Lead
5 | Update all policies and processes to reflect new service delivery | DSL/ Project Lead
6 | Update safeguarding directories for all staff and volunteers to reflect Probation Practitioner and other Outer Circles contacts | DSL/ Project Lead
7 | Senior Team reviews all safeguarding processes for final internal, Circles and probation sign off prior to go-live | DSL/ Project Lead
8 | Share and review all recording documentation and processes with commissioners and stakeholders | DSL/ Project Lead
9 | Share and review all recording documentation and processes with staff, Probation and other stakeholders | DSL/ Project Lead
10 | Update training to reflect any contacts, escalation routes for new service | Training Coord
11 | Board reviews effectiveness of referral systems and other processes | Chair/ CEO | bar: Year One Jul; Year One Jan
Quality Assurance
1 | Complete review of our Quality Assurance Framework to incorporate new service | Project Lead
2 | Share framework with all Circles staff and Volunteers during handover training/ induction | Coordinator | bar: Year One Feb to Year One Mar
3 | Schedule 1-2-1 reviews with staff and volunteers | Coordinator | bar: Year One Feb to Year One Jul
4 | Complete plan of QA checks for forthcoming year | Project Lead | bar: Year One Feb
5 | Schedule senior manager audits | CEO | bar: Year One Feb
6 | Monthly supervisions for all Volunteers and staff | Coordinator
7 | Monthly KPI checks by senior team | CEO
8 | Undertake management/ Board QA checks | Chair/ CEO
9 | Monthly 1-2-1s and team meetings | Project Lead
Reporting
1 | Agree reports to be produced/obtained for commissioners and Probation | Project Lead
2 | Agree reports to be produced/obtained for SLT and Board | Chair/ CEO/ Project Lead
3 | Ensure all staff and Volunteers aware of KPIs and reporting requirements | Coordinator | bar: Year One Feb
4 | Train key mangers/staff to read and draw off reports | Training Coordinator | bar: Year One Feb to Year One Mar
5 | Regular commissioner/Probation meetings | CEO/ Project Lead
6 | Monthly team reports and SLT reports | Project Lead
7 | Monthly Board reporting | CEO/ Project Lead
8 | Produce annual Service Review Report | Project Lead | bar: Year One Jan
Communications Strategy
1 | Meet with Commissioners and Probation to share Nepacs Circles branding | Comms Team
2 | Agree with Commissioners and Probation communication framework, reflective of sensitivities of the service being delivered | Comms Team
3 | Agree with commissioners where we can coordinate communications with other stakeholders; review annually | Comms Team | bar: Year One May; Year One Sep; Year One Jan
4 | Develop and share Directory of Service Provision, including key contacts, for all stakeholders including Probation and MAPPA; review annually | Comms Team/ Project Lead | bar: Year One May; Year One Sep; Year One Jan
5 | Initial communication to inform key stakeholders of change to service | Comms Team | bar: Year One May; Year One Sep
6 | Agree protocol with probation and other stakeholders of communication procedure in event of any negative media involvement with Circles delivery (eg following incident or general interest in the topic); review annually and in conjunction with Circles UK | Comms Team/ Circles UK Comms | bar: Year One Jan
Finances
1 | Update finance system with all service costings and forecasting in readiness for budget monitoring and invoicing | Finance Team
2 | Agree with commissioners invoicing reporting requirements | Project Lead
3 | Update invoicing documentation accordingly | Finance Team
4 | Update procedures for payment of monthly activity expenses to Volunteers | Finance Team
5 | Approval of updated arrangements by SLT and Board | Finance Team
6 | Establish budget lines for Circles activity expenses | Finance Team
7 | Train all transferring/new Volunteers on expenses processes | Finance Team
8 | Begin monthly payments of expenses | Finance Team | bar: Year One Mar
9 | Begin service invoicing once delivery commences | Finance Team | bar: Year One Mar