## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | M20 Lorry Area Brock (Interim) Project – Task Order No.12
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | M20 Op Stack Interim Solution | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | SE 69 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5163040 | Consultant Contact: |  |  | Redacted
Start & End Date: | 01/04/2019 - 31/12/2019 | CTO Authorisation No.
Task Overview
Principal Designer Continuation Commission Fulfill the requirements of the Principal Designer(PD) described in the Construction (Design and Management) Regulations 2015 (CDM 2015) in respect of the Construction Phase (the permanent works) only. The appointment will continue up until the point referenced in the scope of services provision, assumed to be 3rd November 2019. The PD duties are required in respect of material design change to the temporary barrier arrangement and associated potential construction works during the 6-month ‘Operations phase’. Note: The PD role Atkins is carrying out does not include coordination of the traffic operation (which falls outside of CDM). CDM Advisor and H&S Support Commission Provide CDM Advisor support for the duration of the Temporary Solution Construction Contract and prepare and issue the H&S file in January 2020. As discussed (Redacted/Redacted 23rd October 2019) Limit of liability to be reduced to £5m for project Task Orders.
Task Objectives and Milestones
Principal Designer Commission Continue fulfillment of the requirements of the Principal Designer described in the Construction (Design and Management) Regulations 2015 (CDM 2015) in respect of any material change to the permanent works design during the operation of the J8-9 Temporary Solution. To effectively discharge the responsibilities of Principal Designer timely issue of final Traffic Management proposals or details is required prior to their implementation. The duties required are in respect of material design change to the temporary barrier arrangement and associated potential construction works during the 6-month ‘Operations phase’. CDM Advisor and H&S Support Commission • Ensure and monitor that Principal Designer and Principal Contractor are discharging responsibilities under CDM 2015 • Provide CDM Advisor support for the duration of the Temporary Solution Construction Contract • Report to Highways England Senior Health and Safety Manager as required • Carry out Welfare facilities inspections on behalf of Client as required • Ensure all Atkins personnel incidents are recorded on AIRSWEB and support HE complying with IAN 128/15 (HE Supply Chain H&S Incident Reporting) • Review Principal Contractor’s CPP on behalf of Client • Attend contractor safety committee meetings • Provide advice on H&S site investigations when required The Principal Contractor remains responsible for the safe and faithful implementation of the agreed traffic management details and their proper maintenance. Timescales: • 1 April 2019 – to completion of operational phase assumed to be November 2019. • H&S file to be prepared by John Winson with the Principal contractor and issue early 2020. It is assumed that this will require the attention of 8hrs/week from Redacted and 16hrs/month from Redacted. Depending on the potential level of material change and complexity, there may be a requirement for advice from Redacted and an ad-hoc allowance of 3days is included.
Task Outcomes
Outcomes • A safe network and informed users. Demonstrate safety first culture and approach to delivering projects. • Highways England delivers on its customer and business goals and excels on customer service delivery. • Maintains good relationship with stakeholders, the public, and the customer. • Managing risks and delivering value for money projects. • Demonstrate performance through competence.
Project Risk and Management
As discussed (Redacted/Redacted 23rd October 2019) Limit of liability to be reduced to £5m for project Task Orders Atkins Management • Framework Contract management – Redacted • Project Manager – Redacted • Project Director – Redacted • Principal Designer representative – Redacted and Redacted
Project Title: | M20 Lorry Area Brock (Interim) Project – Task Order No.12 |  |  |  | HE Reference: | SE 69 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 69 18/19ATK | 42340.4 | 0 |  |  | 42340.4 | Paul Harwood
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 42340.4
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 42340.4
Total Project Fee Estimate |  |  |  |  | 42340.4
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (M20 Brexit Rate) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2019-03-20 |  | Works Total |  | 42340.4
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 42340.4
|  |  | Expenses |  | 4000
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 46340.4