Specification for research project

ADHERE: Sander quality and performance criteria framework (T1210)

The draft research specification and assessment criteria that follows is subject to change following supplier engagement.

A pre-tender suppliers meeting has been arranged for 7 September 2020 at 12:00 – 13:30. The meeting will be held remotely on Microsoft Teams (the Microsoft Teams link shall be shared ahead of the meeting to confirmed attendees). The purpose of this meeting is to:

- Provide an outline of the project proposal

- Provide interested suppliers an opportunity to discuss, understand and inform the research specification

Suppliers should be prepared to discuss the following:

- What resources and information would suppliers require, in order to deliver robust outcomes?

- Are the timescales sufficient to deliver quality outputs to time?

- What are the challenges and barriers to delivering this work? What enablers would support successful delivery of the project?

- What is the estimated effort to deliver this work to quality and time?

Please note that following the suppliers meeting, RSSB may amend the document before publishing the invitation to tender.

Suppliers wishing to attend the event should email Tanja.Odinsen@rssb.co.uk to confirm arrangements.

- RSSB overview

RSSB is a membership organisation that supports the GB rail industry by:

- Understanding risk – Using safety intelligence with the latest risk modelling to inform members and support safe decision making.

- Guiding standards – Creating, reviewing and simplifying GB standards; managing the Rule Book and making it easier for the railway to deliver efficiently and safely.

- Facilitating cross-industry collaboration – As an independent cross-industry body, supporting activities which require collaboration such as supplier assurance schemes, confidential reporting and developing industry strategies.

- Managing research, development and innovation – Undertaking, commissioning and managing research and innovation programmes to address current and future needs and providing knowledge for decision making; supporting implementation and promoting step changes to deliver industry strategies.

- Background

Previous RSSB research project T796 Understanding the current use of sanders on multiple units, completed in 2010, investigated the sand discharge rates of different types of existing sander systems on multiple units; and recommended steps to improve performance.

Since 2010, major improvements have been made to reduce the variability in performance. In recent years, industry has also undertaken several innovative initiatives to advance sander capabilities, which has shown the considerable improvement sanders can make in low adhesion conditions.

The contribution of sanding to good braking in low-adhesion conditions can be every bit as crucial as that of compressors, brake systems or Wheel Slide Protection (WSP) control systems. However, the application of traditional assessment approaches to existing sander technology does not always make a case to use this performance benefit in defining train operations. With a desire for sanders to have a similar high system integrity as braking systems, Adhesion Research Group has requested research to produce a quality and performance assessment criteria framework for sanding systems. Such a framework would enable rolling stock leasing companies, maintainers and operators to assess the reliability of new sanding systems and supply chains for new or existing rolling stock. Use of the framework would be expected to improve overall understanding and confidence of the on-train equipment during low-adhesion conditions.

T1210 is part of RSSB’s ADHERE (ADHEsion REsearch challenge) programme. The vision for ADHERE is to achieve “adhesion conditions that are unaffected by and independent of the weather and climate”; the programme incorporates several workstreams, including the ‘Changes to Train Design’ workstream. One notable goal of this workstream is “to help drivers become confident in the low adhesion traction and braking performance of their trains”.

- Project objectives

This project aims to provide the GB rail industry with a quality and performance assessment criteria framework for sander design, build, installation, maintenance, overhaul and supply chain.

The framework should:

- Establish a benchmark for overall sanding system quality and performance; and quality and performance of key components, for example sand hopper, valve, and air supply.

- Enable identification of valuable areas for improvement relative to the determined benchmark performance, enabling operators to identify which changes should be made (including changes to the supply chain).

- Enable rolling stock leasing companies, maintainers and operators to assess the reliability of new sanding systems and supply chains for new or existing rolling stock.

Project scope

This section defines the tasks to be undertaken; and the technical content against which the submissions will be assessed.

In scope

- Reliability assessments of the elements of typical on-train sander designs (hardware and software)

  - Sander components – including, but not limited to, sand hopper, sander brackets, control systems, valves and air supply

  - Sand materials – in-hopper storage and discharge

  - Operational usage of sander systems

  - Maintenance of sander systems

  - Sander system supply chain

- Assessment of ideal and compromised performance of sander system based on reliability assessments

- Descriptions of particular sanding systems

  - Configuration of diverse sander components and sub-systems

- Evaluation of the overall dependability of a sanding system

  - Quantifying the likely failure rate and subsequent consequences for the sanding system (for example, reduced sand discharge rates)

- Information on how to reduce the likelihood of failure

- Case studies of the solution as applied to contemporary sanding systems

On-going requirements

In addition to the above, the supplier will be required to undertake the following tasks during delivery:

- Attendance at project kick-off meeting (to either be held remotely, or at RSSB’s offices (London))

- Attendance at four steering group meetings (to either be held remotely, or at RSSB’s or the supplier’s offices)

- Presentation to Adhesion Research Group (to either be held remotely, or at RSSB’s offices)

- Creation and maintenance of project management plan

- Creation and maintenance of project risk register

- Provision of monthly progress reports

Subject to no COVID-19 restrictions (and RSSB meeting room availability), RSSB’s facilities can be provided to the supplier for meetings and/or workshops without cost (where appropriate, meetings can be held elsewhere if RSSB considers this beneficial).

Out of scope

- Laboratory and/or track testing

- Production of prototype sanding system

- Formal production of GB and/or European standard

- Evaluating the wider consequences of a sanding system failure, for example platform overrun, signal passed at danger, etc.

- Deliverables

This project will provide the following deliverables:

| Deliverable Title | ADHERE: Sander quality and performance criteria framework – Framework |
| --- | --- |
| Deliverable Type | Framework |
| Description | The supplier is to: - Establish a benchmark for overall sanding system quality and performance; and quality and performance of key components, for example sand hopper, valve and air supply. - Produce a quality and performance assessment criteria framework (using an established methodology) for sander design, build, installation, maintenance, overhaul and supply chain. The framework should: - Enable user-entered system parameters: - Enable identification of valuable areas for improvement relative to the determined benchmark performance, enabling operators to identify which changes are required (including changes to the supplier chain). - Enable rolling stock leasing companies, maintainers and operators to assess the reliability of new sanding systems and supply chains for new or existing rolling stock. The benchmark criteria should be independent of the solution. |
| Publication | The deliverable shall be reviewed by RSSB and the project steering group, to allow for comment. The deliverable is to be made widely available. |

| Deliverable Title | ADHERE: Sander quality and performance criteria framework – Report |
| --- | --- |
| Deliverable Type | Report |
| Description | The supplier is to produce a supporting document for the quality and performance assessment criteria framework. The deliverable should have an objective method by which sanding systems can be assessed, based on design and build. The deliverable shall include an assessment of the impact of sander installation, maintenance, overhaul and supply chain. The deliverable shall include information on how to use the sander quality and performance criteria framework. |
| Publication | The deliverable is to be produced in the standard RSSB format and is to incorporate appropriate infographics. The deliverable shall be reviewed by RSSB and the project steering group, to allow for comment. The deliverable is to be made widely available. |

| Deliverable Title | ADHERE: Sander quality and performance criteria framework – Good practice guide for sander design and maintenance |
| --- | --- |
| Deliverable Type | Good practice guide |
| Description | The supplier is to produce a code of practice on sander design and maintenance integrity. It should be emphasised that T1210 is not a standards project; and as such shall not be producing a formal standards document. However, the document could form the basis for a potential future standard. |
| Publication | The deliverable is to be produced in the standard RSSB format and is to incorporate appropriate infographics. The deliverable shall be reviewed by RSSB and the project steering group, to allow for comment. The deliverable is to be made widely available. |

| Deliverable Title | ADHERE: Sander quality and performance criteria framework – Presentation |
| --- | --- |
| Deliverable Type | Presentation |
| Description | The supplier is to prepare a summary presentation capturing project methodology and findings. The supplier shall deliver the presentation to two industry group meetings. |
| Publication | The deliverable is to be produced in the standard RSSB format and is to incorporate appropriate infographics. The deliverable shall be reviewed by RSSB and the project steering group, to allow for comment. The deliverable is to be made widely available. |

- Stakeholder roles and responsibilities

The key stakeholders and their responsibilities are detailed in the table below:

| Role | High level description | Specific responsibilities are to: |
| --- | --- | --- |
| RSSB Project Manager | The RSSB Project Manager is the first point of contact for the suppliers once the contract has been put into place. The RSSB Project Manager is responsible for ensuring that the supplier delivers the project as agreed in their proposal. | - Organisation, co-ordination and chair of project meetings. - Monitoring and tracking of project progress and spend - Point of contact for escalation for enquiries from supplier, steering group, or project sponsor. - Dissemination of deliverables to project steering group and client group. - Authorisation of payment within agreed project spend. |
| RSSB Technical Lead | Throughout the project, the Technical Lead, generally a RSSB employee, ensures that technical aspects are considered and reflected accurately. | - Provide input to the specification, either by writing it or reviewing its content, and assure it is technically sound and appropriately scoped - Assess tenders - Review and provide input to draft deliverables - Review final deliverables to ensure that they are technically sound and the conclusions defensible |
| RSSB Sponsor | The RSSB Sponsor is a senior RSSB employee that is best placed to actively monitor the project through development and delivery, keeping the project aligned with and informed by industry's expectations and initiatives; and steers implementation facilitation activities. | - Sponsors the RSSB business case and implementation plan, focusing on how RSSB can support industry benefiting from the findings - Advises the Project Steering Group on shaping the project and its deliverables to most effectively support industry take up and to get most value out of it - Actively monitor the project through delivery working with the Industry Sponsor to successfully navigate the project through any points of conflict between stakeholders, and decision points relating to emerging findings - Keep active awareness of the emerging findings and, as appropriate, bring them (and any related decision points) to the attention of the Industry Sponsor to jointly provide advice to the steering group - Provide advice and steer on activities required to facilitate implementation |
| Industry Sponsor | The industry sponsor acts as figurehead for the research, championing its importance and its outputs. The industry sponsor forms part of the project steering group, however, their key role as sponsor is to provide steer to the research as it progresses and to influence industry to make use of its findings. | - Advises the Project Steering Group on shaping the project and its deliverables to most effectively support industry take up - If required, facilitate access to industry data, people and equipment needed to deliver the project - Oversees the project through delivery working with the RSSB sponsor to successfully navigate the project through any points of conflict between stakeholders, and decision points relating to emerging findings - Promote industry take up and implementation of the research beyond completion of the R&D project - Provide feedback to RSSB during project delivery and after completion |
| Industry Supporters | The two project supporters represent parts of industry complementary to the Industry Sponsor’s organisation. | - Offer expertise during project development and delivery - If required, facilitate access to industry data, people and equipment needed to deliver the project - Support the implementation of findings |
| Project Steering Group | The Project Steering Group ensures the project is specified and delivered to take into account different stakeholders’ needs. The group is made up of representatives from within the rail industry and other industries where appropriate. | - Provides input to and reviews the ‘case for research’ (i.e. the business case, specification and implementation plan) - Monitors and steers the project through delivery - If required, facilitates access to industry data, people and equipment needed to deliver the project - Attends meetings with Project Team and suppliers - Reviews draft and final output(s) |
| Primary Client Group | The primary client group is an established industry group that has responsibility to steer and oversee activities in a specific topic area. | - Comment on research ideas and consider outcomes from idea review activities that RSSB undertakes - Review and endorses the ‘case for research’ before it goes for budget authority - Endorse the findings and support their implementation |

- Budget, timescales and responsibilities

The budget for this work is up to £90,000. If, whilst compiling a response, tenderers determine that it is not feasible to submit a quote to this budget but still wish to provide a response, they shall:

- Provide a quote for all work as requested, even if this exceeds the budget. This allows RSSB to conduct a like-for-like comparison as required by the evaluation criteria. Those who price within RSSB’s budget will score more highly in line with the pricing calculation, however, higher bids will not be automatically disqualified.

- Provide a supporting explanation as to why an increase in budget is required to deliver the work to a good standard.

RSSB expects the work to start in November 2020 and be delivered at pace. We envisage this research to take less than 10 months to complete. However, these are indicative dates and RSSB will consider bids that cannot meet these expectations if the supplier includes a robust project plan and an explanation as to why they cannot meet the preferred start and end dates, while still meeting the project objectives.

- Critical success criteria and risk management

The following critical success criteria have been identified to help ensure successful delivery and to increase likelihood of industry acceptance/implementation:

- Ability to engage with industry stakeholders to secure data and case studies

The following initial risks have been identified to highlight where the project may encounter issues during delivery, the supplier will be expected to propose approaches to mitigate these risks and any others they perceive:

- Issue gaining access to robust data for sander components and sub-systems

- Access to depots and depot staff

- Scope creep

- Selection and award criteria

Tenderers must carefully read the selection criteria in order to address EACH requirement. Tenderers shall fail the selection criteria unless they address EACH requirement, tenderers that fail the selection criteria will not have their award criteria evaluated.

The stated limit on the length of each response must be adhered to. Responses will only be evaluated within the stated length limit, any response exceeding the stated limit will be disregarded beyond that limit.

Selection criteria

| Selection criteria | Detail and Evaluation Criteria |
| --- | --- |
| S1 Tenderer’s organisational expertise in sanding systems and sand materials [Total 1 page for all examples] | The tenderer shall provide a short description of at least two completed examples within the past five years that focused on contemporary GB rail sanding systems. For clarification, a ‘completed example’ refers to work specifically completed by the tenderer. If the completed work forms part of a larger activity (involving other organisations), the overall activity does not need to have been completed. In order to pass the selection criteria, the tenderer’s response must address the above and: - Demonstrate a track record of successfully delivering work with contemporary GB rail sanding systems. This shall involve at minimum one of the following activities – design; build; installation; use; maintenance; overhaul; supply. RSSB shall also accept any activities on low adhesion testing - Give RSSB full confidence in the tenderer’s ability to deliver work with contemporary GB rail sanding systems. This shall involve at minimum one of the following activities – design; build; installation; use; maintenance; overhaul; supply. RSSB shall also accept any activities on low adhesion testing. The tenderer shall fail the selection criteria if it either fails to provide a short description of at least two completed examples within the past five years that focused on contemporary GB rail sanding systems; or the provided example fails to achieve ANY of the following: - Demonstrate a track record of successfully delivering work with contemporary GB rail sanding systems. This shall involve at minimum one of the following activities – design; build; installation; use; maintenance; overhaul; supply. RSSB shall also accept any activities on low adhesion testing - Give RSSB full confidence in the tenderer’s ability to deliver work with contemporary GB rail sanding systems. This shall involve at minimum one of the following activities – design; build; installation; use; maintenance; overhaul; supply. RSSB shall also accept any activities on low adhesion testing |
| S2 Tenderer’s organisational expertise in system risk analysis [Total 1 page for all examples] | The tenderer shall provide a short description of at least one completed example of work within the past five years that analysed system risk. In order to pass the selection criteria, the tenderer’s response must address the above and: - Demonstrate a track record of successfully delivering system risk analyses - Give RSSB full confidence in the tenderer’s ability to analyse system risk The tenderer shall fail the selection criteria if it either fails to provide a short description of at least one completed example of work within the past five years that analysed system risk; or the provided example fails to achieve ANY of the following: - Demonstrate a track record of successfully delivering system risk analyses - Give RSSB full confidence in the tenderer’s ability to analyse system risk |

Award criteria scoring

Each of the criteria set out in the weighted award criteria are scored 0-5. The below gives an explanation of the scoring system used:

| Grade | Definition of grade |
| --- | --- |
| 5 | An Excellent Tender Response that (where applicable): - Addresses all aspects of the question in an informed and comprehensive manner; - Demonstrates a thorough understanding of what is being asked for; - Provides evidence of how that understanding can be applied in practice; - Offers full confidence that the Tenderer will deliver the service in full; - Addresses the majority of areas of doubt and uncertainty; and - Provides certain, unambiguous commitments or statements of intent that permit reliance through translation into contractual terms |
| 4 | A Good Tender Response that (where applicable): - Addresses all aspects of the question and is generally of a good standard; - Demonstrates a good understanding of what is being asked for; - Provides a worked-up methodical approach; - Offers confidence that the Tenderer will deliver the service in full, with limited areas of doubt or uncertainty; - Addresses key areas of doubt and uncertainty; and - Provides commitments that can be translated well into contractual terms |
| 3 | A Satisfactory Tender Response that (where applicable): - Addresses the majority of the question and is generally of a good standard but lacks substance or detail in some areas; - Demonstrates an understanding of what is being asked for; - Provides a satisfactory approach; - Offers a general level of confidence that the Tenderer will deliver the service (but with room for doubt in some areas); - Address some areas of doubt and uncertainty; and - Provides some commitments that can be translated well into contractual terms. |
| 2 | A Poor Tender Response that (where applicable): - Addresses some of the question but either lacks relevant information and detail or lacks substance in a manner that would suggest the response is a “model answer”; - Demonstrates some understanding but with a lack of clarity in key areas; - Provides an approach which is not wholly appropriate or viable or lacks evidence; - Shows that the level of confidence that the supplier can deliver does not outweigh the doubt; - Does not address many areas of doubt and uncertainty; and - Does not offer sufficient commitment (with doubt as to the extent to which would translate into contractual terms). |
| 1 | An Unsatisfactory Tenderer response that (where applicable): - Does not address the question or has omissions; - Lacks understanding in significant areas: - Provides an approach which has gaps or creates concerns; - Shows that the level of confidence that the supplier can deliver is low; - Creates uncertainty; and - Displays significant lack of commitment (with doubt as to the extent to which would translate into contractual terms) |
| 0 | An Unacceptable Tenderer response that (where applicable): - Provides no response or omissions/oversights that prevent scoring; - Refuses to deliver the requirement; and - Creates concerns so significant that the response would be detrimental to the interests of RSSB |

| Award criteria | Detail and Evaluation Criteria | Weighting |
| --- | --- | --- |
| W1 Summary of proposal [Max 1 page] | Tenderers should outline their ability to concisely summarise key aspects of their proposal. The information will be used by RSSB to contextualise the tenderer’s response. The tenderer’s response shall be evaluated on the following criteria within the maximum stated page limit: - The tenderer has clearly outlined their understanding of the project’s objectives and outputs; - The tenderer has summarised their proposal (excluding any pricing information), outlining how it shall clearly address the project’s objectives and outputs. | N/A (For information only) |
| W2 Supplier’s understanding and methodology [Max 5 pages] | Tenderers should clearly outline their understanding and methodology to carry out the required works defined in the project specification. The tenderer’s response shall be evaluated on the following criteria within the maximum stated page limit: - The tenderer clearly demonstrates their understanding of each of the project objectives and outputs; - The tenderer establishes and presents a clear and appropriate methodology to address each of the project objectives and to deliver each of the project outputs, detailing how it shall commit to ensuring the project and outputs are delivered to a sufficient quality; - The tenderer presents a viable and practical approach to: - Configure diverse sander components and sub-systems - Highlight the different elements of a sander and sander supply chain that are most likely to lead to a failure - Assess the reliability rating of a particular sander configuration on a particular train type - The tenderer addresses the success criteria in order to ensure successful project delivery and increased likelihood of industry implementation | 25% |
| W3 Organisational experience and individual expertise [Max 5 pages] | Tenderers should clearly outline how their organisational experience and individual expertise can directly address the required works defined in the project specification. The tenderer’s response shall be evaluated on the following criteria within the maximum stated page limit: - The tenderer outlines relevant activities undertaken by their organisation, that demonstrates suitable experience to meet the project requirements; - The tenderer demonstrates what capabilities individual project team members will bring and how this shall contribute to successfully meeting the project’s objectives and outputs. To support RSSB’s evaluation, the tenderer shall provide a one-page CV for each key project member within an appendix. - The tenderer must not provide any team members or CVs unless that person is expected to have a role in the project | 25% |
| W4 Project management: Planning and engagement [Max 4 pages] | Tenderers should outline the processes and resources it proposes to use in order to fulfil RSSB’s requirements. The tender’s response shall be evaluated on the following criteria within the maximum stated page limit: - The tenderer provides adequate allocation of resource to successfully deliver outcomes to time, cost and quality. To support RSSB’s evaluation, the tenderer shall provide: - A Gantt chart detailing key tasks and timeframes - A resource table that details task, role, name and effort (in days). The table should include total effort (in days). - The tenderer provides a clear engagement plan detailing: - Which stakeholders it intends to engage with - When (and how) it intends to engage with stakeholders - What input it shall seek from stakeholders - A ranking of stakeholders by order of priority, outlining how the stakeholders will have impact on successful delivery of the project. | 20% |
| W5 Risks and opportunities [Max 2 pages] | Using the RSSB supplied ‘Risk and Opportunity register templates and guidance’, tenderers should detail what risks and opportunities are foreseen in the delivery of the project. The tenderer’s response shall be evaluated on the following criteria within the maximum stated page limit: - For each risk, the tenderer shall detail: - Description of the impact and probability of the risk if unmitigated - Impact of the risk on Time, Quality and Cost (scored out of 5) - Likelihood of the risk occurring (scored out of 5) - Provide a risk rating (impact * likelihood) - Actions to address probability and impact of the risk; and revised risk rating with mitigation in place - Actions to be taken should the risk be realised - Specific individual ultimately responsible for the risk control The tenderer must include a minimum of one risk relating to COVID-19. - For each opportunity, the tenderer shall detail: - Description of the opportunity - The benefits of realising the opportunity on project Time, Quality and Cost - Actions to be taken to support the opportunity being realised - Specific individual ultimately responsible for the opportunity Please note: Tenderers must not use their own template for this section. | 10% |
| W6 Cost of project | Tenderers should provide a fixed cost for the project and the associated cost break down. The tender with the lowest total cost will receive 100% of the available weighted score (20%). Other tenderers will receive a pro-rated score relative to the lowest cost according to the following formula: - Score of other tender = lowest tender total cost / other tender total cost x 100%. | 20% |

- Procurement timeline

|  | Start Date |
| --- | --- |
| (Remote) Supplier engagement meeting | 7 September 2020 |
| Request for proposal issued on Delta eSourcing | 18 September 2020 |
| Supplier clarification questions deadline | 13 October 2020; 12:00 hours |
| Deadline for Submitting tenders | 19 October 2020; 15:00 hours |
| Evaluation and moderation | 30 October 2020 |
| Estimated notification of award decision | 13 November 2020 |
| Target contract commencement date | 27 November 2020 |

Note: RSSB reserves the right to amend these dates as business requirements demand and will communicate any changes to tenderers.

Please note: RSSB does not currently have a dial-in functionality for Microsoft Teams, therefore attendees will need to either use a computer or smart phone to access the meeting

For instance, consideration of sanded braking in defining guaranteed performance to signal systems

An established methodology should be used. RSSB does not stipulate what methodology this should be.

The research shall not evaluate the wider consequences of a sanding system failure, for example platform overrun, signal passed at danger, etc.

No more than two case studies

In case COVID-19 remains an ongoing risk

See deliverable ‘Good practice guide for sander design and maintenance’

For clarity, ‘quality’ is defined as the delivery of robust outputs that successfully meet the project’s objectives

For clarity, ‘opportunities’ is defined as an upside beneficial source of risk, for instance, the ability to acquire further data, enabling more robust outputs