## Objectives
DHDO: Scoping and Estimate of Work to Design and Mobilise a full Geographical Pilot in 2019/20 of the Future Defence Health Delivery Model
| (Sep 2018) Bridging Activities | Contributing to:
(0) Framing Pilot Objectives and Scope | *Define objectives and success criteria for Pilot *Define scope for Pilot and how far changes may be adopted nationally before Pilot completed *Select pilot geography and secure strong local as well as national commitment to its success | 1. Project plan design and mobilisation
(1) Programme Leadership | *Design and set up governance framework *Develop Design and Mobilise programme plan and budget with risks, issues, assumptions, inter-dependencies (JMG, Cortisone, wider ISS etc) *Agree outline of evaluation methodology *Determine whether a model is required to capture pilot evidence, forecast the impact of business rule changes and inform the business case for national rollout and, if so, how this should best be provided | 2. Programme management structure and governance
(2) Ops in Geography, Change Mgmt, Framing requirements for Business Ops/Digital/Data/ Workforce Solutions | *Conduct initial workshops with pilot geography, key clinicians and single services *Create an accurate baseline for the Pilot geography of PAR, med assets, resources and local performance and finance *Undertake a change readiness assessment and develop change management approach and plan | 3. Pilot Operating Model
(3) Business Operations and Digital Services | *Work with Clin Ops and Pilot geography region to baseline current Ops Management approach, resourcing, capability and change agenda *Work with business areas i.e. finance, IT, Infrastructure to baseline current management approach and change agendas *Decide patient-facing digital services to be included in Pilot and how these will be accessed (mobile, kiosk), in consultation with JHub, Cortisone and ISS *Agree method and plan with JHub for selection, proof of concept testing, implementation and maintenance of patient-facing solutions *Determine approach to capacity planning and workforce allocation including any new systems requirements, in consultation with Clin Ops and Cortisone | 4. Operational plan for pilot
(4) Data, including financial data | *Convene stakeholders and set up Data/3i Steering arrangements *Reach agreed baseline assessment of data availability and quality *Develop outline approach to delivering the right data foundation (clinical, activity, cost), including the capture of data to enable use of AI and ML, and, in this context, decide ambition for pilot *Develop approach and plan to putting in place required capability for pilot, in consultation with Clin Ops, Finance and Cortisone | 5. Evidence based assumptions for the optimisation of the delivery mdel 6. Roadmap towards achieving AI and ML capacbilities
(5) Workforce Solutions | *Convene JMG workforce leads to reach shared understanding of DHDO implications for the future workforce and JMG role *Identify workforce issues arising for uniformed and civilian staff respectively in Pilot geography that will need to be addressed *Determine how far the allocation process of single Service med staff to DPHC should change for the Pilot geography *Determine potential recruitment, development and training needs to med staff in the Pilot geography and how far these should be provided | 7. Revised workforce skill mix model
(6) Impact and Benefits Model | *Determine whether an interactive model is required to capture pilot evidence, forecast the impact of potential business rule changes during the pilot and inform the business case for national rollout and, if so, how this should best be provided | 8. Interactive impact and benefits model

## Quote
DHDO: Scoping and Estimate of Work to Design and Mobilise a full Geographical Pilot in 2019/20 of the Future Defence Health Delivery Model
Initial Bridging Phase to frame the Pilot and size and plan the Design and Mobilisation Activity
REDACTED