APPENDIX B

SERVICE DESCRIPTION

CONTENTS

1.	INTRODUCTION	2

2.	PURPOSE	2

3.	BACKGROUND TO THE AUTHORITY	2

4.	BACKGROUND TO REQUIREMENT/OVERVIEW OF REQUIREMENT	2

5.	SCOPE OF REQUIREMENTS	3

6.	SERVICE LEVELS AND PERFORMANCE	6

7.	LOCATION	6

8.	SECURITY REQUIREMENTS	6

9.	PROJECT TIMETABLE	7

10.	BUDGET	7

# INTRODUCTION

## The Office for Low Emission Vehicles (OLEV) seeks a service provider or providers to conduct audits of (i) domestic and (ii) non-domestic charging infrastructure funded through its various infrastructure grant schemes (since 2010) by making on-site visits to carry out technical/electrical assessments at the addresses of a sample of installations.

## This Service Description is for a contract to provide services in respect of the domestic charging infrastructure audit.

# PURPOSE

## The purpose of the on-site visits to a sample of domestic chargepoint installations is to determine the level of compliance, by grant claimants and installers, of the terms and conditions of OLEV’s various infrastructure grant schemes.

# BACKGROUND TO THE AUTHORITY

## OLEV has staff and funding from Department of Transport (DfT), the Department for Business, Innovation & Skills (BIS) and the Department of Energy & Climate Change (DECC).  OLEV works across government to support the early market for ultra-low emission vehicles (ULEV).  This will contribute to economic growth and will help reduce greenhouse gas emissions and air pollution on our roads.

## OLEV has had a number of infrastructure grant schemes to support the early ULEV market to help with the cost of domestic chargepoints at home and charging infrastructure away from home.  To date, OLEV has funded the following chargepoint installations:

### 4,200 through OLEV’s Plugged in Places (PiP) schemes (2010–2014);

### 250 rapids through OLEV’s Local authority rapids scheme (2013-2015);

### 80 through OLEV’s Train station car parks (2013-2015);

### 500 through OLEV’s Public sector estate scheme (2013-2015); and

### Over 50,000 domestic chargepoints through the Domestic Recharging Scheme and the Electric Vehicle Homecharge Scheme, with grants of 75% of the installation cost.

# BACKGROUND TO REQUIREMENT/OVERVIEW OF REQUIREMENT

## Background to requirement

## For the domestic infrastructure grant schemes, there are two aspects to the audit requirements as follows:

### An audit (not within the scope of this Service Description) to give a level of independent and objective assurance of compliance of the application and administrative processes managed by Driver and Vehicle Licensing Agency (DVLA) on behalf of OLEV for the Electric Vehicle Homecharge Scheme (EVHS) claims by authorised installers on behalf of their domestic customers.  This has been carried out by Government Internal Audit Agency (GIAA); and

### An audit (of which this Service Description covers) to give a level of independent and objective assurance of compliance by the installers and customers – this to be done through on-site visits to installations for EVHS claims and is also to include earlier installations for DRS claims.

## Domestic chargepoints are typically either 16A or 32A with either mode 2 with a BS EN 60309 socket or connector but not with a 3-pin socket (BS 1363) or mode 3 charging.  Mode 3 is preferred.  Modes 1 and 4 are inhibited.  As part of the DRS and EVHS requirements, there has to be a facility to capture and transmit usage data.

### Overview of requirement (by grant scheme)

## Domestic Recharging Scheme (DRS)

## From February 2013 to 31 August 2014, the DRS provided grants to plug-in vehicle users for domestic chargepoints to be installed at their residential address.  There was an update of the DRS terms and conditions which came into effect 1 July 2014.

## The number of domestic chargepoint installations for the DRS from February 2013 to 31 August 2014 is approximately 44,000.

## For the DRS, this will involve on-site visits to a sample of addresses of domestic installations to ensure compliance with the DRS terms and conditions.  Copies of the DRS terms and conditions applicable for the periods February 2013 to 30 June 2014 and 1 July 2014 to 31 August 2014 are annexed to this document.

## Electric Vehicle Homecharge Scheme (EVHS)

## Since 1 September 2014 the EVHS has provided grants to plug-in vehicle users for domestic chargepoints to be installed at their residential address.  There was an update of the EVHS terms and conditions which came into effect 13 April 2015. This scheme is still open.

## The number of domestic chargepoint installations for the EVHS from 1 September 2014 to 30 September 2015 is approximately 12,500.

## For the EVHS, this will involve on-site visits to a sample of addresses of domestic installations to ensure compliance with the EVHS terms and conditions.  A copy of the current EVHS terms and conditions (v1.8) is annexed to this document.

# SCOPE OF REQUIREMENTS

## All requirements are to be considered mandatory.

## Grant schemes in scope for this audit are:

### the previous schemes (DRS) from February 2013 to 31 August 2014 for domestic chargepoints; and

### the current schemes (EVHS) from 1 September 2014 for domestic chargepoints.

## Desk-checks and on-site visits are required for a sample of installations completed under both above-mentioned schemes.

## On-site visits should be conducted by experienced and qualified electrical inspectors.  The experience should consist of time served as a qualified electrician and of time served as an electrical inspector.  The minimum qualifications should be C&G 2391 & 2392, C&G 2360 Part 1 and 2 with AM1 & 2 or equivalent.  The electrical inspectors needs to be conversant with the theoretical intentions of the technical specifications for installations of chargepoints.

## Auditing grant claims under the Domestic Recharging Scheme (DRS)

## The service provider will be required to carry out desk-checks for a sample taken from the DRS domestic chargepoint installation claims received.

## OLEV will provide a sample of around 290 installations (to include those where OLEV has made a judgement of a higher risk of non-compliance and also to be geographically representative) for desk-checks and on-site visits.

## As part of the desk-checking, the service provider is to obtain customer full contact details (as OLEV only holds postcode details of installations) from the DRS installers, which they are required to make available under the terms of the grant.

## The service provider will also be required to carry out on-site visits to the sampled installations.

## The service provider will provide summary reporting (as detailed below).

## Auditing grant claims under the Electric Vehicle Homecharge Scheme (EVHS)

## Initial sample

## The service provider will be required to carry out desk-checks for a sample taken from the EVHS domestic chargepoint installation claims received since 1 September 2014 to the beginning of the contract.

## OLEV will provide a sample of around 180 installations (to include those where OLEV has made a judgement of a higher risk of non-compliance and also to be geographically representative) for desk-checks and on-site visits.

## As part of the desk-checking, the service provider is to obtain customer full contact details (as OLEV only holds address details of installations) from the EVHS installers, which they are required to make available under the terms of the grant.

## The service provider will also be required to carry out on-site visits to the sampled installations.

## The service provider will provide summary reporting (as detailed below).

## Monthly samples

## The service provider will be required to carry out desk-checks for subsequent monthly samples (after the initial sampling) taken from the EVHS domestic chargepoint installations claims received.

## OLEV will provide a sample of 5% of average monthly domestic chargepoint installations, currently 40 (5% of 800).

## As part of the desk-checking, the service provider is to obtain customer full contact details (as OLEV only holds address details of installations) from the EVHS installers, which they are required to make available under the terms of the grant.

## The service provider will also be required to carry out on-site visits to the sampled installations.

## The service provider will provide summary reporting (as detailed below).

## There is provision for an escalation in the number of on-site visits to a number agreed with OLEV, should OLEV require additional on-site visits following concerns arising from the first on-site visits.

## Desk-checks and on-site visits for DRS and EVHS

## The service provider will need carry out the following checks as a minimum:

## Desk-checks:

### Check the claim evidence including claim form and photographs (for EVHS) for each chargepoint installation to determine any indication of a high risk of non-compliance with any of the terms and conditions as outlined in the DRS and EVHS guidance documents (e.g. evidence of subsidisation, standardisation or over-inflation of costs for stated time and materials); and

### Each desk-check to be recorded on a desk-check worksheet.

## On-site visit checks:

### Determine that a chargepoint has been installed and is working;

### Determine that the chargepoint installation meet the requirements set out in the DRS and EVHS guidance terms and conditions (e.g. off-street parking and proximity of chargepoint to parking);

### Determine compliance with technical specifications (eg. chargepoints are fitted safely and securely; meeting the requirements set out in the IET Code of Practice; UK wiring regulations; and building regulations);

### Assess the chargepoint installation to determine that the stated time and materials taken are realistic and make a judgement as to whether or not declared costs are a true reflection of actual costs; and

### Each on-site visit to be recorded on an on-site worksheet (with photographs).

## Further desk-checks and on-site visits

## There is provision for an escalation in the number of extra on-site visits (on a call-off basis) to a maximum of 100, should OLEV require additional on-site visits following concerns arising from the first on-site visits.

## Reporting

## Summary reports should be produced for the DRS installations and the EVHS installations in the initial period and monthly periods; and submitted to OLEV electronically using a mixture of formats to display information concisely and legibly so they are understandable (e.g. narrative, graphs, charts and tables) demonstrating the range of audit checks.

## The format of the summary reports is to be determined in agreement between OLEV and the service provider, subject to that the summary reports should include as a minimum:

## the numbers of checks carried out (broken down by scheme) by desk-checks and on-site visits to chargepoint locations;

## the number of issues found broken down by issue type;

## the number of passes/fails;

## cumulative number of checks in the financial year;

## cumulative number of issues broken down by issue type in the financial year; and

## cumulative number of passes/fails in the financial year.

## A final review report document is to be provided by the service provider and agreed by OLEV within 4 weeks of the end of the on-site visits.  The final review report is to include lessons learned from both the various infrastructure grant schemes and on the on-site visits audit, with recommendations for the grant schemes including any for risk reduction.

# SERVICE LEVELS AND PERFORMANCE

## OLEV will measure the quality of the service provider’s delivery by achievement of Milestones in The Project Timetable below:

## OLEV shall have the right to require the service provider to include any reasonable changes or provisions in The Project Timetable.

## The service provider shall perform its obligations so as to achieve each Milestone by the Milestone Date.

## Changes to the Milestones shall only be made in accordance to an agreed variation procedure and provided that the service provider shall not attempt to postpone any of the Milestones using the variation procedure or otherwise (except in the event of a OLEV default which affects the service provider's ability to achieve a Milestone by the relevant Milestone Date).

## OLEV will monitor the service provider’s performance through monthly, and ad hoc reporting and through review meetings. Review meetings will be monthly, but for the first 2 months will be every two weeks to ensure the smooth transfer of administration. Ad hoc meetings can be arranged to discuss any issues which arise.

## At the end of the contract, OLEV requires the service provider to do a handover, with a final review report.

# LOCATION

## The location of the chargepoint installations for OLEV’s infrastructure grant schemes are across the United Kingdom.

# SECURITY REQUIREMENTS

## The service provider will hold and process data that is marked as OFFICIAL-SENSITIVE (PERSONAL) under HMG Security Policy Framework and must comply with its mandatory requirements for data processing. The service provider has a duty of confidentiality and a responsibility to safeguard the data that they process and shall not to use it for any other purpose other than is necessary to fulfil these requirements.

# PROJECT TIMETABLE

| Milestone | Deliverables (bulleted list showing all Deliverables (and associated tasks) required for each Milestone) | Duration (Working Days) | Milestone Date | OLEV Responsibilities (if applicable) |
| --- | --- | --- | --- | --- |
| Desk-checks of DRS and EVHS initial period sampled domestic chargepoint installations | Desk-checks evidenced by production of desk-check worksheets | 10 (over 2 weeks) | 2 weeks from contract award | OLEV will provide the locations of the sampled domestic chargepoint installations for desk-checks; and on-site visits OLEV will liaise with service provider regarding summary report format and contents OLEV to attend review meetings |
| On-site visit audit of cross-section of DRS and EVHS initial period sampled domestic chargepoint installations | On-site visits evidenced by production of on-site worksheets and photographs; and monthly summary reports for on-site visits | 40 (over 8 weeks) | 10 weeks of contract award | OLEV to attend review meetings |
| Desk-checks and on-site visits of EVHS monthly sampled domestic chargepoint installations. | Desk-checks evidenced by production of desk-check worksheets On-site visits evidenced by production of on-site worksheets and photographs; and monthly summary reports for on-site visits | Pro-rata to that for initial period | Monthly | OLEV to attend review meetings |
| Production of a final review report document | Final review report document | 20 (over 4 weeks) | 4 weeks following last required monthly period desk-checks and on-site visits. | OLEV will liaise with service provider regarding final review report format and contents |

# BUDGET

## OLEV requires for the following:

## a blended pricing with a capped element and a call-off element;

## the capped element being (for the duration of the DRS and EVHS initial period checking):

## a fixed price for the overheads of the contract;

## a fixed price for each desk-check of a DRS or EVHS domestic chargepoint installation; and

## a fixed price for each on-site visit of a DRS or EVHS domestic chargepoint installation.

## the call-off element being (for the occurrence of any escalation checks and/or for the duration duration of the EVHS monthly period checking):

## a fixed price for each desk-check of a DRS or EVHS domestic chargepoint installation; and

## a fixed price for each on-site visit of a DRS or EVHS domestic chargepoint installation.

## The above excludes any travel and subsistence costs.  Travel and subsistence costs to be submitted as expenses and are to be in accordance with Department for Transport Travel and Subsistence policies.

## These should be submitted in pounds sterling and be inclusive of expenses and exclusive of VAT.

## The duration of this contract will cover the period from contract start date to end of March 2018 with the option to extend at OLEV’s discretion.

## OLEV would expect invoices to be issued in line with the satisfactory completion of the deliverables in accordance with The Project Timetable.