## RAD
ANNEX 1 RAD ITT |  |  |  |  | RAD Use Only
Supplier name
Contact
Company Number
VAT Number
Confirmation that you the supplier are able to meet the requirements outlined in the brief above.
Date of response
| REQUIREMENT | COMMENT | RESPONSE | Sprint No.
2.1 | Undertake concept workshop and develop User Stories with RAD, hardware developer and naval architect at tenderers offices. Define provisional sprint content and work with RAD and other suppliers to agree aligned programme (including dates and deliverables). | Describe approach to workshop.
2.2 | Select COTS development kit for RAD controller, battery and motor controller with RAD and hardware developer | State compliance, estimate sprint number.
2.3 | Build simple control architecture to connect processor board, battery & motor controller | State compliance, estimate sprint number.
2.4 | Research and select Internet of Things (IoT) cloud service | State compliance, estimate sprint number.
2.5 | Build simple interface using cellular connection to IoT service | State compliance, estimate sprint number.
2.6 | Display simple parameters in IoT web interface | State compliance, estimate sprint number.
2.7 | Commission and test COTS prototype on bench | State compliance, estimate sprint number.
2.8 | Interact with thruster designer for motor power and RPM data | State compliance, estimate sprint number.
2.9 | Develop motor controller firmware in partnership with motor controller designer | State compliance, estimate sprint number.
2.1 | Develop interface to motor controller from controller PCB using RAD Bus | State compliance, estimate sprint number.
2.11 | Test motor against thruster specifications on bench | State compliance, estimate sprint number.
2.12 | Develop firmware for Batter Management System (BMS) if required | State compliance, estimate sprint number.
2.13 | Develop BMS interface to RAD Bus and RAD Controller | State compliance, estimate sprint number.
2.14 | Test battery with firmware | State compliance, estimate sprint number.
2.15 | Full prototype RAD Controller software to meet system requirements | State compliance, estimate sprint number.
2.16 | Full prototype IoT interface | State compliance, estimate sprint number.
2.17 | Full prototype IoT web portal (RAD Cloud) | State compliance, estimate sprint number.
2.18 | Full prototype Wifi or bluetooth interface to app | State compliance, estimate sprint number.
2.19 | Full prototype phone app | State compliance, estimate sprint number.
2.2 | Interface onto Full Prototype hardware | State compliance, estimate sprint number.
2.21 | Test integrated Full Prototype hardware and software elements on bench | State compliance, estimate sprint number.
2.22 | Support to trials and tuning of system for 3 days, test each IoT function, allowance for system hardening and documentation to close out project. | State compliance, estimate sprint number.
2.23 | Sprint report meeting will be hosted in Cornwall, UK every two weeks | State compliance
2.24 | Documented experience of at least one ‘electric assist’ project | Please provide evidence (max 1 side A4)
2.25 | Documented experience of at least one brushless motor control project | Please provide evidence (max 1 side A4)
2.26 | Documented experience of embedded firmware development | Please provide evidence (max 1 side A4)
2.27 | Documented evidence of web development | Please provide evidence (max 1 side A4)
2.28 | Documented evidence of phone app development | Please provide evidence (max 1 side A4)
2.29 | Completed at least 5 years of agile software development projects | Table of example projects and dates
2.3 | Space for hardware in the loop testing | Wrtitten description of facilities.
2.31 | At least 3 agile teams to provide a level of redundancy for varying workloads | Written description of business structure and team.
2.32 | All foreground intellectual property will be supplied to RAD Propulsion Ltd and will be subject to a separate agreement to be signed prior to award of contract and any background IP used will be provided with a royalty free license for unlimited use. | Compliance statement.
4 | Conflict of Interest Statement | Please provide statement as per the options at section 4 in the ITT
Costs
| Sprint 1 | £
| Sprint 2 | £
| Sprint 3 | £
| Sprint 4 | £
| Sprint 5 | £
| Sprint N | £
Total (EX VAT) |  | £