|  | Short Contract |
| --- | --- |

# Slade Brook Reservoir Seepage Repairs

# A contract between	North Northamptonshire Council (the Employer)

# and	The Contractor

# for	Slade Brook Reservoir Seepage Repairs

Contents:

Contract Forms

  - Contract Data

    - The Contractor’s Offer

    - The Employer’s Acceptance

    - Price List

    - Works Information

    - Site Information

  - Conditions of Contract

| # Contract Data |  |  |
| --- | --- | --- |
|  | The Employer |  |
| Name | North Northamptonshire Council |  |
| Address | Sheerness House, 41 Meadow Road, Kettering, NN16 8TL |  |
| Telephone | 0300 126 3000 |  |
| E-mail address | Dylan.smith@northnorthants.gov.uk |  |
| The works are | Seepage repairs to the embankment at Slade Brook Reservoir |  |
| The site is | The location of the reservoir is at National Grid Reference SP 864 770. The site is the Slade Brook Reservoir embankment and accesses to the Works from the public highway and the compound areas used by the Contractor. |  |
| The starting date is | xx 2022 |  |
| The completion date is | xx 2022 |  |
| The period for reply is | 2 weeks |  |
| The defects date is | 52 weeks after Completion |  |
| The defects correction period is | 4 weeks |  |
| The delay damages are | £500 per day |  |
| The assessment day is | the last working day of each month |  |
| The retention is | 5% |  |
| Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) Apply? |  | Yes |
| The Adjudicator is | the person appointed as follows: |  |
|  | In the event that a first dispute is referred to adjudication, the referring Party at the same time applies to the Institution of Civil Engineers to appoint an Adjudicator. The application to the Institution includes a copy of this definition of the Adjudicator. The referring Party pays the administrative charge made by the Institution. The person appointed is also Adjudicator for later disputes. |  |
| # Contract Data |  |  |
| The interest on late payment is xx% per complete week of delay or per annum above the Bank of England Base Rate. |  |  |
| The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of £10,000,000 for any one event |  |  |
| The Employer provides this insurance None |  |  |

Insurance Table. Event; Cover; Cover provided until. Loss of or damage to the works; £10,000,000. Loss of or damage to Equipment, Plant and Materials. The Contractor’s liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Works. Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract. Failure of the Contractor to use the skill and care normally used by professionals providing works similar to the works.

The Adjudicator nominating body is The Institution of Civil Engineers

The tribunal is litigation in the courts

If the tribunal is arbitration, the arbitration procedure is The Institution of Civil Engineers Arbitration Procedure (1997).

The conditions of contract are the NEC3 Engineering and Construction Short Contract April 2013

| # Contract Data |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # The Contractor’s Offer |  |  |  |  |  |  |  |  |  |
| The Contractor is |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  |  |
| Address: |  |  |  |  |  |  |  |  |  |
| Telephone Fax |  |  |  |  |  |  |  |  |  |
| E-mail address |  |  |  |  |  |  |  |  |  |
| The percentage for overheads and profit added to the Defined Cost for people is …… %. |  |  |  |  |  |  |  |  |  |
| The percentage for overheads and profit added to other Defined Cost is …… %. |  |  |  |  |  |  |  |  |  |
| The Contractor offers to Provide the Works in accordance with the conditions of contract for an amount to be determined in accordance with the conditions of contract. |  |  |  |  |  |  |  |  |  |
| The offered total of the Prices is | £…………………………….. |  |  |  |  |  |  |  |  |
|  | Enter the total of the Prices from the Price List. |  |  |  |  |  |  |  |  |
| We declare that this tender was prepared and is submitted in good faith. We declare that we have not communicated to any person other than the Employer the amount or the approximate amount of the offered total of the Prices and the Prices have not been adjusted or fixed by arrangement or in collusion with any third party (other than in confidence to obtain insurance quotations or finance required in connection with the tender). We undertake that we will not enter into any such communication or enter into a collusive arrangement whether in relation to this tender or a tender submitted or to be submitted by a third party. We also undertake that we have not and will not - corruptly solicit, receive or agree to receive; or - offer or agree to give directly or indirectly to any employee, consultant or contractor of the Employer; any thing, service or money for doing or not doing anything or showing favour or disfavour to any person, in relation to this contract or any other contract to which the Employer is party. If we or an employee or authorised agent or subcontractor or consultant are in breach of the above declarations and undertakings we agree that the Employer may terminate the contract and the payment due is assessed as if clause 90.3 (Reason 3) applied. |  |  |  |  |  |  |  |  |  |
| Signed on behalf of the Contractor |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  |
| Position |  |  |  |  |  |  |  |  |  |
| Signature |  |  |  |  | Date |  |  |  |  |
| # Contract Data |  |  |  |  |  |  |  |  |  |
| # The Employer’s Acceptance |  |  |  |  |  |  |  |  |  |
| The Employer accepts the Contractor’s Offer to Provide the Works. |  |  |  |  |  |  |  |  |  |
| Signed on behalf of the Employer |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  |
| Position |  |  |  |  |  |  |  |  |  |
| Signature |  |  |  | Date |  |  |  |  |  |

# Contract Data

# Price List

See separate pricing document Pricing Schedule - Sladebrook Reservoir Seepage Repairs

# Contract Data

# Works Information

- Description of the Works

The project involves seepage repairs to the embankment at Slade Brook Reservoir. Works are described in the Scope of Works Note, dated 10th June 2022.

- Drawings

The Drawings show the existing layout/previous works and comprise:

Location Plan

Site Plan

231469/001 Slade Brook Reservoir Crest Repair Works

Gate Valve Technical Layout

The Contractor designs and constructs the works in accordance with the Scope of Works Note and the Drawings.

One paper copy of the Drawings shall be marked up by the Contractor in red as the As-Built drawings and supplemented by sketches prepared by the Contractor to describe the works carried out.

- Specifications

The works shall be in accordance with the Civil Engineering Specification for the Water Industry 7th edition. Particular Specification requirements are detailed in the Scope of Works Note.

- Constraints on how the Contractor Provides the Works

The Contractor Provides the Works in a manner that incorporates best practice techniques. The Contractor will conduct the works in a sustainable manner protecting the environment and implementing high safety standards during construction. In particular the Contractor shall put in place measures to prevent pollution arising from grouting works

The working hours should be limited to 8am to 6pm Monday to Friday. No working on weekends, Bank Holidays or other Public Holidays without prior agreement with the Employer. People do not remain on the site overnight without the written agreement of the Employer.  Any work outside the above working hours will require approval of the Employer.

- Requirements for the Programme

The programme for these works is expected to be approximately 4 weeks long. The Contractor is requested to submit a programme of the expected works detailing the time scale for each task.

- Services and other things provided by the Employer

Details where available of the embankment and bottom outlet will be provided.

The Contractor is to undertake appropriate measures to protect any services affected by the proposed works.

The Contractor ensures that no damage occurs to existing structures, roads, paths and services.  Any such damage is repaired at the Contractor's own expense.

- General Constraints

The Contractor enters the site on the date agreed with the Employer.

The Contractor notifies the Employer of any additional working areas that he has negotiated outside the site before entering them.

The Contractor keeps records of the dates of his first entry onto and departure from all property and lands of each owner and occupier (including public highways, footpaths and thoroughfares) together with the dates of the erection and removal of all temporary fencing.

The Contractor confines his construction operations within the site.

The following working constraints apply to the site:

- The Contractor complies with the operational requirements of the Employer during the works.

- The Contractor’s vehicular traffic shall only use the access route as shown in the Drawings.

- The Contractor’s activities shall not disrupt or prevent access to Kettering Golf Club or neighbouring properties.

- Any hard standing created by the Contractor shall be removed and made good on Completion.

- Access

Access to the embankment shall be via the timber gates at both abutments. No other access shall be used without the Employer’s written agreement.

Any access provisions made by the Contractor shall be removed and made good on Completion.

Access for construction plant across the dam shall be limited to avoid loading the structure of the dam. Details of the plant proposed shall be submitted to the Employer.

- Entry to the site

The Contractor notifies the Employer at least 7 days in advance of his intention to first enter the site.

The Contractor helps the Employer in keeping the owners and occupiers in and around the site informed of the effect of the works on their land as required by the Employer.

The Contractor keeps photographic record of condition of the access route and the site compound.

- Site Tidiness and Site Waste Management plans

The Contractor keeps the site tidy and promptly removes rubbish, waste and surplus. Materials, Plant and Equipment are positioned, stored and stacked in a safe and orderly manner.

- Site Fencing

The Contractor adequately fences the site including all access routes and erects fencing and gates before other work starts in that part of the site. The Contractor regularly inspects and maintains all site fencing and gates, and promptly repairs damage.

- Contractor’s compounds, storage areas and site roads

The compound area location shall be agreed with the Employer.

The Employer arranges for permission for the compound.

Except as may be otherwise required by the Works Information, the Contractor designs, constructs, maintains, and afterwards removes and reinstates temporary accommodation, services, compounds, storage areas, site  roads and accesses required for the works. The Contractor submits details of his design and reinstatement proposals to the Employer for acceptance.

Reinstatement work includes the removal of all materials used in the construction of the roads, and restoring the area to at least its original degree of safety, stability, drainage and appearance - unless specific acceptance is otherwise given by the Employer.

- Surveys of highways, properties and land

Shortly before first entry, the Contractor undertakes a joint inspection with the Employer, a  ‘Pre-starting condition survey’ of all highways,  structures and land including access routes, trees, boundaries, crops and any other features which may be affected by the works, within the boundaries of the site .

The Contractor undertakes a similar joint inspection, a ‘Post-completion condition survey’ when the works are complete, and on dates agreed with the Employer.

The Contractor gives at least 3 working days’ notice to the Employer prior to any condition survey.

Condition surveys include written text descriptions and photographs of the existing condition of the land and other areas.

- Protection against damage

The Contractor does not damage highways, roads, properties, land, trees, roots, crops, boundaries and any other features, and the apparatus of Statutory undertakers, the Highways Authority and others. Damage by the Contractor of anything on the site is a Contractor’s risk.

The Contractor protects the works, Materials, Plant and Equipment liable to damage either by the weather or by the method used for carrying out the works.

The Contractor takes all reasonable measures to control the generation of dust and mud resulting from his activities, including:

- limiting vehicle speeds to a maximum of 5mph on site  and on unsurfaced roads;

- covering dust-creating materials being delivered to or removed from site  on the truck;

- cleaning vehicles leaving site ;

- Immediately removing any debris deposited on the public highway.

- Environmental Best Practice

The Contractor Provides the Works in accordance with environmental best practice. The Contractor’s attention is drawn to the following documents:

- BRE – Green Guide to Specification.

- BRE - Materials Information Exchange

- CIRIA, SP122 – Waste Minimisation and Recycling in Construction (practical guidance)

- CIRIA, C513 – The Reclaimed and Recycled construction materials Handbook.

- CIRIA, C533 – Environnemental Management in Construction

- Considerate Constructor Scheme

- Environment Agency Guidelines for obtaining all timber from sustainable source

- General Guide to the Prevention of Water Pollution: PPG1

- Above ground oil storage tanks: PPG2

- Works in, near or liable to affect Watercourses: PPG5

- Working at Demolition and Construction Sites: PPG6

- Refuelling Facilities: PPG7

- Dewatering underground ducts and chambers:PPG20

- Pollution Incidents Response Planning: PPG 21

- Operational Instructions 63-05: SD02 and SD06 (Environment Agency, 2008d; 2008e)

The Contractor demonstrates his proposals to minimise environmental impacts and to comply with environmental best practice principally through the content of, and adherence to, his Method Statements.

- Control of pollution requirements

The Contractor’s attention is drawn to the control of pollution provisions in the Water Resources Act 1991.  The Contractor takes all necessary precautions to ensure that no polluting discharge either of solid or liquids is made to any watercourse or to the underground strata and that no work carried out in any watercourse is done in such a manner as to cause pollution.  Any materials which accidentally fall into any watercourse are removed immediately.

The Contractor obtains the consent of the Environment Agency before making any discharge to any watercourse or the underground strata.

The Contractor takes all necessary precautions to protect all watercourses, together with water in underground strata, against silting, erosion and pollution.

The Contractor ensures that:

- All fuel, hydraulic fluids, lubricating oils or chemicals are not to be stored on site;

- Equipment which leaks any fuel, lubricant or hydraulic fluid is not used, and all static Equipment using fuel oil is located as far away as reasonably possible from any watercourse and surrounded by oil-absorbent material to contain spills or leaks;

- Refuelling or servicing of Equipment is not permitted on site;

- An adequate supply of oil absorbent Materials is readily available in the Working Areas at all times. Any spillage is immediately contained, removed from the Working Areas and disposed of to a licensed tip and the Employer promptly informed;

- Water pumped from embankment excavations and chambers is to be discharged into the reservoir and not irrigated over the embankments;

- Access roads and approaches to watercourses are regularly scraped and maintained free from deposits of slurry.  Any slurry so removed is disposed of in a location agreed by the Employer avoiding pollution of the watercourse.  Precautions are taken to ensure surface water drains are not contaminated by solids from workings and associated transport;

- Equipment parking and servicing areas and wheel washing facilities are located with the acceptance of the Employer;

- Any imported fill or construction material is free from polluting or toxic substances where drainage from the material can directly enter surface or underground waters;

The Contractor is not permitted to store fuel or hazardous substances on site without prior agreement from the Employer.

The Employer is informed before any hazardous substances are brought on site along with the associated COSSH assessments.

The Contractor ensures that the storage, handling, use and disposal of any potentially hazardous materials is carried out in accordance with the relevant statutory provisions and Health and Safety Executive (HSE) Codes of Practice and Guidance Notes.

The Contractor consults the relevant statutory bodies including the HSE, Fire Authority, the Environment Agency, and the Local Authority (Emergency Planning) and follows any procedures to limit the spread of pollution in the event of an incident.

All site staff are trained so that they can undertake the following actions upon discovery of a pollution incident:

  - raise the alarm and contact the appropriate site  staff and authorities

  - locate the pollution control equipment

  - deploy pollution control equipment in an appropriate and effective manner so as to contain and limit pollution until such a time as the appropriate authorities arrive on site .

- Trees and vegetation

The Contractor protects all trees within the boundaries of the site or whose canopies cross the boundaries of the site that are to be retained, in accordance with BS5837: 1991 Guide for Trees in relation to construction.

The Contractor does not remove or prune any trees, shrubs or hedges unless indicated on the drawings or authorised by the Employer.

- Environmentally considerate hydraulic fluids

The Contractor endeavours to utilise Equipment which uses environmentally considerate hydraulic fluid (either a synthetic ester or a vegetable oil-based derivative) in their hydraulic systems.

- Contractor’s Design

The Contractor shall use the Scope of Work Note to provide a method statement to carry-out the works. If the Contractor provides an update to the design, the design should be submitted to the Employer for acceptance.

- Completion

The work required for Completion is:

- Construction of the works in accordance with the Works Information

- Reinstatement and site clearance

- Programme

The Contractor provides an outline project programme for delivery. The Contractor includes the following information as separate activities in the programme:

- the starting date

- site mobilisation

- dates of commencement of the works

- dates of completion of the works

- The Completion Date.

- Quality

  - Plant and material acceptances

The Contractor supplies samples of Materials to be used to the Employer for acceptance.

Samples are submitted before construction works begin and the Contractor allows the period for reply for gaining the Employer’s acceptance.

The samples are retained on site by the Contractor as references and are disposed of by the Contractor upon Completion.

  - Quality Management System

The Contractor operates a Quality Management System complying with BS EN ISO 9002.

The Contractor describes the Quality Management System in a Quality Plan, which is provided to the Employer for acceptance within 14 days of the date when this contract comes into existence.

The quality of the work is controlled by the Contractor as set out in the Quality Plan accepted by the Employer.

  - Quality Control

The Contractor’s Quality Control Manager certifies that activities have been carried out in accordance with the Works Information when an experienced and qualified works checker has checked and certified that Materials, workmanship, cleanliness and other matters are correct

Copies of relevant supporting certificates relied on by the Quality Control Manager are attached to his certificate.

The Employer may at any time audit the quality control process and for this purpose is given assistance and access by the Contractor to:

- documents used in connection with the certification process, including but not limited to site diaries, calibration certificates, memos, and to interview persons involved in Providing the Works.

  - Efficiency Initiative

The Contractor seeks opportunities to Provide the Works more efficiently and discusses these opportunities with the Employer.

- Management of the works

  - Reporting requirements

Brief weekly reports are submitted in writing to the Employer in a form to be agreed, covering the items listed below:

- Schedule of the main work items in each section of the work showing quantitative progress during the previous week and cumulative progress to date.

- Plant at the site.

- Accidents to Employees reportable by Statute.

- Weather conditions and reservoir water levels on each day and night.

- Photographs of the progress of the works

The Contractor shall also provide information confirming the dimensions of the chamber and the dimensions and condition of the stoplog grooves within the chamber.

  - Photographs

In addition to the photographs taken during ‘pre-starting condition survey’ the Contractor  takes regular photographs of the work as it progresses and as further required by the Employer.

The photographs are taken by a competent photographer using a digital camera. All photographs are date stamped.

Upon Completion, the Contractor ensures that all photographs have been passed to the Employer and they become the property of the Employer. The Contractor ensures that no use is made of the photographs without the written acceptance of the Employer.

  - Progress meetings

No formal progress meetings are required.

  - Contractor’s submissions

All submissions required from the Contractor under the contract are numbered sequentially.

  - VAT certificate

Immediately upon receipt of payment, the Contractor issues to the Employer a VAT receipt.

If the Contractor does not provide a VAT receipt, the Employer may retain further payments due to the Contractor until the receipt is provided and any other consequential requirements of the VAT regulations are satisfied.

- Services and other things to be provided

  - Facilities and Services to be provided by the Contractor

    - Accommodation for the Contractor

For the use of the Contractor’s employees and workforce, the Contractor provides temporary offices, sanitary arrangements, compounds, parking areas and the like necessary for the completion of the works and correction of Defects. The general siting and layout of these is to the acceptance of the Employer.

  - Facilities and services to be provided by the Employer

Not Required.

  - Equipment and materials provided by the Employer

None.

- Health and Safety

  - Site Specific

The work will involve working closely to water and precautionary measures should be undertaken to address the health and safety risks of the works. Method statements should include a risk assessment of each of the works process.

  - CDM Regulations

The Construction (Design and Management) Regulations 2015 (the CDM Regulations) apply to the works. The project is not considered to be notifiable to the HSE. If the Contractor considers that the project will last more than 30 days and has more than 20 workers or involve more than 500 person days of construction work or will involve more than one contractor the Contractor informs the Employer.

The Principal Designer is provided by the Employer.

Pre-construction information is shown on the drawings and described below the Contractor shall prepare a construction phase plan appropriate to the size and complexity of this project.

  - Emergency arrangements

The Contractor maintains arrangements whereby he can call out labour, equipment and material to carry out any work needed for an emergency associated with the works.

The Contractor acquaints himself and his employees with any relevant emergency arrangements including those of the Employer.

The Contractor gives reasonable access to members of the emergency services who may inspect the site.

The Contractor provides access to all parts of the site for the Employer’s Operations staff to undertake emergency inspections or repairs.

  - Floods

The reservoir is classed as a large raised reservoir under the Reservoirs Act 1975. In Providing the Works the Contractor ensures that activities do not increase the risk of an escape of water from the reservoir.

  - Site Security

The Contractor is responsible for the security of the site and of vehicles and pedestrians entering and leaving the site.

The Contractor ensures that the site gates are closed after the passage of vehicles or personnel on each and every occasion. Gates are not left open.

The Contractor ensures that the site is left properly secured at the end of each working day.

- Method Statements

Method statements provided for acceptance include full particulars of the methods, timing and sequence of construction including the use and design of temporary works, Materials and Plant and Equipment proposed by the Contractor.  Method statements contain sufficient information to enable the Employer to assess any likely detriment either to the proposed or the existing works or to the Employer’s overall objectives.

The Contractor issues method statements in advance of carrying out items of work. The Contractor allows the period for reply for acceptance or rejection of method statements. Work does not commence until the Employer has accepted the relevant method statement. The Contractor does the work in accordance with the accepted method statement.

Method statements submitted with a programme for acceptance are to include but are not limited to the following matters:

- Health & safety measures

- Extent of Working Areas and protective barriers

- Access to Working Areas

- Injection grouting

- The implementation of relevant statutory regulations

- The design and construction of temporary works and de-watering measures

- How the environmental impact of the activities are to be minimised

- Equipment requirements, siting and mode of operation

- Labour requirements and supervision

- Delivery and storage of Materials

- Provision of access to third parties

- Details of the construction sequence

- Details of working methods

- Detailed programme with Key Dates

- Result of any consultation with third parties

- Contingency plans in the event of flooding, other difficulties or emergencies

- Risk and COSHH assessments.

# Contract Data.

# Site Information

1 Location of the Works

The project is located at Slade Brook Reservoir. The location of the reservoir is at National Grid Reference SP 864 770.

2 Access

The Contractor protects the condition of all access roads and tracks and access road and track interfaces (such as drop kerbs, footpaths, etc.). The Contractor also repairs any damage caused during access.

Access to the site shall be from Thurston Drive and the access road to Kettering Golf Club. The arrangements of the traffic management and site access should be discussed and approved by the Employer.

3 Landowner Information

Land within the site is owned by the Employer.

4 Pre-construction Health and Safety Information

Pre-construction Health and Safety Information is shown on the Drawings and in the Designers’ Hazard Elimination and Management Record below.