Tender No.	DIOCB2/010

CONTRACT DATA Part one – Data provided by the Employer

Booklet 2 to

DIOCB2/010

Completion of the data in full, according to the Options chosen, is essential to create a complete Works Contract.

Statements given in all contracts

1 General	   The conditions of contract are the core clauses and the clauses for the nec3

Engineering and Construction Contract (Option A) as amended by and read in conjunction with this Standalone Contract.

   Secondary Option clauses specific to this Project are:

Option X4 – Parent Company Guarantee Option X5 – Sectional Completion. Option X6 – Bonus for early Completion.

Option X7 – The delay damages to be paid.

Option X13 – Performance Bond

Option X15 – Limitation of Contractors Liability for his design to reasonable skill and care.

   The works are:

Works Package E - Design and Construction of a New Build Hangar and

Airfield Operating Surfaces (OCU, Feeder, Security, AOS & AGL)

   The Employer is:

Defence Infrastructure Organisation

First Floor, Bazalgette Pavilion, RAF Wyton, Huntingdon, Cambs. PE28 2EA

   The Project Manager is:

Principle Project Manager

First Floor Bazalgette Pavillion

RAF Wyton

Huntingdon

Cambs, PE28 2EA

   The Commercial Officer is:

Senior Commercial Officer, DIO First Floor Bazalgette Pavillion RAF Wyton

Huntingdon

Cambs, PE28 2EA

   The Supervisor is:

To be advised

   The Adjudicator is: TeCSA

Aldwych House

71-91 Aldwych

London

WC2B 4HN

   The Works and Site Information is in Annex W to the Tender Notice.

   The boundaries of the site are shown in the drawings at Annex W to

DIOCB2/010 (Project Specification)

   The period for reply is 2 weeks

   The Adjudicator nominating body is TeCSA

   The following matters will be included in the Risk Register - NOT USED

2 Time	   The starting date is the date of contract award.

   The access date will be no earlier than two weeks after Contract Award.

   The first programme complying with clause 31.2 shall be submitted within 2 weeks of the Contract Award.

   The Contractor submits revised programmes at intervals no longer than monthly intervals.

3 Testing and

Defects

   Tests and inspections to be carried out by the Contractor are:

a)	As detailed within the Works Information (if specific Employer requirements are defined),

b)	as set out in the Accepted Programme,

c)	as proposed by the Contractor in his testing and inspection schedule, and d)	all inspections and tests that a responsible and experienced contractor

would carry out.

	The defects date is 52 weeks after Completion of the whole of the works.

   The defect correction period is 52 weeks except that as detailed in Clause 43.2 to Engineering and Construction Contract (Option A).

4 Payment	   The assessment interval is NOT USED.

5 Compensation events

   The interest rate is as detailed in Engineering and Construction Contract (Option

A) Clause 50.1

   The Bill Paying Branch is Ministry of Defence, DBS Finance, Walker House, Exchange Flags, Liverpool. L2 3YL

 .The place where weather is to be recorded is

.RAF Marham Met Office. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .

.

|  The weather measurements to be recorded for each calendar month are:  the cumulative rainfall (mm)  the number of days with rainfall more than 5 mm  the number of days with minimum air temperature less than 0 degrees Celsius  the number of days with snow lying at 0900 hours GMT  and these measurements: ……NOT USED  The weather measurements are supplied by the …Met Office . . . . . . . . .  The weather data are the records of past weather measurements for each calendar month which were recorded at RAF Marham. Where no recorded data is available Assumed values for the ten year return weather data for each weather measurement for each calendar month are…. NOT USED |  |  |
| --- | --- | --- |
| 6 Risks and insurance |  Insurances and limits of indemnity will be required in accordance with Contract Condition 84. |  |
| Optional statements | If the tribunal is arbitration  The arbitration procedure is detailed in Clause W1.1 to W2.31 of Engineering and Construction Contract (Option A).  The place where arbitration is to be held is to be agreed by both parties.  The person or organisation who will choose an arbitrator if the Parties cannot agree a choice or if the arbitration procedure does not state who selects an arbitrator is TeCSA. |  |
| If the Employer has decided the completion date for the whole of the works  The completion date for the whole of the works is 30th Aug 2019 If the Employer is not willing to take over the works before the Completion Date : NOT USED If no programme is identified in part two of the Contract Data  The Contractor is to submit a first programme for acceptance within 2 weeks of Contract Award. If the Employer has identified work which is to meet a stated condition by a key date – |  |  |
|  | condition to be met 1 Progress the design for all contract works and submit a design review package for a 65% JPO Design Review, in accordance with the JPO Design Review Checklist and Design Review Submittal Criteria. 2 Progress the design for all contract works and submit a design review package for the fully coordinated design to RIBA Stage 3. 3 Progress the design for all contract works and submit a design review package for a 95% JPO Design Review, in accordance with the JPO Design Review | key date 13-Oct-2017 24-Nov-2017 04-Dec-2017 |

Checklist and Design Review Submittal Criteria.

4         Progress the design for all contract works and submit  a  design  review  package  for  the  fully coordinated design to RIBA Stage 4.

5         Completion of AOS / AGL works - Phase 1A

6         Completion of AOS / AGL works - Phase 1B

7         Completion of AOS / AGL works - Phase 2 and installation of frangible fence at the 01 end of the Secondary runway.

8         Completion of AOS / AGL works - Phase 3

9         Completion of AOS / AGL works - Phase 4 and new Aircraft Shades, management cabin and Floodlighting at the Squadron ASP.

10       Completion  of  site  security  works,  (excluding OCU building security measures) and completion of site wide services installations incl. power, water, gas, comms.

11       Completion   of   Pilot   Conditioning   /   Feeder Facility, including installation of specialist equipment, furniture and services.

12       Completion of AOS / AGL works - Phase 5A

13       Completion of AOS / AGL works - Phase 5B

14       Completion of AOS / AGL works - Phase 6A Main Runway and

installation of frangible fence at the 06 end of the Main runway.

15       Completion of AOS/AGL - Phase 6B

16       Completion of AOS/AGL - Phase 6C

17       Completion     of     OCU     Building     including installation of specialist equipment, furniture, services and security measures.

18       Completion of new Ground Service Equipment

Store (GSES).

19       Completion of AOS / AGL works - Phase 7

20       Completion of AOS / AGL works - Phase 8A

21       Completion of AOS / AGL works - Phase 8B

22       Completion of AOS / AGL works - Phase 8C

26-Jan-2018

29-Nov-2017

28-Feb-2018

23-Mar-2018

06-Apr-2018

29-Jun-2018

01-Jun-2018

29-Jun-2018

17-Aug-2018

20-Jul-2018

15-Feb-2019

21-Sep-2018

01-Feb-2019

01-May-2019

03-Jun-2019

15-Feb-2019

22-Feb-2019

29-Mar-2019

26-Apr-2019

23       Completion of AOS / AGL works - Phase 9 and new Aircraft Shades, management cabin and Floodlighting at the OCU ASP.

24       Completion of External Works.

25	Complete submit and gain Employer's approval of all finalised record information, O&M Manuals, Health

& Safety files and associated documentation required

by  the  contract.  Achieve  issue  of  Project  Manager's

Certificate for completion of the works as a whole.

26       Achieve issue of the Project Manager's Defects

Certificate for the works as a whole.

If there are additional Employer’s risks

   These are additional Employer’s risks

21-Aug-2019

13-Aug-2019

30-Aug-2019

30-Aug-2019

| 001 | Delay in Final Capacity Utilities being delivered per programme via other Work Packages. |
| --- | --- |
| 002 | Existing Services not to line and level shown on drawings / design needs to be amended / programme delay and additional works. |
| 003 | Unforeseen ground conditions encountered. |
| 004 | Site access via new South HAS Contractor Gate not possible. |
| 005 | Large delivery loads required / Site access infrastructure may be inadequate / Temporary works may be required. |
| 006 | Japanese knotweed discovered / cost increase and programme delay. |
| 007 | Protected species may be discovered / delay or redesign required. |
| 008 | Uncharted services encountered / programme delay or redesign. |

If the Employer is to provide Plant and Materials

	The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Employer for an amount of ….  NOT USED

A list of the Employer’s Property provided is in….NOT USED

If Option X 4 is used….As indicated in the Tender Notice

If Option X5 is used

   The completion date for each section of the works is

section

Key

Milestone 1

description

Completion of Work as described against Key Date

1 above i.e. 65% JPO DR submission

completion date

13-Oct-2017

Key

Milestone 2

Key

Milestone 3

Key

Milestone 4

Key

Milestone 5

Key

Milestone 6

Key

Milestone 7

Key

Milestone 8

Key

Milestone 9

Key

Milestone

10

Key

Milestone

11

Key

Milestone

12

Key

Milestone

13

Completion of Work as described against Key Date

2 above i.e. completion of RIBA Stage 3

Completion of Work as described against Key Date

3 above i.e. 95% JPO DR submission

Completion of Work as described against Key Date

4 above i.e. completion of RIBA Stage 4

Completion of all Work as described against Key Date 5,6,7 & 8 above i.e Completion of AOS / AGL works – Phases 1A, 1B, 2 & 3

Completion of Work as described against Key Date

9 above i.e Completion of AOS / AGL works - Phase 4 incl shades & Squadron ASP.

Completion of Work as described against Key Date

10 above i.e Completion of site security works, (excluding OCU building security measures) and

completion of site wide services installations incl.

power, water, gas, comms.

Completion of Work as described against Key Date

11 above i.e Completion of Pilot Conditioning / Feeder Facility, including installation of specialist equipment, furniture and services & security measures

Completion of all Work as described against Key Date 12, 13, 14, 15 & 16 above i.e. Completion of AOS / AGL works – Phases 5A, 5B, 6A, 6B & 6C

Completion of Work as described against Key Date

17 above i.e. Completion of OCU Building including installation of specialist equipment, furniture, services and security measures.

Completion of Work as described against Key Date

18 above i.e.Completion of GSES

Completion of all Work as described against Key Date 19, 20, 21, 22 & 23 above i.e. Completion of AOS / AGL works – Phases 7, 8A, 8B, 8C & 9 incl shades & OCU ASP

Completion of Work as described against Key Date

24, 25 &26 above i.e.Completion of External works, Take over docs & Defects

24-Nov-2017

04-Dec-2017

26-Jan-2018

06-Apr-2018

29-Jun-2018

01-Jun-2018

29-Jun-2018

15-Feb-2019

01-May-2019

03-Jun-2019

21-Aug-2019

30-Aug-2019

If Options X5 and X6 are used together

   The bonus for early completion of specific sections of the works  by incentivised dates is

section

Key Milestone 1 (Incentive 1)

Key Milestone 3 (Incentive 2)

Key Milestone 5 (Incentive 3)

Key Milestone 6 (Incentive 4)

Key Milestone 7 (Incentive 5)

Key Milestone 8 (Incentive 6)

description

Completion of Work as described against Key MIlestone 1 above i.e. 65% JPO DR submission

Completion of Work as described against Key MIlestone 3 above i.e. 95% JPO DR submission

Completion of all Work as described against Key MIlestone 5 above i.e Completion of AOS / AGL works – Phases 1A, 1B, 2 &

3

Completion of Work as described against Key MIlestone 5 & 6 above i.e Completion of AOS / AGL works - Phase 4 incl shades

& Squadron ASP.

Completion of Work as described against Key MIlestone 7 above i.e Completion of site security works, (excluding OCU building security measures) and completion of site wide services installations incl. power, water, gas, comms.

Completion of Work as described against Key MIlestone 8 above i.e Completion of Pilot Conditioning / Feeder Facility, including installation of specialist equipment, furniture and services & security measures

Incentived date

29-Sept-2017

20-Nov-2017

09-Mar-2018

15-Jun-2018

04-May-2018

01-Jun-2018

Incentivised

Amount

£50,000

£35,000

£1,000,000

£200,000

£250,000

£100,000

Key Milestone 9 (Incentive 7)

Key Milestone

10

(Incentive 8)

Completion of all Work as described against Key Milestone 9 above i.e. Completion of AOS / AGL works – Phases 5A, 5B, 6A,

6B & 6C

Completion of Work as described against Key MIlestone 10 above i.e. Completion of OCU Building including installation of specialist equipment, furniture, services and security measures.

31-Aug-2018

03-Apr-2019

£200,000

The above key milestones and bonus payments are fixed and cannot be adjusted as a result of any revision to the accepted programme resulting from Compensation Events.

If Option X6 is used (but not if Option X5 is also used)

The bonus for the whole of the works is……. NOT USED ….…..… per day.

If Option X7 is used ……

The delay damages to be paid by the Contractor shall be

if miss Key Milestone 1 & / or 3

per calendar day if miss Key Milestone 5

per calendar day if miss Key Milestone 6

per calendar day if miss Key Milestone 7

per calendar day if miss Key Milestone 8

per calendar day if miss Key Milestone 10

If Option X 13 is used…..  As indicated in the Tender notice

If Option X15 is used……

The Contractor is not liable for Defects in the works due to design so far as he proves that he used reasonable skill and care expected of a competent contractor experienced in undertaking the design of works of the same type, size, nature and complexity of works to ensure that his design complied with Works Information.

Security Aspects Letter

	The Security classification for this Project is set out in Annex W Works

Information and Site Information.

The Contractor shall use BIM (Level 2) (subject to security classification)

Cost Led Procurement

   The total Works Contract award value shall be no more than - NOT USED

For clarity, any reference to Secondary Option Clauses that are not applicable to the Tender requirements have been deleted from the Contract Data Part One