Invitation to Quote (ITQ)

Contract STA-0128-12

Provision of Item Writing for Key Stage 1 English grammar, punctuation and spelling

| Tenderer: |  |
| --- | --- |

TABLE OF CONTENTS

1	INTRODUCTION	3

Purpose	3

Structure	3

Disclaimer and Conditions	3

Freedom of Information and Transparency	3

2	INSTRUCTIONS TO TENDERERS	5

Tender Validity	5

Proposed Contract	5

Procurement Timescales	6

Clarification Questions	6

Preparation of Tender	6

STA Point of Contact	7

Confidentiality	7

Conflict of Interest	7

Value Added Tax	7

Submission of Tenders	7

Right to Reject/Disqualify	8

Debriefing	8

3	EVALUATION METHODOLOGY	9

Basis of Award Decision	9

Evaluation Process	9

Award Decision	9

4	SPECIFICATION OF REQUIREMENTS (SoR)	11

4.1	Background	11

4.2	Revised National Curriculum	11

4.3	Test Frameworks	11

4.4	Project Deliverables/Outputs and Critical Steps	12

4.5	Functional Requirements	16

5.   Tenderer's response…………………………………………………………………………….. 27

5.1 Key stage 1 English grammar, punctuation and spelling	27

6	Annexes	34

Annex A – Test Frameworks	34

Annex B – Item Classification Spreadsheet	34

Annex C – Cost Breakdown	34

Annex D – Copyright permission letter template	34

Annex E – Test Development External Suppliers Security Policy	34

Annex F – National Curriculum Test Design Specification	34

# INTRODUCTION

## Purpose

  - This ITQ has been issued by the Standards and Testing Agency (STA) for the purpose of securing items for tests in key stage 1 English grammar, punctuation and spelling

  - The delivery of the Item Writing Services will be governed by the DfE’s standard Contract for Item Writing Services which will be let in accordance with, and subject to, English law.

## Structure

  - This ITQ:

Outlines the planned procurement process;

Sets out the context for the required services and details of STA’s requirements; and

Contains a tender response section to evaluate the Tenderer's proposed solution to the STA requirements ("Tender").

## Disclaimer and Conditions

  - No information contained in this ITQ or in any communication made between STA and any Tenderer shall be relied upon as constituting a contract, agreement or representation that any contract will be offered.

  - STA reserves the right, subject to compliance with the Public Contracts Regulations 2006 (as amended), ("the Procurement Regulations"), to change without notice the basis of, or the procedures for, this ITQ or to terminate the ITQ at any time. Under no circumstances shall STA incur any liability in respect of this ITQ or any supporting documentation and STA will not reimburse any costs incurred by Tenderers or potential Tenderers in connection with preparation and/or submission of their Tenders.

  - The information contained within this document is confidential and should not be disclosed except for purposes related to the completion of the Tender.

  - STA is responsible for developing the National Curriculum assessments on behalf of DfE and must ensure that all contracted agencies and consultants are aware of, and comply with, the relevant sections of the current Ofqual Regulatory Framework.

For reference please refer to the Regulatory Framework for National Assessments: National Curriculum and Early Years Foundation Stage

http://www.ofqual.gov.uk/files/2011-regulatory-framework-for-national-assessments.pdf

## Freedom of Information and Transparency

  - As the executive agency of a public authority, STA is committed to open government and to meeting its legal responsibilities under the Freedom of Information Act 2000 (“FOIA”). Accordingly, Tenderers should be aware that all information submitted to a public authority may need to be disclosed by the public authority in response to a request under the FOIA and that, in addition, DfE may also decide to include certain information in the publication scheme, which it maintains under FOIA.

  - STA participates fully in the Government’s transparency arrangements. As such, Tenderers should be aware that:

- any contracts or agreements resulting from its procurement exercises may be published in full, subject to limited redactions in line with FOIA exemptions; and

- financial transactions in relation to any contracted goods or services will be published and so cannot be deemed commercially sensitive (see over).

  - If a Tenderer considers that any of the information included in its Tender is commercially sensitive, it should identify this information in the table below and explain a) what harm may result from disclosure if a request is received, and b) the time period applicable to that sensitivity. Tenderers should be aware that, even where they have indicated that information is commercially sensitive, STA may be required to disclose in response to a request under FOIA or as part of the Government's transparency arrangements. For example, the value of a contract must be made publicly available so this information cannot be deemed commercially sensitive.

| - Section | - Commercial Sensitivity | - Time Period |
| --- | --- | --- |

# INSTRUCTIONS TO TENDERERS

  - Tenderers should read these instructions carefully before completing their Tenders.

  - These instructions are designed to ensure that all Tenderers are given equal and fair consideration. It is important therefore that you provide all the information asked for in the format and order specified.

  - The Tenderer shall not make contact with any other employee, agent or consultant of STA who is in any way connected with this ITQ exercise during the period of this ITQ exercise, unless instructed otherwise by the Test Development Procurement Manager at STA, Rashida Akbar.

  - All material issued in connection with this ITQ shall remain the property of STA and shall be used only for the purpose of this ITQ exercise. Any confidential STA Information shall either be returned to STA or securely destroyed by the Tenderer (at STA’s option) at the conclusion of the exercise.

  - The Tenderer shall ensure that each and every proposed sub-contractor, consortium member and adviser abides by the terms of these instructions.

  - STA shall not be committed to any course of action as a result of:

Issuing this ITQ or any invitation to participate in this ITQ exercise;

Communicating with a Tenderer or a Tenderer’s representatives or agents in respect of this ITQ exercise; or

Any other communication between STA (whether directly or by its agents or representatives) and any other party.

  - Tenderers shall accept and acknowledge that, by issuing this ITQ, STA shall not be bound to accept any Tender and reserves the right not to conclude a contract for the services for which Tenders are invited.

  - STA reserves the right to amend, add to, or withdraw all or any part of this ITQ at any time during the ITQ exercise.

## Tender Validity

  - Your Tender should remain valid for a period of 30 days from the submission date.

## Proposed Contract

  - Contracts for the provision of Item Writing Services will be let under STA’s standard Contract for the Provision of Item Writing Services. Contract numbers are provided in the table below:

| - Subject | - Contract Number |
| --- | --- |
| - Key stage 1 English grammar, punctuation and spelling | - STA-0128-12 |

## Procurement Timescales

  - The proposed timetable for the ITQ exercise is set out below. STA reserves the right to change this if it becomes operationally necessary so to do.

| DATE | STAGE |
| --- | --- |
| 14 August 2017 | ITQ issued to Suppliers |
| 12 noon 11 September 2017 | Deadline for submission of Clarification Questions by Tenderers |
| 12 noon 22 September 2017 | Closing Date for receipt by STA of Tenders |
| 27 October 2017 | Notification of Award Decision |
| 13 to 27 November 2017 | Proposed contract Commencement and Start-Up Meeting |

## Clarification Questions

Clarification Questions should be submitted by e-mail only to TendersTD.STA@education.gsi.gov.uk and cc’d to Rashida.Akbar@education.gov.uk. No further requests for clarifications will be accepted after the date shown in the table above. All communications should be clearly headed "Provision of Item Writing" and should include the subject and contract number which the question refers to. The name, contact details and position of the person making the communication should also be included.

  - STA will endeavour to answer all questions as quickly as possible, but cannot guarantee a minimum response time.

  - In order to ensure equality of treatment of Tenderers, STA intends to publish the questions and clarifications raised by Tenderers, together with STA’s responses (but not the source of the questions), to all participants on a regular basis via email.

  - Tenderers should indicate if a query is of a commercially sensitive nature – where disclosure of such query and the answer would or would be likely to prejudice its commercial interests. However, if STA at its sole discretion either does not consider the query to be of a commercially confidential nature, or considers the query to be one which all Tenderers would potentially benefit from seeing, then STA will either:

Invite the Tenderer submitting the query to either declassify the query and allow the query, along with the STA’s response, to be circulated to all Tenderers; or

Request the Tenderer, if it still considers the query to be of a commercially confidential nature, to withdraw the query.

  - STA reserves the right not to respond to a Clarification Question or to circulate such a Question where it considers that the answer to that Question would be likely to prejudice its own commercial interests.

## Preparation of Tender

  - Tenderers are solely responsible for their costs and expenses incurred in connection with the preparation and submission of their Tender. Under no circumstances will STA, or any of its advisers, be liable for any costs or expenses borne by Tenderers, sub-contractors, suppliers or advisers in this process.

  - Tenderers are required to complete and provide all information required by STA. Failure to comply with the ITQ requirements may lead STA to reject a Tender.

  - STA relies on Tenderers' own analysis and review of information provided. Consequently, Tenderers are solely responsible for obtaining the information which they consider is necessary in order to make decisions regarding the content of their Tenders and to undertake any investigations they consider necessary in order to verify any information provided to them by STA during the procurement process.

## STA Point of Contact

  - Unless stated otherwise in these instructions or in writing from STA, all communications from Tenderers (including their sub-contractors, consortium members, consultants and advisers) during the period of this procurement exercise must be directed to the contact identified in paragraph 2.12.

  - All communications should be clearly headed "Provision of Item Writing" and should include the subject and contract number which the question refers to. The name, contact details and position of the person making the communication should also be included.

## Confidentiality

  - All information supplied by STA to you must be treated in confidence and not disclosed to third parties except insofar as this is necessary to obtain sureties or quotations for the purposes of submitting the Tender.

  - All information supplied by Tenderers to STA will similarly be treated in confidence except for the disclosure of such information as may be required in accordance with the requirements of UK government policy on the disclosure of information relating to government contracts including the Freedom of Information Act and forthcoming transparency procedures.

## Conflict of Interest

  - Any known conflicts of interest, or any potential conflicts of interest that may be reasonably foreseen, should be declared in the Tender.

## Value Added Tax

  - STA is VAT registered. It is also an “eligible body” as classified in VAT Notice 701/30 "Education and Vocational Training". Proposals must therefore include VAT where applicable. Where any doubt exists, Tenderers are expected to have sought clarification from HM Customs and Excise. Prices in the Tender will be accepted on this basis.

  - Tenderers are requested to set out their understanding of the VAT status of the contract based on the services to be provided and the status of STA. There will be no adjustment to the contract sum if VAT is subsequently found to be payable.

## Submission of Tenders

  - The Tender must be submitted in the form specified by completing the Tenderer's Response using Arial 11 font and in English and using pounds sterling. Where applicable, word limits must be adhered to and material in excess of these limits will not be evaluated.

  - Tenderers must submit their responses by email to TendersTD.STA@education.gov.uk cc’d to Rashida.Akbar@education.gov.uk. in the following format:

One complete and signed electronic version in MS Word 2010 (or compatible) format labelled 'priced' of their Tender and with their organisation name in the document title for each subject tendered; and

One electronic version in MS Word 2010 format (or compatible) labelled 'not priced' of their Tender excluding the pricing information and with their organisation name in the document title for each subject tendered.

  - Any example test materials and supporting documents submitted in response to Question 3 of the Tenderer’s Response should be merged into a single file per subject and either embedded into your response document, or provided as a separate document. Any passwords should be provided separate to your bid.

  - Tenders must be received by 12:00 noon on 22 September 2017.

  - Tenders will be accepted at any time up to this deadline but will not be opened or evaluated until the deadline has passed.

  - Any Tender received after the deadline may be rejected unless the Tenderer can provide irrefutable evidence that the Tender was capable of being received by the due date and time and that delivery failure was beyond their reasonable control.

## Right to Reject/Disqualify

  - STA reserves the right to reject or disqualify a Tenderer where:

The Tenderer fails to comply fully with the requirements of this ITQ, including proper completion of the format for response, or is guilty of a serious misrepresentation in supplying any information required in this document; or

There is a change in identity, control, financial standing or other factor relating to the Tenderer that impacts on the selection and/or evaluation process.

## Debriefing

  - Following the conclusion of the ITQ exercise, all unsuccessful Tenderers will have the opportunity of a debriefing. Unsuccessful Tenderers should notify STA by email that they wish to be debriefed. STA will aim to debrief unsuccessful Tenderers within 10 working days of receiving such a request.

# EVALUATION METHODOLOGY

## Basis of Award Decision

Technical Evaluation		70%

Commercial Evaluation		30%

## Evaluation Process

  - Tenders will be formally logged upon receipt - any Tender that is received after the deadline for submission will be rejected.

  - Following the deadline for submission, a compliance check will then be conducted on all Tenders that are received on time to determine whether they correspond to the tender requirements. STA may reject any Tender that does not comply with these tender requirements.

  - Tender evaluation will then comprise three stages:

(1) Legal evaluation – confirmation of acceptance of the terms and conditions of the standard Contract for Item Writing Services according to the Declaration by Tenderer.

(2) Technical evaluation – scoring of the un-priced technical responses required in the Tender by an independent evaluation panel using the scores per criterion set out in that section and with the technical criteria weighted according to the table below:

| Technical Criterion | Weighting |
| --- | --- |
| Expertise in item development and design (see question 1) | 35% |
| Project Management (see question 2) | 10% |
| Example test materials (see question 3) | 35% |
| Item Management (see question 4) | 10% |
| Informal Trialling (see question 5) | 10% |

(3) Commercial evaluation – assessment of the price for the services as set out in the pricing schedule

## Award Decision

  - The technical and commercial evaluation scores will then be combined using the following methodology:

Technical Score = 100 x (Tenderer's technical score / Best technical score)

Price Score = 100 x (Lowest price / Tenderer's price)

Combined Score = (70% x Technical Score) + (30% x Price Score)

Quality Threshold: Tenderers scoring over 66% for their technical score will then be considered for award. STA reserves the right to amend this threshold in the event only one supplier scores higher – we will notify all parties if this occurs.

  - The Work Package will be evaluated and will be awarded to the Tenderer with the highest combined score.

  - STA reserves the right to withhold awarding the Work Package if no suppliers pass the Technical Score.

  - Following evaluation, a summary of the relative quality score and relative price score will be fed back to all bidders. An example of the level of information provided for the work package is given below:

|  | Technical threshold result | Relative Quality Score | Relative Price Score | Weighted Combined Score | Rank for Compliant Bidders |
| --- | --- | --- | --- | --- | --- |
|  |  | 70% | 30% |  |  |
| Tenderer A | PASS | 0.73 | 0.12 | 0.55 | 3 |
| WINNER 1 | PASS | 0.93 | 1.00 | 0.95 | 1 |
| Tenderer C | PASS | 0.67 | 0.23 | 0.54 | 4 |
| Tenderer D | PASS | 1.00 | 0.57 | 0.87 | 2 |

# SPECIFICATION OF REQUIREMENTS (SoR)

## 4.1	Background

This section of the ITQ sets out the Specification of Requirements (SoR) with respect to the items and mark schemes for the tests.

This work package is to assess the range of cognitive demand, question styles and content domain of the draft test frameworks in the relevant subject area as specified in section 4.5.

Please note that STA is now using an item banking approach for test development. The item bank will be reviewed on a regular basis to identify areas where there are insufficient questions, meaning that at the point of project start-up, agencies will be provided with a more specific question writing brief to help address any areas of shortfall.

## 4.2	Revised National Curriculum

On 11 September 2013 the Secretary of State for Education published the new national curriculum framework following a series of public consultations. The Government wants the new National Curriculum for primary English, mathematics and science to set out the very highest expectations for all pupils and to be on a par with the highest-performing education jurisdictions in the world.

The new Programmes of Study are available to download:

https://www.gov.uk/government/publications/national-curriculum-in-england-primary-curriculum

The documents are very specific about the content to be covered, given the fundamental importance of these subjects as a foundation for further study and as the basis for our system of school accountability.

## 4.3	Test Frameworks

Test frameworks for key stage 1 and key stage 2 are based on the new National Curriculum published in September 2013. Each framework defines what is assessed, via the content and cognitive domains and sets out the criteria for test construction in the test specification.

https://www.gov.uk/government/collections/national-curriculum-assessments-test-frameworks

Previous versions of the tests of the new National Curriculum are available at the following address.

https://www.gov.uk/government/collections/national-curriculum-assessments-practice-materials

## 4.4	Project Deliverables/Outputs and Critical Steps

The Project deliverables/outputs are provided in the table below, and individual deliverables or outputs are indicated as Critical Steps where appropriate. All deliverables and outputs are categorised as mandatory and it is essential that you confirm that you can meet them in full. Unless indicated below, all dates are negotiable with STA. Failure to provide confirmation in your proposal documents may result in your proposal being rejected.

## 4.5	Functional Requirements

| Functional Requirements |  |
| --- | --- |
| Assessment type: | National Curriculum Assessment – for pupils at the end of key stage 1 |
| Item Development and Design: | 4.5.2 Key stage 1 English grammar, punctuation and spelling |
|  | The number of marks stated for the work package outlined below is the total number of marks which must be provided at final handover. Suppliers will need to ensure sufficient items are created to allow for any losses during the process. The items are destined for tests that assess the new National Curriculum programme of study for key stage 1 English grammar, punctuation and spelling. Work Package (total: 60 marks) STA requires 60 marks of new and acceptable short-answer items and a mark scheme for each item. The items must be written to match the specifications for the content domain and the cognitive demand ratings as described in the key stage 1 test framework for GPS. - Content domain The supplier must ensure that, at handover, the items comprising the short-answer elements of the contract are in the following approximate proportions across the areas of the content domain, further details of which are specified in the test framework: Test reference code; Number of marks (per work package). G1 Grammatical terms/word classes; 12. G2 Functions of sentences; 10. G3 Combining words, phrases and clauses; 6. G4 Verb tenses and consistency; 12. G6 Punctuation; 20. G8 Vocabulary; 0. Total; 60. Suppliers should refer to the framework document for a full list of assessable elements. - Mark allocation For short-answer items, a minimum of 80% of the marks at handover should be derived from single-mark items. Up to 20% may be derived from 2-mark items. - Cognitive demand The supplier must ensure that, at handover, the total marks of the short-answer items reflect the cognitive demand. Further details, definitions and examples can be found in the test framework. |
| Mark schemes | Mark schemes must be developed for all items. The mark schemes must provide sufficient and clear guidance for teachers and markers to: - allow marks to be allocated reliably, with consistency and accuracy - enable marking to be manageable - enable the marking of the tests to be effectively standardised - have a principle to define what is correct - include examples of responses that illustrate the range of correct responses and possible incorrect or insufficient responses. Ideally, mark scheme exemplars should be drawn from informal trialling, where the items have been trialled. The mark schemes should: - Clearly and succinctly communicate the marking principles for creditworthy and possible non-creditworthy responses for each item - Be straightforward to apply and recognise and reward pupils' responses appropriately |
| Item and mark scheme design | Prior to Interim Handover, items and mark schemes should NOT be presented in InDesign format, with Microsoft Word (or equivalent) being preferred. From Interim Handover onwards, the items must be designed, using Adobe InDesign (STA use Creative Cloud) (or equivalent subject to prior agreement), such that they match as closely as possible the style of the supplied key stage 1 tests in relation to all design elements including font, font size, spacing, diagram style and illustration style. Templates will be provided to all winning bidders, and the requirements of the Design Specification. Mark schemes should be submitted in Microsoft Word 2010 (or compatible subject to prior agreement) at Interim and Final Handover (see below). All content in mark schemes handed over to STA should be fully editable in Microsoft Word 2010 (or compatible subject to prior agreement) with the exception of any complex artwork or diagrams which should be embedded in the appropriate place in the document. The mark schemes should also match the style and layout of the supplied key stage 1 mark schemes as far as possible. |
| Artwork, texts and other external materials | Written test item texts, artwork or data All graphics that are fundamental to the questions and mark schemes (e.g. data sources, diagrams, photographs) must be produced and supplied at Final Handover. Where texts, artwork or data have been commissioned, please include the original material, contact details for the creator of the material, and a statement confirming assignment of the intellectual property rights (“IPR”) in the material from the creator to DfE. The formal assignment of the relevant IPR in the commissioned work must be completed by the Final Handover Date. Where there is a third party owner of any materials, it should be referenced as described below. Referencing source materials and artwork Any materials using externally sourced texts, artwork or data need to be fully referenced; including title, name of copyright owner, name of the author/editor/creator, details of the edition, publisher and page/location of the material within the source. If sourced from the web, a print out of the original website, showing the relevant artwork or data must be included. |
| Item classification | The Supplier must classify all items according to the fields on the item classification spreadsheet, and present the item information on the spreadsheet template supplied. An example spreadsheet is provided in Annex B and final version will be provided to successful supplier(s) at or before the start-up meeting. This spreadsheet should be included with the materials presented at Final Handover (see below). |
| Pre-Trial Handover | Approximately 3 weeks prior to the pre-trial meeting, sufficient materials should be submitted to be able to handover the required material at the end of the project and allow for some attrition throughout the process. Items and mark schemes must be handed over in hardcopy – four complete collated sets are required. The materials need to be as finalised as possible in terms of content, wording, and any images or diagrams are fit for purpose, even if they are not final. At this stage, it is preferable for materials to be presented in Microsoft Word (or equivalent), with the layout being reflective of the agreed template without needing to replicate it exactly – the focus should be on the content and wording of questions rather than the design and layout. Items should NOT be presented as InDesign files at this stage. |
| Pre-Trial Meeting | The purpose of the pre-trial meeting is to agree which items need to be informally trialled and which do not within the Supplier’s available resource. It will also be used to determine any amendments which need to be carried out to those items being trialled before they are presented to pupils. The final decision as to which items are trialled will lie with STA. Suppliers must ensure that sufficient materials are presented to STA prior to this meeting to ensure that the agreed number of items and/or marks as defined for each subject are available for handover at the end of the contract. Any item or stimulus produced for this contract that is presented to STA for the pre-trialling meeting and which are not selected by STA as being part of the Final Handover are owned by STA and can be developed further by STA for use in future test cycles. These items must not be used by the supplier for any other contract. If insufficient items are selected for Final Handover to fulfil the requirements of the work package, the supplier may provide substitute items which have been through the full process – including informal trialling – or may provide a reduced amount of items at a reduced cost to be agreed with STA. The meeting will also be used to agree the format and content of the informal trialling report. The outcome of this meeting will determine the final cost for informal trialling. |
| Informal Trialling | The primary aim of informal trialling is to aid development of mature items and to aid mark scheme development. Suppliers must ensure that as far as possible those individuals, or the key individual, who have devised the items (the Item Writer) conduct trialling personally so they get first hand feedback on the language being used, area being assessed, and the interpretation and understanding of the items by pupils and teachers. Whether or not a pupil answers correctly is of secondary concern, rather that they understand what is being asked of them regardless of their answer. Established item types or those where pupil behaviours can be accurately or reasonably predicted should not be trialled. Each item should be trialled with at least 25 pupils, and those pupils should have been taught the particular curriculum area / topic area the item is assessing, or have been taught an equivalent programme of study. Pupils should be of an appropriate age and overall should show the range of abilities expected at the end of key stage 1. The items should be discussed with pupils in small groups of 4-6 pupils. It is not expected that trialling samples will be representative. Suppliers should provide details of the volume of items they will be able to trial with their Item Writers conducting the trialling and any interviews, and provide detail of their trialling model to ensure items and mark schemes are improved or validated as a result of the trial. Suppliers should also provide the following costs: - Informal trialling – fixed costs - Informal trialling – variable costs based on the agreed level of informal trialling to be carried out. There is no requirement to collect quantitative data as a result of this trial as the nature of the samples will not be representative. Any feedback from the trial will consist of qualitative data and evidence only. STA staff may wish to accompany the trialling agency on a small number of visits to schools to observe so dates and locations of schools where trialling is taking place are to be provided to STA at least two weeks in advance of the first trial taking place. For any visits STA staff undertake, they should be provided with a clean set of the informal trialling booklets and mark schemes for the tests they are observing. At the start of the informal trialling STA should be sent three clean hard copies of all the Informal Trialling booklets and mark schemes / coding frames. Informal trialling should be completed by 25th June in the UK (avoiding the period around LIVE test week), as this will make it considerably easier to meet post-trialling deadlines. If trialling takes place after this date in the UK, any risks to the delivery of the requirements will be borne by the supplier. Expected outputs from the trials should be by exception only and should include: - Child-level feedback from discussion in small groups with the administrator on their experience of the items and their level of understanding - Teacher feedback on the same - Detailed amendments to items and mark schemes as a result of the trials Qualitative feedback from the informal trial will be presented at the interim handover meeting within the Microsoft Word version of the mark scheme. |
| Interim Handover | Interim Handover must occur no later than 23rd July 2018 Any item or stimulus produced for this contract that is presented to STA up to and including the Interim Handover meeting and which are not selected by STA as being part of the Final Handover are owned by STA and can be developed further by STA for use in future test cycles. These items must not be used by the supplier for any other contract. If insufficient items are selected for Final Handover to fulfil the requirements of the work package, the supplier may provide substitute items which have been through the full process – including informal trialling – or may provide a reduced amount of items at a reduced cost to be agreed with STA. To provide copies of all materials – including amendments following informal trialling – that are proposed to go forward to final handover. Where final versions are not available, a sketched outline or layout of any proposed illustrations or graphics should be provided, or a suitable placeholder graphic. The following materials must be sent to STA: - InDesign files (STA uses Creative Cloud) of at least 10% of the test items in order for STA to check their compliance with the Design Specification and software compatibility. For this purpose, the files need to be submitted according to the specification and the template (provided at the start-up meetings) but do not need to be the latest or final versions of the files. Remaining items should be supplied in InDesign or MS Word (or compatible) format. - Microsoft Word 2010 (or compatible subject to prior agreement) files for all mark schemes - PDF versions of all items and mark schemes – the PDF of items and mark schemes should be compiled into two files only; one containing all test items/questions and the other containing the mark schemes. - PDFs of the questions and mark schemes with the suggested mark-ups or amendments as a result of informal trialling and any other items that were not trialled. The mark-ups and amendments can be handwritten on and scanned in for the PDFs. - Informal trialling report - Item classification spreadsheet in Microsoft Excel 2010 (or compatible), with summary table(s) showing coverage across Attainment targets and levels and any other information as indicated by the supplied template (Annex B) - For the materials being presented, provide a summary table showing coverage across the content and cognitive domains in all subjects and coverage across the assessable elements in English grammar, punctuation and spelling. As a result of informal trialling, item writing agencies will need to send to STA the following documents prior to the interim handover meeting: - Three electronic copies of all the Informal Trialling booklets and mark schemes / coding frames. - A set of materials containing the suggested mark-ups or amendments as a result of the informal trialling and any other items that were not trialled - A report listing the points specified and other feedback obtained during informal trialling. |
| Interim Review | STA will review the materials submitted at Interim Handover. A meeting will be held between STA and the item writers to review those materials and outputs from informal trialling. Any further changes to materials will be agreed at this meeting. The Supplier will complete these and any other agreed amendments prior to final handover. Feedback will be provided at the Interim Review meeting on adherence to the Design Specification for those items submitted in InDesign format. As a result of this feedback, the Supplier may be required to provide an additional set of all materials prior to final handover to ensure compliance with the Design Specification. |
| Final Handover | Final Handover Meeting must occur no later than 12th September 2018. The following materials must be handed over by the Final Handover Meeting: - 40 hard copies of the following: - short-answer items - short-answer items mark schemes - Copyright statement (including all formal documentation for copyright transfer) NOTE: Each short-answer item should be printed single sided. The short-answer items mark schemes should also be printed single sided and include: the complete item; the mark scheme; content domain attributions; cognitive domain attributions - Electronic copies of the following: - A single Adobe InDesign (STA uses Creative Cloud) file for each individual test item with associated links and files - Microsoft Word 2010 (or compatible) files for the mark schemes - Individual PDF files for each question and associated mark scheme (i.e. two files per question). - A combined PDF of all items and another combined PDF of all mark schemes. - A reference document that details the sources of any data and artwork/images used in the test items - All artwork/images used in the test items as unflattened files with all layers intact within the image file where applicable. Please ask for clarification on specific file types which are acceptable. - A copy or copies of the updated classification spreadsheet(s), including a table summarising the number of marks assessing each assessment focus. - For the materials being presented, provide a summary table showing coverage across the content and cognitive domains. - Assignments and/or licences of IPR in the commissioned and other third party works to be completed by the Final Handover Date – as stated in the PQQ and the Contract, and all documentation relating to IPR. - In addition to the handover of the above materials, the purpose of the Final Handover meeting (which will last at least one full working day) is to discuss the items and the rationale for all amends made. The meeting will be chaired by STA and take place in STA offices in Coventry or London. |
| Acceptance of Final Handover | Following Final Handover, STA will check the provided materials. If any errors are found, all materials will be returned to the supplier for a full check and for amendments to be carried out. An error free set of materials should be returned to STA no later than two weeks after the Final Handover Date. |

Performance Requirements

Quality criteria; the completed work package must contain a range of item types that: - are challenging and motivating for pupils - expose and complement the richness of the National Curriculum where possible - are manageable for pupils and capable of being completed within any given time constraints eliciting optimum performance - provide systems of recording marking decisions which are easy to use and interpret for teachers - reflect good classroom practice - comply with all requirements of the regulatory framework - meet the criteria on pages 16 to 27 as appropriate to the subjects awarded. Accessibility The items in standard or modified form must be capable of being used by all pupils working within the targeted levels who have followed the key stage 1 or key stage 2 programme of study for the relevant subject, including; - Those with special educational needs - Those for whom English is an additional language. Items must provide equality of access and opportunity by: - aiming to minimise ethnic, gender and cultural bias - avoiding disadvantaging pupils from particular backgrounds - being free from overt or covert discrimination either through wording or content. In the development of test items, the Supplier must take account of all current legislation in relation to equality of opportunity, including the specific duties under the Equality Act 2010 and any successor legislation.

Security

The Supplier and any sub-contractor must meet the following security requirements: - The Supplier and any sub-contractor will comply with the STA's security procedures to maintain the integrity of all materials produced. - The Supplier and any sub-contractor is required to give full access to STA representatives for inspection where requested. - Where any breach of security occurs, the Supplier must follow the STA security incident guidelines. All project team members and any other individual working on this project must be made aware of their obligations under the STA security policy. - All test materials are confidential. Pupil data is confidential. If any pupil data is collected as part of this project, the handling of pupil data on tests and forms must comply with the Data Protection Act. STA does not require that pupil data is collected for this project. - All files must be handled in a secure and confidential manner. Transmission of information regarding test materials via unsecured networks or email or by regular postal service is prohibited. - All staff working on the materials must sign a confidentiality agreement. Staff must work on these materials in a secure work area. - Handover forms to be used for all deliveries. Supplier to email to inform and confirm delivery. - See Test Development external Suppliers security policy document, Annex E for further information with regard to the security of the test materials and compliance to the Security Policy Framework (SPF) completed as part of the Pre-Qualification Questionnaire (PQQ). Security Compliance Supplier and any sub-contractor must be compliant with all SPF requirements highlighted by STA Security. Where compliance has not yet been achieved an action plan and risk register must be agreed to address any issues identified within an acceptable timeframe. In the event that STA, in its sole discretion, considers that the required Security policies or processes have not been implemented by the Supplier and any sub-contractor prior to delivery of the Services, STA reserves the right to cancel any Order and/or terminate the Contract with immediate effect.

# Tenderer's Response

## 5.1 Key stage 1 English grammar, punctuation and spelling

| Single Point of Contact: |  |
| --- | --- |
| E-mail: |  |
| Phone: |  |

Please note that all questions in this section will be evaluated according to the following 4 point scoring scale:

| Score | Guidance |
| --- | --- |
| 0 | Solution has low probability of successfully delivering requirements |
| 1 | Solution has some probability of successfully delivering requirements |
| 2 | Solution has good probability of successfully delivering requirements |
| 3 | Solution has high probability of successfully delivering requirements |

English grammar, punctuation and spelling: Expertise in item development and design Q1) Please provide (in no more than 1,000 words) details of the capability, experience and roles of the personnel* who will be directly involved in item development. Please indicate any personnel who are external to the submitting organisation. This should include: - those responsible for writing items and mark schemes - those responsible for managing/revising items and mark schemes (it is understood these may be the same as those in the category above) - those responsible for classifying items. - those responsible for undertaking the pupil interviews in trialling. Please describe explicitly the role of each named individual within the project and the proportion of their time dedicated to the project. In each case, please state whether their availability for the project has or has not been secured. *Please include abridged CV's of key personnel in addition to your response as embedded pdf files. Question weighting = 35%

Bidder’s response:

English grammar, punctuation and spelling: Project Management Q2a) Provide a detailed project plan for this work. The project plan must include: - A proposed timeline with specified dates for all key milestones in the process, including (but not limited to) those listed in the Deliverables/Output section (Section 4.4). - The identification of all risks relevant to this piece of work and associated contingencies. (STA requires a service provider which will be active in identifying risks and opportunities associated with the procurement process and the documentation it reviews, in the context of the Procurement Regulations and also ensuring that the interests of STA are adequately protected at all times.) - An outline of the approach that will be taken to ensure that all key administrative and technical requirements (excluding item writing/development/design) are met to time and quality, including: - Printing of test materials for trialling and handover - Meeting the design specification (for test items) - All other security-critical aspects Q2b) In no more than 500 words, describe your approach to managing the relationship with STA. Question weighting = 10%

Bidder’s response:

Example test materials: English grammar, punctuation and spelling Q3) For each of the work packages, the Supplier should provide: Short-answer items; - six examples of 1 mark items and mark schemes - four examples of 2 mark items and mark schemes - two examples of innovative items and mark schemes For each item, please provide a commentary of no more than 500 words that gives a rationale for the choices made. Note: the Supplier must not re-use items that have previously been submitted to STA under contract. Suppliers can however reuse items previously submitted as part of a bid.. Your items will be judged on: quality and accuracy; clarity of language; accessibility; the extent to which items are absent of issues of bias and construct irrelevant variance. A range of item types will be considered positively, including items that assess the specified content domain in creative and innovative ways. Please include items that cover a range of cognitive levels and response types, and – within the guidance provided above – that can be attributed to the abstraction and strategy support ratings. Where relevant, mark schemes should include identification of possible pupil misconceptions that might arise, in the form of guidance or ‘do not accepts’. Please submit example test materials in Microsoft Word or equivalent. Items should be attributed according to the content and cognitive factors specified in section 4.5.2. Question weighting = 35%

Bidder’s response:

English grammar, punctuation and spelling: Item management Q4) In no more than 750 words, describe how you will ensure that there will be sufficient, high quality items available to handover at the end of the project. Discuss - the number of items you plan to write - where you would target extra item writing - what you would do to minimise item attrition without adversely affecting the quality of the items in the Final Handover. Question weighting = 10%

Bidder’s response:

English grammar, punctuation and spelling: Informal Trialling Q5) In no more than 1000 words, describe how you will ensure the validity of the informal trialling through: - the suitability, from a development perspective, of those administering the informal trials - the collection of evidence - the trialling methodology employed to maximise the qualitative evidence for each item - the final report format and proposed contents and level of detail. Question weighting = 10%

Bidder’s response:

5.2.1 Key stage 1 English grammar, punctuation and spelling pricing proposal

The costs provided must include all charges that are applicable to the delivery of the STA Requirements. The Total Price submitted will be the fixed price included within any subsequent contract and there will be no adjustment to the contract pricing if additional charges are subsequently identified.  The Tenderer must complete the cost breakdown in the attached spreadsheet in Annex C. Please ensure the totals in the spreadsheet correspond with the figures in the table(s) below.

- The Fixed Price to deliver Work Package 1 in full is £                  and is split into two instalments, which correspond to the critical steps, as set out in Section 4.4.

| Milestone Payment | Requirement/Critical Steps | Payment Timescale | Amount £ (Excl. VAT) |
| --- | --- | --- | --- |
| 1 | Interim Handover (50%) | dd/mm/2018 |  |
| 2 | Final Acceptance (50%) | dd/mm/2018 |  |
|  |  | Total £ |  |

Key Stage 1 Work Package 1 GPS Item Writing Cost Breakdown

| No. | Requirement/Output | Cost (£) |
| --- | --- | --- |
| 1 | Item Writing Costs |  |
| 2 | Informal Trialling – Fixed Costs |  |
| 3 | Informal Trialling - Variable Costs to trial 100% of items written |  |
| 4 | DTP Costs |  |
| 5 | Item Review Costs |  |
| 6 | Item amendment costs |  |
| 7 | Meetings, Travel and Subsistence Costs |  |
| 8 | Print and Handover Costs |  |
| 9 | Illustrations / Artwork |  |
| 10 | Other Costs (please specify) |  |
| 11 | Other Costs (please specify) |  |
| 12 | Other Costs (please specify) |  |
|  | TOTAL COSTS | £ |

Additional Information

Informal Trialling - Variable Costs to trial 25% of items written - £

Informal Trialling - Variable Costs to trial 50% of items written - £

Informal Trialling - Variable Costs to trial 75% of items written - £

5.2.2 Key stage 1 English grammar, punctuation and spelling declaration by Tenderer

I have examined the STA requirements and proposed terms and conditions and hereby offer to enter into a contract with STA for the required services at the rates and prices set out in my enclosed Pricing Proposal.

I warrant that I have the required corporate authority to sign this Tender.

I understand that STA is not bound to accept the lowest price or any Tender and that the Contract for Provision of Key stage 1 English grammar, punctuation and spelling: Item Writing will be awarded on the basis of the most economically advantageous tender.

This Tender shall remain open for acceptance by STA for a period of 30 days after the due date for return of tenders.

| Signed: |  |
| --- | --- |
| Name: |  |
| Date: |  |
| Role: |  |
| Authorised to sign tenders on behalf of [organisation name]: |  |

# Annexes

## Annex A – Test Frameworks

https://www.gov.uk/government/collections/national-curriculum-assessments-test-frameworks

## Annex B – Item Classification Spreadsheet

This is an example of the structure of item classification spreadsheets allowing STA to import materials directly to their item bank. Final versions of the spreadsheet for each subject will be provided to the successful supplier(s) at or before the start-up meeting.

## Annex C – Test Development External Suppliers Security Policy

## Annex D – National Curriculum Test Design Specification

People trialling items must have prior knowledge, preferably through integral involvement in origination, but minimally through having reviewed and discussed the materials with the Item Writers.