ANNEX B TO

SCHEDULE 3 TO

ARMYHQ4/00087

Performance Management Regime

1.	Key Performance Indicators (KPIs)

1.1	The Contractor’s performance in providing the requirements of the contract shall be measured on the basis of the following Key Performance Indicators:

1.1.1	delivery of management services (Management KPI);

1.1.2	delivery of Events in accordance with the agreed plan (Event delivery KPI)

1.2	The following areas of the requirement will be measured to indicate the Contractor’s performance in providing the service:

1.2.1 	the provision of initial and updated plans and/or reports in accordance with the SOR;

1.2.2	the provision of a point of contact service;

1.2.3	the provision of a sufficient and suitably qualified contract management team (CMT);

1.2.4	the provision of SME support to Event planning;

1.2.5	the provision of Technical writers for Event planning;

1.2.6	the provision of management support for all Events;

1.2.7	the provision of training support to all Events;

1.2.8	the delivery of Events in accordance with the agreed plan.

1.3	The following table sets out which Key Performance Indicators will be applied to each of the areas set out at 1.2 above:

| Service | Key Performance Indicators applicable |  |
| --- | --- | --- |
|  | Management KPI | Event Delivery KPI |
| initial and updated plans and/or reports | X |  |
| point of contact service | X |  |
| sufficient and suitably qualified contract management team | X |  |
| SME support to Event planning | X |  |
| Technical writers for Event planning | X |  |
| management support for all Events |  | X |
| training support to all Events |  | X |
| delivery of Events |  | X |

2.	Monitoring and Reporting

2.1	The Contractor shall with the exception of Events, monitor its performance of the Contract requirements and shall report its performance against the Key Performance Indicators by within the Monthly Management Status Report to the Monthly Performance Management Meeting

2.2	The Monthly Management Status report shall reflect any Authority feedback and any instances of failure to provide the requirements of the contract to the standard required by the KPI’s, which are either identified by the Contractor or by the Designated Officer which relate to each monthly payment period.

2.3	 At each Monthly Performance Management Meeting:

2.3.1	the Authority shall inform the Contractor of any additional feedback received which has not been included in the Monthly Management Status Report which indicates that the content of the report may be inaccurate;

2.3.2	the Authority and the Contractor shall consider and discuss the content of the Report and any additional feedback;

2.3.3 	the Contractor shall update the Report to reflect any additional feedback; and

2.3.4	the Authority and the Contractor shall agree any amendments to be made to the Report.

The Authority shall confirm its approval of the Report by signing it.

2.4	Event After Action Questionnaires (AAQ) that have been finalised in accordance with paragraph 4.1 below shall be submitted for consideration to the next Monthly Meeting.

2.5	The Authority shall review all Management KPI breaches and all AAQ submissions where Event Delivery KPI breaches have been identified. The Authority shall have the final decision on where KPI remedies are applied.

2.6	In the event of disagreement the matter shall be dealt with in accordance with the provisions of DEFCON 530 - Dispute Resolution (English Law).

Persistent Breach

2.7	Where the Contractor is in persistent breach of the KPI’s the contract shall be in default and condition 2.27 (Termination on Contractor Default) of the Contract shall apply

3.	Management Key Performance Indicator Failures

3.1	Where the Contractor fails to achieve the Management KPI for any of the areas set out at paragraph 1.2 the remedies set out in this paragraph 3 shall apply.

Plans and Reports

3.2	A breach of the Management KPI will occur in relation to the required Plans and Reports where the contractor has failed to provide a complete and accurate Plan/Report to the Authority by;

3.2.1	the date on which it was due in accordance with the Contract; or

3.2.2	where the Authority has informed the Contractor of a new due date, such due date.

3.3	Where a breach of the KPI occurs pursuant to Paragraph 3.2 the Authority shall notify the Contractor of the new due date for the Plan/Report.

Point of Contact Service

3.4	A breach of the Management KPI will occur in relation to the required Point of Contact Service Point of Contact is not available during the times set out within the Statement of Requirement.

Contract Management Team

3.5	A breach of the Management KPI will occur in relation to the Contract Management Team where the contractor has failed to provide;

3.5.1 	A sufficient Contract Management Team in accordance with the Contract Management Plan

3.5.2	A Contract Management Team where all members are suitably qualified

SME Support

3.6 	A breach of the Management KPI will occur where the Contractor has failed to provide suitable SME support for Event planning.

Technical Writers

3.7	A breach of the Management KPI will occur where the Contractor has failed to provide suitable Technical writer for the Event planning meetings

Breach of Management KPI Remedy

3.8 	For each breach of the Management KPI within any monthly payment period, the Authority shall be entitled to make a deduction of 1% to the Management Fee.

3.9	The Authority shall in any monthly payment period be entitled in total to a maximum deduction equivalent to 5% of the Management Fee for Management KPI breaches.

4.	Event Delivery Key Performance Indicators

After Action Questionnaire (AAQ)

4.1	The Contractor performance for each Event shall be measured by use of the After Action Questionnaire (AAQ) at Appendix 1 to this Annex B to Schedule 3.

4.2	The AAQ is to be completed by the Authority on completion of each Event. The AAQ shall be reviewed by both the Authority and the Contractor within the Post Event Review Meeting at which point the Contractor may submit mitigation for any failures identified.

4.3	AAQ’s and any provided mitigation shall be reviewed within the Monthly Meeting which shall determine the amount deductible by the Authority for any breach to the KPI.

4.4	The Authority shall have the final decision on whether a KPI breach has occurred and the remedies applied.

Event Delivery KPI Breach

4.5	A breach of the Event Delivery KPI will occur where the Contractor has failed to provide;

4.5.1	The agreed number of supporting artiste and speaking role personnel;

4.5.2	Any agreed Contractor supplied transportation;

4.5.3	Any personnel identified as being in a Critical Role;

4.5.4	All demonstrations and Event serials in accordance with the agreed briefing and plans;

4.5.5	CASSIM role players with injuries that were realistic;

4.5.6	CASSIM role players with believable performances;

4.5.7 	The agreed level of management support;

4.5.8	All AAQ activities to the standard required

4.5.9 	The training support as detailed within the SOR;

Breach of Event Delivery KPI Remedy

4.6	Where the Contractor fails to provide serial 4.5.1 in any Event, the Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the number of role players that did not attend the event. Where there is no failure of subsequent serials a KPI breach will not be recorded and no further action taken. Where subsequent serial breaches are identified paragraph 4.8 and 4.9 shall apply.

4.7	Where the Contractor fails to provide serial 4.5.2 in any Event, the Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the transportation that was not available. Where there is no failure of subsequent serials a KPI breach will not be recorded and no further action taken. Where subsequent serial breaches are identified paragraph 4.8 and 4.9 shall apply.

4.8	Where the Contractor fails to provide any of the serials 4.5.3 to 4.5.9 in an Event a KPI breach shall be recorded. The Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the number of role players that did not attend the event where the Contractor fails to provide 4.5.3. In addition, the Authority shall be entitled to a payment equal to 7% of the overall price of the Event as stated on the Demand Order Form.

4.9	In addition, where the serials 4.5.3 to 4.5.9 are not provided in full the Authority shall be entitled to a payment equivalent to 1% of the Management Fee.

4.10	Where multiple Events are completed within a monthly payment period the Authority shall be entitled to the remedies set out at paragraphs 4.8 and 4.9. However, a maximum of 3% of the Management Fee may be deducted for Event Delivery KPI breaches in any monthly payment period.

4.11	Where:

4.11.1	a sum has been deducted from the Contractor pursuant to Paragraph 4.8 – 4.9; and

4.11.2	no Event Delivery KPI breaches are recorded within the next monthly payment period where an Event occurs,

The Contractor shall be entitled to a payment equivalent to the amount of the Management Fee deducted pursuant to Paragraph 4.9.

APPENDIX 1 TO

ANNEX B TO

SCHEDULE 3 TO

ARMYHQ4/00087

After Action Questionnaire (AAQ)

1. 	The AAQ below forms part of the receipt of services provided and as such it is an auditable document and must be completed for every demand placed upon the contractor.

| EVENT NAME (Incl Demand Reference) |  |
| --- | --- |
| EVENT DATES |  |

| Question | Score Yes/No/N/A | Comments |
| --- | --- | --- |
| Were the role players competent in their cultural understanding, social and political awareness, quality of role play, dressed in accordance with role play scenarios and authentic/credible in their Role Player (RP)? |  |  |
| Were the critical role players competent in their understanding of role, understanding of military planning, cultural understanding, social and political awareness, quality of role play and authenticity? |  |  |
| Were the RP competent in their depth of language knowledge and did they provide realism to the Event by adding complexity to the Training Audience’s interactions? |  |  |
| Were all demonstrations and all Event serials executed in accordance with agreed briefings and plans? |  |  |
| Did the role players remain engaged, flexible and proactive throughout the Event, making suggestions where appropriate to improve the experience for the Trg Audience? |  |  |
| Were sufficient team leaders deployed in a recognisable and specific C2 Structure to manage the required effect? |  |  |
| Did the DEMFOR properly represent British Military TTPs, values and standards when demonstrating tactical procedures? |  |  |
| Did all the CASSIM role players injuries look realistic and were the actors engaging and believable in their performances as casualties? |  |  |
| Did the correct number of identified critical role players arrive at the right place, at the right time ready for briefing and remain available throughout the Event as stated within the Demand Order Form. |  |  |
| Did the role players who were required to have a specific skill; (Wpn handling, Driving licenses, TTP awareness, etc) have the necessary certification, competence, experience and currency? |  |  |
| Did the correct number of role players arrive at the right place, at the right time ready for briefing and remain available throughout the Event as stated within the Demand Order Form. |  |  |
| Any additional comments |  |  |
| What aspects of the contractor’s performance overall (if any) were particularly good? |  |  |
| What aspects of the contractor’s performance overall (if any) were particularly disappointing? (Comment on any areas not covered in the preceding questions or expand on comments.) |  |  |
| Please provide names of any individuals who you would like to see again on similar scenario Events |  |  |
| How can the contracted service be improved? |  |  |
| Contractor’s comments and or mitigations |  |  |

| Signatures (Authority) |  | Signatures (Contractor) Acknowledgement |  |
| --- | --- | --- | --- |
| Name: Appt: Unit: Contact Tel: Email: |  | Name: Appt: Unit: Contact Tel: Email: |  |