## Benchmark Timeline
ProCure22 Benchmarking Timeline |  |  | Spreadsheet for internal use data to be entered on-line by the PSCP
Introduction |  | The Key Performance Indicators are a key component of the frameworks overall effectiveness and value for money. The majority of the information is generated in the normal course of a project. The PSCP completes ALL Data but will have to obtain client satisfaction scores from the Trust.
What to Complete and When |  | The benchmarking requirements vary dependent on the type of project. This is summarised in the timeline below. Data entry cells are coloured light blue with optional notes at the side.
Project Types: |  | Toolkit | Measure | Project Stage when Toolkits required: colour coding matches worksheet tab
Minor wks and <£1m | >£1m |  |  | Phase 1 | Phase 2 | Phase 3 | Construction | Handover
Mandatory All projects |  | Contract details - PSCP | Performance of time and cost predictability, defects and Client Satisfaction Product |  |  | ►►Go |  | ►►Go
|  | Safety | Accident Incident Rate |  |  |  | ►►Yearly if PSCP is on site
|  | Client Satisfaction | Satisfaction with Service provided by PSCP |  |  |  |  | ►►Go
| All over £1m | Efficiency Form | Efficiency savings achieved (complete at end of each pre construction stage) | ►►Go | ►►Go | ►►Go
Not required | Optional based on DH guidelines | Design Quality | Design Quality |  |  | ►►Go
|  | BREEAM | Environmental Performance |  |  | ►►Go |  | ►►Go
| Mandatory over £1m and if meet criteria in ECA guidance sheet | ECA Details | Details required for interpretation of costs in ECA |  |  | ►►Go
|  | Elemental Cost Analysis | Breakdown of Building Cost |  |  | ►►Go
|  | ECA Specification | Details of construction components within ECA |  |  | ►►Go
|  | Function | Departments and functions within building, to aide interpretation of ECA costs |  |  | ►►Go
Contact Details |  | Further information can by obtained by contacting the following; David Low - Senior Cost & Performance Manager - david.low@dh.gsi.gov.uk, Tel - 0113 254 6024

## KPI Information
ProCure22 Benchmarking KPIs: For information: explanation of the KPIs |  |  | Spreadsheet for internal use data to be entered on-line
| KPI | Data | Calculation | Example | Project
1 | Client Satisfaction - Product: client satisfaction with the product | Contract details PSCP HO.09 | Score out of ten | (10) totally satisfied | Select… ▼
2 | Client Satisfaction - Service: client satisfaction with service rated out of ten | Client Satisfaction Handover questionnaire | Score out of ten provided from an average of each questions score | (8) Mostly satisfied | Score Each Question
3 | Defects - measure of defects at completion. Aim is for zero defects | Contract details PSCP HO.10 | Score out of ten | 10 - Defects Free | Select… ▼
4 | Cost predictability: measures if project delivered to budget two stages | Contract details PSCP and Handover sheets
4.1 | Stage 3 Cost Predictability | F23. Predicted Phase Three costs (FBC) | = F24-(F23+F25) | 100000 | 0
|  | F24. Actual Phase Three Costs (FBC) | F23 | 110000 | 0
|  | F25. Adjustments for costs for Phase Three compensation events |  | 12000 | 0
|  |  | *Result | -2%
4.2 | GMP Cost Predictability | F26. Original agreed GMP | = HO.08-(F26+HO.06) | 815323 | 0
|  | HO.08 Final account | F26 | 908768 | 0
|  | HO.06 Total value of agreed Compensation Events - ECC Clause 60 |  | 169212 | 0
| A positive = over budget, this should not happen and suggest your data is wrong! |  | *Result | -9.29%
5 | Time predictability: measures if project delivered to time | Contract details PSCP and Handover sheets
5.1 | Construction time | F20. Date of possession | =((HO.02-F20)-((F21+HO.04)-F20)) | 2008-03-10 | 0
|  | F21. Contractual completion date | ((F21+HO.04)-F20) | 2008-08-11 | 0
|  | HO.02 Actual completion date |  | 2008-08-11 | 0
|  | HO.04 Adjustment to Phase 4 programme due to Compensation events |  | 0 | 0
|  | Extended completion date = F21+ HO.04 |  | 2008-08-11 | 0
|  |  | *Result | 0%
6 | Safety: accident incident rate | Safety sheet
|  | Nr. of reportable accidents in year | = Accidents * 100,000
|  | Average number employed in year | Ave. nr. Employed
This method is not statistically valid on single projects so the data is aggregated across all projects and compared with the figures produced by Constructing Excellence
7 | Elemental Cost Analysis
P21+ is required to demonstrate cost reductions against published benchmarks as part of the Government Construction Strategy. The measurement of this will be done centrally and projects aggregated together. However individual projects need to take account for this and use the supplementary guidance that has been provided on this.
Formulas:
Example = E18+[Example, row above]

## Efficiency
P22 Efficiency Dataset | [5 empty] | P22 Project Ref. |  |  | PSCP: | [5 empty] | Balfour Beatty | Healthcare Partnership Solutions | Integrated Health Projects | Interserve Project Services | Kier | Willmott Dixon
Project Title:
| PSCP Project Manager: |  |  |  |  | Tel No: |  |  |  | Mobile No:
E-mail address:
Please complete this questionnaire for each project with an estimated GMP over £1m at the end of each project stage, capturing the changes in the forecast/actual GMP through the project stage, in particular the cost savings and efficiencies that the PSCP have achieved. If the stage is the first following PSCP appointment the forecast is the initial forecast provided by the PSCP.
1. Changes to Forecast/ Agreed GMP from start of stage to end of stage
1.1 Project stage: |  |  |  | 1.2 GIFA at stage start: |  |  |  |  | 1.3 GIFA at stage end: | [5 empty] | Stage 1 | Stage 2 | Stage 3 | Stage 4
1.4 Forecast GMP at stage start |  |  |  | 1.5 Forecast/Actual GMP at stage end: |  |  |  |  | 1.6.Change in GMP (1.4-1.5): |  |  |  | 0
2. Schedule of Changes: Describe details of the change: If changes exceed 16 use continuation sheet provided
| Provide specifics and avoid generic descriptions like 'general value engineering'. Provide details of the cost in section 3. | [10 empty] | £ Value + or _ |  | Client change Y/N
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
4. BIM (commonly seen as, but not limited to 3D modelling)
4.1 Did the project use BIM within the project stage? |  |  |  |  | 4.2 If YES indicate which party by typing 'YES' and approx savings/benefits. | [9 empty] | Yes | No
| Architect |  | Cost Manager |  | Project Manager |  |  | M&E Installers |  | Structural S/C
| Structural Engineer |  | PSCP |  | M&E Engineer |  |  | Constructor |  | Groundwork's
| BIM Benefit | Less clashes & abortive work |  | Quicker option appraisal | Design efficiency |  | Less manual quants | Reduced on site labour | Standardisation |  | Other
Value of Benefit
5. Repeatable Rooms and Standard Category Components: The P22 programme will build on the Repeatable Room designs and Standard Category Components started on P21+ and capture details of where they have been used or the reasons for not doing so. The list will therefore increase over the life of the framework. Provide details of where these have or have not been used. Indicate if the deviation from the standard resulted in an increase or decrease in costs. Where the standard was used identify the value of any cost saving.
|  |  |  | 5.A | 5.B |  | 5.C | 5.D |  |  |  |  | 5.E
| Repeatable room / Standard Category component |  |  | Did the project contain any of the room or component types listed? Yes or No | If 5.A is Yes was the P21+ repeatable/ standard used? Yes or No |  | If 5.B is No was deviation at the clients request? Yes or no | Comments |  |  |  |  | Value
1 | Single Bedroom with en-suite
2 | 4 Bed Bay with en-suite
3 | Consultation/Exam room
4 | Consultation room
5 | MH Bedroom with en-suite
5 | Component: Hard Flooring
6 | Component: Suspended Ceilings
7 | Component: Sanitary Ware
8 | Component: Lighting
9 | Component: Doors and Ironmongery
10 | Component: MH Windows
11 | Component: Soft Flooring
12 | Component: Paint
13 | Component: Radiant Panels
14 | Component: Bedhead Services
15
Comments

## Contract Details - PSCP GMP
Contract Details - PSCP GMP Stage |  |  | Spreadsheet for internal use data to be entered on-line | ◄Benchmarking Timeline
This section is completed by the PSCP at the GMP stage. The GMP will have to be agreed to complete the information.
Project Title: |  |  |  | PSCP Select… ▼ | PSCP Select… ▼ | Balfour Beatty | MillerHPS | Integrated Health Projects | Interserve Project Services | Kier | Willmott Dixon
Ref | Question | Data | Guidance Notes | Comments (optional)
575
Project Information
F.05 | P22 Project Reference |  | This is the reference number as per the P22 database e.g P22 0010.01
Dates
F.11 | Date of appointment of the PSCP * |  | MMS letter of appointment date
F.12 | Project Stage at Date of PSCP Appointment * | Select… ▼ | MMS phase at PSCP appointment |  | Select… ▼ | Pre SOC | Pre OBC | Pre FBC | Post FBC | No Formal Business Case
F.13 | At appointment of PSCP- Planned date of FBC submission |  | The forecast provided by the PSCP after appointment. If no formal FBC is required enter the planned date of the submission to the Trust Board.
F.16 | Planned date of Completion as stated in FBC submission |  | This relates to the main works, and not enabling works. If no formal FBC is required enter the date stated in the submission to the Trust Board.
F.17 | Actual Date of FBC submission |  | If no formal FBC is required enter the actual date of the submission to the Trust Board
F.18 | Actual date of FBC Approval |  | If no formal FBC is required enter the actual date of the Trust Board Approval. Has to be after F.17
F.19 | Adjustment to Phase Three Programme due to compensation events |  | Number of days adjustment to the programme due to Compensation Events etc. (Positive are extensions to the Contract Period). If None enter 0.
F.20 | Date of Possession * |  | MMS Start on site date
F.21 | Contractual Completion date *
Costs/Misc |  |  | Note :- ALL costs exclude VAT
F.23 | Predicted Phase Three costs (FBC) |  | The Cost the PSCP has forecast for Phase Three
F.24 | Actual Phase Three Costs (FBC) |  | The Actual Phase Three costs
F.25 | Adjustments for costs for Phase Three compensation events |  | The value of the Compensation events raised in Phase Three
F.26 | Original agreed GMP * |  | MMS 'GMP' field
Question in Bold = KPI information
* the on-line system will take this information from the Monthly Monitoring System (MMS)

## Design Quality GMP
Design Quality Assessment GMP Stage |  | ◄Benchmarking Timeline
This section is completed by the PSCP providing the Design Quality assessment available at the GMP Stage.
Spreadsheet for internal use data to be entered on-line |  | Rating/Score
A | Character and Innovation
B | Forms and Materials
C | Staff and Patient Environment
D | Urban and Social Integration
E | Performance
F | Engineering
G | Construction
H | Use
I | Access
J | Space
Average

## BREEAM GMP
BREEAM Design Stage Assessment |  | ◄Benchmarking Timeline
This section is completed by the PSCP at the GMP Stage
Ref. | Section: Spreadsheet for internal use data to be entered on-line |  | Section Score
3 | Management
4 | Health and Wellbeing
5 | Energy
6 | Transport
7 | Water
8 | Materials
9 | Waste
10 | Land use/Ecology
11 | Pollution
| Total Score |  | 0%
Innovation Credits Achieved
| FINAL BREEAM SCORE |  | 0%
| BREEAM Rating |  | Unclassified
| Minimum Standards for BREEAM Rating Achieved? |  | Select… ▼ | Select… ▼ | Yes | No
BREEAM Rating: | below 30 unclassified, 30 to 44% - Pass, 45 to 54% - Good, 55 to 69% - Very Good, 70 to 84% - Excellent, above 85% -Outstanding

## ECA Guidance
P21+ Elemental Cost Analysis Guidance Note
◄Back to Elemental Analysis
Spreadsheet for internal use data to be entered on-line
1.0 Introduction
The completion of the ‘Elemental Cost Analysis’ generally follows the principles of the ‘Elemental Standard Form of Cost Analysis’ published by the RICS, available below:
http://www.bcis.co.uk/downloads/BCIS_Elemental_Standard_Form_of_Cost_Analysis_4th__NRM__Edition_2012.pdf
2.0 Are the form/s required on all projects?
Not if the value of the analysis is below £1m or if the project is of a miscellaneous nature .e.g. fire works, infrastructure upgrades, minor internal alterations, demolition works, enabling works etc.
3.0 How to we use the form on projects with work to more than one building?
The cost analysis must apply to a single building. Therefore provide an analysis for the building with the largest value only and provide a note explaining is is part of a multi building project within the general description on sheet 'ECA Details' question F.05a. If no single building is above £1m in value then no ECA is required.
4.0 How do we use the form on projects with a mixture of new build and refurbishment?
Provide an analysis of either the new build or refurbishment building dependant upon whichever has the highest value. Please identify this within the general description on sheet 'ECA Details' question F.05a.
5.0 KEY POINTS TO REMEMBER
5.1 Refurbishment and new build cost should not be combined.
5.2 Ensure the 'ECA Details', 'Functional Departments' and 'Specification' sheets are also completed.
5.3 The relevant PSCP fee percentage shall be included within the relevant individual elements and not allocated entirely to site on costs.
5.4 The cost analysis must apply to a single building.
5.5 Items such as: site on costs and design fees can be allocated pro-rata to the value of the building analysed where the analysis is not for the full GMP value.

## ECA Details
Elemental Cost Analysis - This sheet relates only to the building provided in the Cost Analysis |  |  | Spreadsheet for internal use data to be entered on-line | ◄Benchmarking Timeline
This section is completed by the PSCP at the GMP stage. Please read the ECA guidance to see if you need to complete it!
Project Title: |  | Automatically complete once sheet 'Contract Details - PSCP FBC' filled in'
No. | Name | Data | Guidance Notes | Comments
575
Project Structural Details for the Cost Analysis Provided
F.05a | General description of Project |  |  | The cost analysis provided should be for a single building. Please identify in particular where the cost analysis is part of a larger more complex project.
F.06 | Number of storeys |  | Total number of floors, including car park basements, but excluding roof plant rooms.
F.07 | Number of storeys below ground
F.10 | Gross Internal Floor Area of the building detailed in the cost analysis provided |  | This is used to calculate the cost/m2 column in the cost analysis provided.
Dates for the Cost Analysis Provided
F.20a | Date of Possession |  | If the project comprises more than one building this relates to the building provided in the costs analysis only.
F.21a | Contractual Completion date |  | If the project comprises more than one building this relates to the building provided in the cost analysis only.
Costs/Misc |  |  | Note :- ALL costs exclude VAT
F.28 | RICS PUBSEC Index |  | The current RICS PUBSEC index at the start of construction.
F.29 | Indicate if VOP or Firm Price PUBSEC is stated in F.28 |  | The index would normally be Firm Price unless the contract has a VOP fluctuation clause - only normally used if the contract period exceeds 24 months |  | VOP | Firm Price
F.30 | Location Factor |  | The Location Factor for the Site - this will normally be from the BCIS
Contract Information for the Cost Analysis provided
T.05 | Type of Project - Class of work | Select… ▼ | The type of the work detailed in the cost analysis provided. |  | Select… ▼ | New Building Existing Site | New Building New Site | Extension: horizontal | Extension: vertical | Refurbishment | Fitting Out New Building | Fitting Out Existing Building | Shell Only
T.07 | Function | ►►Function | Please complete the 'Function' sheet for the building in the cost analysis provided, adding 'included' where applicable
T.08 | Is the Building Listed | Select… ▼ | Not applicable to new build projects |  | Select… ▼ | Yes (Grade I) | Yes (Grade II) | Partially Listed | No | N/A
T.09 | Is the project within a Conservation Area | Select… ▼ |  |  | Select… ▼ | Yes | No | N/A
T.10 | Site Conditions - Contour | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Level | Gently Sloping | Steeply sloping | Undulating | N/A
T.11 | Site Conditions - Ground Conditions | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Good | Moderate | Bad | N/A
T.12 | Site Conditions - Excavation | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Above water table | Below Water Table | In running water | N/A
T.13 | Site Conditions - Existing Site | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Green Field | Demolition | Demolition by others | Infill | N/A
T.14 | Site Conditions - Working Space | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Unrestricted | Restricted | Highly Restricted
T.15 | Site Conditions - Access | Select… ▼ |  |  | Select… ▼ | Unrestricted | Restricted | Highly Restricted
T.16 | Abnormal Ground Conditions | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | Good Bearing at Reasonable Depth | Other (please clarify in comments)
T.17 | Site Conditions - Existing Services | Select… ▼ | If not new build or extension enter N/A |  | Select… ▼ | No Services | Some light services | Significant existing services | Major Diversions
T.18 | Site Conditions - Location | Select… ▼ |  |  | Select… ▼ | Inner City Restricted | Inner City | Urban | Rural
Trust Advisors Contact Details
T.19 | NHS Trust Cost Advisor - Name
T.20 | NHS Trust Cost Advisor - Company
T.21 | NHS Trust Cost Advisor - Tel
T.22 | NHS Trust Cost Advisor - Email

## Function
Functional Departments within Facility |  | ◄Benchmarking Timeline
This section is completed by the PSCP at the GMP stage and relates only to the building detailed in the cost analysis.
Spreadsheet for internal use data to be entered on-line
Facility types |  | Tick where relevant
Acute
Primary Care
Community hospitals and intermediate care hospitals
GP Premises
Primary Care Centres/ Health Centre
Social, Community / Voluntary Services
Urgent care centres, walk-in centres and minor injury units
Mental Health
Ambulance Services
Other
Departments and Accommodation
In-Patient care (Wards)
Children
Elderley
Ward Accommodation
Intensive care
Intensive therapy
Maternity
Surgery
Main operation theatres
Day surgery
Diagnostic and Treatment
Anaesthetic Services
Cardiology
Critical Care
Endoscopy
Medical investigation
Medical photography
Mmortuary and post-mortem
Neuro-physiology
Oncology
Pathology
Pharmacy
Radiology - MRI Suite
Radiology (imaging)
Rehabilitation Services
Renal
Out-patient Departments
Accident and emergency
Children
Dermatology
ENT and audiology
Maternity
Ophthalmolgy
Oral surgery and Orthodontics
Outpatients Dept
Mental Health
Adult Day Care Unit
Elderly
Intensive care
Medium secure
High Secure
Low Secure
Residential
Education and training
Teaching Accomodation
Library
Administration
Offices
Main entrance
Security
Retail
Staff Facilities
Service Facilities
Boilerhouse and fuel storage
Catering
Kitchens
Estates Maintenance
Infrastructure
Laundry
other
Sterile services
Local Healthcare
Health Authority Clinic
Local Health Resource Centre
Primary Care
Ambulance
Residential

## Elemental Cost Analysis
Elemental Cost Analysis | [5 empty] | Spreadsheet for internal use data to be entered on-line |  |  | ◄Benchmarking Timeline
This section is completed by the PSCP at the GMP Stage. Please refer to the ECA Guidance to see if you need to complete it!. The PSCP Fee Percentage is spread across all elements.
Element |  | ◄ ◄ RICS BCIS Guidance available Online |  |  |  | Element | Cost per m2 |  | Unit Quantity | Unit Quantity Guidance | Unit rate
[6 empty] | Cost £ | GIFA | % | (varies by element, not simply the GIFA) | (more in BCIS guidance) | (E/H)
0 | Facilitating works
| 1. Toxic/hazardous material removal | [8 empty] | Site area
| 2. Major demolition works | [8 empty] | GIFA of demolished bldg
| 3. Specialist ground works | [8 empty] | Site area
| 4. Temporary diversion works | [8 empty] | Site area
| 5. Extraordinary site investigation works | [8 empty] | Site area
[5 empty] | Element Sub Total | 0 | 0
1 | Substructure | [8 empty] | m2 of lowest floor
2 | Superstructure | [8 empty] | m2 of floors with frame, complely framed=GIFA
1. Frame
| 2. Upper Floors | [8 empty] | m2 of upper floors
| 3. Roof | [8 empty] | Plan area of roof
| 4. Stairs and ramps | [8 empty] | Nr. of storey flights
| 5. External Walls | [8 empty] | m2 of external walls
| 6. Windows and External Doors | [8 empty] | m2 of windows and drs
| 7. Internal Walls and Partitions | [8 empty] | m2 of internal walls
| 8. Internal Doors | [8 empty] | Nr.of int. doors
[5 empty] | Element Sub Total | 0 | 0
3 | Internal Finishes
| 1. Wall | [8 empty] | m2 of finished walls
| 2. Floor | [8 empty] | m2 of finished floor
| 3. Ceiling | [8 empty] | m2 of finished ceilings
[5 empty] | Element Sub Total | 0 | 0
4 | Fittings, Furnishings and non mechanical and electrical equipment | [8 empty] | GIFA
5 | Services
| 1. Sanitary Installations | [8 empty] | Nr.of fittings
| 2. Services Equipment | [8 empty] | Nr.of fittings
| 3. Disposal Installation | [8 empty] | Nr.of fittings serviced
| 4. Water Installation | [8 empty] | Floor area serviced
| 5. Heat Source | [8 empty] | Rating of heat source (Kw)
| 6. Space Heating & Air Treatment | [8 empty] | Floor area serviced
| 7. Ventilation Systems | [8 empty] | Floor area serviced
| 8. Electrical Installation | [8 empty] | Floor area serviced
| 9. Fuel Installation/system | [8 empty] | Floor area serviced
| 10. Lifts and conveyor installations | [8 empty] | Nr of stops
| 11. Fire and Lightning Protective Installations | [8 empty] | Floor area serviced
| 12. Communications, security and control systems | [8 empty] | Floor area serviced
| 13. Specialist Installations | [8 empty] | Floor area serviced
| 14. Builders work in connection with services | [8 empty] | GIFA
[5 empty] | Element Sub Total | 0 | 0
Building sub total (excluding External works, facilitating works, on costs, risk and design fees)
[6 empty] | 0 | 0
8 | External Works
| 1. Site preparation works | [8 empty] | m2 of external works
| 2. Roads, paths and pavings | [8 empty] | m2 of external works
| 3. Planting | [8 empty] | m2 of external works
| 4. Fencing, railings and walls | [8 empty] | m2 of external works
| 5. Site/Street furniture and equipment | [8 empty] | m2 of external works
| 6. External Drainage | [8 empty] | m2 of external works
| 7. External Services | [8 empty] | m2 of external works
| 8. Minor Building works and ancillary buildings | [8 empty] | m2 of external works
[5 empty] | Element Sub Total | 0 | 0
9 | Site On Costs (Site Facilties & Admin/Management)
10 | Contingencies (including Risk)
11 | Design Fees (provide breakdown below)
1. Phase 1 (SOC)
2. Phase 2 (OBC)
3. Phase 3 (FBC/GMP)
4. Phase 4 Construction
TOTAL Design Fees | [5 empty] | 0 | 0
| TOTAL |  |  |  |  | 0 |  | 0%
Design Fee breakdown
Role |  | Phase 1 | Phase 2 | Phase 3 | Phase 4
PSCP
Project Manager
Architect
Cost Management
Structural Engineer
M&E Designer
Healthcare Planner
M&E Installer
Constructor
total

## Specification
Elemental Analysis Specification - this relates only to the Cost Analysis provided
This section is completed with the 'Elemental Cost analysis' by the PSCP at the GMP Stage. Identify all relevant specification by ticking the check boxes in column E
◄Benchmarking Timeline |  | Spreadsheet for internal use data to be entered on-line | ◄Back to Elemental Analysis
1. Substructure: |  |  | Tick where relevant
Foundation: | A. | Traditional strip
| B. | Trench fill
| C. | Reinforced concrete (with basements)
| D. | Reinforced concrete (without basements) strip/and beams
| E. | Reinforced concrete (without basements) piers
| F. | Reinforced concrete (without basement) raft
| G. | Piled
| H. | Vibroflotation
2.1 Frame:
Type: | A. | Reinforced concrete (insitu)
| B. | Reinforced concrete (precast)
| C. | Light section steel
| D. | Heavy steel
2.2 Upper Floors:
Type: | A. | Insitu concrete
| B. | Precast concrete
| C. | Prestressed concrete
| D. | Prestressed concrete with structural topping.
| E. | Coffered concrete
| F. | Timber
2.3 Roof:
Type: | A. | Timber pitched
| B. | Steel & timber pitched
| C. | Insitu concrete flat
| D. | Precast concrete flat
| E. | Timber flat
2.4 Stairs and ramps:
Structure: | A. | Precast concrete
| B. | Insitu concrete
| C. | Timber
| D. | Metal
2.5 External walls:
External skin: | A. | Brickwork
| B. | Rendered blockwork
| C. | Fair faced blockwork
| D. | Masonry (stonework etc.)
| E. | Curtain walling & patent glazing
| F. | Precast cladding
| G. | Timber cladding
| H. | Tile/slate hung brickwork
| J. | Metal cladding
| K. | GRP cladding
| L. | Other lightweight sheet cladding
Internal skin: | A. | Integral with external material
| B. | Brickwork/blockwork
| C. | Fabricated timber
| D. | Fabricated metalwork
2.6 Windows and External Doors
Type | A. | Softwood
| B. | Hardwood
| C. | Aluminium
| D. | Steel
| E. | Composite
| F. | Plastic/UPVC
2.7 Internal walls and partitions
Type: | A. | Brickwork
| B. | Brickwork fair faced
| C. | Blockwork
| D. | Blockwork fair faced
| E. | Timber studding & plasterboard
| F. | Metal studding & plasterboard
| G. | Proprietary partitions
3.1 Wall finishes:
Type: | A. | Traditional insitu
| B. | Dry lined plasterboard
| C. | Sheet finishes
| D. | Tile, slab and block
| E. | Wall glaze
| F. | Fair faced unfinished
3.2 Floor finishes:
Type: | A. | Hardwood
| B. | PVC
| C. | Ceramic
| D. | Asphalt
| E. | Carpet
| F. | Other sheet
| G. | Other tile, slab and block
| H. | Other insitu
3.3 Ceiling finishes:
Type: | A. | Traditional insitu
| B. | Plasterboard and finish
| C. | Suspended
4.1 Fittings:
Specification 1) |  | Type:
| A. | General Fittings, Furnishings and Equipment
| B. | Domestic Kitchen Fittings and Equipment
| C. | Special Purpose Fittings, Furnishings and Equipment
| D. | Signs/Notices
| E. | Works of Art
| F. | Non-Mechanical and Non-Electrical Equipment
5.3 Disposal installation:
Type: | A. | Cast iron
| B. | Plastic
| C. | Special effluent pipes
| D. | Copper
5.4 Water installation:
Type: | A. | Copper
| B. | Plastic
| C. | Coated steel
| D. | Stainless steel
5.5 Heat source:
Fuel: | A. | Gas
| B. | Oil
| C. | Solid fuel
| D. | Electricity
| E. | Other
Plant Type: | A. | Centralised
| B. | Local to unit
| C. | Linked to existing central plant
5.6 Space heating and air treatment:
Air Con: | A. | Heating only
| B. | Comfort Cooling
| B. | Air conditioning
Heating: | A. | Warm air
| B. | Radiators
| C. | Natural convectors
| D. | Fan converters
| E. | Ceiling heating
| F. | Pipe coils
Type: | A. | Centralised
| B. | Local to unit
| C. | Linked to existing central plant
5.7 Ventilation:
System type: | A. | Extract only
| B. | Intake and Extract
5.8 Electrical installation:
Service: | A. | High voltage Supplies
| B. | Low voltage Supplies
| C. | Small Power
| D. | Lighting Installations
| E. | Specialist Lighting Installations
| F. | Local Electricity Generation Systems
5.10 Lifts and conveyor installation:
Type: | A. | Passenger
| B. | Service
| C. | Bed
| D. | Mixed
5.11 Protective installations:
Type: | A. | Automatic Fire Suppression Systems
| B. | Fire Fighting Installations
| C. | Lightning Protection
5.12 Communications:
Type: | A. | Communication System
| B. | Security system
| C. | Central Control/BMS
5.13 Specialist Installations:
Type: | A. | Specialist Piped Supply Installations
| B. | Specialist Refrigeration Systems
| C. | Specialist Mechanical Installations
| D. | Specialist Electrical/Electronic Installations
| E. | Water Features
11. Design Fees
Specification 1) | A. | Novated Team
| B. | Non novated team

## Safety
Safety |  | Spreadsheet for internal use data to be entered on-line |  |  | ◄Benchmarking Timeline
This section is completed by the PSCP during construction. It is required at the end of each calendar year.
Safety Accident Incident Rate (AIR) | Year |  | Jan - Mar | April - June | July - Sept | Oct - Dec | Yearly AIR
Identify the average number employed IN THE QUARTER including subcontractors. E.G 80 employed in January, 60 Employed in February and 40 employed in March = (80+60+40)/3 = 60 average no. employed in quarter | 2016 | Ave. No. Employed (in quarter)
*Accidents
| 2017 | Ave. No. Employed (in quarter)
*Accidents
| 2018 | Ave. No. Employed (in quarter)
*Note - Accidents are the number of reported accidents under RIDDOR (i.e over 7 day, major injuries and fatalities) |  | *Accidents
| 2019 | Ave. No. Employed (in quarter)
*Accidents
| 2020 | Ave. No. Employed (in quarter)
*Accidents
| 2021 | Ave. No. Employed (in quarter)
*Accidents
| 2022 | Ave. No. Employed (in quarter)
*Accidents
| 2023 | Ave. No. Employed (in quarter)
*Accidents
| 2024 | Ave. No. Employed (in quarter)
*Accidents
| 2025 | Ave. No. Employed (in quarter)
*Accidents
| 2026 | Ave. No. Employed (in quarter)
*Accidents
| 2027 | Ave. No. Employed (in quarter)
*Accidents

## Contract Details - PSCP HO
Contract Details - PSCP Handover Stage |  |  | Spreadsheet for internal use data to be entered on-line | ◄Benchmarking Timeline
This section is completed by the PSCP at the Handover Stage. The Final Account will have to be agreed to complete the information.
Contract Title: |  | Automatically complete once sheet 'Contract Details - PSCP FBC' filled in
No. | Name | Data | Guidance Notes | Comments
Dates
HO.02 | Actual Completion Date *
HO.03 | Agreement of Final Account |  | Date Final account agreed.
HO.04 | Adjustment to Phase 4 (construction) programme due to Compensation events |  | Number of days adjustment to the completion date due to Compensation Events etc. (Positive are extensions to the Contract Period) If N/A enter 0.
Costs |  |  | Note :- ALL costs exclude VAT
HO.06 | Total value of agreed Compensation Events - ECC Clause 60 |  | Total cost of compensation events - all Phases
HO.07 | Total value of Trust Gain share |  | If the Trust have instructed additional works in anticipation of a saving provide details in comments
HO.08 | FINAL ACCOUNT |  | Actual out turn cost paid to PSCP (including Contractors Share)
HO.09 | Client Satisfaction Score - Product | Select… ▼ | Please select from the options presented |  | Select… ▼ | (10) totally satisfied | (9) | (8) Mostly satisfied | (7) | (6) Neither satisfied or dissatisfied | (5) | (4) | (3) Mostly dissatisfied | (2) | (1) Totally dissatisfied
HO.10 | Defects score at handover | Select… ▼ | Please select from the options presented. For the purpose of this assessment minor cosmetic faults and adjustments to HVAC system are not considered defects. |  | Select… ▼ | 10 - Defects Free | 9 | 8 - Some defects with no significant impact on client | 7 | 6 - some defects with some impact on client | 5 | 4 | 3 - Major defects with major impact on client | 2 | 1 - Totally defective
HO.11 | General Comments - PSCP Handover Stage
Question in Bold = KPI information
* the on-line system will take this information from the Monthly Monitoring System (MMS)

## Client Satisfaction Handover
Client Satisfaction - Service |  | ◄Benchmarking Timeline
This section is completed by the Trust at the Handover Stage. Firstly rate the importance of ALL questions to the Trust USING THE FULL RANGE OF SCORING OPTIONS.
Spreadsheet for internal use data to be entered on-line
No. | Criteria | Score |  | Questions look up
Select… ▼
1 | How would the Trust score the PSCP's site compound, signage and facilities? | Select… ▼ | #N/A | (10) totally satisfied | 10
|  |  |  | (9) | 9
|  |  |  | (8) Mostly satisfied | 8
2 | How would the Trust score the cleanliness of the PSCP's site? | Select… ▼ | #N/A | (7) | 7
|  |  |  | (6) Neither satisfied or dissatisfied | 6
|  |  |  | (5) | 5
3 | How would the Trust score the PSCP's understanding of the Trust's business? | Select… ▼ | #N/A | (4) | 4
|  |  |  | (3) Mostly dissatisfied | 3
|  |  |  | (2) | 2
4 | How would the Trust score the PSCP's attitude and behaviour towards the Trust's customers? | Select… ▼ | #N/A | (1) Totally dissatisfied | 1
5 | How would the Trust score co-operation amongst all the PSCP team members? | Select… ▼ | #N/A
6 | How would the Trust score the PSCP's speed of response to Trust queries? | Select… ▼ | #N/A
7 | How would the Trust score the PSCP's ability to resolve problems quickly? | Select… ▼ | #N/A
8 | How would the Trust score the way the PSCP handled meetings with the Trust? | Select… ▼ | #N/A
9 | How would the Trust score the PSCP consistency in meeting milestone dates? | Select… ▼ | #N/A
10 | How would the Trust score the PSCP's reporting of financial & management information to the Trust? | Select… ▼ | #N/A
11 | How would the Trust score the PSCP's monitoring of expected H&S Standards? | Select… ▼ | #N/A
12 | How would the Trust score the expertise and competency of the PSCP personnel? | Select… ▼ | #N/A
13 | How would the Trust, at Handover, score the quality of H&S file information and training/instruction in new plant and equipment provided by the PSCP? | Select… ▼ | #N/A
| Total Score | Score Each Question | #N/A

## BREEAM Handover
BREEAM Post Construction Assessment |  | ◄Benchmarking Timeline
This section is completed by the PSCP at the Handover Stage
Ref. | Section: Spreadsheet for internal use data to be entered on-line |  | Section Score
3 | Management
4 | Health and Wellbeing
5 | Energy
6 | Transport
7 | Water
8 | Materials
9 | Waste
10 | Land use/Ecology
11 | Pollution
|  | Total Score | 0%
Innovation Credits Achieved
|  | FINAL BREEAM SCORE | 0%
BREEAM Rating | below 30 unclassified, 30 to 44% - Pass, 45 to 54% - Good, 55 to 69% - Very Good, 70 to 84% - Excellent, above 85% -Outstanding |  | Unclassified
|  | Minimum Standards for BREEAM Rating Achieved? | Select… ▼ | Select… ▼ | Yes | No

## Version control
Ref. | Sheet | Workbook Amendments | ►►Benchmarking Timeline
1 | Version FWK4 (ii) - P21 + Project KPI workbook |  | Date